| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | June 2004 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to 1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, 2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $556,196 | 6% | $2,311,655 | 24% |  |  | $2,311,655 | 24% | $7,494,089 |
| Admin | $1,905,210 | $36,691 | 2% | $398,931 | 21% |  |  | $398,931 | 21% | $1,506,279 |
| Marketing | $3,055,234 | $126,507 | 4% | $760,463 | 25% |  |  | $760,463 | 25% | $2,294,771 |
| DI | $4,648,300 | $392,998 | 8% | $1,152,260 | 25% |  |  | $1,152,260 | 25% | $3,496,040 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jun-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 30,500 | 5,329 | 17.5% | 25,999 | 85.2% | 0 | 0% | 25,999 | 85.2% | 4,501 |
| CTAC/AGTAC event seminars | 176 | 14 | 7.9% | 91 | 51.7% | 0 | 0% | 91 | 51.7% | 85 |
| Outreach events | 85 | 12 | 14.1% | 55 | 64.7% | 0 | 0% | 55 | 64.7% | 30 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element - continued program administration tasks including management of activity and budget status reporting.

    - Marketing

In addition to the list in Attachment A:

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| Basic Heating, Ventilation and Air Conditioning (HVAC) Palm Desert | Flyer | US Mail | 200 |
| U.S. Department of Energy Best Practices Series | Flyer | US Mail Hand Deliver | 2,212 200 |
| Pumping System Assessment Workshop | Flyer | US Mail Hand Deliver | 245 250 |
| How to Manage Your Business’s Energy Costs – Hemet | Flyer | US Mail | 135 |
| How to Manage Your Business’s Energy Costs – Hesperia | Flyer | US Mail | 648 |
| Daylighting for Buildings | Flyer | Email | 2,764 |
| 3rd Quarter Calendar of Events | Calendar | US Mail Hand Deliver | 28,143 7,360 |
| www.sce.com/ctac_work_classes | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| 3rd Quarter Calendar of Events | Calendar | US Mail Hand Deliver | 9080 400 |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during June of 2004 include:

Energy Centers:

Following are accomplishments from June 1st – June 30th 2004.

EE Events completed June = 14

Attendance at those events June = 422

EE Events completed YTD = 91

Attendance at those events YTD = 2576

EE HTR Events completed June = 6

Attendance at those events June = 76

EE HTR Events completed YTD = 37

Attendance at those events YTD = 704

Joint Utility events completed June = 4

Joint Utility events YTD = 38

EE consultations June = 61

Attendees in those consultations June = 190

EE consultations YTD = 384

Attendees in those consultations YTD = 932

EE equipment demonstrations June = 129

Attendees at those demonstrations June = 69

EE equipment demonstrations YTD = 572

Attendees at those demonstrations YTD = 608

New displays developed include:

- AGTAC

  - No new displays at AGTAC in June

- CTAC

  - No new displays at CTAC in June

RTTC:

The following provides a summary description of activities which took place at the RTTC in June 2004:

EE Information Dissemination

- Provided a tour of the RTTC for Alamitos Bay Yacht Club kitchen and facility redesign team

- Provided a tour of the RTTC for Ebm-Papst Inc.

- Provided a tour of the RTTC for engineering staff of the Architectural Engineering Corp.

- Provided a tour of the RTTC for AirTest Technologies

- Provided a tour of the RTTC for Reeferseal Company

- Conducted tour of RTTC for Design and Engineering new summer hire

- Conducted tour of RTTC and Lighting Center for SCE Business Solution’s Audit Team

- Developed and presented an energy efficiency refrigeration seminar based on the RTTC’s test results for FSAC.  The RTTC presented this seminar at CTAC.

Information Services Program:

There were 5,329 EE contacts conducted in the month of June 2004; bringing the YTD total EE contacts to 25,999.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Changes to Subcontractors or Staffing

AGTAC hired a supplemental staffing support person, XXXXX, a Business Analyst 1, for overall support to programs and facility operations such as project coordination, audio-visual, PC and graphic support.

- Additional Items

None