| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | September 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $447,318 | 5% | $8,341,130 | 85% |  |  | $8,341,130 | 85% | $1,464,614 |
| Admin | $1,905,210 | $82,623 | 4% | $1,365,525 | 72% |  |  | $1,365,525 | 72% | $539,685 |
| Marketing | $3,055,234 | $150,847 | 5% | $2,758,358 | 90% |  |  | $2,758,358 | 90% | $296,876 |
| DI | $4,648,300 | $213,848 | 5% | $4,217,247 | 91% |  |  | $4,217,247 | 91% | $431,053 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 285 | 0.4% | 88,676 | 145% | 0 | 0% | 88,676 | 145% | 0 |
| CTAC/AGTAC event seminars | 352 | 13 | 3.6% | 343 | 97.4% | 0 | 0% | 343 | 97.4% | 9 |
| Outreach events | 170 | 9 | 5.3% | 184 | 108% | 0 | 0% | 184 | 108% | 0 |

  - Activities/Accomplishments

    - Administrative

- In September, continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| CTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail Handout | 34156 3000 |
| Irwindale Chamber of Commerce | Newsletter | US Mail | n/a |
| 12th Annual Water Conference | Flyer | US Mail | 397 |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail | 9531 |
| Title 24 and Beyond | Flyer | US Mail | 200 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during September of 2005 include:

Energy Centers:

Following are accomplishments from September 1st – September 30th 2005.

EE Events completed September = 10

Attendance at those events September  = 302

EE Events completed YTD = 140

Attendance at those events YTD = 3204

EE HTR Events completed September  = 4

Attendance at those events September  = 79

EE HTR Events completed YTD = 59

Attendance at those events YTD = 848

Joint Utility events completed September  = 6

Joint Utility events YTD = 59

EE consultations September = 35

Attendees in those consultations September = 75

EE consultations YTD = 386

Attendees in those consultations YTD = 896

EE equipment demonstrations September = 5

Attendees at those demonstrations September = 12

EE equipment demonstrations YTD = 709

Attendees at those demonstrations YTD = 667

New displays developed include:

- AGTAC

No new displays in September

- CTAC

No new displays in September

RTTC:

The summary description of activities which took place at the RTTC in September of 2005 is as follows:

EE Information Dissemination

Tours

Provided a tour of the RTTC for XXXXX of the XXXXX

- Toured representatives of XXXXX and the XXXXX through the RTTC

Publications

- As a guest speaker, will present the results of latest SCE’s vending machine research project sponsored by C&S at E-Source Forum in Colorado

- Published a new article in September issue of Contracting Business.  The article discusses SCE’s leading EE research in the area of supermarket display cases.

- Customer Care

None

EE Program Support

- Met with XXXXX representatives to discuss their equipment selection practices and suggest possible areas of improvement.

- Provided support to EE program team by performing technical review and scoring of several 3rd party nonresidential RFI/proposals provided for Direct Install, IDEEA and InDEE programs.

- Assisted 3rd party program team by attending direct install RFP bidders’ conference and monitoring bidders’ technical concerns

- Provided a one day refrigeration training for SCE’s new hires.

- Met with the XXXXX staff to discuss EE opportunities in food service and retail food segments.

- Developed a refrigeration test for SCE employees participating in BCD’s certification

Information Services Program:

There were 285 EE contacts reported in the month of September 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 88,676 – 145%.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Due to the fact that Tab 7 of the workbook is full, below is a list of additional subcontractors that work on the program along with their associated monthly expenditures.