| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | July 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $347,426 | 4% | $7,583,971 | 77% |  |  | $7,583,971 | 77% | $2,221,773 |
| Admin | $1,905,210 | $75,299 | 4% | $1,221,506 | 64% |  |  | $1,221,506 | 64% | $683,704 |
| Marketing | $3,055,234 | $111,155 | 4% | $2,539,027 | 83% |  |  | $2,539,027 | 83% | $516,207 |
| DI | $4,648,300 | $160,972 | 3% | $3,823,437 | 82% |  |  | $3,823,437 | 82% | $824,863 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jul-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 945 | 1.5% | 87,695 | 143% | 0 | 0% | 87,695 | 143% | 0 |
| CTAC/AGTAC event seminars | 352 | 14 | 3.9% | 320 | 90.9% | 0 | 0% | 320 | 90.9% | 32 |
| Outreach events | 170 | 5 | 2.9% | 168 | 98.8% | 0 | 0% | 168 | 98.8% | 2 |

  - Activities/Accomplishments

    - Administrative

- In June, continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| CTAC July Classes | Email | Email | 4394 |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail | 50 |
| AGTAC July Classes | Email | Email | 400 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during June of 2005 include:

Energy Centers:

Following are accomplishments from July 1st – July 31th 2005.

EE Events completed July = 14

Attendance at those events July = 201

EE Events completed YTD = 117

Attendance at those events YTD = 2486

EE HTR Events completed July = 9

Attendance at those events July = 96

EE HTR Events completed YTD = 50

Attendance at those events YTD = 708

Joint Utility events completed July = 6

Joint Utility events YTD = 47

EE consultations July = 33

Attendees in those consultations July =  53

EE consultations YTD =  304

Attendees in those consultations YTD = 752

EE equipment demonstrations July =  155

Attendees at those demonstrations July = 71

EE equipment demonstrations YTD = 669

Attendees at those demonstrations YTD =  577

New displays developed include:

- AGTAC

- AGTAC New Graphic Look - All of the graphics at AGTAC have been reviewed and updated as needed to create a consistent look between both centers. This joint effort between the two Centers included informational banners, with time sensitive program messages, and hallway and facility signage supportive of the various services offered by Edison.

- CTAC

No new displays were created in July.

RTTC:

The summary description of activities which took place at the RTTC in July of 2005 is as follows:

EE Information Dissemination

- Tours

- Performed Toured representatives of Long Beach Unified School District though the RTTC and SCLTC

- Toured XXXXX and XXXXX company staff  though the RTTC and SCLTC

- Toured XXXXX of XXXXX staff  though the RTTC and SCLTC

- Publications

  - None.

- Customer Care

  - Met with representatives of Long Beach Unified School District to discuss issues related to vending machines and other refrigeration equipment on their campuses.

EE Program Support

- Hosted XXXXX of the XXXXX Appliance Efficiency program at the RTTC. Discussed establishing a connection for transfer of RTTC’s test results to interested parties in the Commission.  As a result of this meeting, we have a greater understanding of the Title 20 process and are in a better position to support their activities.

Attended the CEC’s T-20 workshop to share concerns regarding the regulation of vending machines in 2006.

Information Services Program:

There were 945 EE contacts reported in the month of July, also the late June EE results were reported in July of 14,634 EE contacts  of 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 87,695 – 144%.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None