| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | January 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $306,014 | 3% | $5,129,301 | 52% |  |  | $5,129,301 | 52% | $4,676,443 |
| Admin | $1,905,210 | $53,330 | 3% | $831,186 | 44% |  |  | $831,186 | 44% | $1,074,024 |
| Marketing | $3,055,234 | $110,651 | 4% | $1,733,084 | 57% |  |  | $1,733,084 | 57% | $1,322,150 |
| DI | $4,648,300 | $142,033 | 3% | $2,565,030 | 55% |  |  | $2,565,030 | 55% | $2,083,270 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 1,942 | 3.2% | 48,535 | 79.6% | 0 | 0% | 48,535 | 79.6% | 12,465 |
| CTAC/AGTAC event seminars | 352 | 10 | 2.8% | 213 | 60.5% | 0 | 0% | 213 | 60.5% | 139 |
| Outreach events | 170 | 3 | 1.8% | 96 | 56.5% | 0 | 0% | 96 | 56.5% | 74 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element – In January, continued program administration tasks, including management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| DOE Best Practices Series | Flyer | US Mail | 1802 |
| Compressed Air System Efficiency | Flyer | US Mail | 718 |
| Pumping System Assessment Workshop | Flyer | Hand Deliver | 400 |
| CTAC Classes in Spanish | Flyer | Hand Deliver | 300 |
| Restaurant & Foodservice Energy Strategies | Flyer | E-Mail | 126 |
| Mountain View Newspaper CTAC Ad | Newspaper Ad | Newspaper | 65,000 circulation approx. |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| Workshops February Classes | Email Invite | Email | 343 |
| Best Practices Series | Flyer | Hand Deliver | 50 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during January of 2005 include:

Energy Centers:

Following are accomplishments from January 1st – January 31st 2005.

EE Events completed January = 10

Attendance at those events January = 235

EE Events completed YTD = 10

Attendance at those events YTD = 235

EE HTR Events completed January = 5

Attendance at those events January = 96

EE HTR Events completed YTD = 5

Attendance at those events YTD = 96

Joint Utility events completed January = 5

Joint Utility events YTD = 5

EE consultations January = 36

Attendees in those consultations January = 45

EE consultations YTD = 36

Attendees in those consultations YTD = 45

EE equipment demonstrations January = 29

Attendees at those demonstrations January = 70

EE equipment demonstrations YTD = 29

Attendees at those demonstrations YTD = 70

New displays developed include:

- AGTAC

Low pressure Exhibit—Added vibration monitors on 25HP display.

- CTAC

No new displays at CTAC in January.

RTTC:

The summary description of activities which took place at the RTTC in January of 2005 are as follows:

	 EE Information Dissemination

  - None

- Tours

  - Provided a tour of the RTTC for staff of Carl’s Refrigeration company

  - Provided a tour of the RTTC for staff of PG&E’s A/C lab in San Ramon

	EE Program Support

  - Worked closely with SCE’s EE program staff to identify new EE technologies for inclusion in future programs.

- Publications

  - None

- Customer EE Support

  - None

Information Services Program:

There were 1,942 EE contacts conducted in the month of January 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 48,535.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Statewide Education, Training and Services 2004 Program Study - This statewide study has been initiated involving utility-owned energy centers throughout the State of California with two objectives:  (1) To evaluate 2004 program success by measuring indicators of program effectiveness and testing the underlying assumptions for program milestones; (2) To provide feedback and guidance regarding HTR market endeavors.  The study will focus on geographic HTR markets and their unique characteristics that impact program success.  The study is expected to be completed by year end.