| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | November 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $370,155 | 4% | $9,050,666 | 92% |  |  | $9,050,666 | 92% | $755,078 |
| Admin | $1,905,210 | $78,104 | 4% | $1,498,429 | 79% |  |  | $1,498,429 | 79% | $406,781 |
| Marketing | $3,055,234 | $127,223 | 4% | $3,025,894 | 99% |  |  | $3,025,894 | 99% | $29,340 |
| DI | $4,648,300 | $164,829 | 4% | $4,526,343 | 97% |  |  | $4,526,343 | 97% | $121,957 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Nov-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 1,417 | 2.3% | 91,324 | 149% | 0 | 0% | 91,324 | 149% | 0 |
| CTAC/AGTAC event seminars | 352 | 13 | 3.7% | 374 | 106% | 0 | 0% | 374 | 106% | 0 |
| Outreach events | 170 | 6 | 3.5% | 204 | 120% | 0 | 0% | 204 | 120% | 0 |

  - Activities/Accomplishments

    - Administrative

- In November continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| - How to Partner with SCE for your Building Projects | Flyer | Handout | 500 |
| Irwindale Chamber of Commerce | Newsletter | n/a | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail Handout | 50 |
|  | Quarterly Calendar of Events | US Mail |  |

Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during October of 2005 include:

Energy Centers:

Following are accomplishments from November 1st – November 30th 2005.

EE Events completed November =  13

Attendance at those events November  = 516

EE Events completed YTD = 171

Attendance at those events YTD = 4255

EE HTR Events completed November  = 4

Attendance at those events November   = 101

EE HTR Events completed YTD = 74

Attendance at those events YTD = 1141

Joint Utility events completed November  = 2

Joint Utility events YTD = 72

EE consultations November  = 21

Attendees in those consultations November = 29

EE consultations YTD = 433

Attendees in those consultations YTD = 1157

EE equipment demonstrations November = 24

Attendees at those demonstrations November = 58

EE equipment demonstrations YTD = 842

Attendees at those demonstrations YTD = 853

New displays developed include:

- AGTAC

No new displays in November

- CTAC

The Lighting Center at CTAC is undergoing an upgrade that is scheduled to be completed in mid-December.  The Center will feature new interactive lighting displays and text panels that explain lighting technologies and applications for residential and business customers.

RTTC:

The summary description of activities which took place at the RTTC in November of 2005 is as follows:

EE Information Dissemination

Tours

- Performed RTTC Tour: For attendees XXXXX for RTUs class at CTAC

Publications

- None

- Customer Care

None

EE Program Support

- Training Seminars

  - DES Technology Update Seminar:  Presented the latest refrigeration technologies to SCE’s delivery organizations

  - Diagnostic Strategies Seminar - Provided a ½ day training for SCE customers at CTAC on the subject of Diagnostic and EE Opportunities for roof top air conditioners

- 2006 Express Efficiency Program – Reviewed and analyzed the calculation methodologies and reported savings for new food service related measures for 2006.

- 2006 Express Efficiency Program – Modify Savings Calculations for Retrofitting Medium-Temp. (MT) and Low-Temp. (LT) Display Cases with Glass Doors:  This ER was in response to a request from Express Efficiency Program team.  This ER established the demand and energy savings per linear feet of MT and LT display cases as a result of installing glass doors.  RS, SM

- EE Support for Business Solutions (PY 06-08) – RTTC in conjunction with CTAC developed a preliminary proposal to provide technical support and training for Business Solutions team to assist them in meeting their 06-08 EE goals.

Information Services Program:

There were 1,417 EE contacts reported in the month of November of 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 91,324 – 150%.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Due to the fact that Tab 7 of the workbook is full, below is a list of additional subcontractors that work on the program along with their associated monthly expenditures.