| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | February 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $330,347 | 3% | $5,459,648 | 56% |  |  | $5,459,648 | 56% | $4,346,096 |
| Admin | $1,905,210 | $57,016 | 3% | $888,202 | 47% |  |  | $888,202 | 47% | $1,017,008 |
| Marketing | $3,055,234 | $122,465 | 4% | $1,855,549 | 61% |  |  | $1,855,549 | 61% | $1,199,685 |
| DI | $4,648,300 | $150,867 | 3% | $2,715,897 | 58% |  |  | $2,715,897 | 58% | $1,932,403 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 2,530 | 4.1% | 51,065 | 83.7% | 0 | 0% | 51,065 | 83.7% | 9,935 |
| CTAC/AGTAC event seminars | 352 | 18 | 5.1% | 231 | 65.6% | 0 | 0% | 231 | 65.6% | 121 |
| Outreach events | 170 | 5 | 2.9% | 101 | 59.4% | 0 | 0% | 101 | 59.4% | 69 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element – In February, continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| Evaporative Cooling for Commercial & Industrial Facilities | Flyer | US Mail | 500 |
| Restaurant & Foodservice Energy Strategies | Flyer | US Mail | 1955 |
| Lighting Design Seminars | Email | Email | 3025 |
| Major Customer Division - Power Bulletin | Newsletter | US Mail | n/a |
| North American Assoc. of Food Equipment Manufacturers (NAAFEM) Newsletter | Newsletter | US Mail | n/a |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| Workshops February Classes | Email Invite | Email | 350 |
| Best Practices Series | Flyer | Hand Deliver | 50 |
| Workshops 3-1 and 3-10 | Email Invite | Email | 200 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during February of 2005 include:

Energy Centers:

Following are accomplishments from February 1st – February 28th 2005.

EE Events completed February = 18

Attendance at those events January = 348

EE Events completed YTD = 28

Attendance at those events YTD = 583

EE HTR Events completed February = 5

Attendance at those events February = 78

EE HTR Events completed YTD = 10

Attendance at those events YTD = 174

Joint Utility events completed February = 9

Joint Utility events YTD = 14

EE consultations February = 28

Attendees in those consultations February = 272

EE consultations YTD = 64

Attendees in those consultations YTD = 317

EE equipment demonstrations February = 20

Attendees at those demonstrations February = 55

EE equipment demonstrations YTD = 49

Attendees at those demonstrations YTD = 125

New displays developed include:

- AGTAC

No new displays at AGTAC in February.

- CTAC

No new displays at CTAC in February.

RTTC:

The summary description of activities which took place at the RTTC in February of 2005 is as follows:

	 EE Information Dissemination

- Engineers’s Week at CTAC

Made a motivational presentation to over 100 high school and junior college students to persuade them towards the engineering field

- ASHRAE Tri-County Chapter Meeting

In the capacity of guest speaker presented the latest results from the RTTC’s Vending Machine research to an audience of roughly 50 engineers.

- Tours

  - Provided a tour of the RTTC for:

    - ASHRAE Tri-County Chapter meeting. XXXXX

    - Over 100 high school and junior college students for Engineers Week.

    - Mark Modera from Carrier Corporation

	EE Program Support

  - None

- Publications

  - Published a symposium paper at ASHRAE Winter Meeting in Orlando.  The paper discussed the past, present and future research performed in air curtain applications. XXXXX

  - Published an article on Jet Entrainment Rate in Air Curtain of Open Refrigerated Display Cases, International Journal of Refrigeration, Vol. 28, 2nd issue, pages 267-275. XXXXX

- Customer EE Support

  - None

Information Services Program:

There were 2,530 EE contacts conducted in the month of February of 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 51,065.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

The Energy Centers are working with the California Energy Commission and the Department of Energy to provide a series of Best Practice workshops featuring educational training and materials on the following technologies: Compressed Air, Motors, Steam and Heat Processing.

- Changes to Subcontractors or Staffing

None

- Additional Items

None