| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Codes and Standards Advocacy Program – PGC |
| Program Number: | 1266-04 |
| Month: | April 2005 |

1.	Program Status

Program Description

The Statewide Codes and Standards (C&S) program is an information-only program that advocates upgrades and enhancements in energy efficiency standards and codes. Program activities are conducted over long-term code upgrade cycles; for example, support for building code cycles may require four years of continuous support.  Codes and Standards Enhancement (CASE) studies for energy efficiency improvements are performed for promising design practices and technologies and are presented to standards and code-setting bodies.  Since many stakeholders who typically oppose improvements to building and appliance standards participate in public workshops and hearings, the Statewide Codes and Standards Advocacy program provides expert testimony to promote standards that approach best practices in energy efficiency.  Additionally, the program supports implementation of energy efficiency standards through strategic initiatives or training.  The program targets all market segments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $2,485,099 | $76,564 | 3% | $775,722 | 31% | $504,023 | 20% | $1,279,745 | 51% | $1,709,377 |
| Admin | $802,600 | $26,584 | 3% | $376,722 | 47% |  |  | $376,722 | 47% | $425,878 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $1,597,400 | $49,980 | 3% | $399,000 | 25% | $504,023 | 32% | $903,023 | 57% | $1,198,400 |
| EM&V | $85,099 |  |  |  |  |  |  |  |  | $85,099 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Apr-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Initiate or continue case studies | 12 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 12 |
| Evaluation of potential studies | 100% |  | 5% |  | 77.5% |  | 0% |  | 77.5% | 22.5% |
| Commitment of new studies | 12 | 3 | 25% | 13 | 108% | 0 | 0% | 13 | 108% | 0 |
| Conduct training courses | 8 | 0 | 0% | 4 | 50% | 0 | 0% | 4 | 50% | 4 |

  - Activities/Accomplishments

    - Administrative -

- All active studies are being pursued and are on time and within budget.

- CASE study opportunities are being investigated to fulfill our target of 6 new project commitments for 2005.

- Our training goal/targets will be developed along with our research portfolio.

    - Marketing -

N/A

    - Direct Implementation –

SCE had a brainstorming meeting designed to discuss some possible Codes and Standards evaluations for 2005. Members of the Design and Engineering Services staff discussed proposed possible CASE studies.  Potential areas of focus included compressed air dryers for industrial applications, cooking equipment for commercial kitchens, residential air conditioning that utilizes water cooled condensers, agriculture dairy guides and various lighting applications for residential and non-residential applications.

Two specific projects have been committed thus far. They are:

- Single Zone Stage Volume Air Conditioning system

- Dairy Farm Seminar

- Compressed air dryer phase 2

In addition, SCE is coordinating with the CEC to provide training for contractors and building officials on duct leakage. Events are being targeted for the Santa Clarita Valley and the Pasadena area.

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

See direct implementation.

- Changes to Subcontractors or Staffing

None

- Additional Items

None