| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Pump Test and Hydraulic Services Program – PGC |
| Program Number: | 1317-04 |
| Month: | May 2004 |

- Program Status

Program Description

Southern California Edison’s (SCE) Pump Test and Hydraulic Services (PTHS) Local Program proposal represents an energy information and management services program.  The program will be delivered to agricultural and water customers throughout SCE’s service territory.  The PTHS program is designed to increase the adoption rate and implementation of energy efficiency recommendations provided to customers with pumping accounts.   It will accomplish these goals by testing customers’ pumping systems, and delivering information to a customer that contains a site specific energy efficiency report with cost analysis that the customer can easily understand and act upon.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,200,000 | $131,892 | 4% | $547,645 | 17% |  |  | $547,645 | 17% | $2,652,355 |
| Admin | $1,316,600 | $54,231 | 4% | $187,381 | 14% |  |  | $187,381 | 14% | $1,129,219 |
| Marketing | $18,400 |  |  |  |  |  |  |  |  | $18,400 |
| DI | $1,745,000 | $77,661 | 4% | $360,264 | 21% |  |  | $360,264 | 21% | $1,384,736 |
| EM&V | $120,000 |  |  |  |  |  |  |  |  | $120,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings or demand reductions.

    - Performance Goals

| Performance Goals | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Pump Tests | 7200 | 389 | 5.4% | 2065 | 28.7% | 0 | 0% | 2065 | 28.7% | 5135 |

  - Activities/Accomplishments

    - Administrative -

- Held monthly staff meeting to discuss and provide updates on goal status, technical issues, program development and reporting of information.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

| # of Pump Tests | Cost Per Site |
| --- | --- |
| 389 | $339 |

- PTHS continues to work to attract new customer participants, as defined in the PTHS program implementation plan.  In May 2004, 41% of customers receiving a pump test were New Participant customers.

- Recognizing the fact that most customers of the PTHS program are traditionally considered hard-to-reach customers, 30% of tests performed in May 2004 were performed on pumping systems located in hard-to-reach geographic areas.

- PTHS is continuing its outreach to HTR and New Participant customers.  In May 2004, 50 direct mail appeals were sent to HTR/New Participant customers.

- PTHS provided educational resources at the Inland County Water Association Fair (May 11, 2004).  Over 100 brochures and applications for pump testing services were distributed.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None