| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Pump Test and Hydraulic Services Program – PGC |
| Program Number: | 1317-04 |
| Month: | August 2004 |

- Program Status

Program Description

Southern California Edison’s (SCE) Pump Test and Hydraulic Services (PTHS) Local Program proposal represents an energy information and management services program.  The program will be delivered to agricultural and water customers throughout SCE’s service territory.  The PTHS program is designed to increase the adoption rate and implementation of energy efficiency recommendations provided to customers with pumping accounts.   It will accomplish these goals by testing customers’ pumping systems, and delivering information to a customer that contains a site specific energy efficiency report with cost analysis that the customer can easily understand and act upon.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,200,000 | $110,542 | 3% | $902,038 | 28% |  |  | $902,038 | 28% | $2,297,962 |
| Admin | $1,316,600 | $40,730 | 3% | $318,330 | 24% |  |  | $318,330 | 24% | $998,270 |
| Marketing | $18,400 |  |  |  |  |  |  |  |  | $18,400 |
| DI | $1,745,000 | $69,813 | 4% | $583,708 | 33% |  |  | $583,708 | 33% | $1,161,292 |
| EM&V | $120,000 |  |  |  |  |  |  |  |  | $120,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings or demand reductions.

    - Performance Goals

| Performance Goals | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Pump Tests | 7200 | 382 | 5.3% | 3,311 | 45.9% | 0 | 0% | 3,311 | 45.9% | 3,889 |

  - Activities/Accomplishments

    - Administrative -

- Held monthly staff meeting to discuss and provide updates on goal status, technical issues, program development and reporting of information.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

| # of Pump Tests | Cost Per Site |
| --- | --- |
| 382 | $290 |

- PTHS continues to work to attract new customer participants, as defined in the PTHS program implementation plan.  In August 2004, PTHS continued pump testing levels of new customer participants at 41%.

- In August 2004, pumps tested in hard-to-reach (HTR) designation increased slightly to a rate of 31.2%.  Recognition should continue to be given to the fact that most customers receiving benefits of the PTHS program are traditionally considered HTR customers.

- PTHS is continuing its outreach to HTR and New Participant customers.  In August 2004, 100 direct mail appeals were sent to HTR/New Participant customers.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

Follow up with two customers in the Tulare region reported making repairs to their pumping systems as a direct result of the information they received from the SCE pump test provided to them.  One customer’s overall pumping efficiency increased from 44.0% to 51.8%, a 7.8% improvement.  The other increased their OPE by 41.2% (26.0% to 67.2%)!

As a result of PTHS’ services in assisting a municipal customer with the adjusting of their turbine well’s impeller, the customer was able to improve the OPE from 61.9% to 75.7%.

New Customer Participants are customers that have not benefited from an SCE pump test in the last 3 years.

In addition to the generally recognized definition of hard-to-reach customers as they apply to PTHS’ customers, SCE also tracks the participation of hard-to-reach customers as defined by geographical location, i.e. rural zip code.