| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Pump Test and Hydraulic Services Program – PGC |
| Program Number: | 1317-04 |
| Month: | June 2004 |

- Program Status

Program Description

Southern California Edison’s (SCE) Pump Test and Hydraulic Services (PTHS) Local Program proposal represents an energy information and management services program.  The program will be delivered to agricultural and water customers throughout SCE’s service territory.  The PTHS program is designed to increase the adoption rate and implementation of energy efficiency recommendations provided to customers with pumping accounts.   It will accomplish these goals by testing customers’ pumping systems, and delivering information to a customer that contains a site specific energy efficiency report with cost analysis that the customer can easily understand and act upon.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,200,000 | $115,495 | 4% | $663,140 | 21% |  |  | $663,140 | 21% | $2,536,860 |
| Admin | $1,316,600 | $37,694 | 3% | $225,075 | 17% |  |  | $225,075 | 17% | $1,091,525 |
| Marketing | $18,400 |  |  |  |  |  |  |  |  | $18,400 |
| DI | $1,745,000 | $77,801 | 4% | $438,065 | 25% |  |  | $438,065 | 25% | $1,306,935 |
| EM&V | $120,000 |  |  |  |  |  |  |  |  | $120,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings or demand reductions.

    - Performance Goals

| Performance Goals | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Pump Tests | 7,200 | 490 | 6.8% | 2,555 | 35.5% | 0 | 0% | 2,555 | 35.5% | 4,645 |

  - Activities/Accomplishments

    - Administrative -

- Held monthly staff meeting to discuss and provide updates on goal status, technical issues, program development and reporting of information.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

| # of Pump Tests | Cost Per Test |
| --- | --- |
| 490 | $236 |

- PTHS continues to work to attract new customer participants, as defined in the PTHS program implementation plan.  In June 2004, 41% of customers receiving a pump test were New Customer Participants.

- In June, SCE maintains a pump test performance rate of 30% for pumping systems that are considered hard-to-reach.  Recognition should continue to be given to the fact that most customers receiving benefits of the PTHS program are traditionally considered hard-to-reach customers.

- PTHS is continuing its outreach to HTR and New Participant customers.  In June, 100 direct mail appeals were sent to HTR/New Participant customers.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

Significant Customer Activities:

- XXXXX adjusted their pumping system operation as a direct result of a PTHS pump test performed on June 17.  Due to the implemented changes, XXXXX pumping system operating efficiency increased by 12%.

- XXXXX pumping system was tested after a major pumping system replacement.  The operating efficiency was working far below expectations.  As a result of the information provided by PTHS pump test performed on June 22, the customer is pursuing action with the contractor to correct this situation.

New Customer Participants are Customers that have not benefited from an SCE pump test in the last 3 years

In addition to the generally recognized definition of hard-to-reach customers as they apply to PTHS’ customers, SCE also tracks the participation of hard-to-reach customers as defined by geographical location, i.e. rural zip code.