| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Government Initiatives – PGC |
| Program Number: | 1318-04 |
| Month: | June 2004 |

- Program Status

Program Description

Through a partnering with Local Governments, cities, and local governments (collectively referred to as Jurisdictions), Southern California Edison’s (SCE) Local Government Initiative (LGI) will offer energy efficiency information and education, hardware upgrades, and subsidized energy efficiency improvements to SCE’s small to medium-business owners, lower-to-moderate income residential customers, single and multifamily existing residential consumers, and residential and small commercial builders.

The core of this program approach is to work with the jurisdictions as a delivery channel for SCE's broad portfolio of energy efficiency information, services and incentives, thereby deepening the reach of our program offerings.  However, the added benefit of our partnership approach is that it allows us, working side-by-side with the cities, to customize offerings (either through bundled offerings or modifying individual programs) to either fill a specific need within a Jurisdiction, and/or better reach an identified Hard-to-Reach (HTR) component within a city.  Collaboration with Jurisdictions is an effective adjunct to the utility-to-customer approach used in many of SCE’s programs, leveraging the influence of the Jurisdictions who share similar energy efficiency goals.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,800,000 | $2,318 | 0% | $25,058 | 1% |  |  | $25,058 | 1% | $1,774,942 |
| Admin | $297,600 | $2,318 | 1% | $23,224 | 8% |  |  | $23,224 | 8% | $274,376 |
| Marketing | $90,000 |  |  | $1,834 | 2% |  |  | $1,834 | 2% | $88,166 |
| DI | $1,340,400 |  |  |  |  |  |  |  |  | $1,340,400 |
| EM&V | $72,000 |  |  |  |  |  |  |  |  | $72,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jun-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Completed 2004 Enrollment Forms | 32 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 32 |
| Expand to New Jurisdiction Identified as HTR | 10 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 |
| Conduct Building Department Training or Imformation Updates on 2005 Title 24 Code Revisions | 12 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 12 |
| Coordinate Activities Promoting Residential and Multifamily Retrofit Programs | 10 | 1 | 10% | 3 | 30% | 0 | 0% | 3 | 30% | 7 |
| Coordinate Activities Promoting Nonresidential Programs | 10 | 0 | 0% | 1 | 10% | 0 | 0% | 1 | 10% | 9 |

  - Activities/Accomplishments

    - Administrative -

- SCE is currently planning the delivery of this program, both internally and externally.  The XXXXX has been the primary subcontractor for this program and will continue to be in 2004; however, SCE is analyzing ways of better leveraging various internal organizations’ that have regular interface opportunities with local governments (e.g., Public Affairs, Major Customer Division).

- SCE met with XXXXX in the month of June to finalize the budget and scope for implementation of the program in 2004.  The current “enrollment form” is being revised for the ’04-05 program years to be more reflective of a “registration form.”  The reason for this modified approach is due to the hesitation we met with in 2003 when requesting that the participating jurisdictions sign the enrollment form.  The jurisdictions felt the enrollment form, as it was written, could potentially cause internal confusion, or require them to deliver a certain amount of energy savings.

    - Marketing –

- We have recently received draft artwork for new brochures/fact sheets for the LGI program.  SCE is adding CARE and Medical Baseline information to the fact sheet which we distribute to current and prospective jurisdictions, as well as internal SCE entities that have shared interest in the energy efficiency opportunities available to our the cities we serve.

    - Direct Implementation –

      - Audits, Site Surveys and Partnerships -

- SCE will continue to work with the XXXXX on the outreach and implementation of this program, particularly in those areas with significant building activity.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

An RFP was issued for the evaluation of the 2003 program this month.

- Program Challenges

Still focusing on increasing the participation in CEEP by production home builders.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

SCE included information on the Local Government Initiative and CEEP in the booth we sponsored at the recent Pacific Coast Builders Conference, June 16- 18 at the Moscone Convention Center in San Francisco.  This show is the largest home building tradeshow on the west coast and was attended by over 26,000 building industry professionals, government representatives, and some industry regulators.

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Additional Items

None