| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Government Initiatives – PGC |
| Program Number: | 1318-04 |
| Month: | December 2004 |

- Program Status

Program Description

Through a partnering with Local Governments, cities, and local governments (collectively referred to as Jurisdictions), Southern California Edison’s (SCE) Local Government Initiative (LGI) will offer energy efficiency information and education, hardware upgrades, and subsidized energy efficiency improvements to SCE’s small to medium-business owners, lower-to-moderate income residential customers, single and multifamily existing residential consumers, and residential and small commercial builders.

The core of this program approach is to work with the jurisdictions as a delivery channel for SCE's broad portfolio of energy efficiency information, services and incentives, thereby deepening the reach of our program offerings.  However, the added benefit of our partnership approach is that it allows us, working side-by-side with the cities, to customize offerings (either through bundled offerings or modifying individual programs) to either fill a specific need within a Jurisdiction, and/or better reach an identified Hard-to-Reach (HTR) component within a city.  Collaboration with Jurisdictions is an effective adjunct to the utility-to-customer approach used in many of SCE’s programs, leveraging the influence of the Jurisdictions who share similar energy efficiency goals.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | $268,219 | 27% | $323,149 | 32% |  |  | $323,149 | 32% | $676,851 |
| Admin | $277,000 | $3,564 | 1% | $44,105 | 16% |  |  | $44,105 | 16% | $232,895 |
| Marketing | $90,000 |  |  | $13,146 | 15% |  |  | $13,146 | 15% | $76,854 |
| DI | $561,000 | $263,220 | 47% | $263,220 | 47% |  |  | $263,220 | 47% | $297,780 |
| EM&V | $72,000 | $1,436 | 2% | $2,678 | 4% |  |  | $2,678 | 4% | $69,322 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Completed 2004 Enrollment Forms | 16 | 4 | 25% | 18 | 112% | 0 | 0% | 18 | 112% | 0 |
| Expand to New Jurisdiction Identified as HTR | 5 | 1 | 20% | 3 | 60% | 0 | 0% | 3 | 60% | 2 |
| Conduct Building Department Training or Imformation Updates on 2005 Title 24 Code Revisions | 6 | 0 | 0% | 6 | 100% | 0 | 0% | 6 | 100% | 0 |
| Coordinate Activities Promoting Residential and Multifamily Retrofit Programs | 5 | 0 | 0% | 5 | 100% | 0 | 0% | 5 | 100% | 0 |
| Coordinate Activities Promoting Nonresidential Programs | 5 | 0 | 0% | 5 | 100% | 0 | 0% | 5 | 100% | 0 |

  - Activities/Accomplishments

    - Administrative -

- Since the Purchase Order for the LGI was signed in September, 2004 SCE has been working with the XXXXX to assist in achieving the performance goals associated with the LGI in a short period of time. We have provided data regarding “hard to reach” (HTR) area of SCE territory, assisting in the organization of the Builder Energy Code trainings  as well as providing support in the outreach events, oftentimes being the speaker for the LGI program.

    - Marketing –

- SCE worked very closely with Edison’s Marketing group to create new brochures( CEEP and LGI), a new LGI enrollment form, and a luggage tag which says “Partnering with Local Governments” to give out as a promotion item. The information will be put together with all the individual energy efficiency programs being promoted into a folder to be given out (or mailed) at the local government cities or outreach events.

    - Direct Implementation –

      - Audits, Site Surveys and Partnerships -

- SCE will continue to work with the XXXXX on the outreach and implementation of this program, particularly in those areas with significant building activity.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

The final EMV&V study was completed in November and was distributed in December.

- Program Challenges

The SCE challenge is working more closely with both internal and external organizations to promote the value of the LGI program.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

SCE is actively focusing on upcoming opportunities in 2005 to promote the LGI program both internally and externally.  In addition, coordinating outreach and support of the Express Efficiency program, Multifamily Rebates, Home Energy Surveys, CheckPoint, California Energy Star New Homes Program, Community Energy Efficiency Program, CARE, and the Medical Baseline Program.  Residential New Construction has worked closely with the Building Industry Institute to strategize on how is the best way to educate the local governments on all SCE’s energy efficient programs. We will be meeting with the Regional Affairs group, the Planning organization, Program Managers for the LGI programs and the Major Customer Account Management (MCAM) group to get their input in how we can work together to promote the programs in 2005.

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Additional Items

None