| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Government Initiatives – PGC |
| Program Number: | 1318-04 |
| Month: | May 2004 |

- Program Status

Program Description

Through a partnering with Local Governments, cities, and local governments (collectively referred to as Jurisdictions), Southern California Edison’s (SCE) Local Government Initiative (LGI) will offer energy efficiency information and education, hardware upgrades, and subsidized energy efficiency improvements to SCE’s small to medium-business owners, lower-to-moderate income residential customers, single and multifamily existing residential consumers, and residential and small commercial builders.

The core of this program approach is to work with the jurisdictions as a delivery channel for SCE's broad portfolio of energy efficiency information, services and incentives, thereby deepening the reach of our program offerings.  However, the added benefit of our partnership approach is that it allows us, working side-by-side with the cities, to customize offerings (either through bundled offerings or modifying individual programs) to either fill a specific need within a Jurisdiction, and/or better reach an identified Hard-to-Reach (HTR) component within a city.  Collaboration with Jurisdictions is an effective adjunct to the utility-to-customer approach used in many of SCE’s programs, leveraging the influence of the Jurisdictions who share similar energy efficiency goals.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,800,000 | $613 | 0% | $22,740 | 1% |  |  | $22,740 | 1% | $1,777,260 |
| Admin | $297,600 | $613 | 0% | $20,906 | 7% |  |  | $20,906 | 7% | $276,694 |
| Marketing | $90,000 |  |  | $1,834 | 2% |  |  | $1,834 | 2% | $88,166 |
| DI | $1,340,400 |  |  |  |  |  |  |  |  | $1,340,400 |
| EM&V | $72,000 |  |  |  |  |  |  |  |  | $72,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Apr-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Completed 2004 Enrollment Forms | 32 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 32 |
| Expand to New Jurisdicition Identified as HTR | 10 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 |
| Conduct Building Department Training or Imformation Updates on 2005 Title 24 Code Revisions | 12 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 12 |
| Coordinate Activities Promoting Residential and Multifamily Retrofit Programs | 10 | 1 | 10% | 3 | 30% | 0 | 0% | 3 | 30% | 7 |
| Coordinate Activities Promoting Nonresidential Programs | 10 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 |

  - Activities/Accomplishments

    - Administrative -

- SCE is currently planning the delivery of this program, both internally and externally.  The XXXXX has been the primary subcontractor for this program and will continue to be in 2004; however, SCE is analyzing ways of better leveraging various internal organizations’ that have regular interface opportunities with local governments (e.g., Public Affairs, Major Customer Division).

    - Marketing –

- On May 4, SCE took part in an Energy Efficiency Summit sponsored by Navigant Consulting.  Navigant Consulting is an independent energy efficiency consulting firm that received funding for a third party local government program in SCE’s service territory.  SCE, along with local, state and federal government agencies, research facilities, and other utilities and energy efficiency consultants gathered to collaborate on a “best practices” approach to helping local governments identify and implement energy efficiency and conservation programs within their communities/jurisdictions.

    - Direct Implementation –

      - Audits, Site Surveys and Partnerships -

SCE’s Local Government Initiative team and Public Affairs met with city councilman Jim Ferguson from Palm Desert.  The city of Palm Desert is growing rapidly and has indicated on their General Plan that anywhere from 4,000 – 6,000 new homes will be constructed within the “Northern Sphere” region of Palm Desert.  The meeting was a discussion to plan a partnership between the building department of Palm Desert and the builders with construction for the city.  The merits of the Community Energy Efficiency Program (CEEP) were reviewed, emphasizing the voluntary nature of the program.  City Councilman Ferguson entertained the idea of providing high density-housing credits for those builders submitting plans meeting the CEEP criteria.  SCE provided Councilman Ferguson with a Draft Resolution, which he then presented to his colleagues.  The Palm Desert City Council voted unanimously to put a condition of approval on the high density proposal.  SCE’s work with the City of Palm Desert is just beginning, but has the potential for significant opportunities.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

The LGI program is coordinating outreach and support of the Express Efficiency program, Multifamily Rebates, Home Energy Surveys, CheckPoint, California Energy Star New Homes Program, Community Energy Efficiency Program, CARE, and the Medical Baseline Program (information is being included on the 2004 fact sheet).

Additionally, SCE continues to work with our own Public Affairs management staff at the event.

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Additional Items

None