| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Government Initiatives – PGC |
| Program Number: | 1318-04 |
| Month: | January 2005 |

- Program Status

Program Description

Through a partnering with Local Governments, cities, and local governments (collectively referred to as Jurisdictions), Southern California Edison’s (SCE) Local Government Initiative (LGI) will offer energy efficiency information and education, hardware upgrades, and subsidized energy efficiency improvements to SCE’s small to medium-business owners, lower-to-moderate income residential customers, single and multifamily existing residential consumers, and residential and small commercial builders.

The core of this program approach is to work with the jurisdictions as a delivery channel for SCE's broad portfolio of energy efficiency information, services and incentives, thereby deepening the reach of our program offerings.  However, the added benefit of our partnership approach is that it allows us, working side-by-side with the cities, to customize offerings (either through bundled offerings or modifying individual programs) to either fill a specific need within a Jurisdiction, and/or better reach an identified Hard-to-Reach (HTR) component within a city.  Collaboration with Jurisdictions is an effective adjunct to the utility-to-customer approach used in many of SCE’s programs, leveraging the influence of the Jurisdictions who share similar energy efficiency goals.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | -$67,883 | -7% | $255,266 | 26% |  |  | $255,266 | 26% | $744,734 |
| Admin | $277,000 | $2,185 | 1% | $46,290 | 17% |  |  | $46,290 | 17% | $230,710 |
| Marketing | $90,000 |  |  | $13,146 | 15% |  |  | $13,146 | 15% | $76,854 |
| DI | $561,000 | -$70,068 | -12% | $193,152 | 34% |  |  | $193,152 | 34% | $367,848 |
| EM&V | $72,000 |  |  | $2,678 | 4% |  |  | $2,678 | 4% | $69,322 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Completed 2004 Enrollment Forms | 32 | 0 | 0% | 18 | 56.3% | 0 | 0% | 18 | 56.3% | 14 |
| Expand to New Jurisdiction Identified as HTR | 10 | 0 | 0% | 3 | 30% | 0 | 0% | 3 | 30% | 7 |
| Conduct Building Department Training or Imformation Updates on 2005 Title 24 Code Revisions | 12 | 0 | 0% | 6 | 50% | 0 | 0% | 6 | 50% | 6 |
| Coordinate Activities Promoting Residential and Multifamily Retrofit Programs | 10 | 0 | 0% | 5 | 50% | 0 | 0% | 5 | 50% | 5 |
| Coordinate Activities Promoting Nonresidential Programs | 10 | 0 | 0% | 5 | 50% | 0 | 0% | 5 | 50% | 5 |

  - Activities/Accomplishments

    - Administrative –

- SCE continues to work closely with XXXXX and the XXXXX to strategize the best way to market the LGI to local governments. We are coordinating outreach events in both Mission Viejo and Palm Springs for February. We are also discussing a future outreach event in the City of Santa Clarita as well as attending CALBO (Building Officials organization) in February. We anticipated Building Energy Code Training to begin in January, however, CALBO, who is helping organize the trainings needed to cancel for the January sessions. We are anticipating beginning training starting in February and throughout the year.

    - Marketing –

- RNC worked closely with Business Resources and Corporate Communications and are now set with all marketing materials that we will need for 2005. Lisa Brewer also worked with Corporate Communications to ensure that the website was updated with 2005 information.

    - Direct Implementation –

      - Audits, Site Surveys and Partnerships -

- SCE will continue to work with the XXXXX on the outreach and implementation of this program, particularly in those areas with significant building activity.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

RNC is working closely with XXXXX of M&E on the LGI program and what changes and enhancement we can add to the LGI a more valuable and helpful to our local governments. We are working with Public Affairs and attended their quarterly meeting to explain the value of the LGI program and solicit their support. LGI is willing to work directly with the Public Affairs organization on outreach events, city meetings and any other support they may need. RNC feels that in 2005 we will be able to reach more local governments and provide more value than in the past. Having additional internal support at SCE as well as external support at XXXXX and the XXXXX will allow us to spend more time interfacing and supporting the cities.

- Program Challenges

The SCE challenge is working more closely with both internal and external organizations to promote the value of the LGI program.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- RNC has continued to work closely with internal and external groups to promote the LGI program. XXXXX and XXXXX of the Colorado Energy Group did a presentation before the City of Commerce City Council on 1/4/2005. The City Council was most definitely interested in all of the SCE energy efficiency programs (both residential and nonresidential were highlighted) and made the decision to enroll in the LGI program. On January 18th the Commerce City Council added a resolution to the City’s bylaws  to promote energy efficiency throughout their community. XXXXX has received 2 additional re-enrollment forms from Westminster and Corona.

- Changes to Subcontractors or Staffing

XXXXX has joined the staff of RNC to work on all of RNC’s New Construction program. She will be working closely in particular, on the LGI program.

- Additional Items

None