| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | County of Los Angeles/SCE/SCG Partnership - PGC |
| Program Number: | 1321-04 |
| Month: | April 2005 |

- Program Status

Program Description

The County of Los Angeles, Southern California Edison Company, and Southern California Gas Partnership will continue to implement energy efficiency projects in existing County facilities and leverage the County’s existing energy management infrastructure. The County maintains an “in-house” energy management organization including administrators, project managers, energy analysts, technical support, and facility databases.  The County has implemented its Enterprise Energy Management Information System – a “real-time,” internet-based energy management program that archives and displays detailed facility consumption and operations information.  The County’s energy management organization maintains relationships with all 38 County departments, other County affiliated agencies (including the Office of Education, Public Housing, Metropolitan Transit Authority, Office of Small Business), and other local governments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,000,000 | $63,815 | 2% | $387,619 | 13% | $1,771,879 | 59% | $2,159,498 | 72% | $2,612,380 |
| Admin | $298,401 | $16,155 | 5% | $157,349 | 53% |  |  | $157,349 | 53% | $141,052 |
| Marketing | $2 |  |  |  |  |  |  |  |  | $2 |
| DI | $2,580,333 | $46,010 | 2% | $212,212 | 8% | $1,771,879 | 69% | $1,984,092 | 77% | $2,368,120 |
| EM&V | $121,264 | $1,650 | 1% | $18,058 | 15% |  |  | $18,058 | 15% | $103,206 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Apr-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,902 |  |  | 111 | 6% | 1,313 | 69% | 1,424 | 75% | 1,791 |
| Annual kWh | 4,723,641 |  |  | 348,603 | 7% | 3,294,332 | 70% | 3,642,934 | 77% | 4,375,038 |
| Lifecyc kWh | 73,304,294 |  |  | 5,577,643 | 8% | 51,335,241 | 70% | 56,912,884 | 78% | 67,726,651 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Retro-Commissioning Element –

  - XXXXX was selected to implement the RCx element.  The Scope of work includes RCx of 10 County of LA buildings at approximately 1.5 million square feet with a net energy savings of 941 kW and 1.822 MWh.

  - XXXXX aggressively started their implementation with site audits, interviews, and review of building and energy data to create a bench marking report for all 10 buildings.  The whole-building benchmarking reports have been finalized.  These reports benchmarked current building operation with comparable buildings in the industry.  Additional work is being performed for system-level benchmarking and the report shall be included with the pre-functional test plan reports.  Various planning reports were developed for the overall retro-commissioning plan, pre-functional test plan and functional test plan.  The planning report presents the equipment deficiencies identified in the audits and also included the implementation schedule for each building. A pre-functional test plan identifies and provides opportunities to resolve pertinent system operational issues prior to proceeding to the functional test phase.

  - Southern California Gas (SCG) and the County of LA are coordinating the implementation of gas measures in various county buildings. The County has a list of projects where therm savings may be captured by increasing the efficiency of the specified boilers to higher efficiency units.  Under this scenario, an incentive approach would be considered instead of direct installation.  The partners are in the process of determining the feasibility of paying for the incremental cost to install higher efficiency boilers.  Additional boilers, not included in the list, are also being considered for replacement. The partners are in the process of drafting an RFP to select a boiler installation contractor for the boiler replacement projects.

- Retrofit Element

  - Retrofit element has 3 different components (lighting, building-wide lighting controls, chillers)

  - A purchase order was executed with XXXXX.

  - The XXXXX scope of work for lighting retrofit element is for 36 libraries and 5 Fire stations with total square footage of 368,403. Additional facilities will be added contingent on availability of funds.

  - Work for group 1 buildings was completed in January and the reported actual energy savings is 348,603 kWh and 111 kW.  Group 2 and 3 have been audited. Group 2 and 3 buildings have a committed energy savings of  919,628 kWh and 295 kW. Additional buildings (Group 4) will be considered for implementation due to availability of funds and the requirement of additional energy savings to meet the lighting retrofit element program goal.  It is important to note that the measure count for group 1 that was reported in January was modified subsequent to the January reporting period.  There was a change in the as-built reports.  Unfortunately, the workbook does not allow for a negative number in the fields to make an adjustment in subsequent reporting period.  As such, the total implemented measures were accounted for in Group 2 and 3.  Upon the completion of the Groups 2 and 3, the installed measures for Group 1, 2 and 3 will be shown in the workbook.  The estimated energy saving and demand reduction for all the measures for the 3 groups is 1,268,230 kWh and 406 kW.

  - A purchase order with XXXXX was executed on January 27, 2005 for the Chiller and Building-Wide-Lighting Control (BWLC) retrofit projects.

  - The BWLC scope of work is for two buildings.  Ferguson Health Administration Center will receive the BWLC equipment. The Edmund D. Edelman Children’s court also received BWLC equipment with additional occupancy sensor strategy.  The impacted office space will be 543,930 sq. ft.. The committed net energy savings for the BWLC project is 439,495 kWh with no reportable demand (kW) reduction. XXXXX has completed the initial design of the BWLC for the two buildings. Project implementation will commence upon the approval of project submittals.  This is expected to occur in mid June.

  - The Scope of work for chiller retrofit will include the replacement of 2 chillers (235 tons) in two County of Los Angeles buildings (Dorothy Kirby, and ISD Headquarter). The committed net energy savings for the Chiller projects are 112,228 kWh and 77 kW. XXXXX has completed the initial design of the two chiller projects. Project implementation will commence upon the approval of project submittals.  This is expected to occur in mid June as well.

- Public Agency Feasibility Study and Technology Transfer Element

  - Partners have commenced the activities for the feasibility study.  A cover letter and questionnaire was developed to solicit information from potential public agency participants.

  - An on-line survey service was selected to facilitate the data collection process.  The cover letter with a link to the questionnaire site had been emailed to about 400 public agency representatives within the Government and Institution segment of SCE's service territory.  The survey can be viewed at http://www.surveymonkey.com/s.asp?u=5532732588.

  - The partners delivered a successful workshop to 135 public agency representatives, on Wednesday, April 20, 2005 at the Pacific Palms Resort in City of Industry. The workshop presented the results of the feasibility study to prominent public agency officials as well as CPUC and CEC commissioners and representatives from state agencies.  The feedback received from the attendees was very positive.

  - The following speakers presented at the workshop: Commissioner XXXXX h – CPUC, Commissioner XXXXX - CEC, Joe Desmond – State of California Deputy Secretary of Energy, XXXXX – LA County Supervisor, and XXXXX – Assemblyperson – 40th District.

  - The contractor and the County, on behalf of the partners interviewed participants and other people with knowledge about public agency energy efficiency coordination efforts. The contractor had interviewed 42 public agency energy staff from 21 organizations and is in the process of drafting up a final report for the feasibility study.

- Public Housing, Multi Family Metering Element

  - All the partners (SCE/SCG/LACo), including USCL and the Los Angeles County Community Development Commission are on board with the project scope. The scope includes:

    - Meter acceptance testing, purchase and installation of meters,

    - Installation of optical sensors and display units.

    - Los Angeles CDC’s involvement in identifying and providing access to public housing facilities for meter, sensor, and display installation. CDC will also provide notifications and assist in training of tenants on how to fully utilize the LCD display to encourage positive behavioral changes in conservation and to use appliances more efficiently.

    - SCE Emerging Technologies (ET) Group will establish an evaluation protocol to study the impacts of this meter and display technology.  Project will evaluated a test case and a control case for each of the five facilities. Each facility will have an equal number of tenants with meters and without meters. Energy usage analysis will be conducted for all participating tenants to establish the pre and post impacts of the project. ET will generate a final report for the project.

  - SCE completed the meter validation process for the Landis & Gyr Focus 2S meter in mid January.  The meter was approved through SCE material handling system and is ready for installation.

  - About 350 Meters were planned to be installed in 5 different districts within the County of LA. There will be an additional 383 tenants (without meters) that will serve as control cases for the study.

  - Partners had a minor set back with selection of installation sites for the project.  Some of the original buildings scoped for the project had a different meter configuration than the one approved for installation.  As such, the LA County Community Development Commission has identified a complex that uses the L&G Focus 2S meters.  However, this site will only accommodate 100 meters for the project. The partners will proceed with implementation of the 100 Focus 2S meters in the identified site but will continue to look for additional sites that will accommodate the Focus 12S meters.

  - The partners have identified the list of tenants to will receive the meters.  A final list will be generated upon the verification of SCE meter number with the associated apartment number.  This is expected to be completed in the first week of June.  The delivery date for the 100 Focus 2S meters have been changed from early May to mid June.

  - The partners will test another type of meter (L&G Focus 12S network meter) to account for the remainder of the 250 meters required for the project. This meter will be subjected to the rigorous meter validation process.  The Focus 12S meter will start testing in late May and will be completed by late September.  As such, there will be a delay in implementation of the 250 meters by about 3 to 4 months.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Measures Installed in April 2005 |
| --- | --- |
| HID Retrofit | 0 |
| Exit Light Retrofit | 0 |
| T-12 to T8 | 0 |
| Incandescent to Compact Flourescent | 0 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

- Based on input from the evaluation project kick-off meeting and from other discussions with the SCE project manager, RLW modified their proposed scope of work and submitted a Revised Work Plan to the Energy Division and their Master Evaluation Contract Team (MECT) for approval on August 9, 2004, the deadline set by the ALJ in her ruling.  The MECT comments on the plan were sent back to the evaluation team on August 20, 2004 and we have had several phone conversations with MECT representatives and among the evaluation project staff.  The MECT comments had to do with parts of the plan that do not completely correspond to specific M&E requirements in the Energy Efficiency Policy Manual.  To meet the requirements, we need only to add some clarifying text.

- A Revised Work Plan was submitted for approval to the Energy Division's Master Evaluation Contract Team (MECT) on November 12, 2004.  On November 18, 2004, the MECT recommended that the M&E plan be approved by the CPUC.

- Coordination has begun between the retro-commissioning and retrofit contractors and the evaluation team.

- RLW completed the 2004 year-end EM&V report.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

- XXXXX (XXXXX) was the subcontractor for the Feasibility Study and Technology Transfer Workshop element.  Due to XXXXX appointment as CPUC commissioner, XXXXX has terminated all services with its clients.  As such, SCE’s purchase order with XXXXX had been cancelled.

- XXXXX was the primary XXXXX contact to implement this program element. She had been instrumental in coordinating the various aspects of the study.  As such, the partners wanted to retain her services and avoid any program implementation delays.  XXXXX will continue this effort with a new SCE purchase order under XXXXX.

- Additional Items

As noted above in Section 1.2.1 under the Retro-commissioning element, the partners will be providing financial assistance to off-set the cost for purchase and installation of more energy efficient gas retrofit measures compare to those specified for the projects.  This is a deviation from the approved PIP where no incentive payments were specified, only 100% direct installation.