| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | County of Los Angeles/SCE/SCG Partnership - PGC |
| Program Number: | 1321-04 |
| Month: | February 2005 |

- Program Status

Program Description

The County of Los Angeles, Southern California Edison Company, and Southern California Gas Partnership will continue to implement energy efficiency projects in existing County facilities and leverage the County’s existing energy management infrastructure. The County maintains an “in-house” energy management organization including administrators, project managers, energy analysts, technical support, and facility databases.  The County has implemented its Enterprise Energy Management Information System – a “real-time,” internet-based energy management program that archives and displays detailed facility consumption and operations information.  The County’s energy management organization maintains relationships with all 38 County departments, other County affiliated agencies (including the Office of Education, Public Housing, Metropolitan Transit Authority, Office of Small Business), and other local governments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,000,000 | $12,293 | 0% | $130,662 | 4% | $914,618 | 30% | $1,045,280 | 35% | $2,869,338 |
| Admin | $298,401 | $11,039 | 4% | $128,831 | 43% |  |  | $128,831 | 43% | $169,570 |
| Marketing | $2 |  |  |  |  |  |  |  |  | $2 |
| DI | $2,580,333 |  |  | $551 | 0% | $914,618 | 35% | $915,169 | 35% | $2,579,781 |
| EM&V | $121,264 | $1,254 | 1% | $1,279 | 1% |  |  | $1,279 | 1% | $119,985 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,902 |  |  | 111 | 6% | 1,047 | 55% | 1,158 | 61% | 1,791 |
| Annual kWh | 4,723,641 |  |  | 348,603 | 7% | 2,149,142 | 45% | 2,497,745 | 53% | 4,375,038 |
| Lifecyc kWh | 73,304,294 |  |  | 5,577,643 | 8% | 32,563,298 | 44% | 38,140,941 | 52% | 67,726,651 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Retro-Commissioning Element –

  - XXXXX. was selected to implement the RCx element.  The Scope of work includes RCx of 10 County of LA buildings at approximately 1.5 million square feet with a net energy savings of 941 kW and 1.882 MkWh.

  - XXXXX aggressively started their implementation with site audits, interviews, and review of building and energy data to create a bench marking report for all 10 buildings.  The whole-building benchmarking reports have been finalized.  These reports benchmarked current building operation with comparable buildings in the industry.  Additional work is being performed for system-level benchmarking and the report shall be included with the pre-functional test plan reports.  Various planning reports were developed for the overall retro-commissioning plan, pre-functional test plan and functional test plan.  The planning report presents the equipment deficiencies identified in the audits and the implementation schedule for each building. A pre-functional test plan identifies and provides opportunities to resolve pertinent system operational issues prior to proceeding to the functional test phase.

  - Southern California Gas (SCG) and the County of LA are coordinating the implementation of gas measures in various county buildings. The gas measures will include: hot water heaters, instantaneous hot water heaters, hot water boilers and boiler controllers. SCG has scheduled site visits on March 24, 2005 to assess the performance of existing gas boilers in three County buildings.

- Retrofit Element

  - Retrofit element has 3 different components (lighting, building-wide lighting controls, chillers)

  - A purchase order was executed with XXXXX and a Kick-Off meeting was held on December 6, 2004 to commence the Lighting Retrofit Element.

  - The  XXXXX scope of work for lighting retrofit element is for 36 libraries and 5 Fire stations with total square footage of 368,403. Additional facilities will be added contingent on availability of funds.

  - Work for group 1 buildings was completed in January and the reported actual energy savings is 348,603 kWh and 111 kW.  Group 2 and 3 have been audited and Group 2 buildings have a committed energy savings of 326,162 kWh and 105 kW. The team will select a vendor to implement the lighting retrofit element and execute a purchase order by the end of November.

  - A purchase order with XXXXX was executed on January 27, 2005 for the Chiller and Building-Wide-Lighting Control retrofit projects. A kick-off meeting was held on February 1, 2005 with XXXXX and all the stakeholders to discuss project roles and responsibilities, project coordination and implementation timeline.

  - The BWLC scope of work is for two buildings.  One building (Ferguson Health Administration Center) will receive the BWLC equipment. However, occupancy sensor strategy will be implemented for the second building (Edmund D. Edelman Children’s court).  The estimated net energy saving for the BWLC project is 512,370 kWh with no reportable demand (kW) reduction.

  - The Scope of work for chiller retrofit will include the replacement of 2 chillers (230 tons) in two County of Los Angeles buildings (Dorothy Kirby, and ISD Headquarter). The estimated net energy savings for the Chiller projects are 242,850 kWh and 62 kW.

  - Public Agency Feasibility Study and Technology Transfer Element

  - Partners have commenced the activities for the feasibility study.  A cover letter and questionnaire was developed to solicit information from potential public agency participants.

  - The partners selected an on-line survey service to facilitate the data collection process.  The cover letter with a link to the questionnaire site has been emailed to about 400 public agency representatives on the Government and Institution segment of SCE's service territory.  To date, about 80 entities have responded to the on-line survey. The survey can be viewed at http://www.surveymonkey.com/s.asp?u=5532732588.

  - A workshop is also being planned to present the results of the study to prominent public agency officials as well as CPUC and CEC commissioners and representatives from state agencies.  The date of the workshop is Wednesday, April 20, 2005 at the Pacific Palms Resort in City of Industry.

  - The following speakers have been confirmed to speak at the workshop: Commissioner XXXXX – CPUC, Commissioner XXXXX, CEC, XXXXX – State of California Deputy Secretary of Energy, XXXXX – LA County Supervisor, and XXXXX – Assemblyperson – 40th District.

  - The contractor and the County, on behalf of the partners, commenced interviews with possible participants and other people with knowledge about  public agency energy efficiency coordination efforts. The contractor has set up interviews with public agency energy staff for early March.

- Public Housing, Multi Family Metering Element

  - All the partners (SCE/SCG/LACo), including USCL and the Los Angeles County Community Development Commission are on board with the project scope. The scope includes:

    - Meter acceptance testing, purchase and installation of meters,

    - Installation of optical sensors and display units.

    - Los Angeles CDC’s involvement in identifying and providing access to public housing facilities for meter, sensor, and display installation. CDC will also provide notifications and assist in training of tenants on how to fully utilize the LCD display to encourage positive behavioral changes in conservation and to use appliances more efficiently.

    - SCE Emerging Technologies (ET) Group will establish an evaluation protocol to study the impacts of this meter and display technology.  Project will evaluated a test case and a control case for each of the five facilities. Each facility will have an equal number of tenants with meters and without meters. Energy usage analysis will be conducted for all participating tenants to establish the pre and post impacts of the project. ET will generate a final report for the project.

  - SCE completed the meter validation process for the Landis & Gyr Focus 2S meter in mid January.  The meter was approved through SCE material handling system and is ready for installation.

  - About 350 Meters were planned to be installed in 5 different districts within the County of LA. There will be an additional 383 tenants (without meters) that will serve as control cases for the study.

  - Partners had a minor set back with selection of installation sites for the project.  Some of the original buildings scoped for the project had a different meter configuration than the one approved for installation.  As such, the LA County Community Development Commission has identified a complex that uses the L&G Focus 2S meters.  However, this site will only accommodate 100 meters for the project. The partners will proceed with implementation of the 100 Focus 2S meters in the identified site but will continue to look for additional sites that will accommodate the Focus 12S meters.

  - The partners will test another type of meter (L&G Focus 12S network meter) to account for the remainder of the 250 meters required for the project. This meter will be subjected to the rigorous meter validation process.  As such, there will be a delay in implementation of the 250 meters by about 3 to 4 months.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Measures Installed in February 2005 |
| --- | --- |
| HID Retrofit | 49 |
| Exit Light Retrofit | 23 |
| T-12 to T8 | 1448 |
| Incandescent to Compact Flourescent | 165 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

- Based on input from the evaluation project kick-off meeting and from other discussions with the SCE project manager, XXXXX modified their proposed scope of work and submitted a Revised Work Plan to the Energy Division and their Master Evaluation Contract Team (MECT) for approval on August 9, 2004, the deadline set by the ALJ in her ruling.  The MECT comments on the plan were sent back to the evaluation team on August 20, 2004 and we have had several phone conversations with MECT representatives and among the evaluation project staff.  The MECT comments had to do with parts of the plan that do not completely correspond to specific M&E requirements in the Energy Efficiency Policy Manual.  To meet the requirements, we need only to add some clarifying text.

- A Revised Work Plan was submitted for approval to the Energy Division's Master Evaluation Contract Team (MECT) on November 12, 2004.  On November 18, 2004, the MECT recommended that the M&E plan be approved by the CPUC.

- Coordination has begun between the retro-commissioning and retrofit contractors and the evaluation team.

- RLW is in the process of drafting a 2004 year-end EM&V report.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

- XXXXX (XXXXX) was the subcontractor for the Feasibility Study and Technology Transfer Workshop element.  Due to XXXXX appointment as CPUC commissioner, XXXXX has terminated all services with its clients.  As such, SCE’s purchase order with XXXXX had been cancelled.

- XXXXX was the primary XXXXX contact to implement this program element. She had been instrumental in coordinating the various aspects of the study.  As such, the partners wanted to retain her services and avoid any program implementation delays.  XXXXX will continue this effort with a new SCE purchase order under XXXXX.

- Additional Items

None