| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | CU/CSU Partnership Program – PGC |
| Program Number: | 1324-04 |
| Month: | November 2004 |

- Program Status

Program Description

The University of California/California State University (UC/CSU) and Investor-Owned Utility (IOU) Energy Efficiency Partnership is a unique, statewide energy efficiency program that accomplishes immediate, long-term energy efficiency and demand savings, and establishes a permanent framework for a sustainable  comprehensive energy management program at the thirty three (33) UC and CSU campuses served by California’s four large IOUs.  This program capitalizes on the vast resources and expertise of the UC/CSU and the California IOU’s to ensure a successful and cost effective program that meets all objectives of the California Public Utilities Commission (CPUC or Commission) as articulated in Decision 03-08-067. In lays the groundwork for not only a continued UC/CSU comprehensive energy efficiency program but also establishes a model for statewide partnership programs and will allow expansion of this program to California’s community colleges in the next funding cycle. The UC/CSU/IOU partnership program is comprised of three elements, which will operate on a statewide, integrated basis, providing immediate energy savings and setting the foundation for a long-term program focused on sustainability and best practices: Energy Efficiency Retrofits, Facility Retro-and Continuous Commissioning, and Energy Efficiency Education and Best Practices Development and Training.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,500,000 | $395,098 | 9% | $2,203,734 | 49% | $3,079,076 | 68% | $5,282,809 | 117% | $2,296,266 |
| Admin | $618,540 | $59,076 | 10% | $501,285 | 81% |  |  | $501,285 | 81% | $117,255 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $3,746,460 | $323,750 | 9% | $1,641,706 | 44% | $3,079,076 | 82% | $4,720,781 | 126% | $2,104,755 |
| EM&V | $135,000 | $12,272 | 9% | $60,743 | 45% |  |  | $60,743 | 45% | $74,257 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,004 |  |  |  |  | 1,858 | 185% | 1,858 | 185% | 1,004 |
| Annual kWh | 6,817,104 |  |  |  |  | 6,445,159 | 95% | 6,445,159 | 95% | 6,817,104 |
| Lifecyc kWh | 102,778,298 |  |  |  |  | 109,853,096 | 107% | 109,853,096 | 107% | 102,778,298 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

Activities/Accomplishments –

- The Management Team approved the UCSD MBCx proposal at their November 3 meeting.  This project consists of retro-commissioning of the Central Utilities Plant Secondary Chilled Water Supply & Return System and the Sciences and Engineering Research Facility laboratory VAV and exhaust system.

- The MBCx Team, with the help of PECI, held two one-day workshops this month (November 17 at Cal Poly Pomona and November 18 at UC Davis) to assist campus staff in the completion of the Building Nomination Form for MBCx funding.  The workshops were well attended and the participating campuses were able to complete project submittals by the November 30 deadline.  A total of thirty-five projects were submitted for consideration and will be reviewed by the MBCx team by early December.

- The “Exceeding Title 24 for Project Managers Course” was held on November 5 at SCE’s CTAC facility, November 16 at UC Davis and November 17 at UC Merced.  Overall, the course was well attended.

- The T&E Team has issued an announcement regarding the “Labs21 High Performance, Low-Energy Design Course” to be held December 13 at UC Merced and December 14 at Sempra’s Energy Resource Center.  The course is a full-day workshop that introduces strategies for designing and constructing sustainable laboratories in both new and existing facilities.  The T&E Team also agreed upon an overall approach to the 2005 T&E program and budget.

- Work continued on development of a program web site.

    - Marketing -

A news article was provided for the California Commissioning Collaborative’s website providing an update on the MBCx activity.  The article is currently available at http://www.cacx.org.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

Values shown in the workbook do not accurately represent reality at the campus level.  Through October, the total signed commitments to the campuses equal $1,201,161.  The net projected energy savings are 2,893,751 kWh (42% of goal) and 785 kW (78% of goal).  These are obtained as follows:

- T-12 to T-8 Retrofit:

  - Campus project to retrofit 17,884 T12 fixtures.  Campus’ cost estimate of $26 per fixture differs greatly from the workbook estimate of $84 per fixture.  Total estimated project costs are $403,754. Net projected energy savings for the project are 868,530 kWh and 246 kW.

  - Campus project to retrofit existing T12 fixtures with 3,936 T8 fixtures.  Estimated project cost of $674,430 was provided by the campus.  Net projected energy savings for the project are 811,574 kWh and 132 kW.

- LED Exit Sign Retrofit: Actual measure funded was for LED traffic signal retrofit at a cost of $250 per unit (total of red, amber and green lights).  This is slightly higher than the $203 estimate for an exit sign.  Total estimated project costs are $60,000.  Net projected energy savings for the project are 54,416 kWh and 6.4 kW.

- Incandescent to CFL Retrofit: Actual measure funded was for an incandescent to fluorescent retrofit with occupancy sensors at 450 toilet rooms throughout the campus.  Installed cost per unit provided by the campus was $600 per toilet room.  Total estimated project costs are $270,000.  Net projected energy savings for the project are 425,526 kWh and 73 kW.

- Chiller Replacement:	Actual measure funded was five chiller/cooling tower optimization controllers at a cost of just over $18,000 per chiller.  Total estimated project costs are $91,907.  Net projected energy savings for the project are 627,691 kWh and 300 kW.

- HID to T5 Retrofit: Two measures were funded.  One was to replace 32 MH fixtures with 18 T5 (F54T5/HO) and the other was to replace 76 500 W quartz fixtures with 71 F32T8 fixtures.  Estimated project cost of $44,375 was provided by the campus.  Net projected energy savings for the project are 106,014 kWh and 28 kW.

    - EM&V

- The EM&V impact evaluation consultants (SBW) have selected the Retrofit Projects they are sampling and started contacting campuses in November; they will also be evaluating the two MBCx projects approved so far (UCSD and CSU Sonoma).

- In addition, the process evaluation consultant (XXXXX and her staff) started interviewing team members.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The partnership has renamed this program element as “Monitoring Based Commissioning” (MBC) to better reflect the actual scope of the activity.  The program goals and overall approach remain the same.