| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | CU/CSU Partnership Program – PGC |
| Program Number: | 1324-04 |
| Month: | February 2005 |

- Program Status

Program Description

The University of California/California State University (UC/CSU) and Investor-Owned Utility (IOU) Energy Efficiency Partnership is a unique, statewide energy efficiency program that accomplishes immediate, long-term energy efficiency and demand savings, and establishes a permanent framework for a sustainable  comprehensive energy management program at the thirty three (33) UC and CSU campuses served by California’s four large IOUs.  This program capitalizes on the vast resources and expertise of the UC/CSU and the California IOU’s to ensure a successful and cost effective program that meets all objectives of the California Public Utilities Commission (CPUC or Commission) as articulated in Decision 03-08-067. In lays the groundwork for not only a continued UC/CSU comprehensive energy efficiency program but also establishes a model for statewide partnership programs and will allow expansion of this program to California’s community colleges in the next funding cycle. The UC/CSU/IOU partnership program is comprised of three elements, which will operate on a statewide, integrated basis, providing immediate energy savings and setting the foundation for a long-term program focused on sustainability and best practices: Energy Efficiency Retrofits, Facility Retro-and Continuous Commissioning, and Energy Efficiency Education and Best Practices Development and Training.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,500,000 | $553,672 | 12% | $3,161,169 | 70% | $5,866,811 | 130% | $9,027,980 | 201% | $1,338,831 |
| Admin | $618,540 | $53,796 | 9% | $709,099 | 115% |  |  | $709,099 | 115% | -$90,559 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $3,746,460 | $488,050 | 13% | $2,364,999 | 63% | $5,866,811 | 157% | $8,231,810 | 220% | $1,381,461 |
| EM&V | $135,000 | $11,826 | 9% | $87,071 | 64% |  |  | $87,071 | 64% | $47,929 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Feb-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,004 | 267 | 27% | 267 | 27% | 2,403 | 239% | 2,670 | 266% | 737 |
| Annual kWh | 6,817,104 | 825,143 | 12% | 825,143 | 12% | 11,381,929 | 167% | 12,207,072 | 179% | 5,991,961 |
| Lifecyc kWh | 102,778,298 | 13,202,289 | 13% | 13,202,289 | 13% | 184,098,219 | 179% | 197,300,508 | 192% | 89,576,010 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

Activities/Accomplishments –

- The “Integrated Building Design” course was held in Oakland on February 1 and in Irvine on February 15.  This course was developed for university project managers and explored the concept of integrated building design as it relates to new construction projects, emphasizing the reduction of electrical lighting and HVAC loads through the design and implementation of inter-related building envelope systems.  Over 60 people attended the two sessions.

- The MBCx Team released a generic Scope of Work document for use by the campuses.  The document can be customized for each particular MBCx project and is intended to be an attachment to the campus’ normal contract boilerplate document.

- The Management Team approved a retrofit project at UC Davis.

- The Executive Team has identified a replacement for the project management role formally performed by XXXXX.  The details, including the extent of the project manager’s scope and the available budget are being finalized.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

Values shown in the workbook or in the above tables do not accurately represent reality at the campus level.  Through January 2005, the total signed commitments to the campuses equal $2,492,629.  This includes $1,334,029 for Retrofit (this amount represents the total amount committed by the program and does not reflect any campus co-funding contributions.  By including the combined campus contribution of $448,504, the true overall project cost is $1,782,533) and $1,158,600 for MBCx. The net projected energy savings for the portfolio of projects are 5,489,942 kWh (81% of goal) and 883 kW (88% of goal).  These totals are obtained as follows:

- T-12 to T-8 Retrofit:

  - At the present time, this campus project has been scaled back significantly from 17,884 T12 fixtures to 8,889 T12 fixtures.  The campus’ original cost estimate of $26 per fixture proved far too low upon further analysis and the amount allocated to the campus cannot fund the original scope.  The net projected energy savings for the project are revised downward from 868,530 kWh to 304,830 kWh and from 246 kW to 80.8 kW.  Total estimated project costs were revised to $446,311, but the amount of funding provided to the campus remains unchanged at $403,754.

  - This campus project to retrofit existing T12 fixtures with 3,936 T8 fixtures has been completed.  Project cost of $674,430 was provided by the campus.  Upon final verification, the net project savings were revised downward from 811,574 kWh to 737,794 kWh and from 132 kW to 129.6 kW.

  - Campus project to retrofit 3,000 2, 3, and 4 lamp T8 fixtures with advanced T8s.  Total estimated project costs are $66,330.  Net projected energy savings are 125,558 kWh and 32 kW.

- LED Exit Sign Retrofit: Actual measure funded was for LED traffic signal retrofit at a cost of $250 per unit (total of red, amber and green lights).  This is slightly higher than the $203 estimate for an exit sign.  Total estimated project costs are $60,000.  Net projected energy savings for the project are 54,416 kWh and 6.4 kW.

- Incandescent to CFL Retrofit: Actual measure funded was for an incandescent to fluorescent retrofit with occupancy sensors at 450 toilet rooms throughout the campus.  Installed cost per unit provided by the campus was $600 per toilet room.  Total estimated project costs are $270,000.  Net projected energy savings for the project are 425,152 kWh and 73 kW.

- Chiller Replacement:	Actual measure funded was five chiller/cooling tower optimization controllers at a cost of just over $18,000 per chiller.  Total estimated project costs are $91,907.  Net projected energy savings for the project are 627,691 kWh and 300 kW.

- HID to T5 Retrofit:

  - Campus project includes two separate retrofits.  One was to replace 32 MH fixtures with 18 T5 (F54T5/HO) and the other was to replace 76 500 W quartz fixtures with 71 F32T8 fixtures.  Estimated project cost of $44,375 was provided by the campus.  Net projected energy savings for the project are 106,014 kWh and 28 kW.

  - Campus project includes retrofitting a combination of MH and HPS fixtures with T5 fixtures. A total of 295 HPS fixtures will be replaced with 234 T5 fixtures and 392 HPS fixtures will be replaced with 263 T5 fixtures.  Total estimated project costs are $33,180.  Net projected energy savings are 38,330 kWh and 5.4 kW.

- VAV Retrofit:  Retrofit project is to convert an existing gym HVAC system to a VAV system.  Total estimated project cost is $96,000.  Net projected energy savings for the project are 124,857 kWh and 0 kW.

- MBCx Projects.  Various campus MBCx projects have resulted in commitments for 3,939,344 square feet.  This represents an estimated savings of 2,945,300 kWh and 229 kW.  The total combined project costs for these savings are $1,158,600.

The most current project information is always available at http://www.uccsuiouee.org/

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The partnership has renamed this program element as “Monitoring Based Commissioning” (MBC) to better reflect the actual scope of the activity.  The program goals and overall approach remain the same.