| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | CU/CSU Partnership Program – PGC |
| Program Number: | 1324-04 |
| Month: | July 2004 |

- Program Status

Program Description

The University of California/California State University (UC/CSU) and Investor-Owned Utility (IOU) Energy Efficiency Partnership is a unique, statewide energy efficiency program that accomplishes immediate, long-term energy efficiency and demand savings, and establishes a permanent framework for a sustainable  comprehensive energy management program at the thirty three (33) UC and CSU campuses served by California’s four large IOUs.  This program capitalizes on the vast resources and expertise of the UC/CSU and the California IOU’s to ensure a successful and cost effective program that meets all objectives of the California Public Utilities Commission (CPUC or Commission) as articulated in Decision 03-08-067. In lays the groundwork for not only a continued UC/CSU comprehensive energy efficiency program but also establishes a model for statewide partnership programs and will allow expansion of this program to California’s community colleges in the next funding cycle. The UC/CSU/IOU partnership program is comprised of three elements, which will operate on a statewide, integrated basis, providing immediate energy savings and setting the foundation for a long-term program focused on sustainability and best practices: Energy Efficiency Retrofits, Facility Retro-and Continuous Commissioning, and Energy Efficiency Education and Best Practices Development and Training.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,500,000 | $892,576 | 20% | $1,135,788 | 25% | $1,502,256 | 33% | $2,638,044 | 59% | $3,364,212 |
| Admin | $618,540 | $62,913 | 10% | $289,983 | 47% |  |  | $289,983 | 47% | $328,557 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $3,746,460 | $825,661 | 22% | $825,661 | 22% | $1,502,256 | 40% | $2,327,917 | 62% | $2,920,799 |
| EM&V | $135,000 | $4,002 | 3% | $20,144 | 15% |  |  | $20,144 | 15% | $114,856 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jul-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,004 |  |  |  |  | 1,213 | 121% | 1,213 | 121% | 1,004 |
| Annual kWh | 6,817,104 |  |  |  |  | 3,749,202 | 55% | 3,749,202 | 55% | 6,817,104 |
| Lifecyc kWh | 102,778,298 |  |  |  |  | 59,987,228 | 58% | 59,987,228 | 58% | 102,778,298 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

Activities/Accomplishments –

- A kickoff meeting with the EM&V contractor, SBW Consulting, Inc., was held to discuss the EM&V plan which was submitted to the Commission on July 21, 2004.

- The Master Agreement has been fully executed by all six partners.  Invoices for 2004 administrative funds have been submitted by the UC and CSU to the IOUs.

- The Management Team approved a third round of retrofit projects on July 15, 2004.  A total of three projects were pre-screened and submitted by the Retrofit Team.  The three campuses submitted for approval were Cal State Long Beach, Cal Poly San Luis Obispo and Cal State Fresno.  Estimated savings for this third round of projects are approximately 350 kW, 3,200,000 kWh and 5,800 therms with approximately $700,000 in additional statewide direct implementation budget being committed.  The next round of project approvals is slated for early August.

- The MBCx team has decided to contract with PECI as a consultant to help campuses identify potential MBCx projects and prepare submittal packages for the MBCx team to review.  The final contract should be in place in August.

- The MBCx team has created a document library that will be hosted on a password protected UCOP server.  The document library will maintain current revisions of documents in a central place for all team members to review.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

The gross energy savings estimated from the retrofit of 17,884 T-12 to T-8 fixtures listed on sheet tab 2A-RecordedEEActivities is estimated to be 1,085,662 kWh and the gross demand reduction is 307 kW.  These values differ than what is calculated by the workbook (3,749,202 kWh and 1,213 kW).  The estimated savings values were provided by an engineering study conducted for the campus and verified by SCE.

Committed measures that were not originally projected in the workbook include LED traffic signals, chiller optimizer controls and a comprehensive lighting/occupancy sensor retrofit.  These measures are not included on sheet tab 2A-RecordedEEActvities.  The total budget committed for these measures is $421,907 with an estimated gross annual energy savings of 1,384,074 kWh and a gross demand reduction of 474 kW.

      - Calculated and Actual Payment Reconciliation -

The original workbook projected a cost for a T-12 to T-8 retrofit to be $84 per unit.  The actual campus cost realized for the purchase of 17,884 fixtures is $26 per unit.  The total commitment for this campus project is $403,754 and is substantially less than the $1,502,256 calculated by the workbook.

    - EM&V

The EM&V contractor, XXXXX, submitted the EM&V plan to the Commission on July 21, 2004.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

The partnership has renamed this program element as “Monitoring Based Commissioning” (MBC) to better reflect the actual scope of the activity.  The program goals and overall approach remain the same.