| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Bakersfield/Kern County Program – PGC |
| Program Number: | 1325-04 |
| Month: | December 2005 |

- Program Status

Program Description

Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), Southern California Gas Company (SoCalGas), the City of Bakersfield (City), the County of Kern (County), and Staples/Hutchinson and Associates, Inc. (Staples/Hutchinson) entered into a partnership to reduce energy use by providing energy efficiency information and direct installation of energy efficient equipment to the City and County’s local community.

Specifically, this partnership will offer direct install services to hard-to-reach customers, home buyers, and small businesses; free energy audits to both residential and nonresidential hard-to-reach customers; marketing and outreach to encourage participation in statewide energy efficiency programs; municipal building energy efficiency retrofits; support for codes and standards enforcement; and local training seminars for residential contractors as well as design/build firms and engineers and architects working on commercial properties.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | $26,945 | 3% | $145,039 | 15% | $551,569 | 55% | $696,608 | 70% | $854,961 |
| Admin | $154,625 | $5,743 | 4% | $109,526 | 71% |  |  | $109,526 | 71% | $45,099 |
| Marketing | $32,308 |  |  |  |  |  |  |  |  | $32,308 |
| DI | $813,067 | $21,202 | 3% | $35,514 | 4% | $551,569 | 68% | $587,082 | 72% | $777,553 |
| EM&V |  |  | NA |  | NA |  | NA |  | NA |  |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Dec-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 520 | 5 | 1% | 5 | 1% | 288 | 55% | 293 | 56% | 515 |
| Annual kWh | 2,082,199 | 48,972 | 2% | 48,972 | 2% | 1,929,239 | 93% | 1,978,211 | 95% | 2,033,227 |
| Lifecyc kWh | 29,477,295 | 966,980 | 3% | 966,980 | 3% | 26,632,208 | 90% | 27,599,188 | 94% | 28,510,315 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Dec-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Audits of Municipal facilities in Kern County | 5 | 0 | 0% | 5 | 100% | 44 | 880% | 49 | 980% | 0 |
| In-home surveys | 960 | 0 | 0% | 0 | 0% | 555 | 57.7% | 555 | 57.7% | 960 |

  - Activities/Accomplishments

    - Administrative –

- Administrative activities related to standard program implementation included a partnership coordination conference call of all partners on December 15, 2005 in place of the monthly meeting, due to holiday schedules; telephone calls, e-mails and meetings between PG&E and Staples Marketing and between PG&E and residential services vendors; telephone calls and e-mails at each utility to coordinate 2005 activities; meetings, telephone calls and e-mails between the City of Bakersfield, County of Kern and PG&E and between the County of Kern and SCE to discuss progress in municipal building retrofits; and between utilities to coordinate marketing activities.

- Partners continued work related to the additional energy efficiency measures to be installed for PG&E and SCE small business customers using funds shifted into direct implementation and added to the Small Business direct installation contract with Staples Marketing.  SCE has filed a change order with the CPUC for approval to add small business retrofits for its customer, the county of Kern. The modified inter-utility co-funding agreement  is being circulated for signature by all three utilities. It  provides for additional reimbursement to PG&E for the additional expenses incurred on behalf of SCE.

    - Marketing –

A radio schedule was placed December 5-9, 12-16, and 19-23, 2005.  The creative message encouraged listeners to reduce residential use of natural gas through permanent installations. Total budget for the schedule was $27,000 to achieve 485 commercials aired at an average $5 per spot.

| Bakersfield Area Radio Station | Number of Spots |
| --- | --- |
| KUZZ-FM | 105 |
| KERN-AM | 90 |
| KDFO-FM | 85 |
| KDFO-AM | 90 |
| KKDJ (Spanish) | 115 |

The radio spots submitted as MP3 files with the December 2005 monthly report.

    - Direct Implementation –

- Virtually all Energy Watch activities have been completed.

- The Realtor (homebuyer) program element of home energy audits and direct installation of CFLs and programmable thermostats is complete. Staples Marketing conducted 3,072 residential audits, with installation of 690 programmable thermostats and 15,355 CFLs. This represents complete achievement of the Realtor program element goals.

- All original installations targeted for the Small Business Services program element have been completed. Energy Watch conducted 392 small business energy surveys. Subsequently, the HVAC subcontractor completed 62 small business HVAC tune-ups. Energy Watch has completed installation of 815 2-lamp lighting ballasts, 2,935 4- lamp lighting ballasts, 13,210  48” lamp, 2,202 CFLs, 245 occupancy sensors, and 46 LED exit signs.

- The Bakersfield & Kern Energy Watch Partnership has conducted 62 commercial air conditioner charge and air flow tests, resulting in 49.4 kW of demand reduction.  This savings figure was calculated at .52 kW for energy air conditioner repaired of 5 tons or under and 1.04 kW saved for every air conditioner over 5 tons.  The Bakersfield & Kern County Energy Watch partnership has used the “Check Me!” protocol to calculate the savings.  This protocol is also used in PG&E’s recently approved Long-Term Procurement Plan-Verified Charge and Air Flow Program for small businesses.   A Change Order to add these HVAC tune-up savings to the workbook for the Local Crosscutting--PG&E Local Government Partnership:  Bakersfield/Kern Energy Watch Partnership will be submitted for approval prior to the submittal of the December 2005 Monthly Report for inclusion in the December Monthly Report.

- Additional installations using the Small Business Services program element are described below.

- Municipal building retrofit opportunities have been identified and most installations are complete. Installations for Kern County under the Small Business direct installation element will be completed in early 2006.

- Training and education activities have been completed include codes and standards training for building code officials.

- Due to an oversight, the workbook input for Tab 3, NonEE Activities, was not been updated for activities between January and October 2005. The following is a list of all the classes sponsored by the Bakersfield & Kern County Energy Watch Program to date in 2004 and 2005:

August 11, 2004	Title 24 Lighting Overview

August 13, 2004	Lighting Installation Training for Partnership Installers

October 14, 2004	Grocery, Restaurant and Related Food Service Energy Efficiency

January 11, 2005	Manual D Duct Design

January 12, 2005	Manual J Equipment Selection and Sizing

January 13, 2005	Static Air Flow and Pressure

January 14, 2005	Duct Testing and Sealing

January 25/26, 2005	Energy Auditing Techniques for Small Businesses

April 14, 2005	1st Annual Business Customer Energy Efficiency Workshop

April 21, 2005	Restaurant and Food Service Technical Workshop

April 28, 2005	Proper Procedures for Charging Air Conditioners and Heat Pumps

May 19, 2005	2005 Title 24 Overview for City of Bakersfield Building Inspectors

June 15, 2005	Ag I.C.E. (internal combustion engine alternative rate) for Agricultural Customers

June 22, 2005		2005 Title 24 Overview for Business Customers

- Energy Watch has met its education and training goals but continues to explore the need for additional seminars and workshops and respond to the needs of the community by offering courses to meet those needs.

      - Audits, Site Surveys and Partnerships -

- Homebuyer audits have been completed and the goal of 3,000 audits was exceeded.

- Audits for the city of Bakersfield and county of Kern have been completed, including 44 audits on Kern County Firehouses and county buildings, served by SCE.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

The following chart outlines the activity to date in the program, and includes the realtor and small business activity not originally included as part of the workbook:

| MEASURE/ACTIVITY NAME | Paid Units | Committed Units |
| --- | --- | --- |
| Single Family Direct Install |  |  |
| ES Screw-in CFL (21 to 30 watts) for calc. use 25 Watts |  | 2832 |
| ES Interior Hardwired CFL Fixtures (30 Watts) |  | 3154 |
| ES Programmable Thermostats |  | 127 |
| Multi-family Direct Install |  |  |
| ES Screw-in CFL (21 to 30 watts) for calc. use 25 Watts |  | 2068 |
| ES Interior Hardwired CFL Fixtures (30 Watts) |  | 2239 |
| ES Exterior Hardwired CFL Fixtures (27 Watts) |  | 1349 |
| ES Programmable Thermostats |  | 25 |
| T-5 or T-8 Int. lamps with electronic ballasts - (4 ft. 1 lamp) |  | 218 |
| T-5 or T-8 Int. lamps with electronic ballasts - (4 ft. 2 lamps) |  | 9 |
| T-5 or T-8 Int. lamps with electronic ballasts - (8 ft. 1 lamp) |  |  |
| T-5 or T-8 Int. lamps with electronic ballasts - (8 ft. 2 lamps) |  |  |
| SPC PLUS |  |  |
| Lighting |  | 867,825 kWh |
| HVAC/Refrigeration | 66,400 kWh | 13,800 kWh |
| Motors/Other | 3,560 kWh |  |
| Realtor Program |  |  |
| ES Screw-in CFL (14 to 20 watts ) for calc. use 20 Watts (8hrs/day) |  | 570 |
| ES Programmable Thermostats |  | 18 |
| SMALL BUSINESS PROGRAM |  |  |
| Screw-in Compact Fluorescent Lamps - 14-26 watts |  | 169 |
| PREMIUM T8/T5 Lamp & Electronic Ballast/New Fixture-Replacement of T-12 Lamps & EnergySaver Ballast-4 ft |  | 1,112 |
| Occupancy Sensor-Wallbox Lighting Sensor |  | 17 |

- PG&E, SCE, the City of Bakersfield and the County of Kern are completing municipal building energy efficiency retrofits.  Most retrofits for County of Kern small buildings served by SCE, using the Energy Watch small business program, will be completed during 2005.  A few installations will occur in January 2006 due to equipment availability issues.

- In December 2005, Staples Marketing began inspecting 180 non-residential retrofits for PG&E customers, and correcting any deficiencies found.

- Through December 2005, 19 single family and 175 multifamily installations for PG&E customers were completed, and 1 single family and 49 multifamily installations for SCE customers were completed. Total installations for PG&E customers are now at 2,808 single family homes compared to the revised target of 2,928 homes; and 2,850 multifamily installations have been completed compared to the revised target of 2,597. For SCE customers, 1,384 single family homes have been served and 1,114 multifamily installations have been completed compared to the revised target of 1,003.

      - Calculated and Actual Payment Reconciliation –

Since actual incentives payable to customers are capped at maximum program rebate levels with certain measures qualified for partial incentive payment only, the financial incentives to customers in Tab 1A - Expenditures Worksheet may differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

Energy savings and peak demand reduction recorded by SCE may differ from those calculated in the Workbook because measure energy savings/peak demand reduction can vary by market segment or climate zone. Additionally, on tab 3 projected non-EE activities, the municipal audits were completed for less than the listed cost, therefore the workbook is claiming a higher cost than realized through the program.

    - EM&V

XXXXX, the consultant conducting the evaluations of seven of PG&E’s partnership programs, received Energy Division approval to proceed with implementation of its evaluation plan on October 29, 2004. Survey design is proceeding and the revised EM&V project schedule has been reflected in tab 6 of the workbook.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

PG&E, SCE and SCG filed revised Program Implementation Plans (PIP) and workbooks for this program on June 15, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP. In addition, all Energy Watch partners have provided Staples Marketing with supplies of informational materials regarding other energy efficiency programs to be handed out at special events scheduled to promote Energy Watch and statewide energy efficiency programs.

- Changes to Subcontractors or Staffing

None

- Additional Items

None