| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Bakersfield/Kern County Program – PGC |
| Program Number: | 1325-04 |
| Month: | November 2005 |

- Program Status

Program Description

Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), Southern California Gas Company (SoCalGas), the City of Bakersfield (City), the County of Kern (County), and Staples/Hutchinson and Associates, Inc. (Staples/Hutchinson) entered into a partnership to reduce energy use by providing energy efficiency information and direct installation of energy efficient equipment to the City and County’s local community.

Specifically, this partnership will offer direct install services to hard-to-reach customers, home buyers, and small businesses; free energy audits to both residential and nonresidential hard-to-reach customers; marketing and outreach to encourage participation in statewide energy efficiency programs; municipal building energy efficiency retrofits; support for codes and standards enforcement; and local training seminars for residential contractors as well as design/build firms and engineers and architects working on commercial properties.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | $5,039 | 1% | $118,094 | 12% | $544,977 | 54% | $663,071 | 66% | $881,906 |
| Admin | $154,625 | $3,994 | 3% | $103,783 | 67% |  |  | $103,783 | 67% | $50,842 |
| Marketing | $32,308 |  |  |  |  |  |  |  |  | $32,308 |
| DI | $813,067 | $1,046 | 0% | $14,312 | 2% | $544,977 | 67% | $559,289 | 69% | $798,755 |
| EM&V |  |  | NA |  | NA |  | NA |  | NA |  |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Nov-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 520 |  |  |  |  | 277 | 53% | 277 | 53% | 520 |
| Annual kWh | 2,082,199 |  |  |  |  | 1,863,832 | 90% | 1,863,832 | 90% | 2,082,199 |
| Lifecyc kWh | 29,477,295 |  |  |  |  | 26,075,364 | 88% | 26,075,364 | 88% | 29,477,295 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Nov-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Audits of Municipal facilities in Kern County | 5 | 0 | 0% | 5 | 100% | 0 | 0% | 5 | 100% | 0 |
| In-home surveys | 960 | 0 | 0% | 0 | 0% | 554 | 57.7% | 554 | 57.7% | 960 |

  - Activities/Accomplishments

    - Administrative –

Administrative activities related to standard program implementation included the monthly partnership coordination meeting of all partners in Bakersfield on November 30, 2005 in Bakersfield; telephone calls, e-mails and meetings between PG&E and Staples Marketing and between PG&E and residential services vendors; telephone calls and e-mails at each utility to coordinate 2005 activities; meetings, telephone calls and e-mails between the City of Bakersfield, County of Kern and PG&E and between the County of Kern and SCE to discuss progress in municipal building retrofits; and between utilities to coordinate marketing activities.

Partners have identified additional potential for installing energy efficiency measures in a number of PG&E and SCE small business customers.  SCE has filed a change order with the CPUC for approval to add these small business retrofits. The modified inter-utility co-funding agreement is being circulated for signature by all three utilities. It provides for additional reimbursement to PG&E for the additional expenses incurred on behalf of SCE.

    - Marketing –

On Wednesday, November 30, the Bakersfield & Kern County Energy Watch partnership held a media conference at the Bakersfield City Fire Station #1. The conference was held to announce the three-year renewal of the Bakersfield & Kern County Energy Watch Program.  Featured guests included Bakersfield City Mayor XXXXX and County Board of Supervisors Chairman XXXXX. Representatives from PG&E, SCE and SoCal Gas described the Energy Watch accomplishments over the last two years and plans for 2006-2008.

A radio schedule was developed to run in December.  The focus is on reducing residential use of natural gas, and promotes statewide natural gas energy efficiency programs.

Energy Watch staff is scheduled to participate in the following outreach activity:

Bakersfield Home & Garden Show

Kern County Fairgrounds

February 17-19, 2006

    - Direct Implementation –

Virtually all Energy Watch activities have been completed.

The Realtor (homebuyer) program element of home energy audits and direct installation of CFLs and programmable thermostats is complete. Staples Marketing conducted 3,072 residential audits, with installation of 690 programmable thermostats and 15,355 CFLs. This represents complete achievement of the Realtor program element goals.

All original installations targeted for the Small Business Services program element have been completed. Energy Watch conducted 392 small business energy surveys. Subsequently, the HVAC subcontractor completed 62 small business HVAC tune-ups. Energy Watch has completed installation of 815 2-lamp lighting ballasts, 2,935 4-lamp lighting ballasts, 13,210 48” lamp, 2,202 CFLs, 245 occupancy sensors, and 46 LED exit signs.

The Bakersfield & Kern County Energy Watch partnership has conducted 62 commercial air conditioner charge and airflow tests, resulting in 49.4 kW of demand reduction. This was calculated at .52 kW saved for every air conditioner repaired of 5 tons or under and 1.04 kw saved for every air conditioner over 5 tons. The partnership used the Check Me! Protocol, which is also used in PG&E's recently approved Verified Charge and Airflow program for small businesses. A change order will be filed in late December or early January to add these energy savings to the workbook.

Municipal building retrofit opportunities have been identified and most installations are complete. Training and education activities that have been completed include codes and standards training for building code officials.

The following is a list of all the classes sponsored by the Bakersfield & Kern County Energy Watch Program to date in 2004 and 2005:

August 11, 2004	Title 24 Lighting Overview

August 13, 2004	Lighting Installation Training for Partnership Installers

October 14, 2004	Grocery, Restaurant and Related Food Service Energy Efficiency

January 11, 2005	Manual D Duct Design

January 12, 2005	Manual J Equipment Selection and Sizing

January 13, 2005	Static Air Flow and Pressure

January 14, 2005	Duct Testing and Sealing

January 25/26, 2005	Energy Auditing Techniques for Small Businesses

April 14, 2005	1st Annual Business Customer Energy Efficiency Workshop

April 21, 2005	Restaurant and Food Service Technical Workshop

April 28, 2005	Proper Procedures for Charging Air Conditioners and Heat Pumps

May 19, 2005	2005 Title 24 Overview for City of Bakersfield Building Inspectors

June 15, 2005	Ag I.C.E. (internal combustion engine alternative rate) for Agricultural Customers

June 22, 2005	2005 Title 24 Overview for Business Customers

Although the Energy Watch has met its education and training goals, we continue to explore the need for additional seminars and workshops, and respond to the needs of the community by offering courses to meet those needs.  PG&E is continuing to work with SoCalGas to offer an Electric Safety and Energy Efficiency seminar in the early fall.

      - Audits, Site Surveys and Partnerships -

All small business and homebuyer audit goals have been met.

Audits for the city of Bakersfield and county of Kern have been completed.

PG&E, SCE, the city of Bakersfield and the county of Kern continue work on municipal building energy efficiency retrofits.  Most retrofits are near completion. Retrofits for Kern County small buildings served by SCE will use the Energy Watch small business program. Most installations will be completed during 2005, with a few installations not occurring until January 2006 due to equipment availability issues.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

The following chart outlines the activity to date in the program, and includes the realtor and small business activity not originally included as part of the workbook:

| MEASURE/ACTIVITY NAME | Paid Units | Committed Units |
| --- | --- | --- |
| Single Family Direct Install |  |  |
| ES Screw-in CFL (21 to 30 watts) for calc. use 25 Watts |  | 2750 |
| ES Interior Hardwired CFL Fixtures (30 Watts) |  | 3094 |
| ES Programmable Thermostats |  | 126 |
| Multi-family Direct Install |  |  |
| ES Screw-in CFL (21 to 30 watts) for calc. use 25 Watts |  | 1714 |
| ES Interior Hardwired CFL Fixtures (30 Watts) |  | 1878 |
| ES Exterior Hardwired CFL Fixtures (27 Watts) |  | 1179 |
| ES Programmable Thermostats |  | 18 |
| T-5 or T-8 Int. lamps with electronic ballasts - (4 ft. 1 lamp) |  | 116 |
| T-5 or T-8 Int. lamps with electronic ballasts - (4 ft. 2 lamps) |  | 4 |
| T-5 or T-8 Int. lamps with electronic ballasts - (8 ft. 1 lamp) |  |  |
| T-5 or T-8 Int. lamps with electronic ballasts - (8 ft. 2 lamps) |  |  |
| SPC PLUS |  |  |
| Lighting |  | 867,825 kWh |
| HVAC/Refrigeration |  | 80,200 kWh |
| Motors/Other |  | 3,560 kWh |
| Realtor Program |  |  |
| ES Screw-in CFL (14 to 20 watts ) for calc. use 20 Watts (8hrs/day) |  | 570 |
| ES Programmable Thermostats |  | 18 |
| SMALL BUSINESS PROGRAM |  |  |
| Screw-in Compact Fluorescent Lamps - 14-26 watts |  | 169 |
| PREMIUM T8/T5 Lamp & Electronic Ballast/New Fixture-Replacement of T-12 Lamps & EnergySaver Ballast-4 ft |  | 1,112 |
| Occupancy Sensor-Wallbox Lighting Sensor |  | 17 |

During the month of November, Staples Marketing completed small business direct installations of 362 2-lamp ballasts, 1,106 4-lamp ballasts, 4,788 48” fluorescent lamps, 110 CFLs, 40 occupancy sensors and 4 LED exit signs.

For the residential direct install component for November 2005, 19 single family and 175 multifamily installations for PG&E customers were completed, and 1 single family and 49 multifamily installations for SCE customers were completed. Total installations for PG&E customers are now at 2,808 single family homes compared to the revised target of 2,928 homes; and 2,850 multifamily installations have been completed compared to the revised target of 2,597. For SCE customers, 1,384 single family homes have been served compared to the revised of 1,384; and 1,114 multifamily installations have been completed compared to the revised target of 1,003.

The target for households served is revised periodically to account for actual installations of energy efficiency measures and associated energy savings. Additional households can be served when all possible measures cannot be installed in a home or multifamily unit.

      - Calculated and Actual Payment Reconciliation –

Since actual incentives payable to customers are capped at maximum program rebate levels with certain measures qualified for partial incentive payment only, the financial incentives to customers in Tab 1A - Expenditures Worksheet may differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

Energy savings and peak demand reduction recorded by SCE may differ from those calculated in the Workbook because measure energy savings/peak demand reduction can vary by market segment or climate zone. Additionally, on tab 3 projected non-EE activities, the municipal audits were completed for less than the listed cost, therefore the workbook is claiming a higher cost than realized through the program.

    - EM&V

XXXXX, the consultant conducting the evaluations of seven of PG&E’s partnership programs, received Energy Division approval to proceed with implementation of its evaluation plan on October 29, 2004. Survey design is proceeding and the revised EM&V project schedule has been reflected in tab 6 of the workbook.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

PG&E, SCE and SCG filed revised Program Implementation Plans (PIP) and workbooks for this program on June 15, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP. In addition, all Energy Watch partners have provided Staples Marketing with supplies of informational materials regarding other energy efficiency programs to be handed out at special events scheduled to promote Energy Watch and statewide energy efficiency programs.

- Changes to Subcontractors or Staffing

None

- Additional Items

None