| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Bakersfield/Kern County Program – PGC |
| Program Number: | 1325-04 |
| Month: | October 2005 |

- Program Status

Program Description

Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), Southern California Gas Company (SoCalGas), the City of Bakersfield (City), the County of Kern (County), and Staples/Hutchinson and Associates, Inc. (Staples/Hutchinson) entered into a partnership to reduce energy use by providing energy efficiency information and direct installation of energy efficient equipment to the City and County’s local community.

Specifically, this partnership will offer direct install services to hard-to-reach customers, home buyers, and small businesses; free energy audits to both residential and nonresidential hard-to-reach customers; marketing and outreach to encourage participation in statewide energy efficiency programs; municipal building energy efficiency retrofits; support for codes and standards enforcement; and local training seminars for residential contractors as well as design/build firms and engineers and architects working on commercial properties.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | $4,148 | 0% | $113,055 | 11% | $296,653 | 30% | $409,708 | 41% | $886,945 |
| Admin | $154,625 | $4,097 | 3% | $99,789 | 65% |  |  | $99,789 | 65% | $54,836 |
| Marketing | $32,308 |  |  |  |  |  |  |  |  | $32,308 |
| DI | $813,067 | $51 | 0% | $13,266 | 2% | $296,653 | 36% | $309,919 | 38% | $799,801 |
| EM&V |  |  | NA |  | NA |  | NA |  | NA |  |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Oct-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 520 |  |  |  |  | 205 | 39% | 205 | 39% | 520 |
| Annual kWh | 2,082,199 |  |  |  |  | 1,181,910 | 57% | 1,181,910 | 57% | 2,082,199 |
| Lifecyc kWh | 29,477,295 |  |  |  |  | 15,415,405 | 52% | 15,415,405 | 52% | 29,477,295 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Oct-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Audits of Municipal facilities in Kern County | 5 | 0 | 0% | 5 | 100% | 0 | 0% | 5 | 100% | 0 |
| In-home surveys | 960 | 0 | 0% | 0 | 0% | 552 | 57.5% | 552 | 57.5% | 960 |

  - Activities/Accomplishments

    - Administrative -

Administrative activities related to standard program implementation included the monthly partnership coordination meeting of all partners in Bakersfield on October 27, 2005  in Bakersfield; telephone calls, e-mails and meetings between PG&E and Staples Marketing and between PG&E and residential services vendors; telephone calls and e-mails at each utility to coordinate 2005 activities; meetings, telephone calls and e-mails between the City of Bakersfield, County of Kern and PG&E and between the County of Kern and SCE to discuss progress in municipal building retrofits; and between utilities to coordinate marketing activities.

Partners have identified additional potential for installing energy efficiency measures in a number of PG&E and SCE small business customers. PG&E may move $200,000 from administrative and marketing, while SCE has identified $100,000 that may be available for small business retrofits.  In addition, SCE has identified retrofits at small county facilities which, if installed through the Energy Watch program, could be completed before the end of the year. PG&E has prepared a contract change order with Staples Marketing for the additional work.  The inter-utility co-funding agreement has also being modified as PG&E will be incurring additional expenses on behalf of SCE.

Staples Marketing has placed orders for the equipment needed for these additional direct installation program.  Audits of SCE municipal facilities are underway and work is anticipated to take place in November. Actual work will not take place until SCE has identified the specific work locations for their additional installations, and PG&E has executed the contract change order.

Several measures were completed in SCE territory under the Realtor Program and the Small Business Program. These measures were not originally proposed in SCE territory, however several installation were completed and identified as SCE service accounts. The installations have been added to the workbook as follows:

|  | UNIT GOALS | UNIT DEFINITION | FINANCIAL INCENTIVE PER UNIT | INSTALLATION, SERVICE, AND REPAIR LABOR COSTS PER UNIT |
| --- | --- | --- | --- | --- |
| REALTOR PROGRAM |  | - | $ - | $ - |
| ES Screw-in CFL (14 to 20 watts ) for calc. use 20 Watts (8hrs/day) | 570 | - | $ - | $ 4.00 |
| ES Programmable Thermostats | 18 | - | $ - | $ 50.00 |
|  | - | - | $ - | $ - |
| SMALL BUSINESS PROGRAM | - | - | $ - | $ - |
| Screw-in Compact Fluorescent Lamps - 14-26 watts | 169 | Changed | $ - | $ 4.00 |
| PREMIUM T8/T5 Lamp & Electronic Ballast/New Fixture-Replacement of T-12 Lamps & EnergySaver Ballast-4 ft | 1,112 | Changed | $ - | $ 16.50 |
| Occupancy Sensor-Wallbox Lighting Sensor | 17 | Changed | $ - | $ 65.00 |

To cover this cost, $25,000 originally slated for marketing under the realtor program will be used instead to cover these installations.

    - Marketing -

The radio schedule concluded at the end of August.  Currently, $20,000 in marketing/outreach funds are available for further promotion, depending on the outcome of the additional funding for non-residential retrofits.

Representatives of Bakersfield’s Energy Watch staff attended Bakersfield Home Show, October 21, 22, 23, at the Kern County Fair Grounds. Special emphasis was placed on promoting opportunities for reducing natural gas use.

Staples Marketing prepared and received approval for an article for possible use in the special Home Show insert of the Bakersfield Californian. A copy of the article is being submitted with this report.

Staples Marketing also produced radio commercials that will air in late November-early December regarding natural gas savings. Copies of the radio commercials for PG&E and SoCal Gas are included with their respective reports.

Energy Watch staff are scheduled to participate in the following outreach activities:

Bakersfield Home & Garden Show

Kern County Fairgrounds

February 17-19, 2006

    - Direct Implementation –

Most Energy Watch activities have been completed. The Realtor (homebuyer) program element of home energy audits and direct installation of CFLs and programmable thermostats is complete. All original installations targeted for the Small Business Services program element have been completed. Municipal building retrofit opportunities have been identified and installations are underway. Training and education activities have been completed, include codes and standards training for building code officials.

The following is a list of all the classes sponsored by the Bakersfield & Kern County Energy Watch Program to date in 2004 and 2005:

August 11, 2004	Title 24 Lighting Overview

August 13, 2004	Lighting Installation Training for Partnership Installers

October 14, 2004	Grocery, Restaurant and Related Food Service Energy Efficiency

January 11, 2005	Manual D Duct Design

January 12, 2005	Manual J Equipment Selection and Sizing

January 13, 2005	Static Air Flow and Pressure

January 14, 2005	Duct Testing and Sealing

January 25/26, 2005	Energy Auditing Techniques for Small Businesses

April 14, 2005	1st Annual Business Customer Energy Efficiency Workshop

April 21, 2005	Restaurant and Food Service Technical Workshop

April 28, 2005	Proper Procedures for Charging Air Conditioners and Heat Pumps

May 19, 2005	2005 Title 24 Overview for City of Bakersfield Building Inspectors

June 15, 2005	Ag I.C.E. (internal combustion engine alternative rate) for Agricultural Customers

June 22, 2005	2005 Title 24 Overview for Business Customers

Although the Energy Watch has met its education and training goals, we continue to explore the need for additional seminars and workshops, and respond to the needs of the community by offering courses to meet those needs.  PG&E is continuing to work with SoCalGas to offer an Electric Safety and Energy Efficiency seminar.

      - Audits, Site Surveys and Partnerships -

PG&E, SCE, the city of Bakersfield and the county of Kern continue work on municipal building energy efficiency retrofits.  Most retrofits are near completion. As indicated earlier, retrofits in county of Kern small buildings served by SCE may be completed this year by using the Energy Watch small business program. SCE and the county are exploring that option.

All small business and homebuyer audit goals have been met.

Additional small business installations for PG&E and SCE will occur once PG&E and Staples have executed a Contract Change Order.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

The final review has been completed for the municipal retrofit at the Ridgecrest facility in SCE service area, and the final payment is in process. A contract has also been issued for HVAC retrofits at the California City Library building in SCE territory. Lighting audits at libraries, court house building, administration facilities, senior centers, recreation halls, fire stations, and sheriff offices were completed in October. Details of the audits are being reviewed by SCE and installations are expected to begin in November.

The following chart outlines the activity to date in the program, and includes the realtor and small business activity not originally included as part of the workbook:

| MEASURE/ACTIVITY NAME | Paid Units | Committed Units |
| --- | --- | --- |
| Single Family Direct Install |  |  |
| ES Screw-in CFL (21 to 30 watts) for calc. use 25 Watts |  | 2526 |
| ES Interior Hardwired CFL Fixtures (30 Watts) |  | 2810 |
| ES Programmable Thermostats |  | 125 |
| Multi-family Direct Install |  |  |
| ES Screw-in CFL (21 to 30 watts) for calc. use 25 Watts |  | 1572 |
| ES Interior Hardwired CFL Fixtures (30 Watts) |  | 1668 |
| ES Exterior Hardwired CFL Fixtures (27 Watts) |  | 1160 |
| ES Programmable Thermostats |  | 18 |
| T-5 or T-8 Int. lamps with electronic ballasts - (4 ft. 1 lamp) |  |  |
| T-5 or T-8 Int. lamps with electronic ballasts - (4 ft. 2 lamps) |  |  |
| T-5 or T-8 Int. lamps with electronic ballasts - (8 ft. 1 lamp) |  |  |
| T-5 or T-8 Int. lamps with electronic ballasts - (8 ft. 2 lamps) |  |  |
| SPC PLUS |  |  |
| Lighting |  |  |
| HVAC/Refrigeration |  | 80,200 kWh |
| Motors/Other |  | 3,560 kWh |
| Realtor Program |  |  |
| ES Screw-in CFL (14 to 20 watts ) for calc. use 20 Watts (8hrs/day) |  | 570 |
| ES Programmable Thermostats |  | 18 |
| SMALL BUSINESS PROGRAM |  |  |
| Screw-in Compact Fluorescent Lamps - 14-26 watts |  | 169 |
| PREMIUM T8/T5 Lamp & Electronic Ballast/New Fixture-Replacement of T-12 Lamps & EnergySaver Ballast-4 ft |  | 1112 |
| Occupancy Sensor-Wallbox Lighting Sensor |  | 17 |

For the residential direct install component for October 2005, 9 single family and 51 multi-family installations for PG&E customers were completed, and no 106 single family and 187 multifamily installations for SCE customers were completed. Total installations for PG&E customers are now at 2,777 single family homes compared to a target of 2,448 homes; and 2,618 multifamily installations have been completed compared to a target of 2,171. For SCE customers, 1,258 single family homes have been served compared to a target of 1,249; and 872 multifamily installations have been completed compared to a target of 910.

      - Calculated and Actual Payment Reconciliation -

Since actual incentives payable to customers are capped at maximum program rebate levels with certain measures qualified for partial incentive payment only, the financial incentives to customers in Tab 1A - Expenditures Worksheet may differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

Energy savings and peak demand reduction recorded by SCE may differ from those calculated in the Workbook because measure energy savings/peak demand reduction can vary by market segment or climate zone. Additionally, on tab 3 projected non-EE activities, the municipal audits were completed for less than the listed cost, therefore the workbook is claiming a higher cost than realized through the program.

    - EM&V

XXXXX, the consultant conducting the evaluations of seven of PG&E’s partnership programs received Energy Division approval to proceed with implementation of its evaluation plan on October 29, 2004. Survey design is proceeding and the revised EM&V project schedule has been reflected in tab 6 of the workbook.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

PG&E, SCE and SCG filed revised Program Implementation Plans (PIP) and workbooks for this program on June 15, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP. In addition, all Energy Watch partners have provided Staples Marketing with supplies of informational materials regarding other energy efficiency programs to be handed out at special events scheduled to promote Energy Watch and statewide energy efficiency programs.

- Changes to Subcontractors or Staffing

None

- Additional Items

None