| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Local Bakersfield/Kern County Program – PGC |
| Program Number: | 1325-04 |
| Month: | September 2004 |

- Program Status

Program Description

Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), Southern California Gas Company (SoCalGas), the City of Bakersfield (City), the County of Kern (County), and Staples/Hutchinson and Associates, Inc. (Staples/Hutchinson) entered into a partnership to reduce energy use by providing energy efficiency information and direct installation of energy efficient equipment to the City and County’s local community.

Specifically, this partnership will offer direct install services to hard-to-reach customers, home buyers, and small businesses; free energy audits to both residential and nonresidential hard-to-reach customers; marketing and outreach to encourage participation in statewide energy efficiency programs; municipal building energy efficiency retrofits; support for codes and standards enforcement; and local training seminars for residential contractors as well as design/build firms and engineers and architects working on commercial properties.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,000,000 | $6,131 | 1% | $41,853 | 4% | $99,164 | 10% | $141,017 | 14% | $958,147 |
| Admin | $154,625 | $6,131 | 4% | $41,505 | 27% |  |  | $41,505 | 27% | $113,120 |
| Marketing | $32,308 |  |  |  |  |  |  |  |  | $32,308 |
| DI | $813,067 |  |  | $349 | 0% | $99,164 | 12% | $99,512 | 12% | $812,718 |
| EM&V |  |  | NA |  | NA |  | NA |  | NA |  |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 520 |  |  |  |  | 2 | 0% | 2 | 0% | 520 |
| Annual kWh | 2,082,199 |  |  |  |  | 27,405 | 1% | 27,405 | 1% | 2,082,199 |
| Lifecyc kWh | 29,477,295 |  |  |  |  | 424,367 | 1% | 424,367 | 1% | 29,477,295 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Audits of Municipal facilities in Kern County | 5 | 0 | 0% | 5 | 100% | 0 | 0% | 5 | 100% | 0 |
| In-home surveys | 960 | 0 | 0% | 0 | 0% | 4 | 0.4% | 4 | 0.4% | 956 |

  - Activities/Accomplishments

    - Administrative -

- Administrative activities related to standard program implementation included the monthly partnership coordination meeting of all partners in Bakersfield on September 16, 2004; telephone calls, e-mails and meetings between PG&E and Staples/Hutchinson and between PG&E and potential residential services vendors; telephone calls and e-mails at each utility to plan activities; meetings, telephone calls and e-mails between the City of Bakersfield, County of Kern, PG&E, and SCE to refine plans for municipal building retrofits; and between utilities to coordinate marketing activities.

    - Marketing -

- The final collateral piece for the Bakersfield & Kern County Energy Watch Program was completed with the printing of the Spanish language residential energy survey coupon.

- During September, we completed final production of the Bakersfield & Kern County Energy Watch 60-second radio commercial and 30-second television commercial regarding the energy survey and direct installation programs.  Both English and Spanish versions have been created.

- Scripts were developed for a radio and a television commercial that focused on each utility’s energy efficiency rebate programs. Commercials for PG&E and SCE were created, and SoCalGas declined the opportunity as its rebate program has closed.

- The Bakersfield & Kern County Energy Watch radio schedule began airing September 20 in the Bakersfield media market and will continue for a six-week flight. The television schedule is set to begin shortly thereafter.

- Staples Hutchinson worked with G&G Shows to generate editorial coverage of the Bakersfield & Kern County Energy Watch program in the Kern County Fair section inserted into the Bakersfield Californian newspaper.

- Staples Hutchinson employees from the Bakersfield office staffed the Bakersfield & Kern County Energy Watch display booth and distributed program literature at several venues in September:  Walmart on September 9, Foodmax on September 11, Kern County Fair on September 22 through October 3.

    - Direct Implementation –

- Staff from the Energy Watch office in Bakersfield continues to make presentations to partner Realtor® firms. Coupons offering free energy surveys are sent out to homebuyers and requests for homebuyer home energy surveys are scheduled by the Energy Watch office.

- The Bakersfield Energy Watch office distributed approximately 5,000 residential energy survey coupons during September via onsite visits and mailings. This work was done by a subcontractor and will not appear in the workbook until PG&E has paid the invoice for this work.

- In addition, 210 coupons were mailed to PG&E customers of S Realtors. This work was done by a subcontractor and will not appear in the workbook until PG&E has paid the invoice for this work.

- Fifteen residential audits in PG&E service territory were scheduled. Four in-home survey requests for households in SCE territory were referred to SCE’s Home Survey Program. (SCE does not fulfill this element of the program).

- The Energy Watch HVAC subcontractors completed six (6) non-residential HVAC tune-ups in PG&E service territory.  This work was performed by a subcontractor and will not appear in the workbook until PG&E’s has paid the invoice.

      - Audits, Site Surveys and Partnerships -

- PG&E and SCE continued to identify project sites with the City of Bakersfield and the County of Kern.

- During September, the Bakersfield & Kern County energy survey staff completed 20 non-residential surveys.  This work was done by a subcontractor and will not appear in the workbook until PG&E has paid the invoice for this work.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

- The residential direct install component provided services to 294 PG&E customers and 4 SCE single-family customers in September.  This work was done by a subcontractor and will not appear in the workbook until PG&E has paid the invoice for this work.

- One municipal project application was submitted in SCE territory, and is currently under review.

      - Calculated and Actual Payment Reconciliation -

Since actual incentives payable to customers are capped at maximum program rebate levels with certain measures qualified for partial incentive payment only, the financial incentives to customers in Tab 1A - Expenditures Worksheet may differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

Energy savings and peak demand reduction recorded by PG&E can differ from those calculated in the Workbook because measure energy savings/peak demand reduction can vary by market segment or climate zone.

    - EM&V

The Energy Watch partnership is one of 7 local partnerships which will be evaluated as a group. Tab 6 in workbook has the planned schedule of activities for EM&V work.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

PG&E, SCE and SCG filed revised Program Implementation Plans (PIP) and workbooks for this program on June 15, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

The Community Action Partnership of Kern (County) had been identified as the likely subcontractor for the Realtor Program’s residential energy surveys and installations. CAP Kern has decided that the program doesn’t fit their mission. A new Realtor Program residential energy survey and installation subcontractor is being sought.

XXXXX is providing HVAC tune up services for the Small Business component in PG&E territory.

- Additional Items

None