| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Ventura County Regional Energy Alliance – PGC |
| Program Number: | 1403-04 |
| Month: | May 2004 |

- Program Status

Program Description

The Ventura County Regional Energy Alliance (VCREA), in partnership with Southern California Edison (SCE) and the Southern California Gas Company (SCG) proposes to build on the VCREA progress to date to further develop its core capabilities, to complete the development of its Energy Resource Center capability, and to implement a targeted Public Sector Program for public agencies throughout the Ventura County region.  This effort will utilize the strengths of the VCREA and its utility partners to jointly overcome identified participation barriers, better serve local needs and hard-to-reach customers, and increase participation in energy efficiency programs.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,653,446 | -$4,949 | 0% | $1,947 | 0% |  |  | $1,947 | 0% | $1,651,499 |
| Admin | $187,598 | -$4,949 | -3% | $1,947 | 1% |  |  | $1,947 | 1% | $185,651 |
| Marketing | $23,000 |  |  |  |  |  |  |  |  | $23,000 |
| DI | $1,367,589 |  |  |  |  |  |  |  |  | $1,367,589 |
| EM&V | $75,259 |  |  |  |  |  |  |  |  | $75,259 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Conduct at least 6 sessions for businesses | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 6 |
| Conduct at least 4 events for residential customers. | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Promote VCEEC resources and energy efficiency information at 20 community events or more. | 20 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 |
| Respond to every customer inquiry within 48 hours. |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Reduce Energy Consumption in Major facilities of VCREA member agencies by 8 % |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| Reduce peak demand in major facilities of VCREA member agencies by 5% or more |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |

  - Activities/Accomplishments

1.2.1	Administrative -

- Program partners continue to work on an agreement for the partnership and the development of a revised program implementation plan.

- A partnership planning meeting was held on May 19, 2004.

    - Marketing -

None

    - Direct Implementation –

Although direct implementation activities under this program have not yet started, the VCREA has been working to leverage many of the deliverables from the 2002-2003 program (Regional Energy Authority Pilot Projects in Humboldt and Ventura Counties #148-02- Local Government Commission) to best position itself to “hit the ground running.”  These include energy audits for public agencies that will form the basis of a strategy for customer rebates and business and information technology infrastructure that are essential for the program to achieve its information and education objectives.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

Conversations continue with several energy efficiency programs sponsors to coordinate programs in Ventura County.  Initial discussions with XXXXX regarding their building commissioning program suggest that there may be potential synergies between the respective programs.

- Changes to Subcontractors or Staffing

VCREA Board completed their executive director search and selected XXXXX for the position.

- Additional Items

None