| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Ventura County Regional Energy Alliance – PGC |
| Program Number: | 1403-04 |
| Month: | August 2005 |

- Program Status

Program Description

The Ventura County Regional Energy Alliance (VCREA), in partnership with Southern California Edison (SCE) and the Southern California Gas Company (SCG) proposes to build on the VCREA’s progress to date to further develop its core capabilities, to complete the development of its Energy Resource Center capability, and to implement a targeted Public Sector Program for public agencies throughout the Ventura County region.  This effort will utilize the strengths of the VCREA and its utility partners to jointly overcome identified participation barriers, better serve local needs and hard-to-reach customers, and increase participation in energy efficiency programs.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,273,152 | $96,532 | 8% | $646,970 | 51% | $110,055 | 9% | $757,025 | 59% | $626,182 |
| Admin | $126,899 | $6,680 | 5% | $79,451 | 63% | $21,191 | 17% | $100,641 | 79% | $47,448 |
| Marketing | $18,575 | $401 | 2% | $10,421 | 56% | $2,712 | 15% | $13,133 | 71% | $8,154 |
| DI | $1,066,896 | $89,451 | 8% | $536,877 | 50% | $86,153 | 8% | $623,029 | 58% | $530,020 |
| EM&V | $60,781 |  |  | $20,222 | 33% |  |  | $20,222 | 33% | $40,560 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the VCREA to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE processes this information, the costs now shown in the committed column will be reported in the supporting workbook.

    - Energy Effects

| Energy Effects | Goals | Aug-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,618 | 50 | 3% | 238 | 15% | 18 | 1% | 256 | 16% | 1,380 |
| Annual kWh | 6,432,343 | 185,328 | 3% | 1,141,128 | 18% | 199,448 | 3% | 1,340,576 | 21% | 5,291,215 |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

*Amounts shown in the committed column were completed by VCERC but have not yet been processed by SCE.

    - Performance Goals

| Performance Goals | Goal | Aug-05 | % of Goal | Cumulative | % of Goals | Committed | % of Goal | Cumulative & Committed | % of Goal | Goal Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 1 | 25% | 5 | 125% | n/a | n/a | 5 | 125% | 0 |
| Conduct at least 6 sessions for businesses | 6 | 2 | 33% | 7 | 117% | n/a | n/a | 7 | 117% | 0 |
| Conduct at least 4 events for residential customers. | 4 | 0 | 0% | 5 | 125% | n/a | n/a | 5 | 125% | 0 |
| Promote VCEEC resources and energy efficiency information at 20 community events or more. | 20 | 1 | 5% | 19 | 95% | n/a | n/a | 19 | 95% | 1 |
| Respond to every customer inquiry within 48 hours. |  | met | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Good and Excellent | met | Good and Excellent | met | n/a | n/a | Good and Excellent | met |  |
| Reduce Energy Consumption in Major facilities of VCREA member agencies by 8 % |  | 0 | 0% | 0 | 0% | n/a | n/a | 0 | 0% |  |
| Reduce peak demand in major facilities of VCREA member agencies by 5% or more |  | 0 | 0% | 0 | 0% | n/a | n/a | 0 | 0% |  |

  - Activities/Accomplishments

1.2.1	Administrative -

Routine administrative activities to coordinate and manage the program continue.

1.2.2	Marketing and Outreach

- Prepared and released e-fliers regarding September 8 Multi-family Energy Efficiency Training (Attachment A).

- Prepared the September/ edition of the Energy Leader Newsletter for distribution the first week of September.  (Attachment B)

- VCREA staff met again with representatives of Ventura County Economic Development Association (VCEDA) as part of their monthly meeting to develop details associated with the annual Business Opportunities Conference planned for October 14, 2005.  Representatives of the partnership will be present as speakers and participants.

- VCREA staff was invited to meet with members of the Ventura County Sustainability Council to discuss potential joint efforts to bring the subject of energy efficiency to other parties with common interests.

1.2.3 Direct Implementation

Training

- August 23, 2005 Energy Efficiency Best Practices for Water Pumping Operations/Municipal for 24 participants

- August 23,  Energy Efficiency Best Practices for Water Pumping Operations/ Recreational Sector Training for 4 participants

- August 24, 2005 Energy Efficiency Best Practices for Water Pumping Operations/Agricultural Sector for 6 participants.

The above three training events were presented by XXXXX of Cal State Fresno Pump Efficiency Program and included information from SCE representative, XXXXX.  The events attracted a variety of individuals from throughout the region; pre-registration was greater than the final number of attendees, and there is interest to pursue similar trainings in the future.  (Attachment C).

- September 8, 2005 Multi-family Energy Efficiency Training will be presented by representatives of HMG and targeted to housing authorities, developers of multi-family housing and non-profits operating housing programs.

- October 25, 2005 Energy Efficiency Training for Schools will be presented by XXXXX  and focused on public school district business managers, maintenance and operations staff.

Community Events Participation

- None to report

A summary of plans and accomplishments for all training and community events is included in the Program Spreadsheet. (Attachment D)

      - Audits, Site Surveys and Partnerships -

During the reporting period VCREA’s contractor conducted an energy efficiency audit of the Oxnard Unified School District.   The draft audit report is attached.  (Attachment F)

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Projects and Incentives

VCREA continues to support local public agency efforts to complete energy efficiency.  No new projects were completed this month, but a number of projects are in process:

- The City of Ventura has selected a contractor (XXXXX) to perform HVAC upgrades. The contract is being negotiated and the start of construction is anticipated for late September.

- The City of Ventura is still in the process of completing lighting projects at the Police/Fire Headquarters, Sanjon Road Maintenance Complex and City Hall.

- The City of Thousand Oaks is negotiating the contract for the lighting upgrade at the Civic Arts Plaza.  Lighting projects at the Municipal Service Center and Wastewater Treatment Plant are still in construction.

A monthly update of the identified energy efficiency retrofit projects, costs, energy savings and incentives to date is included as Master Project List (Attachment E)

1.2.3.3. Calculated and Actual Payment Reconciliation -

None

1.2.4	EM&V

No activity this month

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

The partnership has been seeking a change in the program implementation plan (PIP) that would allow the Living Wise School Program to be included in this year’s program effort.  The program is targeted to sixth-grade school students and includes both training and savings components.

VCREA staff and Navigant’s CALeep project consultants continue to work on the program which is intended to help leverage the growing regional interest in energy efficiency associated with new construction and “green” building design.  A case study is underway for the month of September.

- Changes to Subcontractors or Staffing

None

- Additional Items

None