| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Ventura County Regional Energy Alliance – PGC |
| Program Number: | 1403-04 |
| Month: | November 2004 |

- Program Status

Program Description

The Ventura County Regional Energy Alliance (VCREA), in partnership with Southern California Edison (SCE) and the Southern California Gas Company (SCG) proposes to build on the VCREA’s progress to date to further develop its core capabilities, to complete the development of its Energy Resource Center capability, and to implement a targeted Public Sector Program for public agencies throughout the Ventura County region.  This effort will utilize the strengths of the VCREA and its utility partners to jointly overcome identified participation barriers, better serve local needs and hard-to-reach customers, and increase participation in energy efficiency programs.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,273,152 | $320 | 0% | $113,794 | 9% | $26,130 | 2% | $139,924 | 11% | $1,159,358 |
| Admin | $126,899 | $320 | 0% | $43,052 | 34% | $8,378 | 7% | $51,430 | 41% | $83,847 |
| Marketing | $18,575 |  |  | $202 | 1% | $888 | 5% | $1,090 | 6% | $18,373 |
| DI | $1,066,896 |  |  | $70,540 | 7% | $16,864 | 2% | $87,404 | 8% | $996,356 |
| EM&V | $60,781 |  |  |  |  |  |  |  |  | $60,781 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the VCREA to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE processes this information, the costs now shown in the committed column will be reported in the supporting workbook.

    - Energy Effects

| Energy Effects | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 1,618 |  |  |  |  |  |  |  |  | 1,618 |
| Annual kWh | 6,432,343 |  |  |  |  |  |  |  |  | 6,432,343 |
| Lifecyc kWh | 97,593,078 |  |  |  |  |  |  |  |  | 97,593,078 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goal | Nov-04 | % of Goal | Cumulative | % of Goals | Committed | % of Goal | Cumulative & Committed | % of Goal | Goal Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 1 | 25% | n/a | n/a | 1 | 25% | 3 |
| Conduct at least 6 sessions for businesses | 6 | 1 | 17% | 1 | 17% | n/a | n/a | 1 | 17% | 5 |
| Conduct at least 4 events for residential customers. | 4 | 0 | 0% | 0 | 0% | n/a | n/a | 0 | 0% | 4 |
| Promote VCEEC resources and energy efficiency information at 20 community events or more. | 20 | 1 | 5% | 6 | 30% | n/a | n/a | 6 | 30% | 14 |
| Respond to every customer inquiry within 48 hours. |  | 0 | 0% | 0 | 0% | n/a | n/a | 0 | 0% |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Good and Excellent | met | Good and Excellent | met | n/a | n/a | Good and Excellent | met% |  |
| Reduce Energy Consumption in Major facilities of VCREA member agencies by 8 % |  | 0 | 0% | 0 | 0% | n/a | n/a | 0 | 0% |  |
| Reduce peak demand in major facilities of VCREA member agencies by 5% or more |  | 0 | 0% | 0 | 0% | n/a | n/a | 0 | 0% |  |

  - Activities/Accomplishments

1.2.1	Administrative -

- VCERC staff continues to work with partners to facilitate program progress.

    - Marketing and Outreach -

VCERC continues to work with the local community as well as state-wide marketing campaigns to promote the Energy Resource Center as well as diligently working with public agencies to promote the Public Facilities Element of the program.

VCREA:

- Prepared and released e-fliers regarding December Training events

- Coordinated with Flex Your Power to participate in state-wide marketing of energy efficiency programs to appear each Sunday of December in 20 newspapers around the state.

- Planned on participating in a Community Event with the Ventura County Regional Sanitation District to be held December 9, 2004 where VCERC will be hosting an informational table.

- Held two outreach events, November 22 and 23, 2004 to introduce County Employees to the ERC and build interest in the December training events.

- Provided guest editorial for Star Press that featured VCERC activities.

- Published advertising insert in Pacific Coast Business Times to expand knowledge of the VCERC and build interest in future energy efficiency training.

    - Direct Implementation –

- VCREA held one (1) training event on November 19, 2004 on Title 24 Changes - Residential (Public Agency Training 1 of 4).  There were twenty-six (26) attendees.

- VCREA issued RFQ 2004-2 on September 13, 2004.  The purpose of this request for qualifications was to qualify and recommend VFD/motor vendors who can perform a wide variety of energy efficient services for the member agencies of the VCREA.  The RFQ process was patterned after the successful lighting RFQ with intent to develop a competitive selection process that will allow each member agency to move forward with efficiency upgrades without having to bid each separate project.

The RFQ was advertised via the VCREA website, and publicized in the Daily Construction Service, FW Dodge Report and the Ventura County Contractors’ Association.  A number of e-mail notifications were sent to vendors who had a record of interest in this area.  A pre-application meeting was held on October 4, 2004.  Two applicants met the deadline and were in attendance: XXXXX and XXXXX.

- VCREA staff met with each member agency’s purchasing department to discuss the RFQ process, the results, and the steps necessary to begin moving forward with lighting efficiency projects.

- VCREA continues to work with public agencies to secure approvals to commence work on the identified energy efficiency retrofit projects.  A list of projects for which incentives have been reserved is attached.

- VCREA attended the Southern California Gas Summit on September 9 and the Ventura County Council of Governments meeting on September 13, 2004.  These events were not reported in the September report.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

The EM&V consultants toured the VCERC and met with VCREA staff as part of the first interview process.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- VCREA completed discussions with KEMA-Xenergy regarding offering the EEGOV Business Energy Services (B.E.S.T.) Team Program to VCREA member cities within Ventura County and anticipates meeting with KEMA-Xenergy staff in December. A Letter of Cooperation between VCREA and KEMA was approved by the partners and signed by VCREA.

- VCREA staff attended the NAESCO conference event in Orange County to coordinate with managers and officials of other energy efficiency programs.

- VCREA consultant conducted a number of discussions with XXXXX to determine whether they could provide residential new construction training under contract to the VCREA.  Training materials developed under another SCE CPUC-EE Program will be used for the program.  XXXXX to conduct this training during the first quarter of 2005.

- SCE AgTag courses, Pump Test Program information along with relevant SCG offerings are also available.  These programs will be integrated into the partnership’s training activities.

- Changes to Subcontractors or Staffing

- Administrative Assistant XXXXX left the VCREA.  The position will remain vacant and duties will be reassigned to existing staff and new contractor consultants.

- XXXXX has been contracted to develop a detailed marketing plan associated with ERC operations, training and outreach activities.

- XXXXX has been contracted to assist with administrative matters and manage various data base entries.

- Additional Items

None