| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1405-04 |
| Month: | October 2004 |

- Program Status

Program Description

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $610,987 | $156 | 0% | $199,540 | 33% | $20,599 | 3% | $220,139 | 36% | $411,442 |
| Admin | $126,157 | $156 | 0% | $35,766 | 34% | $2,936 | 3% | $38,702 | 37% | $69,888 |
| Marketing | $18,406 |  |  | $15,335 | 83% | $336 | 2% | $15,671 | 85% | $3,071 |
| DI | $439,384 |  |  | $148,439 | 32% | $17,327 | 4% | $165,766 | 36% | $311,443 |
| EM&V | $27,040 |  |  |  |  |  |  |  |  | $27,040 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the SBCCOG to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE processes this information, the costs shown in the committed column, will be reported in the supporting workbook.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Oct-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 2 | 50% | 0 | % | 2 | 50% | 2 |
| Conduct at least 12 sessions for businesses | 12 | 0 | 0% | 1 | 8% | 0 | 0% | 1 | 0% | 11 |
| Conduct at least 4 events for residential customers. | 4 | 1 | 25% | 1 | 50% | 0 | 0% | 2 | 40% | 3 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 3 | 25% | 14 | 116% | 0 | 0% | 14 | 116% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 0 | n/a | 8 | n/a | 0 | n/a | 8 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |

  - Activities/Accomplishments

    - Administrative -

- SBESC continues to work with the Web site contractor to improve and upgrade the website.

- SBESC followed-up with program attendees by mailing thank-you letters and personalized certificates of participation.

    - Marketing –

- SBESC mailed out IOU energy center information to thirty-eight attendees of the workshops held in June and September with cover letter resulting in enrollments in an SCG Energy Resource Center workshop.

- SBESC purchased 500 promotional pens displaying the SBESC telephone number and logo as well as the Save Energy / Save Money message.

- SBESC marketed the October 20 workshop through 768 e-mail blasts, a targeted distribution of 10,000 flyers in The Daily Breeze newspaper, OUT and ABOUT announcement in The Daily Breeze newspaper, event flyers at two Torrance city libraries, and additional flyer distribution to neighboring businesses.

- In furtherance of its goal to market to hard-to-reach customers, SBESC created a Spanish version of its marketing information as well as created an informational leaflet in Spanish from the SCE CARE application for use at the training for mobile home residents.

- SCE posted partnership information on SCE.com.

Outreach Activities

SBESC continues to work with member cities, public officials and community organizations to secure assistance in disseminating energy efficiency information and co-sponsoring and endorsing of training events and displaying energy efficiency information in their facilities.  As the marketing efforts take hold, the center is handling walk-ins and telephone calls from the community and signing out resources from the lending library:

- SBESC collaborated with State of California’s “Flex Your Power” to display their brochures at the SBESC.

- A meeting was held with the manager of the Paradise Mobile Home Park, to discuss the program and plan the upcoming direct install and training event.

- SBESC collaborated with El Camino College to distribute November event flyer to 1,890 manufacturing companies in their database.

- SBESC provided energy efficiency gift bags to “The Torrance Players” and was mentioned as a sponsor of their program.

    - Direct Implementation

- A residential energy efficiency workshop was held at the SBESC on October 20, 2004.  There were fourteen participants.

- SBESC exhibited at the following events:

  - City of Carson event commemorating Ride Share Week on October 6, 2004

  - South Bay 2005 Economic Forecast conference on October 20, 2004

  - The 6th Annual Water Harvest produced by the West Basin Municipal Water District

- In addition to the above events, SBESC worked with a local environmental organization VOICE to promote the center at the Manhattan Beach Old Hometown Fair on October 2 and 3, 2004 and contributed energy efficiency gift bags to the South Bay Family Health Center Community 21st Annual Golf Tournament.

- Work has commenced on the Local Energy Efficiency Action Plan.  A data request was forwarded to SCE and has subsequently been revised.  The work plan for this program element is being developed by SBESC.

- SCE CTAC delivered energy efficiency demonstration units and exhibits for display in the SBESC.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

- A new self-evaluation survey was incorporated provided by the EM&V contractors.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- The SBESC is working with American Synergy Corporation to deliver its Hard-to-reach Mobile Home program to the South Bay.  This is a direct install program and will result in actual kWh savings.  Residential energy efficiency training is being planned in concert with this direct install.  The hard-to-reach mobile home community in the city of Carson is being targeted and the Mayor has expressed a great deal of interest in the program.

- The local SCE Hard-to-reach Small Business Direct Install Program has been identified for participation by South Bay small businesses.  The Multi-family torchiere exchange has also been identified for the South Bay.

- Changes to Subcontractors or Staffing

None

- Additional Items

None