| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1405-04 |
| Month: | March 2005 |

- Program Status

Program Description

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $610,987 | $65,249 | 11% | $419,289 | 69% | $19,322 | 3% | $438,611 | 72% | $191,698 |
| Admin | $126,157 | $7,886 | 6% | $61,043 | 48% | $3,878 | 3% | $64,921 | 51% | $65,114 |
| Marketing | $18,406 | $4,118 | 22% | $13,646 | 74% |  |  | $13,646 | 74% | $4,760 |
| DI | $439,384 | $48,449 | 11% | $337,433 | 77% | $15,444 | 4% | $352,878 | 80% | $101,950 |
| EM&V | $27,040 | $4,795 | 18% | $7,166 | 27% |  |  | $7,166 | 27% | $19,874 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

The partnership agreement allows for an upfront payment to the SBCCOG to fund start-up costs.  Although the payment was made and recorded, actual costs along with supporting documentation have not yet been processed by SCE.  At the time SCE processes this information, the costs shown in the committed column, will be reported in the supporting workbook.

*Includes SCE Reserve payment of $90,268

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 4 | 100% | 0 | 0% | 4 | 100% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 1 | 8% | 5 | 42% | 0 | 0% | 5 | 42% | 7 |
| Conduct at least 4 events for residential customers. | 4 | 4 | 100% | 16 | 400% | 0 | 0% | 16 | 400% | 0 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 1 | 8% | 21 | 175% | 0 | 0% | 21 | 175% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 4 | n/a | 20 | n/a | 0 | n/a | 20 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Activities/Accomplishments

    - Administrative -

- SBESC continues to work with SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

    - Marketing –

SBESC:

- Updated the SBESC website with current information

- Designed ad to be published in The Daily Breeze (circulation 222,008 households.) for the March 31 Business Workshop

- Personalized promotional flyers for five training events.

Outreach Activities

SBESC continues to work with member cities, public officials and community organizations to secure assistance in disseminating energy efficiency information and co-sponsoring training events.  SBESC continues to handle walk-ins and telephone calls from the community and signing out resources from the lending library.  SBESC responded to all calls to the center in less than twenty-four hours.

- SBESC Program Manager attended an Economic Development Committee meeting on March 1 at Inglewood Chamber of Commerce to promote SBESC’s two upcoming energy efficiency training classes scheduled for April 27 and May 11.  These training sessions will be in collaboration with the CPUC-funded FCI Small Business Direct Install Program.

- On March 18 160 CFLs and flyers promoting the upcoming Inglewood business training events were delivered to the Inglewood Chamber of Commerce for distribution to golf tournament participants.

- SBESC Staff met with XXXXX of Torrance Environmental Quality and Energy Conservation Commission, on March 23 to develop a plan of action to involve the council and commission in helping to promote residential and business training for the City of Torrance.

- SBESC is collaborating with the Torrance Volunteer Center’s “A+ for Energy”, a British Petroleum and South High School’s Special Education Department program.   Many students volunteered to brand thousands of pieces of SCE and SCG marketing materials with SBESC logo and contact information.   SBESC is planning to offer an energy efficiency training workshop for students at South High and award Certificates of Participation.   Dr. Sharon Harris of South High was interviewed by ABC television and mentioned SBE$C many times.

    - Direct Implementation

- Training

- SBESC delivered energy efficiency workshops for residential customers during the reporting period as follows:

  - March 10 - Residential training for City of El Segundo staff

  - March 17 - Residential training for City of Carson staff

  - March 31 – Commercial training for local businesses(Central Plant Best Practices) at the Savings Center in Torrance.

- An additional two residential training events were done in cooperation with the American Synergy Hard-to-Reach Mobile Home Program in Carson as follows:

  - March 1 - Imperial Avalon Mobile Home Park.

  - March 29 - Colony Cove  Mobile Home Park

Follow-up for each training event included thank you letters and participation certificates. Most of the attendees rated the events as excellent.

Community Event

- March 5 - Whale of a Day in Rancho Palos Verdes.  Approximately 3,000 visitors attended the event.

Energy Efficiency Action Plan

- SBCCOG has proposed a change in the name of Planning element of the program from The ‘Energy Efficiency Action Plan’ to the ‘Energy Efficiency Assessment’.  The plan is currently being worked on and a first draft will be completed by the end of May 2005.

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

SBESC is reviewing the interim EM&V report to identify ways in which the program may be improved.

Some workshop attendees find the evaluation form prepared by EM&V consultant earlier this program year time consuming and overwhelming.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination/Cooperation Activities

- The local SCE Hard-to-reach Small Business Direct Install Program has been identified for participation by South Bay small businesses.  The Multi-family torchiere exchange has also been identified for the South Bay.

- SBESC is also exploring opportunities to cooperate with various organizations in the City of Inglewood, including a non-IOU direct install program to deliver energy efficiency training to Inglewood businesses.

- SBCCOG is participating in the XXXXX CaLEEP Pilot Program.  XXXXX will complete energy efficiency planning for South Bay Cities.

- Changes to Subcontractors or Staffing

None

- Additional Items

None