| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | VeSM Advantage Plus2 Program - Procurement |
| Program Number: | 1502-04 |
| Month: | November 2004 |

- Program Status

Program Description

The VeSM Advantage Plus2 program will improve manufacturing process efficiency by up to 25%, while improving energy efficiency per unit of output up to 10%, in conjunction with a 4-step approach designed to encourage energy efficiency, meet the needs of small to large size manufactures, and provide an economic boost to the region. VeSM Advantage Plus2 focuses on process improvements that first, improve energy efficiency and second, enhance productivity.  VeSM Advantage Plus2 will:

- Identify and quantify energy efficient process improvement solutions on the shop floor through a unique Value and Energy Stream Mapping assessment (VeSM)

- Implement one or more high-impact, lower-cost energy efficient process improvement solution(s) in an approximate range of savings from 100,000 to 180,000 annual kWh savings (Tier 1 Choices) in energy waste (per participating manufacturer) in accordance with a tailored contractual agreement.

- Lead to additional implementation of one or more high-impact, higher-cost energy efficiency process improvement solution(s) requiring additional incentive to align with acceptable customer payback; identify utility and non utility incentive programs that may lead to the improvements being installed.

- Conduct energy audits to identify additional facility – related energy efficiency opportunities inherent in manufacturing facilities, to encourage upgrading equipment such as lighting, HVAC and refrigeration.

VeSM Advantage Plus2 has improved upon “lean” manufacturing principals including “value stream mapping” (a floor map of the production process) by integrating “energy use” in a unique and first of its kind assessment tool called Value and Energy Stream Mapping (VeSM).

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $940,000 | $50,410 | 5% | $59,822 | 6% | $17,500 | 2% | $77,322 | 8% | $880,178 |
| Admin | $188,500 | $200 | 0% | $5,296 | 3% |  |  | $5,296 | 3% | $183,204 |
| Marketing | $115,500 |  |  |  |  |  |  |  |  | $115,500 |
| DI | $576,000 | $50,210 | 9% | $54,526 | 9% | $17,500 | 3% | $72,026 | 13% | $521,474 |
| EM&V | $60,000 |  |  |  |  |  |  |  |  | $60,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 235 |  |  |  |  | 7 | 3% | 7 | 3% | 235 |
| Annual kWh | 2,822,400 |  |  |  |  | 84,000 | 3% | 84,000 | 3% | 2,822,400 |
| Lifecyc kWh | 56,448,000 |  |  |  |  | 1,680,000 | 3% | 1,680,000 | 3% | 56,448,000 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency Referral Projects From 3 Eight Hour Workshops to 100 Manufacturing Companies | 3 | 0 | 0% | 0 | 0% | 3 | 100% | 3 | 100% | 3 |
| Value Energy Stream Mapping (VeSM) MNR | 12 | 0 | 0% | 0 | 0% | 1 | 8.3% | 1 | 8.3% | 12 |
| Value Energy Stream Mapping (VeSM) LNR | 12 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 12 |
| VeSM Advantage Plus Workshops to 15 Companies Per Event | 3 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3 |

  - Activities/Accomplishments

    - Administrative -

- The project scope of work, budget and purchase order documents have been prepared.

- Purchase Order No. V2114901 was approved and issued on November 17 to the California Manufacturing Technology Center (CMTC), SCE’s primary Program implementation partner.

- CMTC has devised project management protocols to establish roles, assign responsibilities, and track progress.

    - Marketing –

- Screening of potential customers and participating customer intake are now under way.

- The VeSM Workshop is being redesigned to fit the 8-hour timeframe:

    - Revise the lean manufacturing simulation to demonstrate waste in manufacturing

    - New VSM’s are being redrawn to relate to the lean manufacturing simulations

    - Educate the attendees about the relationship between waste in manufacturing and energy use

    - Incorporate benchmarking, energy tools, and best practices to show the financial benefits

    - Add real examples of common efficiency measures at industrial sites with the help of Rudy Marloth at the DOE local program

- Three workshop dates and sites have been selected:

    - February 9, Holiday Inn, Torrance

    - March 16, Embassy Suites, Garden Grove

    - April 20, Hilton Ontario Airport, Ontario

- A brochure promoting the three workshops is under development.  A final copy will be provided in the December Report

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

- Conducted meetings to discuss the VeSM Program with Potential Customers:

    - Windsor Foods (Golden Tiger), Los Angeles

    - Trojan Batteries, Sante Fe Springs

    - Cannon Safe, San Bernardino

    - Lorber Industries, Gardena

- Golden Tiger, a division of Windsor Foods, 6711 Alameda Street, Los Angeles is the first customer to commit to participating in the VeSM Program.

- Recruited Mr. Rudy Marloth from Loyola Maramount University to be a presenter at the workshops.  Mr. Marloth is from the local DOE-sponsored Industrial Assessment Center at Loyola Maramount.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Charges of $49,775 and $4,751, located on Lines 150 and 181, respectively of the Expenditures Tab in the Workbook, were erroneously charged to the program and are in the process of being reversed.

Funding for the VeSM Advantage Plus2 program came as a result of a fundshift from the Direct Implementation budget of the procurement-funded Savings By Design Program that occurred in the month of September.