| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | VeSM Advantage Plus2 Program - Procurement |
| Program Number: | 1502-04 |
| Month: | January 2005 |

- Program Status

Program Description

The VeSM Advantage Plus2 program will improve manufacturing process efficiency by up to 25%, while improving energy efficiency per unit of output up to 10%, in conjunction with a 4-step approach designed to encourage energy efficiency, meet the needs of small to large size manufactures, and provide an economic boost to the region. VeSM Advantage Plus2 focuses on process improvements that first, improve energy efficiency and second, enhance productivity.  VeSM Advantage Plus2 will:

- Identify and quantify energy efficient process improvement solutions on the shop floor through a unique Value and Energy Stream Mapping assessment (VeSM)

- Implement one or more high-impact, lower-cost energy efficient process improvement solution(s) in an approximate range of savings from 100,000 to 180,000 annual kWh savings (Tier 1 Choices) in energy waste (per participating manufacturer) in accordance with a tailored contractual agreement.

- Lead to additional implementation of one or more high-impact, higher-cost energy efficiency process improvement solution(s) requiring additional incentive to align with acceptable customer payback; identify utility and non utility incentive programs that may lead to the improvements being installed.

- Conduct energy audits to identify additional facility – related energy efficiency opportunities inherent in manufacturing facilities, to encourage upgrading equipment such as lighting, HVAC and refrigeration.

VeSM Advantage Plus2 has improved upon “lean” manufacturing principals including “value stream mapping” (a floor map of the production process) by integrating “energy use” in a unique and first of its kind assessment tool called Value and Energy Stream Mapping (VeSM).

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $940,000 | -$912 | 0% | $16,037 | 2% | $35,000 | 4% | $51,037 | 5% | $923,963 |
| Admin | $188,500 | $45 | 0% | $6,239 | 3% |  |  | $6,239 | 3% | $182,261 |
| Marketing | $115,500 |  |  | $3 | 0% |  |  | $3 | 0% | $115,497 |
| DI | $576,000 | -$957 | 0% | $9,796 | 2% | $35,000 | 6% | $44,796 | 8% | $566,204 |
| EM&V | $60,000 |  |  |  |  |  |  |  |  | $60,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 235 |  |  |  |  | 20 | 8% | 20 | 8% | 235 |
| Annual kWh | 2,822,400 |  |  |  |  | 235,200 | 8% | 235,200 | 8% | 2,822,400 |
| Lifecyc kWh | 56,448,000 |  |  |  |  | 4,704,000 | 8% | 4,704,000 | 8% | 56,448,000 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency Referral Projects From 3 Eight Hour Workshops to 100 Manufacturing Companies | 3 | 0 | 0% | 0 | 0% | 3 | 100% | 3 | 100% | 3 |
| Value Energy Stream Mapping (VeSM) MNR | 12 | 0 | 0% | 0 | 0% | 1 | 8.3% | 1 | 8.3% | 12 |
| Value Energy Stream Mapping (VeSM) LNR | 12 | 0 | 0% | 0 | 0% | 1 | 8.3% | 1 | 8.3% | 12 |
| VeSM Advantage Plus Workshops to 15 Companies Per Event | 3 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3 |

  - Activities/Accomplishments

    - Administrative -

- CMTC has devised project management protocols to establish roles, assign responsibilities, and track progress.

- CMTC is cultivating an ongoing relationship with LAEDC, Inland Empire and Orange County EDC partners to market workshops and solicit Program Participants.

- Two Direct Implementation contracts are in place.

- Developed Research Intern position description and requirements.

    - Marketing –

- Plans for three workshops continue:

    - February 9, Holiday Inn, Torrance

    - March 16, Embassy Suites, Garden Grove

    - April 20, Hilton Ontario Airport, Ontario

- E-mail messages have been sent to companies identified at the Made in California Conference as potential VeSM prospects, and other follow-up activities will follow.

- The sales meeting target has been set at 8 per month to meet the goal of generating 4-5 proposals and 2-3 contracts per month.  Project activity is quickly ramping up to that level.

- CMTC Personnel are scheduled to present the VeSM Program at the Society of Plastics on 2/10/05 and at the AEE Annual Expo Conference 2/16/05

- Screening of potential customers and participating customer intake are under way.

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

- Five sales meetings were held in January.  VeSM Team members have conducted meetings to discuss the Program with  the following potential participants:

    - XXXXX, Bell Gardens

    - XXXXX, Irvine

    - XXXXX, Paramount

    - XXXXX Co., Orange

    - XXXXX, La Mirada

- Results are 4 proposals, one decline, 3 Pending Decisions with one highly likely – XXXXX.

- Two projects have been contracted and are in early stages of implementation:

XXXXX (Div. of XXXXX), 6711 Alameda Street, Los Angeles, 90001, XXXXX, VP & General Manager

XXXXX, 12380 Clark Street, Sante Fe Springs, 90670-3804, XXXXX, Dir. of Manufacturing

- One project expected to sign 2/07/05; XXXXX

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None