Confirmation Number:

Program Title:  Statewide Building Operator Certification Program

Proposed by:

Southern California Edison

Contact Person:  	Don Arambula

Address:  		2131 Walnut Grove

Rosemead California  91770

Telephone:  		626-302-8179

Email address:  	don.arambula@sce.com

List of all other public goods charge programs proposed:

- Statewide Residential Appliance Recycling

- Statewide Single Family Energy Efficiency Rebates

- Statewide Multifamily Energy Efficiency Rebates

- Statewide Home Energy Efficiency Surveys

- Statewide CA Energy Star New Homes – Single Family, Multifamily programs

- Statewide Standard Performance Contract

- Statewide Express Efficiency

- Statewide Nonresidential Energy Audits

- Statewide Building Operator Certification

- Statewide Emerging Technologies

- Statewide Savings By Design

- Statewide Education and Training

- Statewide Codes and Standards Advocacy

- Local Small Nonresidential Hard to Reach

- Local Pump Test and Hydraulic Services

- Local Government Initiatives

- Local Community Partnership – 12 Cities

- Local Community Partnership - Ventura County

- Local Community Partnership - South Bay Cities Council of Governments

- Local Los Angeles County program

- Local UC/CSU program

- Local Bakersfield/Kern program

- Local City of Pomona program

Table of Contents

Statewide Building Operator Certification Program	2

I.	Program Overview	2

II.	Program Process	6

III.	Customer Description	8

IV.	Measure and Activity Descriptions	9

IV.	Goals	10

VI.	Program Evaluation, Measurement and Verification (EM&V)	10

VII.	Qualifications	12

VIII.	Budget	15

## Statewide Building Operator Certification Program

## I.	Program Overview

A.	Program Concept

The Building Operator Certification (BOC) and Training Program offered by Pacific Gas and Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E) and Southern California Gas Company (SoCalGas) is a continuation of the uniform statewide building operator training and certification program that began in 2002.  Operators of medium and large commercial buildings (including governmental and institutional buildings and complexes) are the primary target group for this program.  The program content trains operators of these buildings to identify and implement long term annual energy savings and electric peak demand reduction opportunities as an integral part of their operations and maintenance activities.  As a certification program, BOC seeks to establish a recognized professional credential for building operators.

- Program Rationale

The rationale for this information program is to educate operators of commercial buildings including public buildings, on long term annual energy savings and electric peak demand reduction strategies for their buildings.  This is accomplished by educating building operators on how to get the most out of their operating systems by improving their analytical and practical skills on the job.  Through the certification component, BOC provides a consistent benchmark of competencies for participants, competencies expected to be of high value to building owners.  The BOC training will include equipment operations, the latest innovative methods of building operation and maintenance and how to incorporate energy efficiency and peak reduction opportunities.  These opportunities range from installing more energy efficient equipment to proper maintenance of existing equipment for more efficient operations.  The knowledge gained from this training program is expected to improve facility operation skills in both the short-term and long-term post-class periods.  The increased awareness of energy saving knowledge for the building operator community will help achieve electric power demand reductions and energy savings statewide.

The BOC training program was approved for funding in 2002 and 2003.  The first BOC training course series began in October 2002.  Attendance at the initial classes was very encouraging, and recommendations from these early BOC attendees have generated additional interest among their peers.  In 2003, a total of thirteen (11 Level I and 2 Level II courses) statewide training course series were scheduled.  The BOC course is expected to draw over 200 participants on a statewide level.  The 2003 BOC program is expected to be successful with the second BOC graduation class receiving certification in early 2004.

Although this is relatively new program in California, the contractor selected to implement this program has extensive past experience in the Northwest area of the country, and the number of building operators enrolling in the course has steadily continued to climb.  The investor-owned utilities (IOUs) have worked with the Northwest Energy Efficiency Council (NEEC) to develop and improve the training curricula for the Level I and Level II BOC courses in 2003.  NEEC’s training curricula covers subjects pertaining to the equipment and day-to-day operations encountered by building operators, specifically aimed at addressing the energy environment in California.  Classroom homework requires participants to identify energy saving opportunities at their facilities.  The standard Level I curriculum may include, but is not limited to, the following full day training modules:

- 1st class—Building Systems Overview:  Provides an overview of preventive maintenance, energy efficiency principles, and fundamentals of building systems, equipment, and operations.  Reviews heating, cooling, ventilation and control systems, water, lighting, and indoor air quality.  Covers system interaction and relationship to overall building performance.  Provides the foundation for Level I certification courses.

- 2nd class—Facility Electrical Systems:  Develops an understanding of how electricity is distributed in a facility and common electrical distribution problems.  Emphasizes the fundamentals of electricity and its application to the workplace.

- 3rd class—Energy Conservation Techniques:  Helps operators gain a better understanding of how energy is used in commercial buildings and how to identify and prioritize conservation opportunities.  Includes basic principles of energy accounting, evaluation of fuel options, operation and maintenance strategies to improve efficiency, and energy management planning techniques.

- 4th class—HVAC Systems and Controls (Part1):  Focuses on operation and maintenance of equipment and components typically found in commercial buildings, including central heating, cooling, air and ventilating systems in buildings. Provides introduction to automatic control systems and equipment, particularly for central air systems.  Emphasis is placed on group problem solving and exercises with respect to preventive maintenance.

- 5th class—HVAC Systems and Controls (Part 2):  Continued focus on operation and maintenance of equipment and components typically found in commercial buildings, including central heating, cooling, air and ventilating systems in buildings. Provides introduction to automatic control systems and equipment, particularly for central air systems.  Emphasis is placed on group problem solving and exercises with respect to preventive maintenance.

- 6th class—Efficient Lighting Fundamentals:  Covers lighting fundamentals and types of lighting for economical and energy efficient lighting systems.  Participants learn principles of efficient lighting, including evaluation of lighting levels, quality and maintenance.  Other topics include lighting fixture and control technologies, common upgrades, retrofit and redesign options, and management strategies as they apply to space use and function.

- 7th class—Environmental Health & Safety Regulations:  Provides an overview of health, safety, energy, and environmental codes that impact facility operation.  Stresses how to comply with the requirements of the most important health and safety codes and how to use the energy and maintenance-related codes to improve energy efficiency.

- 8th class—Indoor Air Quality:  Introduces the basic causes of indoor air quality problems and begins to develop a method of diagnosis and solution.  Students will gain an understanding of the dynamic components of indoor air quality in relation to source control, occupant sensitivity and ventilation.  Emphasis will be placed on communications with building occupants for reliable investigations without aggravating existing issues.

Level II curriculum may include, but is not limited to, the following full-day training modules:

- 1st class---Preventive Maintenance & Operations:  Covers the step-by-step process for starting and operating a preventive maintenance program that produces energy savings and equipment reliability.  The primary focus is using the system set up to manage and implement preventive maintenance.  Emphasis is on effective troubleshooting methods for problem identification, testing procedures, problem solving and operational analysis.

- 2nd class---Advanced Electrical Diagnostics:  Students will learn to locate and repair electrical opens, shorts, overloads, and high resistance.  The use of digital electric meters is taught along with maintenance and operational procedures to prevent electrical problems and evaluate power quality issue for the facility.

- 3rd class---HVAC Troubleshooting & Maintenance:  Students will learn to troubleshoot and improve the efficiencies of the primary heating, cooling and ventilation systems of their building.  The focus is on system performance evaluation and efficiency optimization of central boiler and chiller systems, vapor-compression cycles of AC and heat pump system, and of distribution and ventilation systems.  (2 days).

- 4th class---HVAC Controls & Optimization:  Provides instruction on energy efficient operation, maintenance and service of HVAC controls and related devices for central air systems commonly found in commercial buildings.  Covers control principles, components, computerized controls, and calibrating the controlled sub-systems.

- 5th class---Mastering Electric Control Circuits:  Introduces basic electric control concept, wiring schematic fundamentals and blueprint to panel-board recognition.  Hands-on activities provide an understanding of ladder logic diagram symbols and their equivalent component counterpart.

- 6th class---Electric Motor Management:  Provides an understanding of how motors work and identifies their uses and applications in facilities.  The student learns about the steps involved in a quality motor repair and how to make effective repair/replacement decisions when motors fail.

All participants are tested to evaluate the amount of knowledge retained.  These tests are designed to confirm the participant’s mastery of the subject material. A certificate of course completion and recognition are awarded to all students that successfully complete this training program and the required testing.  This certificate provides documentation and recognition that the recipient has achieved a fundamental level of knowledge in facility operations and building management in addition to identifying and implementing energy savings opportunities in their facilities.

The BOC training program addresses three distinct market barriers involving information.

- The lack of information:  building operators simply do not have a thorough knowledge of the energy and demand savings available to them.  The BOC program provides thorough knowledge and practical experience in achieving energy and demand savings for successful participants.

- Asymmetric Information:  building operators are often forced to rely on promotional material from vendors and service providers. Although operators are not necessarily naive regarding the objectivity of such information, it is often their only convenient information source.  The BOC course provides tools, information and capability to operators to help evaluate vendor claims. The utilities are uniquely qualified to provide unbiased foundation of knowledge for energy-using systems.

- High information search costs:  many building operators are aware of various methods of getting information regarding technical solutions and services, but lack the time to perform the necessary research.  The BOC program provides in-depth information in a venue that is accessible to any large-building operator.

Through its series of course offerings, the BOC training program offers a systematic approach to reducing information barriers to efficient building operation.  The continuation of the building operator certification program in California is an economical way to promote and market the benefits of operating an energy efficient facility now and in the future.  Moreover the training will increase the likelihood of early identification and adoption of innovative technologies by building operators.

C.	Program Objectives

The IOUs propose to continue the very successful statewide BOC program by providing training and certification to operators of building energy systems within the IOU service areas in 2004 and 2005.  The program’s objective is to educate operators of commercial buildings including public buildings, on long term annual energy savings and electric peak demand reduction strategies for their buildings.  This is accomplished by providing professional credentials to the participating building operators increasing the potential for long term annual energy savings and electric peak demand reduction for the buildings they operate while adding value to their jobs and recognition by their supervisors and throughout the state of California.

## II.	Program Process

- Program Implementation

The IOUs plan to renegotiate with the Northwest Energy Efficiency Council (NEEC) to continue the implementation of the statewide BOC training in 2004 and 2005.  The IOUs will work with NEEC to develop and improve the training curricula for the Level I and Level II BOC courses.  NEEC’s training curricula covers subjects pertaining to the equipment and day-to-day facility operations.

The IOUs plan to contract directly with NEEC for regional classes and certification.  In addition to offering training classes at IOUs facilities, some on-site training may be provided at customer sites, subject to the availability of training, facilities, amount of participants and cost to implement.

All IOUs are expecting to offer the Level II BOC training curricula in 2004 and 2005 subject to the success of the 2003 pilot conducted by PG&E and SCE.  After the Level I BOC training, this is the next phase of training for student participants and focuses on applications learned from the Level I training.  The IOUs will work with NEEC to enhance the training curricula.

This program coordinates with all IOU programs and third party programs related to nonresidential energy efficiency.  Financial incentive programs will be highlighted during the classes along with other educational and seminar events as appropriate.  The statewide IOU Education and Training program will be used as a potential lead generator for customer participation in the BOC program.

- Marketing Plan

The IOUs and NEEC will coordinate marketing efforts to promote this program to nonresidential customers.  NEEC and the IOUs plan to use a proven, systematic approach to recruit building operators to participate in the BOC training.  Marketing activities include e-mail, direct mail and targeted follow up calls to targeted customers, vendors, IOU account representatives and IOU seminar attendees.  The IOU mailing lists and account executives were instrumental in recruiting participants in the 2002 and 2003 course series. The same or greater level of marketing efforts will continue in 2004 and 2005.

Employer-targeted marketing can be effectively accomplished with presentations to local California chapters of facility management associations such as the International Facility Management Association (IFMA), American Society of Hospital Engineers (ASHE), National School Plant Management Association (NSPMA), and the Association of Facility Engineers (AFE).  Members of these associations are directors and managers of facilities and operation and maintenance departments across the full spectrum of facility sectors.  Presentations to associations may feature BOC case studies developed by the IOU’s showing direct benefits to companies with BOC certified operators.  This activity will generate student participation in the short term, while building long-term recognition of the BOC credential among key employers in the state.

Most marketing and communications are handled electronically for the BOC program in order to keep program costs low.  Past use of such methods has proven successful and has resulted in fully subscribed course sessions.  A breakdown of all marketing materials, quantity and projected cost is listed below.

| Item | Quantity (Approx.)* | Method of distribution | Projected Cost* |
| --- | --- | --- | --- |
| BOC brochure | 5000 | E-mailed, mailed or distributed at various customer events | Under $5000 |
| BOC direct mail piece | 5000 | Mailed to potential customers based on input from IOU account representatives | Under $5000 |
| BOC Informational meetings | 2 | Brochures and direct mail invitations are distributed; prospective BOC participants attend informational meeting (usually at course locations) | Under $2000 |

*Annual amounts.  The same amounts are expected to be distributed in each of the years 2004 and 2005.

- Customer Enrollment

BOC training informational meetings will be held in each IOU service area approximately a month before the classes begin to provide information and answer questions about the BOC training.  Customers are directed to contact NEEC for registration in a BOC training course.

- Materials

Not applicable.  The program does not procure, deliver or install equipment.

- Payment of Incentives

Not applicable.  The program does not provide incentive payments.

- Staff and Subcontractor Responsibilities

A program manager at SCE will direct the BOC program within SCE’s service territory.  That program manager will be responsible for overall contractor oversight and contract negotiations, project strategic direction, review of course materials and course enhancements, determination of locations for course delivery, oversight of contractor deliverables, budget management, regulatory reporting and filings and integration with other SCE program efforts.

The prime contractor is responsible for program delivery, including program marketing, participant enrollment, tuition fee collection, course content, course delivery, site logistics and participant certification activities (including record-keeping).  The prime contractor plans to use local independent affiliates as course instructors:  the contractor maintains an instructor certification program to assure quality and consistency for course instruction.

- Work Plan and Timeline for Program Implementation

The following lists the important milestones along with expected target dates:

| Target Dates | Activity |
| --- | --- |
| January 2004 | Program implementation (if CPUC approval) |
| March, 2004 | Statewide BOC brochure available for distribution |
| May, 2004 | 2004 Direct Mail marketing campaign completed |
| July, 2004 | 2004 courses #1 and #2 begin |
| September, 2004 | 2004 courses #3 and #4 begin |
| October, 2004 | 2004 courses #5 and #6 begin |
| February, 2005 | 2005 Direct Mail marketing campaign completed |
| May, 2005 | 2005 course #1 begins |
| July, 2005 | 2005 courses #2 and #3 begin |
| September, 2005 | 2005 courses #4 and #5 begin |
| October, 2005 | 2005 course #6 begins |

Note:  BOC courses consist of eight one-day classes offered approximately once per month over a seven-month period.  To accommodate participant needs, various course start dates are offered throughout the year (to be determined after program approval).  As such, a course beginning in the fall of a given program year will necessarily extend into the following calendar year although funding, accounting and record-keeping remains associated with the original program year.

## III.	Customer Description

- Customer Description

This program primarily targets medium and large nonresidential customers, specifically facility directors and managers, and building operators in the following sectors: government (state, city and federal), military, hospitals, schools and universities, hotels, manufacturing and property management.  Interested small nonresidential customers may also participate in the training program if they have a building operator for their facility.

- Customer Eligibility

This statewide program is open to all PG&E, SCE, SoCalGas or SDG&E nonresidential customers with a building operator at their facility.

- Customer Complaint Resolution

The BOC contractor (NEEC) or the IOU program manager typically handles customer questions, concerns or disputes about the BOC program.  The BOC contractor has procedures in place to identify participant dissatisfaction and is well positioned to make initial efforts to resolve any complaints.  If the BOC contractor is unable to resolve a complaint, the IOU program manager will be contacted.  The IOU program manager will make every effort to resolve the situation to the participant’s satisfaction.  In those rare instances, where a program manager is unable to resolve the issue, the matter will be referred to their management for resolution.

- Geographic Area

This program primarily targets medium and large nonresidential customers, specifically facility directors and managers, and building operators in the service areas of Pacific Gas and Electric Company, Southern California Edison Company, San Diego Gas and Electric Company and Southern California Gas Company.

## IV.	Measure and Activity Descriptions

- Energy Savings Assumptions

Section IV.A is not applicable.  Based upon the California Public Utilities Commission’s approved Energy Efficiency Policy Manual, an information-only program is not reasonably expected to provide an estimate of energy savings.  The lack of energy savings, capacity savings, therm savings, resource benefits, or a TRC ratio for any particular program, i.e., information programs, should not imply that a measure or program does not promote energy efficiency.  Neither should it imply that there is no impact to the customer’s use of electricity or natural gas, nor a corresponding impact to the electricity or natural gas system. Although this program does not create immediate short-term energy savings, it provides a clear, logical, and verifiable link between program activities and eventual energy savings.

- Deviations in Standard Cost-effectiveness Values

Section IV.B is not applicable.

- Rebate Amounts

Section IV.C is not applicable.

- Activities Descriptions

The main activity of the statewide BOC training program is to educate operators of commercial buildings including public buildings, on long term annual energy savings and electric peak demand reduction strategies for their buildings.  In support of this objective, there will be a Level I BOC training course and a Level II BOC training course.  SCE plans on offering 5 Level I courses and 1 Level II course in 2004, and a similar number of offerings in 2005.  The cost per course is expected to be approximately $50,000.

## IV.	Goals

The statewide BOC program progress will be measured through the following metrics:

| BOC Program Annual Deliverables 2004 | Annual Quantity* | Schedule* |
| --- | --- | --- |
| Level I BOC Courses | 5 | Courses initiated by 12/31/04 |
| Level I BOC Course Attendees | 100 | Documented registrants by 12/31/04 |
| Level II BOC Courses | 1 | Course initiated by 12/31/04 |
| Level II BOC Course Attendees | 15 | Documented registrants by 12/31/04 |

*Note:  similar accomplishments are expected for 2005.

## VI.	Program Evaluation, Measurement and Verification (EM&V)

A.	General Approach to Evaluating Program Success

This statewide EM&V plan is based on the Commission’s objectives as outlined in the Energy Efficiency Policy Manual (EE Policy Manual) and adheres to the guidelines in the International Performance Measurement and Verification Protocol (IPMVP).

This statewide EM&V plan will continue to use the existing EE Policy Manual and established EM&V methods to evaluate the program’s success while the M&V Protocols and Framework are being completed.  At such time, a detailed M&V plan will defer to the M&E protocols and framework as appropriate to evaluate the program’s success.

The primary measurement of program success will be the documentation of courses conducted and the number of participants completing the courses.  Another key measurement of program success will be the level of participant satisfaction — one component of a process evaluation which will help refine and optimize program delivery.  The first time the BOC program was delivered in California was PY2002, and data from the evaluation of that program will help establish the baseline for this evaluation.  For 2004 and 2005, an impact evaluation will be added to estimate the energy and demand savings resulting from the program, although it is not required by the EE Policy Manual.  These studies will provide (a) ongoing feedback and corrective guidance regarding program implementation and delivery to customers, (b) indicators of the program’s effectiveness based on analyses of market baseline data and participants’ satisfaction, and (c) qualification of the energy and demand reductions that can be attributed to the program.

B.	Approach to Measure and Verify Energy and Peak Demand Savings

The Measurement and Verification (M&V) approach for the program will be an assessment of the energy and demand savings achieved as a result of the program. Evaluations done elsewhere in the nation have found that it can take 2 to 3 years after participants complete the BOC classes before measurable energy savings are achieved.  The BOC program started in California in 2002, so 2004 is the first year that measurable results would be expected from the PY2002 program.  The participants of that program will be surveyed, and the results of an impact evaluation of those 2002 participants will be applied to the 2004 participants, based on the program theory and identified correlates.  A second phase of the impact evaluation will be done in 2005, building on the findings from the 2004 impact evaluation and surveys of current and previous participants.  Estimates will be based on interviews with program participants and possibly some onsite verification of any efficiency-related operational changes or equipment installations that the participants attribute to their participation in the BOC program.  Savings estimates will be updated to reflect the best available information, as needed.

C.	Approach to Evaluation Program Success

To comply with the objectives of the Commission for ongoing assessment and improvement of programs, the EM&V plan will focus on process issues.  The plan will include 1) analysis of program accomplishments; 2) analysis of program design, delivery and implementation with recommendations for program enhancements; 3) an assessment of participant and participant supervisor satisfaction with BOC; and, 4) possible additional market assessment.  More specifically, these activities may include the following:

- Market Assessment and Customer Behavior Analyses:  Market saturation/potential data from statewide studies currently underway, as well as program evaluation results for the Standard Performance Contracting and Savings by Design programs, will contribute to the market assessment and baseline analysis.

- Process Evaluations:  The research will provide ongoing feedback and corrective guidance regarding program implementation through participant satisfaction studies, and it will provide indicators of the program effectiveness through these studies and program manager interviews.  It will build on the process evaluations done on the 2002 and 2003 BOC programs.

D.	Potential EM&V Contractors

The contactors proposed below can objectively evaluate program success and have performed impact evaluations, measurement and verification studies, process evaluations, markets assessments, and verifications of program accomplishments.  These are firms that have a track record of completing high quality, objective evaluations of energy efficiency programs either for the California investor-owned utilities or for other entities whose studies we have been able to review.  This list does not include all of the qualified evaluators who could objectively evaluate program success.  The final list of evaluation consultants will be based on several factors including: future Commission decisions, the mix of approved programs and the experience of the evaluation consultants.

- ADM Associates

- Aspen Systems Corporation

- Energy & Environmental Economics

- Equipoise Consulting

- Global Energy Partner

- Heschong-Mahone Group

- Itron (RER)

- Kema/Xenergy

- Opinion Dynamics

- Quantum Consulting

- Research into Action

- Ridge & Associates

- RLW Analytics

- TecMRKT Works

## VII.	Qualifications

- Primary Implementer

SCE is responsible for managing and implementing the statewide Building Operator Certification program within SCE’s service territory.  As a whole, SCE is uniquely qualified to provide the core of statewide and local programs that form a solid and reliable foundation of energy savings opportunities that our customers and the State can rely upon.  Over the years, SCE has developed energy efficiency experience, expertise and a support infrastructure that is second to none.  Moreover, our long-term commitment to and credibility with our customers are critical to widespread acceptance of energy efficiency information and recommendations for action.  Finally, SCE provides ironclad accountability to our regulators and the customers we’ve served for over a century that is invaluable to ensuring that public money is appropriately spent.

SCE’s experience in energy efficiency is a century long.  We began assisting customers is the wise use of energy in the early 1900s, when we first began helping our agricultural customers to test the efficiency of their electric pumps.  Beginning in the 1980’s, the energy efficiency programs designed by SCE have been nationally recognized and have helped California assume a leadership role in energy efficiency.  Continuing this tradition of excellence in energy efficiency, SCE’s 2004 - 2005 portfolio of statewide and local programs incorporates innovation into our proven track record of program success in all program areas:

Residential - SCE’s participation in the delivery of residential programs began in the early 1980s, when we began offering comprehensive audits that linked information collected in customer homes by certified energy service representatives to actual billing histories.  Through this unique service, customers received immediate audit results that directed them to rebate programs available for recommended energy-saving measure and device retrofits.  Conservation information materials were also made available to customers for the first time. Today, SCE continues this two-decade tradition through a similar close combination of residential information, energy survey, and rebate services, but updated to reflect today’s technological advances. With a staff comprised of energy efficiency experts with professional experience in other business fields, SCE has designed modern programs that offer a variety of energy efficiency tools on-line, including information, energy use calculator/estimators and an energy survey that provides instantaneous recommendations based on each participating customer’s energy use.  Strong business relationships between SCE and major retailers now enable SCE to pay incentives directly to a customer through several delivery mechanisms: as the result of an application process, at the cash register, or as part of price buy downs at the manufacturer level.  Staff with marketing knowledge develops strategies that call out the best and most efficient method of reaching the right customer group with the program mix that best matches their needs.

Nonresidential - Southern California Edison has provided nonresidential customers with energy efficiency programs under the direction of the Commission since 1976.  Early programs provided information to customers on how to use energy more efficiently through improved operations and maintenance practices.   Since that time, SCE’s programs have evolved, expanded, and diversified into a comprehensive mixture of information and incentive programs.  SCE is a national leader in the development and operation of performance-based energy efficiency incentive programs including DSM Bidding and Standard Performance Contract Programs.  Our programs have grown and contracted, shifted focus and emphasis, or completely changed philosophy as needed to incorporate the changing goals of the Commission, the needs of the marketplace and input of the many stakeholders in the energy efficiency industry.  Most important, SCE’s customers have grown to trust the utility as the single, unbiased source of energy efficiency information, services and programs.  No matter what else was happening to affect customer opinion of the utility industry, our business customers continued to look to SCE for assistance in managing their energy use and costs.

New Construction – For over 20 years, Southern California Edison has designed and operated programs aimed at improving the energy efficiency of new buildings, both residential and nonresidential.  Whether through financial incentives, technology showcases, builder and consumer education, or assistance to design professionals, SCE programs have effected significant, permanent improvements in the energy efficiency of new buildings in its service territory.  Since the early 1990s, builders participating in SCE’s residential programs have built over 50,000 homes that exceeded state building standards.  For nonresidential new construction, SCE has refined and enhanced a wide array of educational and design assistance tools, including free state-of-the-art online technical assistance, for the commercial building industry.  We have a well-respected group of design professionals on our staff including architects and engineers, and we have established alliances throughout the design and construction industry with organizations such as AIA, ASHRAE, IES, AEE, IEEE, CEE.

The program design and implementation team who plan, administer, deliver and support our programs provides unparalleled expertise in energy efficiency programs.  Our program managers have an average of ten years of experience in energy efficiency and related customer service activities and are supported by a veteran staff of technical experts in all facets of energy efficiency.  Our design and technical support staff have over 300 years of combined experience, over two-thirds are licensed by state or federal organizations, and over half have advanced degrees.  Our program design and evaluation staffs also have extensive first-hand knowledge of the customer demographics unique to SCE’s service territory.  After all, for over 100 years we’ve lived and worked with the customers we serve.

Finally, as a utility who serves all of the energy needs of all of our customers, SCE also has an existing infrastructure of support functions (such as accounting, regulatory and legal departments), systems (such as our program tracking and reporting systems) and facilities (such as our energy centers) that we use to facilitate the successful implementation of our programs.  Further, our long-term relationship with the Commission and the customers we serve further ensures that our customers will be well served and protected.  Using the experience and resources described above, SCE stands ready to satisfy our customers’ energy efficiency needs and meet the Commission’s policy objectives.

- Subcontractors

The Northwest Energy Efficiency Council (NEEC) has offered a Building Operator Certification program outside of California for seven years, having conducted 70 full-course series in 17 states, and has awarded over 1200 certifications.  NEEC has been the IOU subcontractor for the BOC training program since the program began is 2002.  To the extent practical, NEEC uses independent affiliates in the local area to conduct individual training sessions; NEEC maintains its own certification requirements for instructors it hires

- Description of Expertise

David Bruder, Nonresidential Manager

Mr. Bruder is a registered mechanical engineer with over 22 years of experience in energy efficiency program management, facility design and construction.  As a project engineer for a major engineering and construction firm, David led and coordinated multi-discipline teams of engineers and architects in the design of large, complex industrial facilities.  At Southern California Edison, David oversees all aspects of a portfolio of non-residential energy efficiency programs, including DSM Bidding, Standard Performance Contracts, and Express Efficiency.  His responsibilities include design and implementation of programs, as well as managing cost and schedule, and tracking and reporting program status to management and the CPUC.

Grant Hjelsand,  Manager, Large Business Energy Efficiency Programs

Grant Hjelsand has had 10 years of experience in program management with Southern California Edison. As a program manager at SCE, Grant has implemented and administered the Demand Side Management Bidding Pilot since 1993, and the Standard Performance Contract program since 1998.  He has also served as program manager of the Building Operators Certification program in 2003.  His prior business experience includes marketing positions in the airline, electronics and banking industries.

## VIII.	Budget