## Net Plant
Southern California Edison
Forecast Additions to Net Plant
| Non-Incentive |  | Incentive |  | Total Non-Incentive and Incentive
Forecast Period Mon-Yr | Gross Additions | CWIP | Gross Additions | CWIP | Gross Additions | CWIP
2017-01-01 | 14441210.6187 | 134080.6217 | 1056402.04 | 908846.65 | 15497612.6587 | 1042927.2717
2017-02-01 | 31772934.5787 | 16379140.5817 | 1350043.13 | 0 | 33122977.7087 | 16379140.5817
2017-03-01 | 14441210.6187 | 134080.6217 | 1328767.64 | 0 | 15769978.2587 | 134080.6217
2017-04-01 | 33332623.6439 | 17282136.6468 | 32542039.55 | 26336912.5 | 65874663.1939 | 43619049.1468
2017-05-01 | 14441210.6187 | 134080.6217 | 936909.14 | 0 | 15378119.7587 | 134080.6217
2017-06-01 | 32633394.6687 | 15939298.6717 | 23124445.83 | 14613775.41 | 55757840.4987 | 30553074.0817
2017-07-01 | 14441210.6187 | 134080.6217 | 2155272.4033 | 0 | 16596483.022 | 134080.6217
2017-08-01 | 14441210.6187 | 134080.6217 | 1484272.4033 | 0 | 15925483.022 | 134080.6217
2017-09-01 | 14441210.6187 | 134080.6217 | 1798475.5233 | 0 | 16239686.142 | 134080.6217
2017-10-01 | 14441210.6187 | 134080.6217 | 1172272.4033 | 0 | 15613483.022 | 134080.6217
2017-11-01 | 53365668.6187 | 14896038.6217 | 853384.2433 | 0 | 54219052.862 | 14896038.6217
2017-12-01 | 147330867.3846 | 52539995.9658 | 4713015.3133 | 0 | 152043882.6979 | 52539995.9658
2018-01-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-02-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-03-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-04-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-05-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-06-01 | 71448147.5 | 17086758.8 | 0 | 0 | 71448147.5 | 17086758.8
2018-07-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-08-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-09-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-10-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-11-01 | 19600304.3379 | 0 | 0 | 0 | 19600304.3379 | 0
2018-12-01 | 103959611.9652 | 5717664.2363 | 0 | 0 | 103959611.9652 | 5717664.2363

## Load Summary
Southern California Edison
Transmission High / Low Voltage Summary ($000)
| High Voltage |  |  | Low Voltage
Month | Incentive | Non-Incentive | Total | Non-Incentive | Total Adds
2017-01-01 | 1056.402 | 14398.8927 | 15455.2947 | 42.3179 | 15497.6127
2017-02-01 | 2406.4452 | 46129.5094 | 48535.9545 | 84.6358 | 48620.5904
2017-03-01 | 3735.2128 | 60528.4021 | 64263.6149 | 126.9538 | 64390.5686
2017-04-01 | 36277.2524 | 93818.7078 | 130095.9602 | 169.2717 | 130265.2318
2017-05-01 | 37214.1615 | 108217.6005 | 145431.762 | 211.5896 | 145643.3516
2017-06-01 | 60338.6073 | 140808.6772 | 201147.2846 | 253.9075 | 201401.1921
2017-07-01 | 62493.8797 | 155207.5699 | 217701.4497 | 296.2254 | 217997.6751
2017-08-01 | 63978.1521 | 169606.4627 | 233584.6148 | 338.5433 | 233923.1581
2017-09-01 | 65776.6277 | 184005.3554 | 249781.983 | 380.8613 | 250162.8443
2017-10-01 | 66948.9001 | 198404.2481 | 265353.1481 | 423.1792 | 265776.3273
2017-11-01 | 67802.2843 | 251727.5988 | 319529.8831 | 465.4971 | 319995.3801
2017-12-01 | 72515.2996 | 399016.1482 | 471531.4478 | 507.815 | 472039.2628
2018-01-01 | 72515.2996 | 418616.4526 | 491131.7522 | 507.815 | 491639.5672
2018-02-01 | 72515.2996 | 438216.7569 | 510732.0565 | 507.815 | 511239.8715
2018-03-01 | 72515.2996 | 457817.0612 | 530332.3609 | 507.815 | 530840.1759
2018-04-01 | 72515.2996 | 477417.3656 | 549932.6652 | 507.815 | 550440.4802
2018-05-01 | 72515.2996 | 497017.6699 | 569532.9695 | 507.815 | 570040.7845
2018-06-01 | 72515.2996 | 568465.8174 | 640981.117 | 507.815 | 641488.932
2018-07-01 | 72515.2996 | 588066.1218 | 660581.4214 | 507.815 | 661089.2364
2018-08-01 | 72515.2996 | 607666.4261 | 680181.7257 | 507.815 | 680689.5407
2018-09-01 | 72515.2996 | 627266.7304 | 699782.03 | 507.815 | 700289.845
2018-10-01 | 72515.2996 | 646867.0348 | 719382.3344 | 507.815 | 719890.1494
2018-11-01 | 72515.2996 | 666467.3391 | 738982.6387 | 507.815 | 739490.4537
2018-12-01 | 72515.2996 | 770426.9511 | 842942.2507 | 507.815 | 843450.0657
Formulas:
Month = DATE(YEAR([Month, row above]),MONTH([Month, row above])+1,1)

## Non-Inc Plant
Southern California Edison
Non-Incentive Plant Additions Forecast
First Forecast Month | 2017-01-01
Blanket Forecast
WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % |  | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less COR/Collectible | 2018 ISO Expenditures Less COR/Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
COS-00-RE-MA-NE7637 | Substation Capital Maintenance | 7637 | High | Blanket | TR-SUB | 0% | 10.02% |  |  | 13300.1884 | 15635.2735 |  | 1332.6789 | 1566.6544 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 111.0566 | 130.5545 | 130.5545 | 130.5545 | 130.5545 | 130.5545 | 130.5545 | 130.5545 | 130.5545 | 130.5545 | 130.5545 | 130.5545 | 130.5545
COS-00-SP-BR-000000 | Seismic assessment and preliminary engineering | 7392 | High | Blanket | TR-SUB | 0% | 100% |  |  | 445.5817 | 0 |  | 445.5817 | 0 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 37.1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COS-00-SP-TD-000000 | Seismic Mitigations for Transmission Substation Assets | 7392 | High | Blanket | TR-SUB | 0% | 100% |  |  | 0 | 13117.2003 |  | 0 | 13117.2003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1093.1 | 1093.1 | 1093.1 | 1093.1 | 1093.1 | 1093.1 | 1093.1 | 1093.1 | 1093.1 | 1093.1 | 1093.1 | 1093.1
CET-ET-IR-CB-421100 | Replace Bulk Power Circuit Breakers | 4211 | High | Blanket | TR-SUB | 0% | 100% |  |  | 2558.84 | 6020.6999 |  | 2558.84 | 6020.6999 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 213.2367 | 501.725 | 501.725 | 501.725 | 501.725 | 501.725 | 501.725 | 501.725 | 501.725 | 501.725 | 501.725 | 501.725 | 501.725
CET-ET-IR-CB-432911 | Non-Bulk Circuit Breaker Replacement Program (115kV and Below) | 4329 | Low | Blanket | TR-SUB | 0% | 100% |  |  | 507.815 | 0 |  | 507.815 | 0 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 42.3179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-OT-OT-ME-313800 | LADWP/Sylmar Miscellaneous Equipment | 3138 | High | Blanket | TR-SUB | 0% | 100% |  |  | 3317.402 | 0 |  | 3317.402 | 0 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 276.4502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-IR-ME-619700 | On-line Dissolved Gas Analysis of Bulk Power Transformer Banks | 6197 | High | Blanket | TR-SUB | 0% | 100% |  |  | 1026.3 | 2129.2198 |  | 1026.3 | 2129.2198 | 85.525 | 85.525 | 85.525 | 85.525 | 85.525 | 85.525 | 85.525 | 85.525 | 85.525 | 85.525 | 85.525 | 85.525 | 177.435 | 177.435 | 177.435 | 177.435 | 177.435 | 177.435 | 177.435 | 177.435 | 177.435 | 177.435 | 177.435 | 177.435
CET-ET-IR-RP-434301 | Non-Bulk Relay Replacement Program ("SRRP") | 4343 | High | Blanket | TR-SUB | 0% | 100% |  |  | 2042.688 | 1209.5125 |  | 2042.688 | 1209.5125 | 170.224 | 170.224 | 170.224 | 170.224 | 170.224 | 170.224 | 170.224 | 170.224 | 170.224 | 170.224 | 170.224 | 170.224 | 100.7927 | 100.7927 | 100.7927 | 100.7927 | 100.7927 | 100.7927 | 100.7927 | 100.7927 | 100.7927 | 100.7927 | 100.7927 | 100.7927
CET-ET-IR-RP-508900 | Bulk Power 500kV Line Relay Replacement | 5089 | High | Blanket | TR-SUB | 0% | 100% |  |  | 9121.8721 | 17248.2254 |  | 9121.8721 | 17248.2254 | 760.156 | 760.156 | 760.156 | 760.156 | 760.156 | 760.156 | 760.156 | 760.156 | 760.156 | 760.156 | 760.156 | 760.156 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521 | 1437.3521
CET-ET-IR-ME-475600 | Substation Equipment Additions & Betterment | 4756 | High | Blanket | TR-SUB | 0% | 100% |  |  | 8656.567 | 11253.085 |  | 8656.567 | 11253.085 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 721.3806 | 937.7571 | 937.7571 | 937.7571 | 937.7571 | 937.7571 | 937.7571 | 937.7571 | 937.7571 | 937.7571 | 937.7571 | 937.7571 | 937.7571
CET-ET-IR-TB-521001 | Substation Transformer Bank Replacement Program (AA-Bank & A-Bank) | 5210 | High | Blanket | TR-SUB | 0% | 100% |  |  | 17485.8017 | 16325.0332 |  | 17485.8017 | 16325.0332 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1457.1501 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194 | 1360.4194
CET-OT-OT-BP-642800 | Generation Interconnection RAS | 6428 | High | Blanket | TR-SUB | 0% | 100% |  |  | 0 | 12658.3511 |  | 0 | 12658.3511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626 | 1054.8626
CET-ET-GA-EM-644600 | Phasor Measurement System Installations | 6446 | High | Blanket | TR-SUB | 0% | 15.06% |  |  | 10193.5001 | 5827.75 |  | 1535.1275 | 877.6514 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 127.9273 | 73.1376 | 73.1376 | 73.1376 | 73.1376 | 73.1376 | 73.1376 | 73.1376 | 73.1376 | 73.1376 | 73.1376 | 73.1376 | 73.1376
CET-PD-IR-SP-SUBSNW | Substation Planned Maintenance Replacements | 3363 | High | Blanket | TR-SUB | 0% | 12.06% |  |  | 18223.3117 | 18672.7117 |  | 2198.0548 | 2252.2604 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 183.1712 | 187.6884 | 187.6884 | 187.6884 | 187.6884 | 187.6884 | 187.6884 | 187.6884 | 187.6884 | 187.6884 | 187.6884 | 187.6884 | 187.6884
CET-PD-BM-SU-SUBSNW | Substation Unplanned Maintenance Replacements | 3363 | High | Blanket | TR-SUB | 0% | 9.46% |  |  | 8282.6102 | 8486.8653 |  | 783.5461 | 802.8689 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 65.2955 | 66.9057 | 66.9057 | 66.9057 | 66.9057 | 66.9057 | 66.9057 | 66.9057 | 66.9057 | 66.9057 | 66.9057 | 66.9057 | 66.9057
CET-PD-ST-SS-SUBSNW | Substation - Storm | 3363 | High | Blanket | TR-SUB | 0% | 7.951% |  |  | 1109.4622 | 1136.8223 |  | 88.2145 | 90.3899 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.3512 | 7.5325 | 7.5325 | 7.5325 | 7.5325 | 7.5325 | 7.5325 | 7.5325 | 7.5325 | 7.5325 | 7.5325 | 7.5325 | 7.5325
CET-PD-IR-TP-TREAST | Transmission Maintenance Planned - Eastern | 3364 | High | Blanket | TR-LINE | 0% | 13.65% |  |  | 16693.0619 | 0 |  | 2279 | 0 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 189.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-PD-IR-TP-TRMETE | Transmission Maintenance Planned - Metro West | 3364 | High | Blanket | TR-LINE | 0% | 73% |  |  | 3000 | 0 |  | 2190 | 0 | 182.5 | 182.5 | 182.5 | 182.5 | 182.5 | 182.5 | 182.5 | 182.5 | 182.5 | 182.5 | 182.5 | 182.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-PD-IR-TP-TRORAN | Transmission Maintenance Planned - Orange | 3364 | High | Blanket | TR-LINE | 0% | 2% |  |  | 3250.764 | 0 |  | 65.0153 | 0 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 5.4179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-PD-IR-TP-HIGH | Transmission Maintenance Planned - Highland | 3364 | High | Blanket | TR-LINE | 0% | 24.72% |  |  | 0 | 33585.1772 |  | 0 | 8303.6523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691.971 | 691.971 | 691.971 | 691.971 | 691.971 | 691.971 | 691.971 | 691.971 | 691.971 | 691.971 | 691.971 | 691.971
CET-PD-BM-TU-TREAST | Transmission Breakdown Maintenance Unplanned | 3364 | High | Blanket | TR-LINE | 0% | 24.95% |  |  | 2257.473 | 2313.1439 |  | 563.3214 | 577.2133 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 46.9434 | 48.1011 | 48.1011 | 48.1011 | 48.1011 | 48.1011 | 48.1011 | 48.1011 | 48.1011 | 48.1011 | 48.1011 | 48.1011 | 48.1011
CET-PD-IR-TR-TREAST | Transmission Deteriorated Pole Repl & Restoration - Eastern | 3364 | High | Blanket | TR-LINE | 0% | 7.992% |  |  | 80937.5747 | 0 |  | 6468.531 | 0 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 539.0442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-PD-IR-TR-TRMETW | Transmission Deteriorated Pole Repl & Restoration - Metro West | 3364 | High | Blanket | TR-LINE | 0% | 1.128% |  |  | 0 | 64361.8155 | 0 | 0 | 725.9545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.4962 | 60.4962 | 60.4962 | 60.4962 | 60.4962 | 60.4962 | 60.4962 | 60.4962 | 60.4962 | 60.4962 | 60.4962 | 60.4962
CET-PD-IR-PT-TREAST | Pole Loading Transmission Pole Replacements - Eastern | 3364 | High | Blanket | TR-LINE | 0% | 7.992% |  |  | 14654.9386 | 0 |  | 1171.2227 | 0 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 97.6019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-PD-IR-PT-TRMETW | Pole Loading Transmission Pole Replacements - Metro West | 3364 | High | Blanket | TR-LINE | 0% | 1.128% |  |  | 0 | 24628.4635 |  | 0 | 277.7912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1493 | 23.1493 | 23.1493 | 23.1493 | 23.1493 | 23.1493 | 23.1493 | 23.1493 | 23.1493 | 23.1493 | 23.1493 | 23.1493
CET-PD-OT-PJ-729800 | Transmission Line Rating Remediation - Metro West, Highland & Eastern Grids | 7298 | High | Blanket | TR-LINE | 0% | 87.1% |  |  | 54454.9043 | 0 |  | 47430.2217 | 0 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 3952.5185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-PD-OT-PJ-TRSJAC | Transmission Line Rating Remediation | 7298 | High | Blanket | TR-LINE | 0% | 87.1% |  |  | 55545.1454 | 146418.2207 |  | 48379.8216 | 127530.2702 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 4031.6518 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225 | 10627.5225
CET-PD-CI-CI-CRINSP | Critical Infrastructure Spare | 3362 | High | Blanket | TR-SUB | 0% | 100% |  |  | 10793 | 0 |  | 10793 | 0 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 899.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-PD-CL-SC-SUBSNW | Substation Claim | 3367 | High | Blanket | TR-SUB | 50% | 7.229% |  |  | 908.5511 | 930.9567 |  | 32.8395 | 33.6493 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.7366 | 2.8041 | 2.8041 | 2.8041 | 2.8041 | 2.8041 | 2.8041 | 2.8041 | 2.8041 | 2.8041 | 2.8041 | 2.8041 | 2.8041
CET-PD-CL-TC-TREAST | Transmission Claim | 3367 | High | Blanket | TR-LINE | 50% | 6.274% |  |  | 2814.9624 | 2884.3814 |  | 88.2989 | 90.4764 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.3582 | 7.5397 | 7.5397 | 7.5397 | 7.5397 | 7.5397 | 7.5397 | 7.5397 | 7.5397 | 7.5397 | 7.5397 | 7.5397 | 7.5397
CET-PD-ST-TS-TREAST | Transmission Storm | 3367 | High | Blanket | TR-LINE | 0% | 18.89% |  |  | 4796.3316 | 4914.6126 |  | 906.0477 | 928.3915 | 75.504 | 75.504 | 75.504 | 75.504 | 75.504 | 75.504 | 75.504 | 75.504 | 75.504 | 75.504 | 75.504 | 75.504 | 77.366 | 77.366 | 77.366 | 77.366 | 77.366 | 77.366 | 77.366 | 77.366 | 77.366 | 77.366 | 77.366 | 77.366
Total Blankets | [8 empty] | 0 | 346378.647 | 409757.5215 | 0 | 171467.809 | 224018.551 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 14288.9841 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126 | 18668.2126
Total Incremental Blankets Plant Balance | [14 empty] | 14288.9841 | 28577.9682 | 42866.9522 | 57155.9363 | 71444.9204 | 85733.9045 | 100022.8886 | 114311.8726 | 128600.8567 | 142889.8408 | 157178.8249 | 171467.809 | 190136.0215 | 208804.2341 | 227472.4467 | 246140.6593 | 264808.8719 | 283477.0844 | 302145.297 | 320813.5096 | 339481.7222 | 358149.9348 | 376818.1473 | 395486.3599
Non-Incentive Specifics Forecast
WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % |  | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less COR/Collectible | 2018 ISO Expenditures Less COR/Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
COS-00-RE-AD-SR0001 | Antelope: Substation Maintenance and Test Building Improvements program | 7924 | High | 2017-12-01 | TR-SUB | 0% | 100% |  | 0 | 5802.9241 | 304.1131 | 0 | 5802.9241 | 304.1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5802.9241 | 25.3428 | 25.3428 | 25.3428 | 25.3428 | 25.3428 | 25.3428 | 25.3428 | 25.3428 | 25.3428 | 25.3428 | 25.3428 | 25.3428
COS-00-RE-AD-SR0003 | Pardee: Substation Maintenance and Test Building Improvements program | 7956 | High | 2017-12-01 | TR-SUB | 0% | 89.1% |  | 0 | 5595.6768 | 304.1131 | 0 | 4985.748 | 270.9648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4985.748 | 22.5804 | 22.5804 | 22.5804 | 22.5804 | 22.5804 | 22.5804 | 22.5804 | 22.5804 | 22.5804 | 22.5804 | 22.5804 | 22.5804
COS-00-RE-AD-SR0004 | Devers: Substation Maintenance and Test Building Improvements program | 7957 | High | 2017-12-01 | TR-SUB | 0% | 84.06% |  | 0 | 6113.795 | 304.1131 | 0 | 5139.2561 | 255.6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5139.2561 | 21.3031 | 21.3031 | 21.3031 | 21.3031 | 21.3031 | 21.3031 | 21.3031 | 21.3031 | 21.3031 | 21.3031 | 21.3031 | 21.3031
COS-00-RE-AD-SR0005 | Santa Clara: Substation Maintenance and Test Building Improvements program | 7958 | High | 2017-12-01 | TR-SUB | 0% | 26.15% |  | 0 | 5751.1122 | 354.7986 | 0 | 1503.9159 | 92.7798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1503.9159 | 7.7317 | 7.7317 | 7.7317 | 7.7317 | 7.7317 | 7.7317 | 7.7317 | 7.7317 | 7.7317 | 7.7317 | 7.7317 | 7.7317
COS-00-RE-AD-SR0006 | Rector: Substation Maintenance and Test Building Improvements program | 7959 | High | 2017-12-01 | TR-SUB | 0% | 57.83% |  | 0 | 6787.3487 | 912.3394 | 0 | 3925.1237 | 527.6059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3925.1237 | 43.9672 | 43.9672 | 43.9672 | 43.9672 | 43.9672 | 43.9672 | 43.9672 | 43.9672 | 43.9672 | 43.9672 | 43.9672 | 43.9672
COS-00-CS-CS-782000 | NERC CIP-14 Physical Security Enhancements | 7820 | High | 2017-12-01 | TR-SUB | 0% | 89% |  | 0.00038952 | 16494.28 | 0 | 0.00034667 | 14679.9092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14679.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-OT-OT-ME-313802 | LADWP DC electrode replacement | 3138 | High | 2017-11-01 | TR-LINE | 0% | 100% |  | 14761.958 | 24162.5 | 5000 | 14761.958 | 24162.5 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38924.458 | 0 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 416.6667 | 416.6667
CET-ET-IR-ME-768101 | Devers: NERC CIP-14 Physical Security Enhancements | 7681 | High | 2017-04-01 | TR-SUB | 0% | 88.21% |  | 19439.238 | 1976.29 | 0 | 17148.056 | 1743.357 | 0 | 0 | 0 | 0 | 18891.413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-IR-ME-782001 | Mira Loma: NERC CIP-14 Physical Security Enhancements | 7820 | High | 2018-12-01 | TR-SUB | 0% | 85.03% |  | 349.727 | 2247.7609 | 16988.319 | 297.3729 | 1911.2711 | 14445.1676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16653.8116
CET-ET-IR-ME-782002 | Pardee: NERC CIP-14 Physical Security Enhancements | 7820 | High | 2018-12-01 | TR-SUB | 0% | 89.1% |  | 271.414 | 1328.3628 | 10787.036 | 241.8299 | 1183.5713 | 9611.2491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11036.6502
CET-ET-IR-ME-782005 | Vincent: NERC CIP-14 Physical Security Enhancements | 7820 | High | 2018-12-01 | TR-SUB | 0% | 100% |  | 322.5858 | 2657.6137 | 12898.765 | 322.5858 | 2657.6137 | 12898.765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15878.9644
CET-ET-IR-ME-782008 | Eldorado: NERC CIP-14 Physical Security Enhancements | 7820 | High | 2018-12-01 | TR-SUB | 0% | 100% |  | 91.8215 | 3746.0536 | 4317.396 | 91.8215 | 3746.0536 | 4317.396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8155.2711
CET-ET-GA-CR-766600 | Colorado River Substation: install Two (2) GE N60 relays (one for CRAS-A and one for CRAS-B) to monitor the status of the Colorado River-Red Bluff No. 1 500 kV transmission line; Two (2) GE N60 relays (one for CRAS-A and one for CRAS-B) to monitor the status of the Colorado River-Red Bluff No. 2 500 kV transmission line; One (1) SEL-2407 Satellite Synchronized Clock; and Two (2) GE D400S Gateways (one for CRAS-A and one for CRAS-B) | 7666 | High | 2017-12-01 | TR-SUB | 0% | 100% |  | 40.866 | 3691.799 | 0 | 40.866 | 3691.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3732.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-GA-CR-766601 | Devers Substation: install Two (2) GE N60 relays (one for CRAS-A and one for CRAS-B) to monitor the status of the Devers-Red Bluff No. 1 500 kV transmission line; Two (2) GE N60 relays (one for CRAS-A and one for CRAS-B) to monitor the status of the Devers-Red Bluff No. 2 500 kV transmission line; One (1) SEL-2407 Satellite Synchronized Clock; and Two (2) GE D400S Gateways (one for CRAS-A and one for CRAS-B). | 7666 | High | 2017-12-01 | TR-SUB | 0% | 100% |  | 32.178 | 645.479 | 0 | 32.178 | 645.479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677.657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-GA-CR-766602 | Red Bluff Substation: install Two (2) GE N60 relays (one for CRAS-A and one for CRAS-B) to monitor the status of the Colorado River – Red Bluff No. 1 500 kV transmission line; and Two (2) GE N60 relays (one for CRAS-A and one for CRAS-B) to monitor 6the status of the Colorado River – Red Bluff No. 2 500 kV transmission line. | 7666 | High | 2017-12-01 | TR-SUB | 0% | 100% |  | 24.354 | 2066.438 | 0 | 24.354 | 2066.438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2090.792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RN-775602 | Whirlwind Sub (POS) a. Equip one (1) 220 kV position at Whirlwind Substation to terminate the Rattlesnake-Whirlwind 220kV Transmission Line with the following Network Upgrades (plan of service):  Two (2) 3000A – 63 kA 220 kV circuit breakers  Four (4) 3000A – 80 kA horizontal –mounted group-operated disconnect switches  One (1) grounding switch attachment  2-1590 KCMIL ACSR conductors as required  Two (2) G.E. C60 breaker management relays (breaker failure) b. Power System Controls. Expand the Whirlwind Substation RTU to provide additional points required for the Project’s 220 kV generation tie-line position. | 7756 | High | 2018-06-01 | TR-SUB | 0% | 100% |  | 57.116 | 1200 | 1000 | 57.116 | 1200 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257.116 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RN-777500 | Whirlwind Subsation (NU): a. Equip one (1) 220 kV position at Whirlwind Substation to terminate the Desert Flower-Whirlwind 220kV Transmission Line with the following Network Upgrades (plan of service): -Two (2) 3000A – 63 kA 220 kV circuit breakers -Four (4) 3000A – 80 kA horizontal–mounted group-operated disconnect switches -One (1) grounding switch attachment 2-1590 KCMIL ACSR conductors as required - Two (2) G.E. C60 breaker management relays (breaker failure) b. Power System Controls. Expand the Whirlwind Substation RTU to provide additional points required for the Project’s 220 kV generation tie-line position. | 7775 | High | 2018-06-01 | TR-SUB | 0% | 100% |  | 0.552 | 50 | 150 | 0.552 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.552 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-LG-TS-538331 | Chino 220/66kV - Add a 4th 280MVA, 220/66kV Transformer Bank and Split the Chino 66kV System | 5383 | High | 2017-12-01 | TR-SUB | 0% | 35% |  | 2724.835 | 1600 | 600 | 953.6922 | 560 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513.6923 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5
CET-ET-LG-TS-682400 | La Fresa Sub (Phase 2 Scope): Install new MEER building and cut over existing protection and upgrade CTs on existing banks. Upgrade SAS from 5.5 to 6X. | 6824 | High | 2017-12-01 | TR-SUB | 0% | 37% |  | 31048.0314 | 1600 | 600 | 11487.7716 | 592 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12079.7716 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5
CET-ET-LG-TS-711300 | El Nido: Install 230 kV (63 kA) double breakers on No. 1 A bank at position 3 and No. 3A bank at position 6. | 7113 | High | 2017-12-01 | TR-SUB | 0% | 100% |  | 4805.7223 | 3617.88 | 0 | 4805.7223 | 3617.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8423.6023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-646800 | Victor Sub: Upgrade protection and install 4 SEL-351 relays | 6468 | High | 2016-12-01 | TR-SUB | 0% | 100% | CWIP Evenly Closed | 1249.983 | 100 | 0 | 1249.983 | 100 | 0 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 112.4986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-711200 | Devers: Equip the 230 KV A-Bank positions (3 & 4) with circuit breakers | 7112 | High | 2017-06-01 | TR-SUB | 0% | 100% |  | 4313.084 | 1450 | 0 | 4313.084 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 5763.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-641503 | Devers Sub: PHASE 1 - Install relays, meters and logic controllers as necessary for IID's new SPS | 6415 | High | 2016-12-01 | TR-SUB | 0% | 100% | CWIP Evenly Closed | 0 | 5 | 0 | 0 | 5 | 0 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-641504 | Mirage Sub: PHASE 1 - Install relays, meters and logic controllers as necessary for IID's new SPS | 6415 | High | 2016-12-01 | TR-SUB | 0% | 100% | CWIP Evenly Closed | 0 | 5 | 0 | 0 | 5 | 0 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-768000 | Santiago Substation: Remove and replace following equipment to other locations within Santiago to vacate synchronous condenser footprint: - Existing 66 kV cap bank; install new 66 kV cap bank adjacent to the 66 kV switchrack. - Relocate existing distribution facilities (underground circuits and station light and power). Equip existing vacant 220 kV switchrack Position 2 with double breakers and disconnects and relocate 1A bank leads to terminate in newly equipped Position 2. Install one 225 MVAR synchronous condenser system. SCE to install leads to interconnect condenser to 220 kV switchrack. | 7680 | High | 2017-12-01 | TR-SUB | 0% | 96% |  | 31410.0564 | 30268.928 | 3000 | 30153.6541 | 29058.1709 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59211.825 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
CET-ET-TP-RL-745100 | Bailey Substation: Engineer and construct a new Mechanical Electrical Equipment Room (MEER) approximately 51' X 72'. Convert existing 66 kV switchrack to double-breaker (ultimate breaker-and-a-half) configuration. Expand 220 kV and 66 kV control cable trenches to the new MEER. Install new protection, control, and metering equipment for all station components. Install new station service AC switchboards. Provide new battery, battery charger, and station DC switchboard. Convert station DC system to radial type. Remove old protection, metering, and control equipment from the existing control house. | 7451 | High | 2017-02-01 | TR-SUB | 0% | 100% |  | 16245.06 | 1086.664 | 0 | 16245.06 | 1086.664 | 0 | 0 | 17331.724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-745101 | Pastoria Substation: Replace relays due to work at Bailey Sub. | 7451 | High | 2016-12-01 | TR-SUB | 0% | 100% | CWIP Evenly Closed | 36.9662 | 64 | 0 | 36.9662 | 64 | 0 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 8.4139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-751800 | Springville Sub: Redesign high side feed from bank on bus to double CB at 220kV position 4 equipped with two (2) new 3000A 220kV CB’s and disconnects. Rebuild the low side at 66kV position 20, with two (2) new 3000A 66kV CB’s, disconnects/ Remove and re-install the existing 1A ground bank to the new 1A ground bank. | 7518 | High | 2017-12-01 | TR-SUB | 0% | 80% |  | 5041.2749 | 2906.762 | 1200 | 4033.0199 | 2325.4096 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6358.4295 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
CET-ET-TP-RL-711900 | Walnut Substation: 1) Convert the Mesa 220 kV Line Position to Double Breaker. 2) Convert the No. 3A and 4A Bank High Side Positions to Double Breaker. 3) Remove the 220 kV North and South Bus Circuit Breakers. | 7119 | High | 2018-12-01 | TR-SUB | 0% | 100% |  | 3631.9908 | 4211.97 | 5693.5302 | 3631.9908 | 4211.97 | 5693.5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13537.491
CET-ET-TP-RL-779000 | Eagle Mountain Substation: Install a 45 MVAR tertiary reactor (effective 34 MVAR @ 12 kV) on the 5A bank at Eagle Mountain substation. Extend Eagle Mountain 230 kV operating bus and install a 45 MVAR shunt reactor at west end of the operating bus. Build a new MEER. | 7790 | High | 2018-12-01 | TR-SUB | 0% | 100% |  | 156.0599 | 3817.391 | 702.8184 | 156.0599 | 3817.391 | 702.8184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4676.2693
CET-ET-TP-RL-754700 | Eldorado Sub: Engineer, remove and install equipment for changing the 500kV line positions at Eldorado substation for the Eldorado – Mohave and Eldorado –Moenkopi 500kV lines. | 7547 | High | 2018-06-01 | TR-SUB | 0% | 100% |  | 400.9857 | 4230 | 1929 | 400.9857 | 4230 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6559.9857 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-754701 | Eldorado-Mohave 500kV: Remove two (2) existing transmission structures. Install three (3) new transmission structures. | 7547 | High | 2018-06-01 | TR-LINE | 0% | 100% |  | 453.5803 | 3000 | 5900 | 453.5803 | 3000 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9353.5803 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-754702 | Eldorado-Moenkopi 500 kV: Remove one (1) existing transmission structure. Install one (1) new transmission structure. | 7547 | High | 2018-06-01 | TR-LINE | 0% | 100% |  | 284.0444 | 1896 | 998 | 284.0444 | 1896 | 998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3178.0444 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-772700 | Inyokern Substation: Expand existing MEER at Inyokern Substation. Install four (4) N60 relays and one (1) satellite clock in the expanded MEER at Inyokern Substation. Replace legacy RTU with new RTU at Inyokern Substation. Program and test RAS. | 7727 | High | 2018-12-01 | TR-SUB | 0% | 37% |  | 8.9439 | 129.05 | 717 | 3.3092 | 47.7485 | 265.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316.3477
CET-ET-TP-RL-772701 | Control Substation: Install 12 (12) N60 relays, one (1) satellite clock, and two (2) ethernet switches in the existing MEER at Control Substation. Add points to existing RTU at Control Substation. Program and test RAS. | 7727 | High | 2018-12-01 | TR-SUB | 0% | 86% |  | 44.9355 | 153.8 | 221 | 38.6446 | 132.268 | 190.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360.9726
CET-ET-TP-RL-772704 | Kramer Substation Install six (6) N60 relays and one (1) satellite clock in the existing MEER at Kramer Substation. Add points to existing RTU at Kramer Substation. Program and test RAS. | 7727 | High | 2018-12-01 | TR-SUB | 0% | 78% |  | 14.2541 | 90 | 176 | 11.1182 | 70.2 | 137.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218.5982
CIT-00-OP-NS-000475 | Cima-Pisgah Optical Ground Wire (OPGW) Cable | 7763 | High | 2018-12-01 | TR-LINE | 0% | 100% |  | 30.212 | 1260 | 456 | 30.212 | 1260 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1746.212
CET-ET-TP-RN-776301 | Lugo 500/220 kV (T) Install two (2) N60 relays Install one (1) ethernet switch Install one (1) satellite switch PSC- RTU Point additions at Lugo PSC-Modify Lugo-Victorville SPS program and test | 7763 | High | 2017-12-01 | TR-SUB | 0% | 100% |  | -1.4848e-13 | 1 | 0 | -1.4848e-13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RN-776304 | Eldorado-Lugo 500 kV line: California (CA) side - Install 85 miles of new OPGW between CA/NV border and Pisgah Substation. | 7763 | High | 2018-12-01 | TR-LINE | 0% | 100% |  | 819.8457 | 2895 | 7357 | 819.8457 | 2895 | 7357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11071.8457
CET-ET-TP-RN-776305 | Eldorado-Lugo 500 kV line: Nevada (NV) Side -Install 2 miles of new OPGW between CA/NV border and MI52-T2 | 7763 | High | 2017-12-01 | TR-LINE | 0% | 100% |  | 72.593 | 150 | 62 | 72.593 | 150 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.593 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667
CET-ET-TP-RL-776300 | Pisgah Sub: Install new telecommunication room. | 7763 | High | 2018-12-01 | TR-SUB | 0% | 100% |  | 72.8738 | 581 | 53 | 72.8738 | 581 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706.8738
CET-ET-TP-RL-764500 | Loop Kramer-Lugo 230 kV #1 & #2 lines into Victor substation | 7645 | High | 2017-06-01 | TR-SUB | 0% | 100% |  | 11126.6776 | 810.966 | 0 | 11126.6776 | 810.966 | 0 | 0 | 0 | 0 | 0 | 0 | 11937.6436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-764501 | Lugo Sub: Perform Protection upgrade | 7645 | High | 2017-06-01 | TR-SUB | 0% | 100% |  | 269.7794 | 3 | 0 | 269.7794 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 272.7794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-764502 | Kramer Sub: Perform Protection upgrade | 7645 | High | 2016-12-01 | TR-SUB | 0% | 100% | CWIP Evenly Closed | 322.0182 | 43.751 | 0 | 322.0182 | 43.751 | 0 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 30.4808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-764503 | Kramer-Lugo lines: Loop into Victor Sub | 7645 | High | 2017-06-01 | TR-LINE | 0% | 100% |  | 95.677 | 123 | 0 | 95.677 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 218.677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-780601 | Kramer Substation: Install One (1) 220kV, 45MVAR Bus Shunt Reactor at Pos. 1x | 7806 | High | 2017-12-01 | TR-SUB | 0% | 100% |  | 626.5407 | 1638.688 | 0 | 626.5407 | 1638.688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2265.2287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-712000 | Chino Sub: equip the No.1A 220kV A-Bank positions with circuit breakers | 7120 | High | 2018-06-01 | TR-SUB | 0% | 65% |  | 24446.893 | 11044.0597 | 10972.5632 | 15890.4805 | 7178.6388 | 7132.1661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30201.2853 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-712002 | Mira Loma Sub: Upgrade protection as needed | 7120 | High | 2018-06-01 | TR-SUB | 0% | 100% |  | 0 | 23.9421 | 73.3374 | 0 | 23.9421 | 73.3374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97.2795 | 0 | 0 | 0 | 0 | 0 | 0
CET-ET-TP-RL-788402 | Tap the remaing Lighthipe 220kV line to Harborgen substation | 7884 | High | 2017-12-01 | TR-LINE | 0% | 100% |  | 175.523 | 100 | 400 | 175.523 | 100 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275.523 | 33.3333 | 33.3333 | 33.3333 | 33.3333 | 33.3333 | 33.3333 | 33.3333 | 33.3333 | 33.3333 | 33.3333 | 33.3333 | 33.3333
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Specifics | [8 empty] | 175320.252 | 169224.2855 | 94432.2425 | 140779.5979 | 150173.6474 | 84495.1609 | 152.2265 | 17483.9505 | 152.2265 | 19043.6396 | 152.2265 | 18344.4106 | 152.2265 | 152.2265 | 152.2265 | 152.2265 | 39076.6845 | 133041.8833 | 932.0918 | 932.0918 | 932.0918 | 932.0918 | 932.0918 | 52779.9349 | 932.0918 | 932.0918 | 932.0918 | 932.0918 | 932.0918 | 85291.3994
Total Incremental Non-Incentive Specifics Plant Balance | [14 empty] | 152.2265 | 17636.177 | 17788.4036 | 36832.0431 | 36984.2697 | 55328.6803 | 55480.9068 | 55633.1333 | 55785.3599 | 55937.5864 | 95014.271 | 228056.1543 | 228988.246 | 229920.3378 | 230852.4295 | 231784.5213 | 232716.6131 | 285496.548 | 286428.6397 | 287360.7315 | 288292.8232 | 289224.915 | 290157.0068 | 375448.4061
Total Incremental Non-Incentive Plant Balance | [14 empty] | 14441.2106 | 46214.1452 | 60655.3558 | 93987.9795 | 108429.1901 | 141062.5847 | 155503.7954 | 169945.006 | 184386.2166 | 198827.4272 | 252193.0958 | 399523.9632 | 419124.2676 | 438724.5719 | 458324.8762 | 477925.1806 | 497525.4849 | 568973.6324 | 588573.9368 | 608174.2411 | 627774.5454 | 647374.8498 | 666975.1541 | 770934.7661

## Inc CWIP & Plant
Southern California Edison
Incentive CWIP & Plant Additions Forecast
|  | First Forecast Month | 2017-01-01
Devers Colorado River (DCR)
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date No AFUDC on Incentive Projects (*INC), Trailing Charges are closed the month expenditures are incurred
Projects | Balance Type | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Devers Colorado River (DCR) | Closings | CET-ET-TP-EC-484716 | Devers: Replace Eleven 230kV CB'S | 4847 | High | 2013-05-01 | TR-SUBINC | 0% | 100% | 0 | -80.2877 | 0 | 0 | -80.2877 | 0 | 0 | -80.2697 | -0.01802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DCR | Total Specifics | [7 empty] | 0 | -80.2877 | 0 | 0 | -80.2877 | 0 | 0 | -80.2697 | -0.01802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Devers Colorado River (DCR) | [13 empty] | 0 | -80.2697 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877 | -80.2877
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Devers Colorado River (DCR) | Expenditures | CET-ET-TP-EC-484716 | Devers: Replace Eleven 230kV CB'S | 4847 | High | 2013-05-01 | TR-SUBINC | 0% | 100% | 0 | -80.2877 | 0 | 0 | -80.2877 | 0 | 0 | -80.2697 | -0.01802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Devers Colorado River (DCR) | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 0 | -80.2877 | 0 | 0 | -80.2877 | 0 | 0 | -80.2697 | -0.01802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date No AFUDC on Incentive Projects (*INC), Trailing Charges are closed the month expenditures are incurred
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Tehachapi Segments 3B & 3C | Closings | CET-ET-TP-RN-718300 | 230 kV Transmission Line Between Highwind and Windhub Substations | 7183 | High | 2012-12-01 | TR-LINEINC | 0% | 100% | 0 | 4.6648 | 0 | 0 | 4.6648 | 0 | -7.5018 | 4.4475 | 7.7191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Closings | CET-ET-TP-RN-718301 | Highwind Substation: Visual Mitigation Measures | 7183 | High | 2015-08-01 | TR-SUBINC | 0% | 100% | 0 | -0.52109 | 0 | 0 | -0.52109 | 0 | 0 | -0.52097 | -0.00012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TRTP All Segments | Total Specifics | [7 empty] | 0 | 4.1437 | 0 | 0 | 4.1437 | 0 | -7.5018 | 3.9265 | 7.719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Tehachapi Segments 3B & 3C | [13 empty] | -7.5018 | -3.5753 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437 | 4.1437
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Tehachapi Segments 3B & 3C | Expenditures | CET-ET-TP-RN-718300 | 230 kV Transmission Line Between Highwind and Windhub Substations | 7183 | High | 2012-12-01 | TR-LINEINC | 0% | 100% | 0 | 4.6648 | 0 | 0 | 4.6648 | 0 | 2017-01-01: -7.5018; 2017-02-01: 4.4475; 2017-03-01: 7.7191; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Tehachapi Segments 3B & 3C | Expenditures | CET-ET-TP-RN-718301 | Highwind Substation: Visual Mitigation Measures | 7183 | High | 2015-08-01 | TR-SUBINC | 0% | 100% | 0 | -0.52109 | 0 | 0 | -0.52109 | 0 | 2017-01-01: 0; 2017-02-01: -0.52097; 2017-03-01: -0.00012
Tehachapi Segments 3B & 3C | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 3B & 3C | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 0 | 4.1437 | 0 | 0 | 4.1437 | 0 | -7.5018 | 3.9265 | 7.719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date No AFUDC on Incentive Projects (*INC), Trailing Charges are closed the month expenditures are incurred
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-643500 | I: TRTP 4-1: Antelope-Whirlwind 500kV T/L: Construct new 14-mile single-circuit 500kV T/L. | 6435 | High | 2012-04-01 | TR-LINEINC | 0% | 100% | 0 | 331.707 | 0 | 0 | 331.707 | 0 | 1.5694 | 1.4175 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 314.5959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-RP-TP-RN-643500 | TRTP Segment 4 Land & Easements | 6435 | High | 2013-01-01 | TR-LANDRGTINC | 0% | 100% | 0 | 500 | 0 | 0 | 500 | 0 | 2.151 | 0.2337 | -15.6253 | 8 | 25 | 50 | 50 | 85 | 95 | 75 | 75 | 50.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-547202 | I: TRTP 5-3: Antelope-Vincent #2 500kV: Construct new 18-miles single-circuit T/L on existing right of way. | 5472 | High | 2013-01-01 | TR-LINEINC | 0% | 100% | 0 | 7.8914 | 0 | 0 | 7.8914 | 0 | 1.5694 | 1.4175 | 1.5694 | 1.569 | 1.569 | 0.19715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-524301 | I: TRTP 6-2: New Vincent-Duarte 500kV: Construct new 27 miles single-circuit 500kV T/L on existing ROW vacated by Antelope-Mesa line. | 5243 | High | 2014-11-01 | TR-LINEINC | 0% | 100% | 0 | 1600 | 0 | 0 | 1600 | 0 | 30.6323 | 146.7429 | 217.789 | 30.6323 | 30.6323 | 30.6323 | 30.6323 | 30.6323 | 30.6323 | 30.6323 | 30.6323 | 959.7773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-643803 | I: TRTP 7-2: Vincent-Rio Hondo #2: Construct 0.61 mile DC 500kV T/L cutover to connect new 27-miles 500kV T/L to existing Vincent-Rio Hondo #2. | 6438 | High | 2015-01-01 | TR-LINEINC | 0% | 100% | 0 | 3.0795 | 0 | 0 | 3.0795 | 0 | 10.2101 | -8.3274 | 1.1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-643801 | I: TRTP 7-3: Antelope-Mesa 230kV T/L: Construct new 16-mile double-circuit 500kV T/L (2B-2156 ACSR)between the City of Duarte and near the Mesa SS. | 6438 | High | 2014-12-01 | TR-LINEINC | 0% | 100% | 0 | 2000 | 0 | 0 | 2000 | 0 | 28.0003 | 88.3334 | 65.1186 | 50 | 50 | 1583.6663 | 50 | 50 | 34.8814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-643907 | I: TRTP 8-8: Mira Loma-Vincent: Construct new 33 miles 500kV T/L between Mesa and Mira Loma (Section of Mira Loma and Vincent). | 6439 | High | 2015-03-01 | TR-LINEINC | 0% | 100% | 0 | 3200 | 0 | 0 | 3200 | 0 | 83.3236 | 258.0145 | 378.6783 | 250 | 250 | 1658.6619 | 250 | 50 | 21.3217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-755304 | Mira Loma-Vincent 500 kV T/L (UG): Civil & Cable Portion | 7553 | High | 2016-08-01 | TR-LINEINC | 0% | 100% | 0 | 6979 | 0 | 0 | 6979 | 0 | 161.3776 | 559.6817 | 262.0038 | 250 | 250 | 2300 | 700 | 300 | 300 | 250 | 250 | 1395.9369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-755300 | Mira Loma Substation | 7553 | High | 2016-12-01 | TR-SUBINC | 0% | 100% | 0 | 233.7975 | 0 | 0 | 233.7975 | 0 | 212.0408 | 12.4271 | 9.3297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-755301 | Vincent Substation | 7553 | High | 2016-10-01 | TR-SUBINC | 0% | 100% | 0 | 42.9356 | 0 | 0 | 42.9356 | 0 | 13.3177 | 16.9528 | 12.6651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-RP-TP-RN-755300 | Acquire easements for CHUG - TRTP-Segment 8 | 7553 | High | 2016-01-01 | TR-FEELANDINC | 0% | 100% | 0 | 15.3022 | 0 | 0 | 15.3022 | 0 | 0.84663 | 15.4138 | -0.95822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-RP-TP-RN-755300 | TRTP-Segment 8A CHUG: Land/ Easements Acquisition/ Condemnation | 7553 | High | 2017-06-01 | TR-FEELANDINC | 0% | 100% | 149.0589 | 2000.0033 | 0 | 149.0589 | 2000.0033 | 0 | 0 | 0 | 0 | 0 | 0 | 454.1811 | 300 | 300 | 300 | 300 | 250 | 244.8812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-755302 | East Transition Station | 7553 | High | 2017-06-01 | TR-SUBINC | 0% | 100% | 13857.642 | 750 | 0 | 13857.642 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 14106.3838 | 25 | 25 | 200 | 200 | 31.1118 | 20.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-755303 | West Transition Station | 7553 | High | 2016-12-01 | TR-SUBINC | 0% | 100% | 0 | 750 | 0 | 0 | 750 | 0 | 28.2462 | 24.5083 | 12.6916 | 25 | 25 | 25 | 25 | 25 | 200 | 200 | 100 | 59.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-755305 | Chino Hills Related OH Line Work | 7553 | High | 2016-08-01 | TR-LINEINC | 0% | 100% | 0 | 36.5819 | 0 | 0 | 36.5819 | 0 | 35.5737 | 1.6051 | -0.59692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-644017 | TRTP SEGMENT 9: WHIRLWIND - CONSTRUCT NEW SUBSTATION | 6440 | High | 2012-12-01 | TR-SUBINC | 0% | 100% | 0 | 58.6523 | 0 | 0 | 58.6523 | 0 | 1.5691 | 1.4175 | 1.5704 | 1.5691 | 1.5691 | 1.5691 | 1.5691 | 1.5691 | 1.5691 | 1.5691 | 1.5691 | 41.5425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-644006 | TRTP 9: VINCENT-UPGRADE 500KV & 220KV POSITIONS | 6440 | High | 2017-01-01 | TR-SUBINC | 0% | 100% | 908.8466 | 0 | 0 | 908.8466 | 0 | 0 | 908.8466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-644100 | I: TRTP 10-1: Whirlwind-Windhub 500kV: Construct approx. 17 miles of new single-circuit 500kV T/L between Whirlwind and Windhub Substations. | 6441 | High | 2012-04-01 | TR-LINEINC | 0% | 100% | 0 | 1965.1195 | 0 | 0 | 1965.1195 | 0 | 1.5694 | 1.4175 | 1.7209 | 1.5694 | 1.5694 | 1947.8569 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 1.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-644203 | I: TRTP 11-1: Mesa-Vincent #1 500kV: Construct 18.6 miles Mesa-Vincent #1 500kV T/L. Construct approx. 18 miles of new single-circuit 500kV T/L from Vincent SS to the Gould SS area. | 6442 | High | 2015-05-01 | TR-LINEINC | 0% | 100% | 0 | 6629.8143 | 0 | 0 | 6629.8143 | 0 | -121.8204 | 190.7909 | 2648.0045 | 100 | 100 | 100 | 600 | 600 | 600 | 100 | 100 | 1612.8392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-644202 | I: TRTP 11-2: Mesa-Gould 220kV: String approx. 18 miles of new 220kV conductor on vacant position of existing 220kV double-circuit tower line between Mesa and Gould area. | 6442 | High | 2015-05-01 | TR-LINEINC | 0% | 100% | 0 | 792.0562 | 0 | 0 | 792.0562 | 0 | 0 | 0 | 792.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | CET-ET-TP-RN-644200 | I: TRTP 11-4: Eagle Rock-Pardee 230kV: Construct 2 miles of single-circuit T/L to terminate Eagle Rock-Pardee 230kV T/L into Vincent. Construct approx. 0.2 mile of single-circuit T/L to connect Eagle Rock-Pardee T/L into Gould SS. | 6442 | High | 2015-05-01 | TR-LINEINC | 0% | 100% | 0 | -3321.2628 | 0 | 0 | -3321.2628 | 0 | -0.03812 | 0 | -3168.2247 | -153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TRTP All Segments | Total Specifics | [7 empty] | 14915.5475 | 24574.6779 | 0 | 14915.5475 | 24574.6779 | 0 | 1398.9853 | 1312.0467 | 1220.5585 | 566.9091 | 736.9091 | 22259.7179 | 2035.3401 | 1470.3401 | 1786.5433 | 1160.3401 | 841.452 | 4701.0831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Tehachapi Segments 4-11 | [13 empty] | 1398.9853 | 2711.032 | 3931.5905 | 4498.4996 | 5235.4088 | 27495.1267 | 29530.4668 | 31000.807 | 32787.3502 | 33947.6904 | 34789.1424 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254 | 39490.2254
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-643500 | I: TRTP 4-1: Antelope-Whirlwind 500kV T/L: Construct new 14-mile single-circuit 500kV T/L. | 6435 | High | 2012-04-01 | TR-LINEINC | 0% | 100% | 0 | 331.707 | 0 | 0 | 331.707 | 0 | 2017-01-01: 1.5694; 2017-02-01: 1.4175; 2017-03-01: 1.5694; 2017-04-01: 1.5694; 2017-05-01: 1.5694; 2017-06-01: 1.5694; 2017-07-01: 1.5694; 2017-08-01: 1.5694; 2017-09-01: 1.5694; 2017-10-01: 1.5694; 2017-11-01: 1.5694; 2017-12-01: 314.5959
Tehachapi Segments 4-11 | Expenditures | CET-RP-TP-RN-643500 | TRTP Segment 4 Land & Easements | 6435 | High | 2013-01-01 | TR-LANDRGTINC | 0% | 100% | 0 | 500 | 0 | 0 | 500 | 0 | 2017-01-01: 2.151; 2017-02-01: 0.2337; 2017-03-01: -15.6253; 2017-04-01: 8; 2017-05-01: 25; 2017-06-01: 50; 2017-07-01: 50; 2017-08-01: 85; 2017-09-01: 95; 2017-10-01: 75; 2017-11-01: 75; 2017-12-01: 50.2406
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-547202 | I: TRTP 5-3: Antelope-Vincent #2 500kV: Construct new 18-miles single-circuit T/L on existing right of way. | 5472 | High | 2013-01-01 | TR-LINEINC | 0% | 100% | 0 | 7.8914 | 0 | 0 | 7.8914 | 0 | 2017-01-01: 1.5694; 2017-02-01: 1.4175; 2017-03-01: 1.5694; 2017-04-01: 1.569; 2017-05-01: 1.569; 2017-06-01: 0.19715
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-524301 | I: TRTP 6-2: New Vincent-Duarte 500kV: Construct new 27 miles single-circuit 500kV T/L on existing ROW vacated by Antelope-Mesa line. | 5243 | High | 2014-11-01 | TR-LINEINC | 0% | 100% | 0 | 1600 | 0 | 0 | 1600 | 0 | 2017-01-01: 30.6323; 2017-02-01: 146.7429; 2017-03-01: 217.789; 2017-04-01: 30.6323; 2017-05-01: 30.6323; 2017-06-01: 30.6323; 2017-07-01: 30.6323; 2017-08-01: 30.6323; 2017-09-01: 30.6323; 2017-10-01: 30.6323; 2017-11-01: 30.6323; 2017-12-01: 959.7773
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-643803 | I: TRTP 7-2: Vincent-Rio Hondo #2: Construct 0.61 mile DC 500kV T/L cutover to connect new 27-miles 500kV T/L to existing Vincent-Rio Hondo #2. | 6438 | High | 2015-01-01 | TR-LINEINC | 0% | 100% | 0 | 3.0795 | 0 | 0 | 3.0795 | 0 | 2017-01-01: 10.2101; 2017-02-01: -8.3274; 2017-03-01: 1.1968; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-643801 | I: TRTP 7-3: Antelope-Mesa 230kV T/L: Construct new 16-mile double-circuit 500kV T/L (2B-2156 ACSR)between the City of Duarte and near the Mesa SS. | 6438 | High | 2014-12-01 | TR-LINEINC | 0% | 100% | 0 | 2000 | 0 | 0 | 2000 | 0 | 2017-01-01: 28.0003; 2017-02-01: 88.3334; 2017-03-01: 65.1186; 2017-04-01: 50; 2017-05-01: 50; 2017-06-01: 1583.6663; 2017-07-01: 50; 2017-08-01: 50; 2017-09-01: 34.8814
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-643907 | I: TRTP 8-8: Mira Loma-Vincent: Construct new 33 miles 500kV T/L between Mesa and Mira Loma (Section of Mira Loma and Vincent). | 6439 | High | 2015-03-01 | TR-LINEINC | 0% | 100% | 0 | 3200 | 0 | 0 | 3200 | 0 | 2017-01-01: 83.3236; 2017-02-01: 258.0145; 2017-03-01: 378.6783; 2017-04-01: 250; 2017-05-01: 250; 2017-06-01: 1658.6619; 2017-07-01: 250; 2017-08-01: 50; 2017-09-01: 21.3217
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-755304 | Mira Loma-Vincent 500 kV T/L (UG): Civil & Cable Portion | 7553 | High | 2016-08-01 | TR-LINEINC | 0% | 100% | 0 | 6979 | 0 | 0 | 6979 | 0 | 2017-01-01: 161.3776; 2017-02-01: 559.6817; 2017-03-01: 262.0038; 2017-04-01: 250; 2017-05-01: 250; 2017-06-01: 2300; 2017-07-01: 700; 2017-08-01: 300; 2017-09-01: 300; 2017-10-01: 250; 2017-11-01: 250; 2017-12-01: 1395.9369
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-755300 | Mira Loma Substation | 7553 | High | 2016-12-01 | TR-SUBINC | 0% | 100% | 0 | 233.7975 | 0 | 0 | 233.7975 | 0 | 2017-01-01: 212.0408; 2017-02-01: 12.4271; 2017-03-01: 9.3297; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-755301 | Vincent Substation | 7553 | High | 2016-10-01 | TR-SUBINC | 0% | 100% | 0 | 42.9356 | 0 | 0 | 42.9356 | 0 | 2017-01-01: 13.3177; 2017-02-01: 16.9528; 2017-03-01: 12.6651; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Tehachapi Segments 4-11 | Expenditures | CET-RP-TP-RN-755300 | Acquire easements for CHUG - TRTP-Segment 8 | 7553 | High | 2016-01-01 | TR-FEELANDINC | 0% | 100% | 0 | 15.3022 | 0 | 0 | 15.3022 | 0 | 2017-01-01: 0.84663; 2017-02-01: 15.4138; 2017-03-01: -0.95822; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Tehachapi Segments 4-11 | Expenditures | CET-RP-TP-RN-755300 | TRTP-Segment 8A CHUG: Land/ Easements Acquisition/ Condemnation | 7553 | High | 2017-06-01 | TR-FEELANDINC | 0% | 100% | 149.0589 | 2000.0033 | 0 | 149.0589 | 2000.0033 | 0 | 2017-01-01: 0.07422; 2017-02-01: 0.0446; 2017-03-01: 0.00333; 2017-04-01: 5; 2017-05-01: 150; 2017-06-01: 150; 2017-07-01: 300; 2017-08-01: 300; 2017-09-01: 300; 2017-10-01: 300; 2017-11-01: 250; 2017-12-01: 244.8812
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-755302 | East Transition Station | 7553 | High | 2017-06-01 | TR-SUBINC | 0% | 100% | 13857.642 | 750 | 0 | 13857.642 | 750 | 0 | 2017-01-01: 140.6238; 2017-02-01: 28.2644; 2017-03-01: 4.8537; 2017-04-01: 25; 2017-05-01: 25; 2017-06-01: 25; 2017-07-01: 25; 2017-08-01: 25; 2017-09-01: 200; 2017-10-01: 200; 2017-11-01: 31.1118; 2017-12-01: 20.1463
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-755303 | West Transition Station | 7553 | High | 2016-12-01 | TR-SUBINC | 0% | 100% | 0 | 750 | 0 | 0 | 750 | 0 | 2017-01-01: 28.2462; 2017-02-01: 24.5083; 2017-03-01: 12.6916; 2017-04-01: 25; 2017-05-01: 25; 2017-06-01: 25; 2017-07-01: 25; 2017-08-01: 25; 2017-09-01: 200; 2017-10-01: 200; 2017-11-01: 100; 2017-12-01: 59.5539
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-755305 | Chino Hills Related OH Line Work | 7553 | High | 2016-08-01 | TR-LINEINC | 0% | 100% | 0 | 36.5819 | 0 | 0 | 36.5819 | 0 | 2017-01-01: 35.5737; 2017-02-01: 1.6051; 2017-03-01: -0.59692; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-644017 | TRTP SEGMENT 9: WHIRLWIND - CONSTRUCT NEW SUBSTATION | 6440 | High | 2012-12-01 | TR-SUBINC | 0% | 100% | 0 | 58.6523 | 0 | 0 | 58.6523 | 0 | 2017-01-01: 1.5691; 2017-02-01: 1.4175; 2017-03-01: 1.5704; 2017-04-01: 1.5691; 2017-05-01: 1.5691; 2017-06-01: 1.5691; 2017-07-01: 1.5691; 2017-08-01: 1.5691; 2017-09-01: 1.5691; 2017-10-01: 1.5691; 2017-11-01: 1.5691; 2017-12-01: 41.5425
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-644006 | TRTP 9: VINCENT-UPGRADE 500KV & 220KV POSITIONS | 6440 | High | 2017-01-01 | TR-SUBINC | 0% | 100% | 908.8466 | 0 | 0 | 908.8466 | 0 | 0 | 2017-01-01: 0; 2017-02-01: 0; 2017-03-01: 0; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-644100 | I: TRTP 10-1: Whirlwind-Windhub 500kV: Construct approx. 17 miles of new single-circuit 500kV T/L between Whirlwind and Windhub Substations. | 6441 | High | 2012-04-01 | TR-LINEINC | 0% | 100% | 0 | 1965.1195 | 0 | 0 | 1965.1195 | 0 | 2017-01-01: 1.5694; 2017-02-01: 1.4175; 2017-03-01: 1.7209; 2017-04-01: 1.5694; 2017-05-01: 1.5694; 2017-06-01: 1947.8569; 2017-07-01: 1.5694; 2017-08-01: 1.5694; 2017-09-01: 1.5694; 2017-10-01: 1.5694; 2017-11-01: 1.5694; 2017-12-01: 1.5694
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-644203 | I: TRTP 11-1: Mesa-Vincent #1 500kV: Construct 18.6 miles Mesa-Vincent #1 500kV T/L. Construct approx. 18 miles of new single-circuit 500kV T/L from Vincent SS to the Gould SS area. | 6442 | High | 2015-05-01 | TR-LINEINC | 0% | 100% | 0 | 6629.8143 | 0 | 0 | 6629.8143 | 0 | 2017-01-01: -121.8204; 2017-02-01: 190.7909; 2017-03-01: 2648.0045; 2017-04-01: 100; 2017-05-01: 100; 2017-06-01: 100; 2017-07-01: 600; 2017-08-01: 600; 2017-09-01: 600; 2017-10-01: 100; 2017-11-01: 100; 2017-12-01: 1612.8392
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-644202 | I: TRTP 11-2: Mesa-Gould 220kV: String approx. 18 miles of new 220kV conductor on vacant position of existing 220kV double-circuit tower line between Mesa and Gould area. | 6442 | High | 2015-05-01 | TR-LINEINC | 0% | 100% | 0 | 792.0562 | 0 | 0 | 792.0562 | 0 | 2017-01-01: 0; 2017-02-01: 0; 2017-03-01: 792.0562; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Tehachapi Segments 4-11 | Expenditures | CET-ET-TP-RN-644200 | I: TRTP 11-4: Eagle Rock-Pardee 230kV: Construct 2 miles of single-circuit T/L to terminate Eagle Rock-Pardee 230kV T/L into Vincent. Construct approx. 0.2 mile of single-circuit T/L to connect Eagle Rock-Pardee T/L into Gould SS. | 6442 | High | 2015-05-01 | TR-LINEINC | 0% | 100% | 0 | -3321.2628 | 0 | 0 | -3321.2628 | 0 | 2017-01-01: -0.03812; 2017-02-01: 0; 2017-03-01: -3168.2247; 2017-04-01: -153; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
Tehachapi Segments 4-11 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 14915.5475 | 24574.6779 | 0 | 14915.5475 | 24574.6779 | 0 | 630.8366 | 1340.3558 | 1225.4155 | 596.9091 | 911.9091 | 7874.153 | 2035.3401 | 1470.3401 | 1786.5433 | 1160.3401 | 841.452 | 4701.0831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Red Bluff Substation
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date No AFUDC on Incentive Projects (*INC), Trailing Charges are closed the month expenditures are incurred
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Red Bluff Substation | Closings | CET-ET-TP-RN-692900 | Remaining Red Bluff Substation Work (Minor Additions to Red Bluff) | 6929 | High | 2016-01-01 | TR-SUBINC | 0% | 100% | 0 | 5.2984 | 0 | 0 | 5.2984 | 0 | 0 | 3.2694 | 2.0289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Red Bluff Substation | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Red Bluff Substation | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Red Bluff Substation | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Red Bluff Substation | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Red Bluff | Total Specifics | [7 empty] | 0 | 5.2984 | 0 | 0 | 5.2984 | 0 | 0 | 3.2694 | 2.0289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Red Bluff Substation | [13 empty] | 0 | 3.2694 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984 | 5.2984
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Red Bluff Substation | Expenditures | CET-ET-TP-RN-692900 | Remaining Red Bluff Substation Work (Minor Additions to Red Bluff) | 6929 | High | 2016-01-01 | TR-SUBINC | 0% | 100% | 0 | 5.2984 | 0 | 0 | 5.2984 | 0 | 2017-01-01: 0; 2017-02-01: 3.2694; 2017-03-01: 2.0289; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Red Bluff Substation | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Red Bluff Substation | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Red Bluff Substation | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Red Bluff Substation | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 0 | 5.2984 | 0 | 0 | 5.2984 | 0 | 0 | 3.2694 | 2.0289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eldorado - Ivanpah
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date No AFUDC on Incentive Projects (*INC), Trailing Charges are closed the month expenditures are incurred
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Eldorado - Ivanpah | Closings | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eldorado - Ivanpah | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eldorado - Ivanpah | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eldorado - Ivanpah | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Eldorado-Ivanpah | Total Specifics | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Eldorado - Ivanpah | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Eldorado - Ivanpah | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Eldorado - Ivanpah | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Eldorado - Ivanpah | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Eldorado - Ivanpah | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lugo-Pisgah
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date No AFUDC on Incentive Projects (*INC), Trailing Charges are closed the month expenditures are incurred
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Lugo-Pisgah | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lugo-Pisgah | Total Specifics | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Lugo-Pisgah | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Lugo-Pisgah | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer)
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date No AFUDC on Incentive Projects (*INC), Trailing Charges are closed the month expenditures are incurred
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Calcite Southern (formerly Jasper; part of South of Kramer) | Closings | CET-ET-TP-RN-690200 | Jasper: LGIA Engineer and construct a new interconnection facility | 6902 | High | 2020-11-01 | TR-SUBINC | 0% | 100% | 4204.9271 | 550.2492 | 2900 | 4204.9271 | 550.2492 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Closings | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0
| South of Kramer | Total Specifics | [7 empty] | 4204.9271 | 550.2492 | 2900 | 4204.9271 | 550.2492 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Calcite Southern (formerly Jasper; part of South of Kramer) | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Calcite Southern (formerly Jasper; part of South of Kramer) | Expenditures | CET-ET-TP-RN-690200 | Jasper: LGIA Engineer and construct a new interconnection facility | 6902 | High | 2020-11-01 | TR-SUBINC | 0% | 100% | 4204.9271 | 550.2492 | 2900 | 4204.9271 | 550.2492 | 2900 | 23.9737 | 42.8823 | 91.2492 | 50 | 50 | 50 | 43.144 | 50 | 50 | 40 | 35 | 24 | 75 | 75 | 125 | 125 | 200 | 250 | 375 | 375 | 375 | 375 | 300 | 250
Calcite Southern (formerly Jasper; part of South of Kramer) | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Calcite Southern (formerly Jasper; part of South of Kramer) | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 4204.9271 | 550.2492 | 2900 | 4204.9271 | 550.2492 | 2900 | 23.9737 | 42.8823 | 91.2492 | 50 | 50 | 50 | 43.144 | 50 | 50 | 40 | 35 | 24 | 75 | 75 | 125 | 125 | 200 | 250 | 375 | 375 | 375 | 375 | 300 | 250
West of Devers
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
West of Devers | Closings | CET-ET-TP-RN-642001 | Pre-Engineering (Morongo Transmission Relocation Project) | 6420 | High | 2021-08-01 | TR-LINEINC | 0% | 100% | 63970.4512 | 366.7224 | 55 | 63970.4512 | 366.7224 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West of Devers | Closings | CET-ET-TP-RN-642012 | Devers Sub: Install 220kV CBs & DSs | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 121.0308 | 949.6564 | 500 | 121.0308 | 949.6564 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West of Devers | Closings | CET-ET-TP-RN-642013 | El Casco Sub: Install 220kV Terminal Equipment | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 59.5197 | 1410.0452 | 500 | 59.5197 | 1410.0452 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West of Devers | Closings | CET-ET-TP-RN-642014 | Etiwanda Sub: Install 220kV Relay Equipment | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 52.0649 | 479.8177 | 267 | 52.0649 | 479.8177 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West of Devers | Closings | CET-ET-TP-RN-642015 | San Bernardino : Install Disconnects | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 78.9689 | 899.5519 | 1100 | 78.9689 | 899.5519 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West of Devers | Closings | CET-ET-TP-RN-642017 | Rebuild Devers-El Casco & El Casco-San Bernardino 220kV | 6420 | High | 2021-08-01 | TR-LINEINC | 0% | 100% | 4633.3488 | 24399.3451 | 230350 | 4633.3488 | 24399.3451 | 230350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West of Devers | Closings | CET-ET-TP-RN-642016 | Vista Sub: Install Disconnects | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 112.6959 | 1032.2773 | 698 | 112.6959 | 1032.2773 | 698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West of Devers | Closings | CET-RP-TP-RN-642000 | Acquire Easements for West of Devers | 6420 | High | 2021-08-01 | TR-LANDRGTINC | 0% | 100% | 657.1645 | 8223.1717 | 6344 | 657.1645 | 8223.1717 | 6344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| West of Devers | Total Specifics | [7 empty] | 69685.2447 | 37760.5877 | 239814 | 69685.2447 | 37760.5877 | 239814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - West of Devers | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
West of Devers | Expenditures | CET-ET-TP-RN-642001 | Pre-Engineering (Morongo Transmission Relocation Project) | 6420 | High | 2021-08-01 | TR-LINEINC | 0% | 100% | 63970.4512 | 366.7224 | 55 | 63970.4512 | 366.7224 | 55 | 309.2541 | 5.5508 | 7.6826 | 12.235 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
West of Devers | Expenditures | CET-ET-TP-RN-642012 | Devers Sub: Install 220kV CBs & DSs | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 121.0308 | 949.6564 | 500 | 121.0308 | 949.6564 | 500 | 15.3384 | 36.2193 | 4.5498 | 65.549 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 78 | 10 | 10 | 10 | 10 | 50 | 50 | 50 | 50 | 80 | 80 | 50 | 50
West of Devers | Expenditures | CET-ET-TP-RN-642013 | El Casco Sub: Install 220kV Terminal Equipment | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 59.5197 | 1410.0452 | 500 | 59.5197 | 1410.0452 | 500 | 2.1781 | 12.8916 | 2.0016 | 512.974 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 130 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 25 | 15
West of Devers | Expenditures | CET-ET-TP-RN-642014 | Etiwanda Sub: Install 220kV Relay Equipment | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 52.0649 | 479.8177 | 267 | 52.0649 | 479.8177 | 267 | 13.84 | 9.3067 | 24.369 | 0.06 | 10 | 10 | 10 | 10 | 10 | 10 | 30 | 342.242 | 10 | 10 | 10 | 10 | 10 | 10 | 40 | 40 | 40 | 47 | 20 | 20
West of Devers | Expenditures | CET-ET-TP-RN-642015 | San Bernardino : Install Disconnects | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 78.9689 | 899.5519 | 1100 | 78.9689 | 899.5519 | 1100 | 25.3145 | 15.1691 | 92.0913 | 21.977 | 0 | 0 | 0 | 200 | 200 | 200 | 100 | 45 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 50 | 50
West of Devers | Expenditures | CET-ET-TP-RN-642017 | Rebuild Devers-El Casco & El Casco-San Bernardino 220kV | 6420 | High | 2021-08-01 | TR-LINEINC | 0% | 100% | 4633.3488 | 24399.3451 | 230350 | 4633.3488 | 24399.3451 | 230350 | 6.3161 | 532.5815 | 1119.8484 | 342.547 | 1072.006 | 1133.255 | 1362.014 | 1844.682 | 2489.466 | 3613.262 | 3236.76 | 7646.607 | 8000 | 8000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 22000 | 28175 | 22000 | 22175
West of Devers | Expenditures | CET-ET-TP-RN-642016 | Vista Sub: Install Disconnects | 6420 | High | 2021-08-01 | TR-SUBINC | 0% | 100% | 112.6959 | 1032.2773 | 698 | 112.6959 | 1032.2773 | 698 | 6.8553 | 40.0459 | 977.297 | 8.079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 50 | 50 | 100 | 100 | 100 | 100 | 79 | 79
West of Devers | Expenditures | CET-RP-TP-RN-642000 | Acquire Easements for West of Devers | 6420 | High | 2021-08-01 | TR-LANDRGTINC | 0% | 100% | 657.1645 | 8223.1717 | 6344 | 657.1645 | 8223.1717 | 6344 | 48.8864 | 95.8253 | 261.661 | 30.188 | 295.297 | 195.297 | 2195.297 | 2195.297 | 1938.297 | 695.297 | 196.829 | 75 | 300 | 500 | 800 | 800 | 800 | 800 | 800 | 853 | 691 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 69685.2447 | 37760.5877 | 239814 | 69685.2447 | 37760.5877 | 239814 | 427.9829 | 747.5901 | 2489.5007 | 993.609 | 1393.303 | 1354.552 | 3567.311 | 4249.979 | 5137.763 | 5018.559 | 4063.589 | 8316.849 | 8471 | 8671 | 20991 | 20991 | 21071 | 21060 | 21140 | 21193 | 23061 | 28552 | 22224 | 22389
Colorado River Substation
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Colorado River Substation | Closings | CET-ET-TP-RL-707600 | Colorado River Substation: Install Equipment to support Large Generation Interconnections. | 7076 | High | 2013-07-01 | TR-SUBINC | 0% | 100% | 0 | -377.5108 | 0 | 0 | -377.5108 | 0 | -377.4247 | -0.0014 | -0.08473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Colorado River Substation | Closings | CET-ET-TP-RN-706102 | Devers: Relays for D-RB 500kV N-2 SPS | 7061 | High | 2015-05-01 | TR-SUBINC | 0% | 100% | 0 | 399.9787 | 0 | 0 | 399.9787 | 0 | 42.3432 | 111.0716 | 98.564 | 15 | 50 | 50 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Colorado River Substation | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Colorado River Substation | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Colorado River | Total Specifics | [7 empty] | 0 | 22.468 | 0 | 0 | 22.468 | 0 | -335.0815 | 111.0702 | 98.4793 | 15 | 50 | 50 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Colorado River Substation | [13 empty] | -335.0815 | -224.0113 | -125.532 | -110.532 | -60.532 | -10.532 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468 | 22.468
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Colorado River Substation | Expenditures | CET-ET-TP-RL-707600 | Colorado River Substation: Install Equipment to support Large Generation Interconnections. | 7076 | High | 2013-07-01 | TR-SUBINC | 0% | 100% | 0 | -377.5108 | 0 | 0 | -377.5108 | 0 | 2017-01-01: -377.4247; 2017-02-01: -0.0014; 2017-03-01: -0.08473; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Colorado River Substation | Expenditures | CET-ET-TP-RN-706102 | Devers: Relays for D-RB 500kV N-2 SPS | 7061 | High | 2015-05-01 | TR-SUBINC | 0% | 100% | 0 | 399.9787 | 0 | 0 | 399.9787 | 0 | 2017-01-01: 42.3432; 2017-02-01: 111.0716; 2017-03-01: 98.564; 2017-04-01: 15; 2017-05-01: 50; 2017-06-01: 50; 2017-07-01: 33; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Colorado River Substation | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Colorado River Substation | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 0 | 22.468 | 0 | 0 | 22.468 | 0 | -335.0815 | 111.0702 | 98.4793 | 15 | 50 | 50 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Whirlwind Substation Expansion Project
Incentive Specifics Forecast
Note: Incentive Specific Projects are loaded for OH and closed based on the specific date
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Whirlwind Substation Expansion Project | Closings | CET-ET-TP-RL-769500 | Install N60 relays to add generation to Whirlwind AA Bank SPS | 7695 | High | 2017-06-01 | TR-SUBINC | 0% | 100% | 607.0746 | 129.2469 | 0 | 607.0746 | 129.2469 | 0 | 0 | 0 | 0 | 0 | 0 | 664.7279 | 11.9323 | 11.9323 | 11.9323 | 11.9323 | 11.9323 | 11.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Whirlwind Substation Expansion Project | Closings | CET-ET-TP-RN-765000 | Whirlwind 3rd AA bank and SPS | 7650 | High | 2017-04-01 | TR-SUBINC | 0% | 100% | 26336.9125 | 6000.2179 | 0 | 26336.9125 | 6000.2179 | 0 | 0 | 0 | 0 | 31960.1304 | 150 | 150 | 75 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Whirlwind Substation Expansion Project | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Whirlwind Substation Expansion Project | Closings | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Whirlwind | Total Specifics | [7 empty] | 26943.987 | 6129.4648 | 0 | 26943.987 | 6129.4648 | 0 | 0 | 0 | 0 | 31960.1304 | 150 | 814.7279 | 86.9323 | 13.9323 | 11.9323 | 11.9323 | 11.9323 | 11.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incremental Plant Balance - Whirlwind Substation Expansion Project | [13 empty] | 0 | 0 | 0 | 31960.1304 | 32110.1304 | 32924.8583 | 33011.7906 | 33025.7228 | 33037.6551 | 33049.5874 | 33061.5196 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519 | 33073.4519
CWIP Incentive Expenditure Forecast
Note: Incentive CWIP is part of Rate Base as Expenditures are made, No AFUDC is applied, Includes Incentive LHFFU
|  | WBS | WBS Description | Pin # | Voltage | Forecast Date | Asset Class | Collectible % | ISO % | 2016 CWIP | 2017 Total Expenditures | 2018 Total Expenditures | 2016 ISO CWIP Less Collectible | 2017 ISO Expenditures Less Collectible | 2018 ISO Expenditures Less Collectible | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Whirlwind Substation Expansion Project | Expenditures | CET-ET-TP-RL-769500 | Install N60 relays to add generation to Whirlwind AA Bank SPS | 7695 | High | 2017-06-01 | TR-SUBINC | 0% | 100% | 607.0746 | 129.2469 | 0 | 607.0746 | 129.2469 | 0 | 2017-01-01: 3.4416; 2017-02-01: 7.5815; 2017-03-01: 10.8334; 2017-04-01: 11.9323; 2017-05-01: 11.9323; 2017-06-01: 11.9323; 2017-07-01: 11.9323; 2017-08-01: 11.9323; 2017-09-01: 11.9323; 2017-10-01: 11.9323; 2017-11-01: 11.9323; 2017-12-01: 11.9323
Whirlwind Substation Expansion Project | Expenditures | CET-ET-TP-RN-765000 | Whirlwind 3rd AA bank and SPS | 7650 | High | 2017-04-01 | TR-SUBINC | 0% | 100% | 26336.9125 | 6000.2179 | 0 | 26336.9125 | 6000.2179 | 0 | 2017-01-01: 650.7221; 2017-02-01: 871.7498; 2017-03-01: 3450.746; 2017-04-01: 650; 2017-05-01: 150; 2017-06-01: 150; 2017-07-01: 75; 2017-08-01: 2; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0
Whirlwind Substation Expansion Project | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Whirlwind Substation Expansion Project | Expenditures | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Incentive CWIP Expenditures (Excludes OH) | [7 empty] | 26943.987 | 6129.4648 | 0 | 26943.987 | 6129.4648 | 0 | 654.1637 | 879.3313 | 3461.5795 | 661.9323 | 161.9323 | 161.9323 | 86.9323 | 13.9323 | 11.9323 | 11.9323 | 11.9323 | 11.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Inc CWIP & Plant Summary
Southern California Edison
Incentive CWIP and Plant Summary
Incentive CWIP Expenditures
| Month |  | Total All Projects | Devers Colorado River (DCR) | Tehachapi Segments 1 - 3A | Tehachapi Segments 3B & 3C | Tehachapi Segments 4-11 | Red Bluff Substation | Eldorado - Ivanpah | Lugo-Pisgah | Calcite Southern (formerly Jasper; part of South of Kramer) | West of Devers | Colorado River Substation | Whirlwind Substation Expansion Project | Rancho Vista
Recorded | 2016-12-01 | Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast | 2017-01-01 | Expenditures | 1394.3736 | 0 | 0 | -7.5018 | 630.8366 | 0 | 0 | 0 | 23.9737 | 427.9829 | -335.0815 | 654.1637 | 0
| 2017-02-01 | Expenditures | 3048.1558 | -80.2697 | 0 | 3.9265 | 1340.3558 | 3.2694 | 0 | 0 | 42.8823 | 747.5901 | 111.0702 | 879.3313 | 0
| 2017-03-01 | Expenditures | 7375.9541 | -0.01802 | 0 | 7.719 | 1225.4155 | 2.0289 | 0 | 0 | 91.2492 | 2489.5007 | 98.4793 | 3461.5795 | 0
| 2017-04-01 | Expenditures | 2317.4504 | 0 | 0 | 0 | 596.9091 | 0 | 0 | 0 | 50 | 993.609 | 15 | 661.9323 | 0
| 2017-05-01 | Expenditures | 2567.1444 | 0 | 0 | 0 | 911.9091 | 0 | 0 | 0 | 50 | 1393.303 | 50 | 161.9323 | 0
| 2017-06-01 | Expenditures | 9490.6373 | 0 | 0 | 0 | 7874.153 | 0 | 0 | 0 | 50 | 1354.552 | 50 | 161.9323 | 0
| 2017-07-01 | Expenditures | 5765.7274 | 0 | 0 | 0 | 2035.3401 | 0 | 0 | 0 | 43.144 | 3567.311 | 33 | 86.9323 | 0
| 2017-08-01 | Expenditures | 5784.2514 | 0 | 0 | 0 | 1470.3401 | 0 | 0 | 0 | 50 | 4249.979 | 0 | 13.9323 | 0
| 2017-09-01 | Expenditures | 6986.2385 | 0 | 0 | 0 | 1786.5433 | 0 | 0 | 0 | 50 | 5137.763 | 0 | 11.9323 | 0
| 2017-10-01 | Expenditures | 6230.8314 | 0 | 0 | 0 | 1160.3401 | 0 | 0 | 0 | 40 | 5018.559 | 0 | 11.9323 | 0
| 2017-11-01 | Expenditures | 4951.9732 | 0 | 0 | 0 | 841.452 | 0 | 0 | 0 | 35 | 4063.589 | 0 | 11.9323 | 0
| 2017-12-01 | Expenditures | 13053.8643 | 0 | 0 | 0 | 4701.0831 | 0 | 0 | 0 | 24 | 8316.849 | 0 | 11.9323 | 0
| 2018-01-01 | Expenditures | 8546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 8471 | 0 | 0 | 0
| 2018-02-01 | Expenditures | 8746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 8671 | 0 | 0 | 0
| 2018-03-01 | Expenditures | 21116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 20991 | 0 | 0 | 0
| 2018-04-01 | Expenditures | 21116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 20991 | 0 | 0 | 0
| 2018-05-01 | Expenditures | 21271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 21071 | 0 | 0 | 0
| 2018-06-01 | Expenditures | 21310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 21060 | 0 | 0 | 0
| 2018-07-01 | Expenditures | 21515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 21140 | 0 | 0 | 0
| 2018-08-01 | Expenditures | 21568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 21193 | 0 | 0 | 0
| 2018-09-01 | Expenditures | 23436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 23061 | 0 | 0 | 0
| 2018-10-01 | Expenditures | 28927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 28552 | 0 | 0 | 0
| 2018-11-01 | Expenditures | 22524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 22224 | 0 | 0 | 0
| 2018-12-01 | Expenditures | 22639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 22389 | 0 | 0 | 0
Incentive Plant Closings
| Month |  | Total All Projects | Devers Colorado River (DCR) | Tehachapi Segments 1 - 3A | Tehachapi Segments 3B & 3C | Tehachapi Segments 4-11 | Red Bluff Substation | Eldorado - Ivanpah | Lugo-Pisgah | Calcite Southern (formerly Jasper; part of South of Kramer) | West of Devers | Colorado River Substation | Whirlwind Substation Expansion Project | Rancho Vista
Recorded | 2016-12-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast | 2017-01-01 | Closings | 1056.402 | 0 | 0 | -7.5018 | 1398.9853 | 0 | 0 | 0 | 0 | 0 | -335.0815 | 0 | 0
| 2017-02-01 | Closings | 1350.0431 | -80.2697 | 0 | 3.9265 | 1312.0467 | 3.2694 | 0 | 0 | 0 | 0 | 111.0702 | 0 | 0
| 2017-03-01 | Closings | 1328.7676 | -0.01802 | 0 | 7.719 | 1220.5585 | 2.0289 | 0 | 0 | 0 | 0 | 98.4793 | 0 | 0
| 2017-04-01 | Closings | 32542.0395 | 0 | 0 | 0 | 566.9091 | 0 | 0 | 0 | 0 | 0 | 15 | 31960.1304 | 0
| 2017-05-01 | Closings | 936.9091 | 0 | 0 | 0 | 736.9091 | 0 | 0 | 0 | 0 | 0 | 50 | 150 | 0
| 2017-06-01 | Closings | 23124.4458 | 0 | 0 | 0 | 22259.7179 | 0 | 0 | 0 | 0 | 0 | 50 | 814.7279 | 0
| 2017-07-01 | Closings | 2155.2724 | 0 | 0 | 0 | 2035.3401 | 0 | 0 | 0 | 0 | 0 | 33 | 86.9323 | 0
| 2017-08-01 | Closings | 1484.2724 | 0 | 0 | 0 | 1470.3401 | 0 | 0 | 0 | 0 | 0 | 0 | 13.9323 | 0
| 2017-09-01 | Closings | 1798.4755 | 0 | 0 | 0 | 1786.5433 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9323 | 0
| 2017-10-01 | Closings | 1172.2724 | 0 | 0 | 0 | 1160.3401 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9323 | 0
| 2017-11-01 | Closings | 853.3842 | 0 | 0 | 0 | 841.452 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9323 | 0
| 2017-12-01 | Closings | 4713.0153 | 0 | 0 | 0 | 4701.0831 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9323 | 0
| 2018-01-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-02-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-03-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-04-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-05-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-06-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-07-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-08-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-09-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-10-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-11-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-12-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2016 CWIP Balances closed in Forecast Period
| Month |  | Total All Projects | Devers Colorado River (DCR) | Tehachapi Segments 1 - 3A | Tehachapi Segments 3B & 3C | Tehachapi Segments 4-11 | Red Bluff Substation | Eldorado - Ivanpah | Lugo-Pisgah | Calcite Southern (formerly Jasper; part of South of Kramer) | West of Devers | Colorado River Substation | Whirlwind Substation Expansion Project | Rancho Vista
Recorded | 2016-12-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast | 2017-01-01 | Closings | 908.8466 | 0 | 0 | 0 | 908.8466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-02-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-03-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-04-01 | Closings | 26336.9125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26336.9125 | 0
| 2017-05-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-06-01 | Closings | 14613.7754 | 0 | 0 | 0 | 14006.7009 | 0 | 0 | 0 | 0 | 0 | 0 | 607.0746 | 0
| 2017-07-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-08-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-09-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-10-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-11-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2017-12-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-01-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-02-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-03-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-04-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-05-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-06-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-07-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-08-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-09-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-10-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-11-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2018-12-01 | Closings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Month = EOMONTH([Month, row above],0)+1

## Incentive CWIP
Southern California Edison
Incentive CWIP - FERC Projects Detail
As of December 2016
Month | TRTP All Segments | DCR | Red Bluff | Eldorado-Ivanpah | Lugo-Pisgah | Colorado River | West of Devers | Whirlwind | South of Kramer | Rancho Vista | Coolwater-Lugo | Total
2015-12-01 | 225689500.47 | 0 | 9220094.26 | 0 | 0 | 0 | 52084175.73 | 6769086.51 | 2844116.01 | 0 | 0 | 296606972.98
2016-01-01 | 234537305.76 | 0 | 0 | 0 | 0 | 0 | 52498623.75 | 6799084.63 | 2844116.01 | 0 | 0 | 296679130.15
2016-02-01 | 246277834.85 | 0 | 0 | 0 | 0 | 0 | 52874292.21 | 7321352.62 | 2844116.01 | 0 | 0 | 309317595.69
2016-03-01 | 249130156.33 | 0 | 0 | 0 | 0 | 0 | 53618762.61 | 10374907.74 | 2902845.83 | 0 | 0 | 316026672.51
2016-04-01 | 264263822.87 | 0 | 0 | 0 | 0 | 0 | 54251602.7 | 15007356.55 | 3081401.44 | 0 | 0 | 336604183.56
2016-05-01 | 272082291.68 | 0 | 0 | 0 | 0 | 0 | 54675188.14 | 15552213.44 | 3292806.55 | 0 | 0 | 345602499.81
2016-06-01 | 281130584.02 | 0 | 0 | 0 | 0 | 0 | 55165591.2 | 16127880.22 | 3401901.55 | 0 | 0 | 355825956.99
2016-07-01 | 288522861.49 | 0 | 0 | 0 | 0 | 0 | 55846692.37 | 19385391.74 | 3505384.18 | 0 | 0 | 367260329.78
2016-08-01 | 297512902.42 | 0 | 0 | 0 | 0 | 0 | 56943643.79 | 20738420.35 | 3578265.95 | 0 | 0 | 378773232.51
2016-09-01 | 61004683.08 | 0 | 0 | 0 | 0 | 0 | 57634501.06 | 21474805.13 | 3745750.92 | 0 | 0 | 143859740.19
2016-10-01 | 48827981.02 | 0 | 0 | 0 | 0 | 0 | 58274959.82 | 24189564.04 | 3889871.92 | 0 | 0 | 135182376.8
2016-11-01 | 49593829.6 | 0 | 0 | 0 | 0 | 0 | 58866560.95 | 25194209.93 | 3997681.78 | 0 | 0 | 137652282.26
2016-12-01 | 14915547.51 | 0 | 0 | 0 | 0 | 0 | 69685244.67 | 26943987.05 | 4204927.07 | 0 | 0 | 115749706.3
13 Mo. Avg | 194883792.3923 | 0 | 709238.02 | 0 | 0 | 0 | 56339987.6154 | 16606019.9962 | 3394860.4015 | 0 | 0 | 271933898.4254
Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Current 2016 File
Month | TRTP All Segments | DCR | Red Bluff | Eldorado-Ivanpah | Lugo-Pisgah | Colorado River | West of Devers | Whirlwind | South of Kramer | Rancho Vista | Coolwater-Lugo | Total
2015-12-01 | 225689500.47 | 0 | 9220094.26 | 0 | 0 | 0 | 52084175.73 | 6769086.51 | 2844116.01 | 0 | 0 | 296606972.98
2016-01-01 | 234537305.76 | 0 | 0 | 0 | 0 | 0 | 52498623.75 | 6799084.63 | 2844116.01 | 0 | 0 | 296679130.15
2016-02-01 | 246277834.85 | 0 | 0 | 0 | 0 | 0 | 52874292.21 | 7321352.62 | 2844116.01 | 0 | 0 | 309317595.69
2016-03-01 | 249130156.33 | 0 | 0 | 0 | 0 | 0 | 53618762.61 | 10374907.74 | 2902845.83 | 0 | 0 | 316026672.51
2016-04-01 | 264263822.87 | 0 | 0 | 0 | 0 | 0 | 54251602.7 | 15007356.55 | 3081401.44 | 0 | 0 | 336604183.56
2016-05-01 | 272082291.68 | 0 | 0 | 0 | 0 | 0 | 54675188.14 | 15552213.44 | 3292806.55 | 0 | 0 | 345602499.81
2016-06-01 | 281130584.02 | 0 | 0 | 0 | 0 | 0 | 55165591.2 | 16127880.22 | 3401901.55 | 0 | 0 | 355825956.99
2016-07-01 | 288522861.49 | 0 | 0 | 0 | 0 | 0 | 55846692.37 | 19385391.74 | 3505384.18 | 0 | 0 | 367260329.78
2016-08-01 | 297512902.42 | 0 | 0 | 0 | 0 | 0 | 56943643.79 | 20738420.35 | 3578265.95 | 0 | 0 | 378773232.51
2016-09-01 | 61004683.08 | 0 | 0 | 0 | 0 | 0 | 57634501.06 | 21474805.13 | 3745750.92 | 0 | 0 | 143859740.19
2016-10-01 | 48827981.02 | 0 | 0 | 0 | 0 | 0 | 58274959.82 | 24189564.04 | 3889871.92 | 0 | 0 | 135182376.8
2016-11-01 | 49593829.6 | 0 | 0 | 0 | 0 | 0 | 58866560.95 | 25194209.93 | 3997681.78 | 0 | 0 | 137652282.26
2016-12-01 | 14915547.51 | 0 | 0 | 0 | 0 | 0 | 69685244.67 | 26943987.05 | 4204927.07 | 0 | 0 | 115749706.3
Adjustments
Month | TRTP All Segments | DCR | Red Bluff | Eldorado-Ivanpah | Lugo-Pisgah | Colorado River | West of Devers | Whirlwind | South of Kramer | Rancho Vista |  | Total
2015-12-01 | [11 empty] | 0
2016-01-01 | [11 empty] | 0
2016-02-01 | [11 empty] | 0
2016-03-01 | [11 empty] | 0
2016-04-01 | [11 empty] | 0
2016-05-01 | [11 empty] | 0
2016-06-01 | [11 empty] | 0
2016-07-01 | [11 empty] | 0
2016-08-01 | [11 empty] | 0
2016-09-01 | [11 empty] | 0
2016-10-01 | [11 empty] | 0
2016-11-01 | [11 empty] | 0
2016-12-01 | [11 empty] | 0
Formulas:
Month = EOMONTH([Month, row above],0)+1
Note on C26: Neff, Lauren Michelle: Removed 3 work orders with trailing Property Tax charges 800148387 800148389 800148388