## DCR
WO | SumOfYTD2012 | Order | Project
900716073- Mirage: Install additional conduits with | 55102.27 | 900716073 | DCR
800504836- I: DCR: Loop-in DPV#1 500kV T/L into Col | 7957964.2 | 800504836 | DCR
800504834- I: DCR: Devers-Valley: Relocate approxim | 4697892.64 | 800504834 | DCR
800418261- Devers-Valley & Devers-Colorado River T/ | 6397619.24 | 800418261 | DCR
800403645- I: DCR: Colorado River Switchyard: Const | 63479401.55 | 800403645 | DCR
800063033- I: DCR: DEVERS-Colorado River 500KV SERI | 11289621.8 | 800063033 | DCR
800062902- I: Valley: Equip line position 8X with t | 5682379.81 | 800062902 | DCR
800062856- I: DCR: Devers: Install 2 500kV Shunt Ca | -6364.58 | 800062856 | DCR
800062855- I: DCR: Devers: Install Line Pos for Dev | -53270.76 | 800062855 | DCR
800062850- I: DEVERS: Extend 500kV bus two position | 13872960.52 | 800062850 | DCR
800062846- I: DCR: Devers: Replace Eleven 230kV Cir | 2874049.83 | 800062846 | DCR
800062527- I: DCR: Devers - Valley #2 500kV T/L: BU | 77432791.14 | 800062527 | DCR
800062522- DCR: Preliminary Engineering, Licensing | 991617.9 | 800062522 | DCR
800062494- I: Devers - Colorado River 500KV No.2 T/ | 187924630.44 | 800062494 | DCR
800051691- 9219-2080/Devers-Valley 500kV T/L | 37661.67 | 800051691 | DCR
800051690- 9219-2079/FERC-DEVERS-PALO VERDE ACQ | 81223.67 | 800051690 | DCR

## 900716073
Pin: 4847 | Project: DCR
Order: 900716073 | 900716073- Mirage: Install additional conduits with
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [6 empty] | 2012 Total
SubCategory | Prime | Group | Details | 5 | 6 | 7 | 8 | 9 | 10 | 12
1. Project Support | ENGINEERING | Labor | Labor Entries <$5,000 | 1005.35 | 2566.76 | [5 empty] | 3572.11
|  | Labor Total |  | 1005.35 | 2566.76 | [5 empty] | 3572.11
| ENGINEERING Total |  |  | 1005.35 | 2566.76 | [5 empty] | 3572.11
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  |  | 200 |  |  |  |  | 200
|  | Contract Total |  |  |  | 200 |  |  |  |  | 200
| Engineering/Technical Professional Servi Total |  |  |  |  | 200 |  |  |  |  | 200
| Labor - Other | Labor | Labor Entries <$5,000 |  | -67.68 | 67.68 |  |  |  |  | 0
|  | Labor Total |  |  | -67.68 | 67.68 |  |  |  |  | 0
| Labor - Other Total |  |  |  | -67.68 | 67.68 |  |  |  |  | 0
| Other | Other | Other |  |  | 601.84 | -601.84 |  |  |  | 0
|  | Other Total |  |  |  | 601.84 | -601.84 |  |  |  | 0
| Other Total |  |  |  |  | 601.84 | -601.84 |  |  |  | 0
1. Project Support Total |  |  |  | 1005.35 | 2499.08 | 869.52 | -601.84 |  |  |  | 3772.11
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | OLD CASTLE PRECAST |  |  |  |  | 9700 |  |  | 9700
|  | Material - Direct Purchase Total | [5 empty] | 9700 |  |  | 9700
| Building, Shop & Industrial Products/Eqp Total | [6 empty] | 9700 |  |  | 9700
| Communication Systems and Equipment -DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 294.4 |  |  |  | 294.4
|  | Material - Direct Purchase Total |  |  |  |  | 294.4 |  |  |  | 294.4
| Communication Systems and Equipment -DP Total | [5 empty] | 294.4 |  |  |  | 294.4
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 714.71 |  | 67.68 |  | 782.39
|  | Material - Direct Purchase Total |  |  |  |  | 714.71 |  | 67.68 |  | 782.39
| Electric Wiring and Components-DP Total | [5 empty] | 714.71 |  | 67.68 |  | 782.39
| Material - Other | Material | Material - Other |  |  |  | 99.44 | 761.95 | 5.31 |  | 866.7
|  | Material Total |  |  |  |  | 99.44 | 761.95 | 5.31 |  | 866.7
| Material - Other Total | [5 empty] | 99.44 | 761.95 | 5.31 |  | 866.7
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 258.8 |  |  |  | 258.8
|  | Material - Direct Purchase Total |  |  |  |  | 258.8 |  |  |  | 258.8
| Pole Line Hdwe & Connectors-DP Total | [5 empty] | 258.8 |  |  |  | 258.8
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 21.84 |  |  |  | 21.84
|  | Material - Direct Purchase Total |  |  |  |  | 21.84 |  |  |  | 21.84
| Transportation & Mobile Equip-DP Total | [5 empty] | 21.84 |  |  |  | 21.84
2. Material Total | [6 empty] | 1389.19 | 10461.95 | 72.99 |  | 11924.13
3. Construction | SC&M | Labor | Labor Entries <$5,000 |  | 281.39 | [5 empty] | 281.39
|  | Labor Total |  |  | 281.39 | [5 empty] | 281.39
| SC&M Total |  |  |  | 281.39 | [5 empty] | 281.39
3. Construction Total |  |  |  |  | 281.39 | [5 empty] | 281.39
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 90.98 | 317.8 | 164.98 | 26.11 | 64.02 | 1226.04 | -572.19 | 1317.74
|  |  | PDP-Devers Mirage Loop-In-MPO | [5 empty] | 20324.87 | 8551.58 | 28876.45
|  | Chargeback Total |  | 90.98 | 317.8 | 164.98 | 26.11 | 64.02 | 21550.91 | 7979.39 | 30194.19
| Chargebacks Total |  |  | 90.98 | 317.8 | 164.98 | 26.11 | 64.02 | 21550.91 | 7979.39 | 30194.19
| Labor - Other | Labor | Labor Entries <$5,000 | 320 | 869.16 | 37.83 | 95.58 | 631.47 | 5.51 |  | 1959.55
|  | Labor Total |  | 320 | 869.16 | 37.83 | 95.58 | 631.47 | 5.51 |  | 1959.55
| Labor - Other Total |  |  | 320 | 869.16 | 37.83 | 95.58 | 631.47 | 5.51 |  | 1959.55
4. Allocated Total |  |  |  | 410.98 | 1186.96 | 202.81 | 121.69 | 695.49 | 21556.42 | 7979.39 | 32153.74
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G | 117.88 | 141.6 | 16.52 | 42.74 | 499.84 | 558.83 | 224.03 | 1601.44
|  |  | Capitalized Overhead - Inj & Damages | 12.64 | 5.13 | 0.25 | 1.97 | 10.11 | 4.12 | 8.99 | 43.21
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1516.74 | 3721.87 | 87.64 |  |  |  |  | 5326.25
|  | Non Budgeted Total |  | 1647.26 | 3868.6 | 104.41 | 44.71 | 509.95 | 562.95 | 233.02 | 6970.9
| Non Budget - Other Total |  |  | 1647.26 | 3868.6 | 104.41 | 44.71 | 509.95 | 562.95 | 233.02 | 6970.9
5. Corporate Overhead Total |  |  |  | 1647.26 | 3868.6 | 104.41 | 44.71 | 509.95 | 562.95 | 233.02 | 6970.9
Grand Total |  |  |  | 3063.59 | 7836.03 | 1176.74 | 953.75 | 11667.39 | 22192.36 | 8212.41 | 55102.27

## 800504836
Pin: 4847 | Project: DCR
Order: 800504836 | 800504836- I: DCR: Loop-in DPV#1 500kV T/L into Col
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [6 empty] | 209.96 | [5 empty] | 209.96
|  | Labor Total | [7 empty] | 209.96 | [5 empty] | 209.96
| BP&FM Total | [8 empty] | 209.96 | [5 empty] | 209.96
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 4794.6 |  |  |  |  | 2.59 | [6 empty] | 4797.19
|  | Contract Total |  | 4794.6 |  |  |  |  | 2.59 | [6 empty] | 4797.19
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 4794.6 |  |  |  |  | 2.59 | [6 empty] | 4797.19
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -16385.05 | 16385.05 |  |  | 0
|  | Contract Total | [9 empty] | -16385.05 | 16385.05 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -16385.05 | 16385.05 |  |  | 0
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 2371.74 | 2371.74 | -513.63 | -1516.19 | -6921.95 | 2184.66 | -9981.87 | -1054.2 | 212786.15 | -215818.55 | -162.4 |  | -16254.5
|  | IMM Correction Total |  | 2371.74 | 2371.74 | -513.63 | -1516.19 | -6921.95 | 2184.66 | -9981.87 | -1054.2 | 212786.15 | -215818.55 | -162.4 |  | -16254.5
| IMM/Allocated - Correction Total |  |  | 2371.74 | 2371.74 | -513.63 | -1516.19 | -6921.95 | 2184.66 | -9981.87 | -1054.2 | 212786.15 | -215818.55 | -162.4 |  | -16254.5
| Labor - Other | Labor | Labor Entries <$5,000 | [5 empty] | 2853.12 | 356.58 | 1.55 | 22979.58 | -22341.48 | 30.21 | -30.77 | 3848.79
|  | Labor Total | [6 empty] | 2853.12 | 356.58 | 1.55 | 22979.58 | -22341.48 | 30.21 | -30.77 | 3848.79
| Labor - Other Total | [7 empty] | 2853.12 | 356.58 | 1.55 | 22979.58 | -22341.48 | 30.21 | -30.77 | 3848.79
| Other | Other | Other | 262436.4 | -219790 | 1217870 | 1149809 | -305755 | -1754470.59 | 40048 | 575837.4 | -690970.83 | 192430.83 | 826967.9 | -693986.94 | 600426.17
|  | Other Total |  | 262436.4 | -219790 | 1217870 | 1149809 | -305755 | -1754470.59 | 40048 | 575837.4 | -690970.83 | 192430.83 | 826967.9 | -693986.94 | 600426.17
| Other Total |  |  | 262436.4 | -219790 | 1217870 | 1149809 | -305755 | -1754470.59 | 40048 | 575837.4 | -690970.83 | 192430.83 | 826967.9 | -693986.94 | 600426.17
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -695.48 | 695.48 |  |  | 0
|  | Contract Total | [9 empty] | -695.48 | 695.48 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -695.48 | 695.48 |  |  | 0
1. Project Support Total |  |  |  | 269602.74 | -217418.26 | 1217356.37 | 1148292.81 | -312676.95 | -1749430.22 | 30632.67 | 574784.75 | -472285.63 | -28648.67 | 826835.71 | -694017.71 | 593027.61
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -20.65 | 20.65 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -20.65 | 20.65 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -20.65 | 20.65 |  |  | 0
| Material - Other | Material | Material - Other |  | 22946.03 | 60106.55 | 30234 | -616.69 | 3908.56 | 5237.77 | 18706.77 | 11460.11 | 2.93 | 1.66 | 1746.13 | 153733.82
|  | Material Total |  |  | 22946.03 | 60106.55 | 30234 | -616.69 | 3908.56 | 5237.77 | 18706.77 | 11460.11 | 2.93 | 1.66 | 1746.13 | 153733.82
| Material - Other Total |  |  |  | 22946.03 | 60106.55 | 30234 | -616.69 | 3908.56 | 5237.77 | 18706.77 | 11460.11 | 2.93 | 1.66 | 1746.13 | 153733.82
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | ONE SOURCE DISTRIBUTORS INC |  | 104946.75 |  | 6120.45 | [8 empty] | 111067.2
|  | Material - Direct Purchase Total |  |  | 104946.75 |  | 6120.45 | [8 empty] | 111067.2
| Pole Line Hdwe & Connectors-DP Total |  |  |  | 104946.75 |  | 6120.45 | [8 empty] | 111067.2
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 167.28 | -167.28 |  | -644190.02 | [7 empty] | -644190.02
|  |  | SAE TOWERS |  | 93763.79 | 517604.91 | 263234.12 | 640921.95 | 6660.51 | 14465.2 | 24427.89 | 84335.04 |  |  | 16477.72 | 1661891.13
|  | Material - Direct Purchase Total |  |  | 93931.07 | 517437.63 | 263234.12 | -3268.07 | 6660.51 | 14465.2 | 24427.89 | 84335.04 |  |  | 16477.72 | 1017701.11
| Steel Lattice Towers (T/S)-DP Total |  |  |  | 93931.07 | 517437.63 | 263234.12 | -3268.07 | 6660.51 | 14465.2 | 24427.89 | 84335.04 |  |  | 16477.72 | 1017701.11
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | SABRE COMMUNICATIONS CORPORATION |  |  |  |  | 15051 |  |  | 149565 |  |  |  |  | 164616
|  | Material - Direct Purchase Total | [5 empty] | 15051 |  |  | 149565 |  |  |  |  | 164616
| Towers/Poles, Steel & Concrete-DP Total | [6 empty] | 15051 |  |  | 149565 |  |  |  |  | 164616
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | AFL TELECOMMUNICATIONS LLC |  |  | 14469.25 |  |  | 29029.77 | 35074.88 | [5 empty] | 78573.9
|  |  | Material Entries <$5,000 |  | 288.4 | 4461.25 | [9 empty] | 4749.65
|  | Material - Direct Purchase Total |  |  | 288.4 | 18930.5 |  |  | 29029.77 | 35074.88 | [5 empty] | 83323.55
| Wire, Cable & Bus Bar-DP Total |  |  |  | 288.4 | 18930.5 |  |  | 29029.77 | 35074.88 | [5 empty] | 83323.55
2. Material Total |  |  |  |  | 222112.25 | 596474.68 | 299588.57 | 11166.24 | 39598.84 | 54777.85 | 192699.66 | 95774.5 | 23.58 | 1.66 | 18223.85 | 1530441.68
3. Construction | Construction Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -1272.48 | 1272.48 |  |  | 0
|  | Contract Total | [9 empty] | -1272.48 | 1272.48 |  |  | 0
| Construction Services - Correction Total | [10 empty] | -1272.48 | 1272.48 |  |  | 0
| Electrical Construction | Contract | Contract Entries <$50,000 |  |  |  |  | 6232.5 |  |  |  |  | 6232.5 |  |  | 12465
|  |  | PAR ELECTRICAL CONTRACTORS INC |  | 238011.3 | 52712.1 | 1138779.9 |  | 1754855.1 | 360434.7 |  | 689440.5 |  |  | 476529.08 | 4710762.68
|  | Contract Total |  |  | 238011.3 | 52712.1 | 1138779.9 | 6232.5 | 1754855.1 | 360434.7 |  | 689440.5 | 6232.5 |  | 476529.08 | 4723227.68
| Electrical Construction Total |  |  |  | 238011.3 | 52712.1 | 1138779.9 | 6232.5 | 1754855.1 | 360434.7 |  | 689440.5 | 6232.5 |  | 476529.08 | 4723227.68
| TRANSMISSION | Labor | Labor Entries <$5,000 | [11 empty] | 467.68 | 467.68
|  | Labor Total | [12 empty] | 467.68 | 467.68
| TRANSMISSION Total | [13 empty] | 467.68 | 467.68
3. Construction Total |  |  |  |  | 238011.3 | 52712.1 | 1138779.9 | 6232.5 | 1754855.1 | 360434.7 |  | 688168.02 | 7504.98 |  | 476996.76 | 4723695.36
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 685.05 | 17332.15 | 10853.77 | 9410.9 | 9303.03 | 22151.48 | 12114.75 | 21406.41 | 35044.36 | -45880.58 | -15189.13 | -12853.31 | 64378.88
|  |  | DPV2/DCR Project OE T/L Work |  |  | 5703.95 | 5217.74 | 5857.9 | 6302.12 | 5461.14 | 5114.91 | 6880.48 | 5811.3 | 6599.27 | 5826.14 | 58774.95
|  |  | PDP-CRS Loop in's -MPO |  |  |  |  | 23100 |  | 30563.44 | 127486.07 |  | 82718.36 | 76442.03 | 26506.12 | 366816.02
|  |  | PDP-DPV2 General Mtg Support-MPO | [6 empty] | 6449.5 |  |  | 7517.93 | 5986.76 |  | 19954.19
|  |  | PROCUREMENT TDBU |  |  |  | 9293.69 |  | 11817.6 | [6 empty] | 21111.29
|  | Chargeback Total |  | 685.05 | 17332.15 | 16557.72 | 23922.33 | 38260.93 | 40271.2 | 54588.83 | 154007.39 | 41924.84 | 50167.01 | 73838.93 | 19478.95 | 531035.33
| Chargebacks Total |  |  | 685.05 | 17332.15 | 16557.72 | 23922.33 | 38260.93 | 40271.2 | 54588.83 | 154007.39 | 41924.84 | 50167.01 | 73838.93 | 19478.95 | 531035.33
| Labor - Other | Labor | Division Overhead |  | 6645.1 | 14727.01 | 43088.91 |  | 79858.33 | 6682.59 |  | 21226.79 |  |  |  | 172228.73
|  |  | Labor Entries <$5,000 | 34.52 | 9486.75 | 6715.52 | 2112.2 | 785.47 | 8.59 | 10430.73 | 7134.15 | 2367.92 | 1763.25 |  | 6689.32 | 47528.42
|  | Labor Total |  | 34.52 | 16131.85 | 21442.53 | 45201.11 | 785.47 | 79866.92 | 17113.32 | 7134.15 | 23594.71 | 1763.25 |  | 6689.32 | 219757.15
| Labor - Other Total |  |  | 34.52 | 16131.85 | 21442.53 | 45201.11 | 785.47 | 79866.92 | 17113.32 | 7134.15 | 23594.71 | 1763.25 |  | 6689.32 | 219757.15
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -440.62 | 440.62 |  |  | 0
|  | Overhead Total | [9 empty] | -440.62 | 440.62 |  |  | 0
| Overhead Correction Total | [10 empty] | -440.62 | 440.62 |  |  | 0
4. Allocated Total |  |  |  | 719.57 | 33464 | 38000.25 | 69123.44 | 39046.4 | 120138.12 | 71702.15 | 161141.54 | 65078.93 | 52370.88 | 73838.93 | 26168.27 | 750792.48
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 32397.93 | 1889.44 | [6 empty] | 51225.91 | 85513.28
|  |  | Capitalized Overhead - A&G | 172.52 | 14529.71 | 24476.24 | 53703.97 | 4121.79 | 68525.95 | 16766.4 | 9978.74 | 39242.36 | 789.53 | 1947.91 | 14637.85 | 248892.97
|  |  | Capitalized Overhead - Inj & Damages | -1.59 | 428.58 | 656.82 | 296.16 | 259.88 | 190.97 | 90.5 | 448.23 | 176.6 | -296.49 | -32.84 | 4.71 | 2221.53
|  |  | Capitalized Overhead - P&B/Payroll Tax |  | 1704.95 | 1384.12 | 1963.38 | 2914.21 | 3798.59 | 2370.18 | 1777.82 | -758.83 | 2000.41 | 1445.84 | 4778.62 | 23379.29
|  | Non Budgeted Total |  | 170.93 | 16663.24 | 26517.18 | 88361.44 | 9185.32 | 72515.51 | 19227.08 | 12204.79 | 38660.13 | 2493.45 | 3360.91 | 70647.09 | 360007.07
| Non Budget - Other Total |  |  | 170.93 | 16663.24 | 26517.18 | 88361.44 | 9185.32 | 72515.51 | 19227.08 | 12204.79 | 38660.13 | 2493.45 | 3360.91 | 70647.09 | 360007.07
5. Corporate Overhead Total |  |  |  | 170.93 | 16663.24 | 26517.18 | 88361.44 | 9185.32 | 72515.51 | 19227.08 | 12204.79 | 38660.13 | 2493.45 | 3360.91 | 70647.09 | 360007.07
Grand Total |  |  |  | 270493.24 | 292832.53 | 1931060.58 | 2744146.16 | -247046.49 | 237677.35 | 536774.45 | 940830.74 | 415395.95 | 33744.22 | 904037.21 | -101981.74 | 7957964.2

## 800504834
Pin: 4847 | Project: DCR
Order: 800504834 | 800504834- I: DCR: Devers-Valley: Relocate approxim
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 3474 | [11 empty] | 3474
|  | Contract Total |  | 3474 | [11 empty] | 3474
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 3474 | [11 empty] | 3474
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -28799.64 | 28799.64 |  |  | 0
|  | Contract Total | [9 empty] | -28799.64 | 28799.64 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -28799.64 | 28799.64 |  |  | 0
| ENGINEERING | Labor | Labor Entries <$5,000 | [5 empty] | 169.25 | [6 empty] | 169.25
|  | Labor Total | [6 empty] | 169.25 | [6 empty] | 169.25
| ENGINEERING Total | [7 empty] | 169.25 | [6 empty] | 169.25
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 2229.74 | 1047.64 | 1001.86 | -1861.43 | -241.45 | 2165.64 | 1725.82 | -9775.02 | 115792.48 | -112876.58 | -210.47 |  | -1001.77
|  | IMM Correction Total |  | 2229.74 | 1047.64 | 1001.86 | -1861.43 | -241.45 | 2165.64 | 1725.82 | -9775.02 | 115792.48 | -112876.58 | -210.47 |  | -1001.77
| IMM/Allocated - Correction Total |  |  | 2229.74 | 1047.64 | 1001.86 | -1861.43 | -241.45 | 2165.64 | 1725.82 | -9775.02 | 115792.48 | -112876.58 | -210.47 |  | -1001.77
| Labor - Other | Labor | Labor Entries <$5,000 | [8 empty] | 13942.71 | -13942.71 |  |  | 0
|  | Labor Total | [9 empty] | 13942.71 | -13942.71 |  |  | 0
| Labor - Other Total | [10 empty] | 13942.71 | -13942.71 |  |  | 0
| Other | Other | Other | 194484.89 | 117853 | -106780 | -209502 | 1125303 | 902708 | -1716328 | -0.5 | -78042.3 | 78042.3 | 0 | 65798.14 | 373536.53
|  | Other Total |  | 194484.89 | 117853 | -106780 | -209502 | 1125303 | 902708 | -1716328 | -0.5 | -78042.3 | 78042.3 | 0 | 65798.14 | 373536.53
| Other Total |  |  | 194484.89 | 117853 | -106780 | -209502 | 1125303 | 902708 | -1716328 | -0.5 | -78042.3 | 78042.3 | 0 | 65798.14 | 373536.53
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -1375.41 | 1375.41 |  |  | 0
|  | Contract Total | [9 empty] | -1375.41 | 1375.41 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -1375.41 | 1375.41 |  |  | 0
1. Project Support Total |  |  |  | 200188.63 | 118900.64 | -105778.14 | -211363.43 | 1125061.55 | 905042.89 | -1714602.18 | -9775.52 | 21517.84 | -18601.94 | -210.47 | 65798.14 | 376178.01
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -36.45 | 36.45 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -36.45 | 36.45 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -36.45 | 36.45 |  |  | 0
| Material - Inventory | Material | Material - Inventory | [8 empty] | -3.02 | 3.02 |  |  | 0
|  | Material Total | [9 empty] | -3.02 | 3.02 |  |  | 0
| Material - Inventory Total | [10 empty] | -3.02 | 3.02 |  |  | 0
| Material - Other | Material | Material - Other | 18700.41 | 932.22 | 9298.8 |  | -0.66 | 2.02 | 0.13 | 0.03 | -3.4 | 4.88 | 1.56 | 1.35 | 28937.34
|  | Material Total |  | 18700.41 | 932.22 | 9298.8 |  | -0.66 | 2.02 | 0.13 | 0.03 | -3.4 | 4.88 | 1.56 | 1.35 | 28937.34
| Material - Other Total |  |  | 18700.41 | 932.22 | 9298.8 |  | -0.66 | 2.02 | 0.13 | 0.03 | -3.4 | 4.88 | 1.56 | 1.35 | 28937.34
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | ONE SOURCE DISTRIBUTORS INC |  |  | 82965.45 | [9 empty] | 82965.45
|  | Material - Direct Purchase Total |  |  |  | 82965.45 | [9 empty] | 82965.45
| Pole Line Hdwe & Connectors-DP Total |  |  |  |  | 82965.45 | [9 empty] | 82965.45
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | FORMET | 164180.88 | 8090.48 | [10 empty] | 172271.36
|  | Material - Direct Purchase Total |  | 164180.88 | 8090.48 | [10 empty] | 172271.36
| Steel Lattice Towers (T/S)-DP Total |  |  | 164180.88 | 8090.48 | [10 empty] | 172271.36
2. Material Total |  |  |  | 182881.29 | 9022.7 | 92264.25 |  | -0.66 | 2.02 | 0.13 | 0.03 | -42.87 | 44.35 | 1.56 | 1.35 | 284174.15
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  | 470.11 | [10 empty] | 470.11
|  | Contract Total |  |  | 470.11 | [10 empty] | 470.11
| Construction Management Services Total |  |  |  | 470.11 | [10 empty] | 470.11
| Construction Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -1678.05 | 1678.05 |  |  | 0
|  | Contract Total | [9 empty] | -1678.05 | 1678.05 |  |  | 0
| Construction Services - Correction Total | [10 empty] | -1678.05 | 1678.05 |  |  | 0
| Electrical Construction | Contract | PAR ELECTRICAL CONTRACTORS INC |  | 177481.8 | 536908.5 | 374423.4 |  |  | 1716328.8 |  |  |  |  | 586261.44 | 3391403.94
|  | Contract Total |  |  | 177481.8 | 536908.5 | 374423.4 |  |  | 1716328.8 |  |  |  |  | 586261.44 | 3391403.94
| Electrical Construction Total |  |  |  | 177481.8 | 536908.5 | 374423.4 |  |  | 1716328.8 |  |  |  |  | 586261.44 | 3391403.94
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | [10 empty] | 330.77 |  | 330.77
|  | Labor Total | [11 empty] | 330.77 |  | 330.77
| TRNS CAPITAL Total | [12 empty] | 330.77 |  | 330.77
3. Construction Total |  |  |  |  | 177951.91 | 536908.5 | 374423.4 |  |  | 1716328.8 |  | -1678.05 | 1678.05 | 330.77 | 586261.44 | 3392204.82
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 3500.1 | 14109.63 | -4375.6 | 19147.09 | 2998.6 | 22007.28 | 14494.52 | 15248.22 | 16714.92 | 6570.61 | -12596.37 | -10928.23 | 86890.77
|  |  | DPV2/DCR Project OE T/L Work | [8 empty] | 5030.27 |  |  |  | 5030.27
|  |  | PDP-Devers to valley Relocation-MPO (Install Only) |  |  | 15201.3 |  |  |  |  | 55564.1 |  | 18544.24 | 46960.15 | 18840.05 | 155109.84
|  |  | PDP-DPV2 General Mtg Support-MPO |  | 28086.31 |  |  |  |  | 6046.41 | 9341.83 |  | 7048.06 | 5612.58 |  | 56135.19
|  |  | PROCUREMENT TDBU | [6 empty] | 11327.77 | [5 empty] | 11327.77
|  | Chargeback Total |  | 3500.1 | 42195.94 | 10825.7 | 19147.09 | 2998.6 | 22007.28 | 31868.7 | 80154.15 | 21745.19 | 32162.91 | 39976.36 | 7911.82 | 314493.84
| Chargebacks Total |  |  | 3500.1 | 42195.94 | 10825.7 | 19147.09 | 2998.6 | 22007.28 | 31868.7 | 80154.15 | 21745.19 | 32162.91 | 39976.36 | 7911.82 | 314493.84
| Labor - Other | Labor | Division Overhead |  |  | 15496.85 | 5766.12 |  |  | 71399.28 | [5 empty] | 92662.25
|  |  | Labor Entries <$5,000 | 4589.24 | 6864.96 | 7066.56 | 6252.88 |  | 46.81 |  |  | -1820.42 | 2569.29 | 72.53 | 7855.9 | 33497.75
|  | Labor Total |  | 4589.24 | 6864.96 | 22563.41 | 12019 |  | 46.81 | 71399.28 |  | -1820.42 | 2569.29 | 72.53 | 7855.9 | 126160
| Labor - Other Total |  |  | 4589.24 | 6864.96 | 22563.41 | 12019 |  | 46.81 | 71399.28 |  | -1820.42 | 2569.29 | 72.53 | 7855.9 | 126160
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -770.66 | 770.66 |  |  | 0
|  | Overhead Total | [9 empty] | -770.66 | 770.66 |  |  | 0
| Overhead Correction Total | [10 empty] | -770.66 | 770.66 |  |  | 0
4. Allocated Total |  |  |  | 8089.34 | 49060.9 | 33389.11 | 31166.09 | 2998.6 | 22054.09 | 103267.98 | 80154.15 | 19154.11 | 35502.86 | 40048.89 | 15767.72 | 440653.84
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 11711.43 | 1104.82 | [6 empty] | 30453.19 | 43269.44
|  |  | Capitalized Overhead - A&G | 10782.42 | 6945.63 | 23652.5 | 14397.18 | 229.42 | 870.52 | 63951.93 | 1990.7 | 1744.96 | 481.17 | 1061.6 | 16902.84 | 143010.87
|  |  | Capitalized Overhead - Inj & Damages | 177.17 | 87.49 | 122.99 | 16.39 | -107.93 | 14.86 | 79.94 | 78.92 | 57.53 | -144.75 | -34.17 | -16.18 | 332.26
|  |  | Capitalized Overhead - P&B/Payroll Tax | 561.01 | 1914.58 | 1620.28 | 2219.99 | 2532.42 | 2029.07 | 1747.03 | 1558.34 | -3722.4 | 2687.57 | 1551.44 | 3369.92 | 18069.25
|  | Non Budgeted Total |  | 11520.6 | 8947.7 | 25395.77 | 28344.99 | 3758.73 | 2914.45 | 65778.9 | 3627.96 | -1919.91 | 3023.99 | 2578.87 | 50709.77 | 204681.82
| Non Budget - Other Total |  |  | 11520.6 | 8947.7 | 25395.77 | 28344.99 | 3758.73 | 2914.45 | 65778.9 | 3627.96 | -1919.91 | 3023.99 | 2578.87 | 50709.77 | 204681.82
5. Corporate Overhead Total |  |  |  | 11520.6 | 8947.7 | 25395.77 | 28344.99 | 3758.73 | 2914.45 | 65778.9 | 3627.96 | -1919.91 | 3023.99 | 2578.87 | 50709.77 | 204681.82
Grand Total |  |  |  | 402679.86 | 363883.85 | 582179.49 | 222571.05 | 1131818.22 | 930013.45 | 170773.63 | 74006.62 | 37031.12 | 21647.31 | 42749.62 | 718538.42 | 4697892.64

## 800418261
Pin: 4847 | Project: DCR
Order: 800418261 | 800418261- Devers-Valley & Devers-Colorado River T/
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BSVHCC | Labor | Labor Entries <$5,000 | [9 empty] | 40.86 |  |  | 40.86
|  | Labor Total | [10 empty] | 40.86 |  |  | 40.86
| BSVHCC Total | [11 empty] | 40.86 |  |  | 40.86
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 578077.75 |  |  | 578077.75
|  |  | Contract Entries <$50,000 | [8 empty] | -578077.75 |  |  |  | -578077.75
|  | Contract Total | [9 empty] | -578077.75 | 578077.75 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -578077.75 | 578077.75 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  |  | 385 | 3329.49 | 11870.82 | [5 empty] | 15585.31
|  | Contract Total | [5 empty] | 385 | 3329.49 | 11870.82 | [5 empty] | 15585.31
| Contract Consult/Contract Ord to Ord Total | [6 empty] | 385 | 3329.49 | 11870.82 | [5 empty] | 15585.31
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 4635.54 | 2878 | 3927.03 | 3592.46 | 5640.02 | 1211.59 | 893.53 |  | 424.43 |  | 882.75 | 21694.78 | 45780.13
|  | Contract Total |  | 4635.54 | 2878 | 3927.03 | 3592.46 | 5640.02 | 1211.59 | 893.53 |  | 424.43 |  | 882.75 | 21694.78 | 45780.13
| Environmental/Safety Professional Servic Total |  |  | 4635.54 | 2878 | 3927.03 | 3592.46 | 5640.02 | 1211.59 | 893.53 |  | 424.43 |  | 882.75 | 21694.78 | 45780.13
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 3421.66 | 3103.18 | 1842.17 | 2879.64 | 2888.91 | -14147.77 | 2234.77 | 1868.77 | 705353.7 | -701262.31 | -4199.9 | -483.44 | 3499.38
|  | IMM Correction Total |  | 3421.66 | 3103.18 | 1842.17 | 2879.64 | 2888.91 | -14147.77 | 2234.77 | 1868.77 | 705353.7 | -701262.31 | -4199.9 | -483.44 | 3499.38
| IMM/Allocated - Correction Total |  |  | 3421.66 | 3103.18 | 1842.17 | 2879.64 | 2888.91 | -14147.77 | 2234.77 | 1868.77 | 705353.7 | -701262.31 | -4199.9 | -483.44 | 3499.38
| Labor - Other | Labor | Labor - Other | [9 empty] | 14582.25 |  |  | 14582.25
|  |  | Labor Correction | [9 empty] | 72548.6 |  |  | 72548.6
|  |  | Labor Entries <$5,000 | 681.56 | 130.59 | -44.68 | -160.99 | 218.2 | 147.3 | 591.93 | 23.36 | -74210.16 | -12441.76 | 57.55 | 141.46 | -84865.64
|  | Labor Total |  | 681.56 | 130.59 | -44.68 | -160.99 | 218.2 | 147.3 | 591.93 | 23.36 | -74210.16 | 74689.09 | 57.55 | 141.46 | 2265.21
| Labor - Other Total |  |  | 681.56 | 130.59 | -44.68 | -160.99 | 218.2 | 147.3 | 591.93 | 23.36 | -74210.16 | 74689.09 | 57.55 | 141.46 | 2265.21
| Other | Other | Other | -72175.29 | 3358.79 |  |  | 3552.05 |  | 315.55 |  | -12937.94 | 12937.94 |  |  | -64948.9
|  | Other Total |  | -72175.29 | 3358.79 |  |  | 3552.05 |  | 315.55 |  | -12937.94 | 12937.94 |  |  | -64948.9
| Other Total |  |  | -72175.29 | 3358.79 |  |  | 3552.05 |  | 315.55 |  | -12937.94 | 12937.94 |  |  | -64948.9
| PLGHCC | Labor | Labor Entries <$5,000 | [11 empty] | 441.27 | 441.27
|  | Labor Total | [12 empty] | 441.27 | 441.27
| PLGHCC Total | [13 empty] | 441.27 | 441.27
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -5822.4 | 5822.4 |  |  | 0
|  | Contract Total | [9 empty] | -5822.4 | 5822.4 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -5822.4 | 5822.4 |  |  | 0
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 4536.62 | 5253.38 | [10 empty] | 9790
|  | Labor Total |  | 4536.62 | 5253.38 | [10 empty] | 9790
| TRNS CAPITAL Total |  |  | 4536.62 | 5253.38 | [10 empty] | 9790
1. Project Support Total |  |  |  | -58899.91 | 14723.94 | 5724.52 | 6311.11 | 12684.18 | -9459.39 | 15906.6 | 1892.13 | 34729.88 | -29694.27 | -3259.6 | 21794.07 | 12453.26
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -143.6 | 143.6 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -143.6 | 143.6 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -143.6 | 143.6 |  |  | 0
| Material - Inventory | Material | Material - Inventory | 14.04 | [7 empty] | -20.1 | 20.1 |  |  | 14.04
|  | Material Total |  | 14.04 | [7 empty] | -20.1 | 20.1 |  |  | 14.04
| Material - Inventory Total |  |  | 14.04 | [7 empty] | -20.1 | 20.1 |  |  | 14.04
| Material - Other | Material | Material - Other | 10.87 | 3.73 | 4.26 | 0.99 | -11.48 | 6.85 | 2.53 | 0.53 | -16.61 | 18.41 | 2.39 | 2.07 | 24.54
|  | Material Total |  | 10.87 | 3.73 | 4.26 | 0.99 | -11.48 | 6.85 | 2.53 | 0.53 | -16.61 | 18.41 | 2.39 | 2.07 | 24.54
| Material - Other Total |  |  | 10.87 | 3.73 | 4.26 | 0.99 | -11.48 | 6.85 | 2.53 | 0.53 | -16.61 | 18.41 | 2.39 | 2.07 | 24.54
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 96.14 | [11 empty] | 96.14
|  | Material - Direct Purchase Total |  | 96.14 | [11 empty] | 96.14
| Transportation & Mobile Equip-DP Total |  |  | 96.14 | [11 empty] | 96.14
2. Material Total |  |  |  | 121.05 | 3.73 | 4.26 | 0.99 | -11.48 | 6.85 | 2.53 | 0.53 | -180.31 | 182.11 | 2.39 | 2.07 | 134.72
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 39501.99 | 156736.12 | 48201.84 | 75920.62 | 33266.66 | 58237.67 | 74127.67 | 47982.55 | 30567.24 | 22578.6 | 6300 | 44100 | 637520.96
|  | Contract Total |  | 39501.99 | 156736.12 | 48201.84 | 75920.62 | 33266.66 | 58237.67 | 74127.67 | 47982.55 | 30567.24 | 22578.6 | 6300 | 44100 | 637520.96
| Construction Management Services Total |  |  | 39501.99 | 156736.12 | 48201.84 | 75920.62 | 33266.66 | 58237.67 | 74127.67 | 47982.55 | 30567.24 | 22578.6 | 6300 | 44100 | 637520.96
| Construction Services - Correction | Contract | Construction Services - Correction |  |  |  |  | 2597906 | [7 empty] | 2597906
|  |  | Contract Entries <$50,000 | [8 empty] | 103697.81 | 5063.19 |  |  | 108761
|  | Contract Total | [5 empty] | 2597906 |  |  |  | 103697.81 | 5063.19 |  |  | 2706667
| Construction Services - Correction Total | [6 empty] | 2597906 |  |  |  | 103697.81 | 5063.19 |  |  | 2706667
| Construction Services - Other | Contract | Construction Services - Other | [8 empty] | 128604.92 |  | 63660 |  | 192264.92
|  |  | Contract Entries <$50,000 |  | 942.2 | 29643.99 | [6 empty] | 22250 |  | 17680 | 70516.19
|  | Contract Total |  |  | 942.2 | 29643.99 | [5 empty] | 128604.92 | 22250 | 63660 | 17680 | 262781.11
| Construction Services - Other Total |  |  |  | 942.2 | 29643.99 | [5 empty] | 128604.92 | 22250 | 63660 | 17680 | 262781.11
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 |  |  | 352 | 1206.48 | 1056 | 3216.86 | 2859.12 | 1922.14 | 3033.36 | 2412.96 | 1910.48 | 1558.48 | 19527.88
|  | Contract Total |  |  |  | 352 | 1206.48 | 1056 | 3216.86 | 2859.12 | 1922.14 | 3033.36 | 2412.96 | 1910.48 | 1558.48 | 19527.88
| Construction, Civil/Structural Total |  |  |  |  | 352 | 1206.48 | 1056 | 3216.86 | 2859.12 | 1922.14 | 3033.36 | 2412.96 | 1910.48 | 1558.48 | 19527.88
| Construction, Earthwork | Contract | Construction, Earthwork |  | 75514 | [10 empty] | 75514
|  | Contract Total |  |  | 75514 | [10 empty] | 75514
| Construction, Earthwork Total |  |  |  | 75514 | [10 empty] | 75514
| Construction, Property/Building | Contract | Contract Entries <$50,000 |  |  |  |  | 9262.25 |  |  | 8162.15 |  |  | 495 |  | 17919.4
|  | Contract Total | [5 empty] | 9262.25 |  |  | 8162.15 |  |  | 495 |  | 17919.4
| Construction, Property/Building Total | [6 empty] | 9262.25 |  |  | 8162.15 |  |  | 495 |  | 17919.4
| Material - Other | Material | Material - Other | 65.12 | 83.07 | 41.06 | 30.45 | 87.07 | 126.68 | 88.68 | 17.54 | 21.45 |  |  |  | 561.12
|  | Material Total |  | 65.12 | 83.07 | 41.06 | 30.45 | 87.07 | 126.68 | 88.68 | 17.54 | 21.45 |  |  |  | 561.12
| Material - Other Total |  |  | 65.12 | 83.07 | 41.06 | 30.45 | 87.07 | 126.68 | 88.68 | 17.54 | 21.45 |  |  |  | 561.12
| Other | Other | Other | 12314.58 | 83820 | 27333.57 | 24314.58 | 102685.42 | 100401.25 | 108000 | 6000.4 | 180000 | 2115 | 88632 |  | 735616.8
|  | Other Total |  | 12314.58 | 83820 | 27333.57 | 24314.58 | 102685.42 | 100401.25 | 108000 | 6000.4 | 180000 | 2115 | 88632 |  | 735616.8
| Other Total |  |  | 12314.58 | 83820 | 27333.57 | 24314.58 | 102685.42 | 100401.25 | 108000 | 6000.4 | 180000 | 2115 | 88632 |  | 735616.8
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 689 | 12877.25 | 3006.46 | 22563.18 | 689 | 1378 | 9838.68 | 71114.66 | 28432.89 | 23600.38 | 28432.89 | 25702.47 | 228324.86
|  | Contract Total |  | 689 | 12877.25 | 3006.46 | 22563.18 | 689 | 1378 | 9838.68 | 71114.66 | 28432.89 | 23600.38 | 28432.89 | 25702.47 | 228324.86
| Short Term Equipment Rent Total |  |  | 689 | 12877.25 | 3006.46 | 22563.18 | 689 | 1378 | 9838.68 | 71114.66 | 28432.89 | 23600.38 | 28432.89 | 25702.47 | 228324.86
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 887.69 | 1689.61 | 771.37 |  |  |  | 200.84 |  | 67 |  |  |  | 3616.51
|  | Labor Total |  | 887.69 | 1689.61 | 771.37 |  |  |  | 200.84 |  | 67 |  |  |  | 3616.51
| TRNS CAPITAL Total |  |  | 887.69 | 1689.61 | 771.37 |  |  |  | 200.84 |  | 67 |  |  |  | 3616.51
3. Construction Total |  |  |  | 53458.38 | 331662.25 | 109350.29 | 124035.31 | 2744952.4 | 163360.46 | 195114.99 | 135199.44 | 474424.67 | 78020.13 | 189430.37 | 89040.95 | 4688049.64
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 13362.14 | 14260.75 | -126588.17 | -94906.99 | -29042.64 | 14303.32 | -29350.52 | 13729.94 | 18453.2 | 1907.64 | 10904.02 | -2267.26 | -195234.57
|  |  | PDP-2010 Material/Helicopter Yds-TDBU | 162071.18 | 84231.85 | 272054.3 | 92646.38 | 17059.71 | 7783.31 | 16198.44 | 45174.36 |  | 59940.35 | 68349.84 | 55926.52 | 881436.24
|  |  | PDP-DPV2 General Mtg Support-MPO |  | 193179.57 | 8476 | 37155.63 |  | 6298.86 | 9271.16 | 14324.15 |  | 10807.04 | 8605.96 |  | 288118.37
|  |  | PROCUREMENT TDBU |  |  |  |  | 17471.06 | [7 empty] | 17471.06
|  | Chargeback Total |  | 175433.32 | 291672.17 | 153942.13 | 34895.02 | 5488.13 | 28385.49 | -3880.92 | 73228.45 | 18453.2 | 72655.03 | 87859.82 | 53659.26 | 991791.1
| Chargebacks Total |  |  | 175433.32 | 291672.17 | 153942.13 | 34895.02 | 5488.13 | 28385.49 | -3880.92 | 73228.45 | 18453.2 | 72655.03 | 87859.82 | 53659.26 | 991791.1
| Labor - Other | Labor | Division Overhead |  |  |  |  | 115599.82 |  |  |  |  | 34252.39 |  |  | 149852.21
|  |  | Labor Entries <$5,000 | 2508.87 | 10411.35 | 3228.42 | 3258.59 | 5.03 | 2881.97 | 3801.4 | 5297.23 | -27682.04 | 20985.62 | 1087.98 | 1613.29 | 27397.71
|  | Labor Total |  | 2508.87 | 10411.35 | 3228.42 | 3258.59 | 115604.85 | 2881.97 | 3801.4 | 5297.23 | -27682.04 | 55238.01 | 1087.98 | 1613.29 | 177249.92
| Labor - Other Total |  |  | 2508.87 | 10411.35 | 3228.42 | 3258.59 | 115604.85 | 2881.97 | 3801.4 | 5297.23 | -27682.04 | 55238.01 | 1087.98 | 1613.29 | 177249.92
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -14555.37 | 14555.37 |  |  | 0
|  | Overhead Total | [9 empty] | -14555.37 | 14555.37 |  |  | 0
| Overhead Correction Total | [10 empty] | -14555.37 | 14555.37 |  |  | 0
4. Allocated Total |  |  |  | 177942.19 | 302083.52 | 157170.55 | 38153.61 | 121092.98 | 31267.46 | -79.52 | 78525.68 | -23784.21 | 142448.41 | 88947.8 | 55272.55 | 1169041.02
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 41154.33 | 3591.18 | [6 empty] | 71713.59 | 116459.1
|  |  | Capitalized Overhead - A&G | 13771.93 | 18997.8 | 9704.24 | 6008.85 | 239594.22 | 6608.96 | 7406.88 | 6098.82 | 21735.94 | 4933.7 | 7270.69 | 4663.76 | 346795.79
|  |  | Capitalized Overhead - Inj & Damages | 71.64 | 639.84 | -84.74 | -16.44 | 1939.06 | 141.9 | 90.91 | 198.06 | 726.77 | -1484.84 | 279.78 | 53.77 | 2555.71
|  |  | Capitalized Overhead - P&B/Payroll Tax | 11645.15 | 20678.09 | 12275.66 | 11297.75 | 15517.61 | 12618.4 | 9517.36 | 9318.2 | -119489.26 | 50313.82 | 5977.65 | 22459.57 | 62130
|  | Non Budgeted Total |  | 25488.72 | 40315.73 | 21895.16 | 58444.49 | 260642.07 | 19369.26 | 17015.15 | 15615.08 | -97026.55 | 53762.68 | 13528.12 | 98890.69 | 527940.6
| Non Budget - Other Total |  |  | 25488.72 | 40315.73 | 21895.16 | 58444.49 | 260642.07 | 19369.26 | 17015.15 | 15615.08 | -97026.55 | 53762.68 | 13528.12 | 98890.69 | 527940.6
5. Corporate Overhead Total |  |  |  | 25488.72 | 40315.73 | 21895.16 | 58444.49 | 260642.07 | 19369.26 | 17015.15 | 15615.08 | -97026.55 | 53762.68 | 13528.12 | 98890.69 | 527940.6
Grand Total |  |  |  | 198110.43 | 688789.17 | 294144.78 | 226945.51 | 3139360.15 | 204544.64 | 227959.75 | 231232.86 | 388163.48 | 244719.06 | 288649.08 | 265000.33 | 6397619.24

## 800403645
Pin: 4847 | Project: DCR
Order: 800403645 | 800403645- I: DCR: Colorado River Switchyard: Const
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  | 208.3 |  | 929.13 | 90.35 | 559.9 | 214.54 | 978.04 | 165.52 |  |  | 3145.78
|  | Labor Total |  |  |  | 208.3 |  | 929.13 | 90.35 | 559.9 | 214.54 | 978.04 | 165.52 |  |  | 3145.78
| BP&FM Total |  |  |  |  | 208.3 |  | 929.13 | 90.35 | 559.9 | 214.54 | 978.04 | 165.52 |  |  | 3145.78
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 |  |  |  |  | 700 | 3100.8 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 12571.3
|  | Contract Total | [5 empty] | 700 | 3100.8 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 12571.3
| Cleaning / Janitorial Services Total | [6 empty] | 700 | 3100.8 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 1461.75 | 12571.3
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  | 10352.75 | [5 empty] | 2639 |  |  |  | 12991.75
|  | Contract Total |  |  |  | 10352.75 | [5 empty] | 2639 |  |  |  | 12991.75
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  |  | 10352.75 | [5 empty] | 2639 |  |  |  | 12991.75
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 2085097.73 |  |  | 2085097.73
|  |  | Contract Entries <$50,000 | [8 empty] | -2085097.73 |  |  |  | -2085097.73
|  | Contract Total | [9 empty] | -2085097.73 | 2085097.73 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -2085097.73 | 2085097.73 |  |  | 0
| ELEC SYS PLANNING | Labor | ELEC SYS PLANNING / Engineer | [11 empty] | 5955.04 | 5955.04
|  |  | Labor Entries <$5,000 | [11 empty] | 4075.19 | 4075.19
|  | Labor Total | [12 empty] | 10030.23 | 10030.23
| ELEC SYS PLANNING Total | [13 empty] | 10030.23 | 10030.23
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 89.47 | 137.78 | 1168.29 | 365.92 | 287.92 | 24.56 | 89.54 | [5 empty] | 2163.48
|  | Labor Total |  | 89.47 | 137.78 | 1168.29 | 365.92 | 287.92 | 24.56 | 89.54 | [5 empty] | 2163.48
| ENG ADVANCEMENT Total |  |  | 89.47 | 137.78 | 1168.29 | 365.92 | 287.92 | 24.56 | 89.54 | [5 empty] | 2163.48
| ENGINEERING | Labor | Engineer | [10 empty] | 7923.76 |  | 7923.76
|  |  | Labor Entries <$5,000 | 9667.72 | 18056.94 | 9505.3 | 5254.63 | 10008.61 | 10923.47 | 8785.5 | 7262.82 | 4446.68 | 4912.46 | 2094.42 |  | 90918.55
|  |  | Techn Spl/Scientist | 5309.28 | [11 empty] | 5309.28
|  | Labor Total |  | 14977 | 18056.94 | 9505.3 | 5254.63 | 10008.61 | 10923.47 | 8785.5 | 7262.82 | 4446.68 | 4912.46 | 10018.18 |  | 104151.59
| ENGINEERING Total |  |  | 14977 | 18056.94 | 9505.3 | 5254.63 | 10008.61 | 10923.47 | 8785.5 | 7262.82 | 4446.68 | 4912.46 | 10018.18 |  | 104151.59
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  | 11533.54 |  | 24578.13 | 14719.84 | 68755.71 | 8303.57 | 27784.38 | 17317.2 | 59166.24 | 38151.3 | 44458.93 | 314768.84
|  |  | MONTANA GEOTECHNICAL I | [5 empty] | 135393.4 |  | 105595.4 | 104290.8 | 98923.95 | 119089.68 | 77083.85 | 640377.08
|  |  | PGA ENGINEERS, INC. | [7 empty] | 51158 |  |  |  |  | 51158
|  | Contract Total |  |  | 11533.54 |  | 24578.13 | 14719.84 | 204149.11 | 8303.57 | 184537.78 | 121608 | 158090.19 | 157240.98 | 121542.78 | 1006303.92
| Engineering/Technical Professional Servi Total |  |  |  | 11533.54 |  | 24578.13 | 14719.84 | 204149.11 | 8303.57 | 184537.78 | 121608 | 158090.19 | 157240.98 | 121542.78 | 1006303.92
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | [6 empty] | 4169.35 | 7413.63 | 5730.2 | 4707.37 | 6587.5 | 11157.27 | 39765.32
|  | Contract Total | [7 empty] | 4169.35 | 7413.63 | 5730.2 | 4707.37 | 6587.5 | 11157.27 | 39765.32
| Environmental/Safety Professional Servic Total | [8 empty] | 4169.35 | 7413.63 | 5730.2 | 4707.37 | 6587.5 | 11157.27 | 39765.32
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 23296.73 | 22430.32 | -1420.41 | -7148 | 13200.62 | -23926.99 | 9665.65 | 12696.3 | 4041220.49 | -4057169.82 | -47510.27 | -38559.2 | -53224.58
|  | IMM Correction Total |  | 23296.73 | 22430.32 | -1420.41 | -7148 | 13200.62 | -23926.99 | 9665.65 | 12696.3 | 4041220.49 | -4057169.82 | -47510.27 | -38559.2 | -53224.58
| IMM/Allocated - Correction Total |  |  | 23296.73 | 22430.32 | -1420.41 | -7148 | 13200.62 | -23926.99 | 9665.65 | 12696.3 | 4041220.49 | -4057169.82 | -47510.27 | -38559.2 | -53224.58
| Information System Professional Services | Contract | Contract Entries <$50,000 | [6 empty] | 656.25 | [5 empty] | 656.25
|  | Contract Total | [7 empty] | 656.25 | [5 empty] | 656.25
| Information System Professional Services Total | [8 empty] | 656.25 | [5 empty] | 656.25
| Labor - Other | Labor | Labor - Other | [9 empty] | 9052.79 |  |  | 9052.79
|  |  | Labor Correction | [9 empty] | 45039.15 |  |  | 45039.15
|  |  | Labor Entries <$5,000 | 164.48 | 2480.32 | -2621.92 | 996.16 | 1316.37 | -2029.89 | -298.13 | -31618.35 | 103635.09 | -156653.16 | -1845.65 | 3078.86 | -83395.82
|  | Labor Total |  | 164.48 | 2480.32 | -2621.92 | 996.16 | 1316.37 | -2029.89 | -298.13 | -31618.35 | 103635.09 | -102561.22 | -1845.65 | 3078.86 | -29303.88
| Labor - Other Total |  |  | 164.48 | 2480.32 | -2621.92 | 996.16 | 1316.37 | -2029.89 | -298.13 | -31618.35 | 103635.09 | -102561.22 | -1845.65 | 3078.86 | -29303.88
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 |  |  |  | 495.22 | [5 empty] | 486.47 |  |  | 981.69
|  | Labor Total |  |  |  |  | 495.22 | [5 empty] | 486.47 |  |  | 981.69
| MAJOR PROJECT ORG Total | [5 empty] | 495.22 | [5 empty] | 486.47 |  |  | 981.69
| Other | Other | Other | 1008737.69 | 170998.24 | 2169276.43 | 1252692.23 | -1852316.4 | 3348143.2 | -1574959.8 | -4082239.56 | 1635897.19 | 2909775.88 | -1321371.59 | -3594764.89 | 69868.62
|  | Other Total |  | 1008737.69 | 170998.24 | 2169276.43 | 1252692.23 | -1852316.4 | 3348143.2 | -1574959.8 | -4082239.56 | 1635897.19 | 2909775.88 | -1321371.59 | -3594764.89 | 69868.62
| Other Total |  |  | 1008737.69 | 170998.24 | 2169276.43 | 1252692.23 | -1852316.4 | 3348143.2 | -1574959.8 | -4082239.56 | 1635897.19 | 2909775.88 | -1321371.59 | -3594764.89 | 69868.62
| PWRD OTHER | Labor | Labor Entries <$5,000 | [11 empty] | 425.43 | 425.43
|  | Labor Total | [12 empty] | 425.43 | 425.43
| PWRD OTHER Total | [13 empty] | 425.43 | 425.43
| SC&M | Labor | Labor Entries <$5,000 | 4963.16 | 5848.23 | 4091.38 | 1040.21 | 358.04 | 682.27 | 1001.5 | 2300.63 | 1227.98 | 405.01 | 506.64 | 1113.79 | 23538.84
|  | Labor Total |  | 4963.16 | 5848.23 | 4091.38 | 1040.21 | 358.04 | 682.27 | 1001.5 | 2300.63 | 1227.98 | 405.01 | 506.64 | 1113.79 | 23538.84
| SC&M Total |  |  | 4963.16 | 5848.23 | 4091.38 | 1040.21 | 358.04 | 682.27 | 1001.5 | 2300.63 | 1227.98 | 405.01 | 506.64 | 1113.79 | 23538.84
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 | [5 empty] | 212.02 | 211.27 | 619.21 | 207.17 | 406.82 |  |  | 1656.49
|  | Labor Total | [6 empty] | 212.02 | 211.27 | 619.21 | 207.17 | 406.82 |  |  | 1656.49
| TEC SRVCS SUMMARY Total | [7 empty] | 212.02 | 211.27 | 619.21 | 207.17 | 406.82 |  |  | 1656.49
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -8796.96 | 8796.96 |  |  | 0
|  | Contract Total | [9 empty] | -8796.96 | 8796.96 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -8796.96 | 8796.96 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 816.26 | 642.03 | 3092.6 | 4143.73 | 1521.56 | 1829.7 | 638.88 | 798.5 | 146.08 | 775.48 | 10668.15 | 26435.86 | 51508.83
|  | Contract Total |  | 816.26 | 642.03 | 3092.6 | 4143.73 | 1521.56 | 1829.7 | 638.88 | 798.5 | 146.08 | 775.48 | 10668.15 | 26435.86 | 51508.83
| Temporary/Supplementary - Trade/Labor Total |  |  | 816.26 | 642.03 | 3092.6 | 4143.73 | 1521.56 | 1829.7 | 638.88 | 798.5 | 146.08 | 775.48 | 10668.15 | 26435.86 | 51508.83
1. Project Support Total |  |  |  | 1053044.79 | 232127.4 | 2193652.72 | 1282418.23 | -1809274.31 | 3543198.6 | -1539714.77 | -3896552.75 | 3825302.98 | 1015350.6 | -1184244.31 | -3458078.12 | 1257231.06
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | ABB INC |  |  | 3138030 | 512826 |  |  | 125766.62 | [5 empty] | 3776622.62
|  | Material - Direct Purchase Total |  |  |  | 3138030 | 512826 |  |  | 125766.62 | [5 empty] | 3776622.62
| Breakers - Circuit-DP Total |  |  |  |  | 3138030 | 512826 |  |  | 125766.62 | [5 empty] | 3776622.62
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp |  |  | 93498.17 |  |  |  | 118029.68 |  |  | 17960.91 |  | 15769.55 | 245258.31
|  |  | CAL-DUCT INC | [9 empty] | 5392.5 |  |  | 5392.5
|  |  | COMPASS POWER SERVICES CO |  |  |  | 5086.62 |  | 11038 | [6 empty] | 16124.62
|  |  | JENSEN PRECAST |  |  | 15840 | 7200 | 44287.94 | [7 empty] | 67327.94
|  |  | Material Entries <$5,000 |  | 752.43 |  |  | 213.16 | 30.98 |  | 4289.5 | 360.35 | 3367.47 | 3273.37 | 690 | 12977.26
|  |  | OLD CASTLE PRECAST | [10 empty] | 11838 |  | 11838
|  | Material - Direct Purchase Total |  |  | 752.43 | 109338.17 | 12286.62 | 44501.1 | 11068.98 | 118029.68 | 4289.5 | 360.35 | 26720.88 | 15111.37 | 16459.55 | 358918.63
| Building, Shop & Industrial Products/Eqp Total |  |  |  | 752.43 | 109338.17 | 12286.62 | 44501.1 | 11068.98 | 118029.68 | 4289.5 | 360.35 | 26720.88 | 15111.37 | 16459.55 | 358918.63
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Cabinets, Panels and Switchboards-DP | [11 empty] | 88958 | 88958
|  |  | ELECTRICAL POWER PRODUCTS INC | [7 empty] | 705658 |  | 309121 |  |  | 1014779
|  |  | NORTON & NORTON ELECTRIC CO LTD | [7 empty] | 143363 |  |  | 195769 |  | 339132
|  | Material - Direct Purchase Total | [8 empty] | 849021 |  | 309121 | 195769 | 88958 | 1442869
| Cabinets, Panels and Switchboards-DP Total | [9 empty] | 849021 |  | 309121 | 195769 | 88958 | 1442869
| Capacitors and Regulators-DP | Material - Direct Purchase | Material Entries <$5,000 | -21250 | [11 empty] | -21250
|  | Material - Direct Purchase Total |  | -21250 | [11 empty] | -21250
| Capacitors and Regulators-DP Total |  |  | -21250 | [11 empty] | -21250
| Communication Systems and Equipment -DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 31.01 |  |  |  | 31.01
|  | Material - Direct Purchase Total | [9 empty] | 31.01 |  |  |  | 31.01
| Communication Systems and Equipment -DP Total | [10 empty] | 31.01 |  |  |  | 31.01
| Electric Wiring and Components-DP | Material - Direct Purchase | CROSS BROTHERS INC | [10 empty] | 20700 |  | 20700
|  |  | Electric Wiring and Components-DP | [11 empty] | 50187.39 | 50187.39
|  |  | Material Entries <$5,000 | [9 empty] | 908.37 | 113.56 |  | 1021.93
|  |  | OLD CASTLE PRECAST | [5 empty] | 15980 | [6 empty] | 15980
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [8 empty] | 18373.86 | 8911.54 | 84488.58 | 449274.8 | 561048.78
|  |  | SOUTHWIRE COMPANY | [8 empty] | 46520 | 63720 |  |  | 110240
|  |  | WALKER AND ASSOCIATES INC | [7 empty] | 7024.18 |  |  |  |  | 7024.18
|  | Material - Direct Purchase Total | [6 empty] | 15980 |  | 7024.18 | 64893.86 | 73539.91 | 105302.14 | 499462.19 | 766202.28
| Electric Wiring and Components-DP Total | [7 empty] | 15980 |  | 7024.18 | 64893.86 | 73539.91 | 105302.14 | 499462.19 | 766202.28
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 2259 |  |  | 303.48 | [5 empty] | 2562.48
|  | Material - Direct Purchase Total |  |  |  |  | 2259 |  |  | 303.48 | [5 empty] | 2562.48
| Fuels, Chemicals & Petrochem-DP Total | [5 empty] | 2259 |  |  | 303.48 | [5 empty] | 2562.48
| Insulators & Bushings-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 230.8 |  |  | 230.8
|  | Material - Direct Purchase Total | [10 empty] | 230.8 |  |  | 230.8
| Insulators & Bushings-DP Total | [11 empty] | 230.8 |  |  | 230.8
| Line Switches & Switchgear-DP | Material - Direct Purchase | SOUTHERN STATES LLC |  |  |  |  | 1503054 | [7 empty] | 1503054
|  | Material - Direct Purchase Total | [5 empty] | 1503054 | [7 empty] | 1503054
| Line Switches & Switchgear-DP Total | [6 empty] | 1503054 | [7 empty] | 1503054
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -249.52 | 249.52 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -249.52 | 249.52 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -249.52 | 249.52 |  |  | 0
| Material - Inventory | Material | Material - Inventory | 624389.24 |  | 732503.76 |  | 5784.61 | 23516.24 | 25926.24 | 306337.2 | 229455.49 | 1192372.9 | 106452.25 | 202003.57 | 3448741.5
|  | Material Total |  | 624389.24 |  | 732503.76 |  | 5784.61 | 23516.24 | 25926.24 | 306337.2 | 229455.49 | 1192372.9 | 106452.25 | 202003.57 | 3448741.5
| Material - Inventory Total |  |  | 624389.24 |  | 732503.76 |  | 5784.61 | 23516.24 | 25926.24 | 306337.2 | 229455.49 | 1192372.9 | 106452.25 | 202003.57 | 3448741.5
| Material - Other | Material | Material - Other | 49279.7 | 216201.08 | 356328.32 | 65431.62 | 242697.41 | 9052.21 | 27149.63 | 148429.97 | 70246.92 | 319793.05 | 151524.06 | 75467.14 | 1731601.11
|  | Material Total |  | 49279.7 | 216201.08 | 356328.32 | 65431.62 | 242697.41 | 9052.21 | 27149.63 | 148429.97 | 70246.92 | 319793.05 | 151524.06 | 75467.14 | 1731601.11
| Material - Other Total |  |  | 49279.7 | 216201.08 | 356328.32 | 65431.62 | 242697.41 | 9052.21 | 27149.63 | 148429.97 | 70246.92 | 319793.05 | 151524.06 | 75467.14 | 1731601.11
| Material Handling Services | Contract | Contract Entries <$50,000 | [9 empty] | 892 |  | 21065 | 21957
|  |  | ELECTRICAL POWER PRODUCTS INC | [11 empty] | 91913 | 91913
|  | Contract Total | [10 empty] | 892 |  | 112978 | 113870
| Material Handling Services Total | [11 empty] | 892 |  | 112978 | 113870
| Mechanical Systems and Components-DP | Material - Direct Purchase | GENERATOR SERVICES CO INC |  |  |  |  | 118600 | [6 empty] | 6600 | 125200
|  |  | HILTI, INC. | [10 empty] | 23800 |  | 23800
|  |  | Material Entries <$5,000 |  |  |  |  | 3020 | [7 empty] | 3020
|  |  | OLD CASTLE PRECAST | [9 empty] | 50223.72 | 11310.36 |  | 61534.08
|  | Material - Direct Purchase Total | [5 empty] | 121620 |  |  |  |  | 50223.72 | 35110.36 | 6600 | 213554.08
| Mechanical Systems and Components-DP Total | [6 empty] | 121620 |  |  |  |  | 50223.72 | 35110.36 | 6600 | 213554.08
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 1128.34 |  | 68.92 |  | 1338.51 |  | 2535.77
|  |  | Metals & Fabricated Metal Products-DP | [9 empty] | 20103.82 |  | 7896.38 | 28000.2
|  | Material - Direct Purchase Total | [7 empty] | 1128.34 |  | 68.92 | 20103.82 | 1338.51 | 7896.38 | 30535.97
| Metals & Fabricated Metal Products-DP Total | [8 empty] | 1128.34 |  | 68.92 | 20103.82 | 1338.51 | 7896.38 | 30535.97
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | MAGNETIC INSTRUMENTATION INC | [8 empty] | 121655 |  |  |  | 121655
|  |  | RONAN ENGINEERING COMPANY | [9 empty] | 65908 |  |  | 65908
|  | Material - Direct Purchase Total | [9 empty] | 121655 | 65908 |  |  | 187563
| Meters, Monitor and Warnings-DP Total | [10 empty] | 121655 | 65908 |  |  | 187563
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 212.95 |  |  | 212.95
|  | Material - Direct Purchase Total | [10 empty] | 212.95 |  |  | 212.95
| Monitor Equipment, Gauges and Hoses-DP Total | [11 empty] | 212.95 |  |  | 212.95
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 533.37 |  | 1931.38 | 2464.75
|  | Material - Direct Purchase Total | [10 empty] | 533.37 |  | 1931.38 | 2464.75
| Office & Office Support Products-DP Total | [11 empty] | 533.37 |  | 1931.38 | 2464.75
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 1362.9 |  |  | 4184.15 |  | 2763 | 8310.05
|  | Material - Direct Purchase Total | [7 empty] | 1362.9 |  |  | 4184.15 |  | 2763 | 8310.05
| Pipe/Tubing, Fittings and Gaskets-DP Total | [8 empty] | 1362.9 |  |  | 4184.15 |  | 2763 | 8310.05
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 3475.18 |  | 2190 |  |  | 5665.18
|  |  | Pole Line Hdwe & Connectors-DP | [6 empty] | 7946.29 |  |  | 80576.24 | 7199.82 | 7627.69 | 103350.04
|  | Material - Direct Purchase Total | [7 empty] | 7946.29 | 3475.18 |  | 82766.24 | 7199.82 | 7627.69 | 109015.22
| Pole Line Hdwe & Connectors-DP Total | [8 empty] | 7946.29 | 3475.18 |  | 82766.24 | 7199.82 | 7627.69 | 109015.22
| Poles & Wood Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 128.2 | [10 empty] | 128.2
|  | Material - Direct Purchase Total |  |  | 128.2 | [10 empty] | 128.2
| Poles & Wood Products-DP Total |  |  |  | 128.2 | [10 empty] | 128.2
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | AMERON INTERNATIONAL CORPORATION |  |  |  |  | 369772 | [7 empty] | 369772
|  |  | BENNING POWER ELECTRONICS INC | [5 empty] | 21194 | [6 empty] | 21194
|  |  | C&D TECHNOLOGIES |  |  |  |  | 69000 | [7 empty] | 69000
|  |  | M & M POWER PRODUCTS | [8 empty] | 27000 |  |  |  | 27000
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [9 empty] | 186620.21 |  |  | 186620.21
|  | Material - Direct Purchase Total | [5 empty] | 438772 | 21194 |  |  | 27000 | 186620.21 |  |  | 673586.21
| Power Systems, Batteries and Light-DP Total | [6 empty] | 438772 | 21194 |  |  | 27000 | 186620.21 |  |  | 673586.21
| Protection and Test-DP | Material - Direct Purchase | ABB INC | [7 empty] | 92881.14 |  |  |  |  | 92881.14
|  |  | Material Entries <$5,000 | [9 empty] | 4059.93 | 153.46 |  | 4213.39
|  | Material - Direct Purchase Total | [8 empty] | 92881.14 |  | 4059.93 | 153.46 |  | 97094.53
| Protection and Test-DP Total | [9 empty] | 92881.14 |  | 4059.93 | 153.46 |  | 97094.53
| Reactors and Line Traps-DP | Material - Direct Purchase | HYUNDAI CORPORATION USA | [9 empty] | 1811616.8 |  |  | 1811616.8
|  |  | Material Entries <$5,000 |  | 25020 |  | 0 | [5 empty] | 0 |  |  | 25020
|  | Material - Direct Purchase Total |  |  | 25020 |  | 0 | [5 empty] | 1811616.8 |  |  | 1836636.8
| Reactors and Line Traps-DP Total |  |  |  | 25020 |  | 0 | [5 empty] | 1811616.8 |  |  | 1836636.8
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO |  | 2443113.12 | 309274.21 | 27100 | 580001.54 | 30258.16 | 5900 | 204270.42 |  |  | 78584 |  | 3678501.45
|  |  | Material Entries <$5,000 | [9 empty] | 267.02 |  |  | 267.02
|  |  | PARCELL STEEL CO |  | 191214.07 | [5 empty] | 19789.46 |  |  |  |  | 211003.53
|  |  | Steel / Fabricated / Structural-DP | [10 empty] | 23980 | 9553.95 | 33533.95
|  | Material - Direct Purchase Total |  |  | 2634327.19 | 309274.21 | 27100 | 580001.54 | 30258.16 | 5900 | 224059.88 |  | 267.02 | 102564 | 9553.95 | 3923305.95
| Steel / Fabricated / Structural-DP Total |  |  |  | 2634327.19 | 309274.21 | 27100 | 580001.54 | 30258.16 | 5900 | 224059.88 |  | 267.02 | 102564 | 9553.95 | 3923305.95
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 24298.75 | 450.23 | 2131.59 | 514.2 |  | 85.95 | 18.24 | 3670.75 | 2211.68 | 8312.27 | 41693.66
|  |  | Transportation & Mobile Equip-DP |  |  | 38656.91 | 11154.97 | 41086.09 |  |  |  | 5034.75 |  |  |  | 95932.72
|  | Material - Direct Purchase Total |  |  |  | 62955.66 | 11605.2 | 43217.68 | 514.2 |  | 85.95 | 5052.99 | 3670.75 | 2211.68 | 8312.27 | 137626.38
| Transportation & Mobile Equip-DP Total |  |  |  |  | 62955.66 | 11605.2 | 43217.68 | 514.2 |  | 85.95 | 5052.99 | 3670.75 | 2211.68 | 8312.27 | 137626.38
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | ANIXTER INC |  |  |  |  | 13452.15 | [7 empty] | 13452.15
|  |  | Material Entries <$5,000 | 2926.5 | [6 empty] | 21.98 | 1929 | 867.77 |  |  | 5745.25
|  | Material - Direct Purchase Total |  | 2926.5 |  |  |  | 13452.15 |  |  | 21.98 | 1929 | 867.77 |  |  | 19197.4
| Wire, Cable & Bus Bar-DP Total |  |  | 2926.5 |  |  |  | 13452.15 |  |  | 21.98 | 1929 | 867.77 |  |  | 19197.4
2. Material Total |  |  |  | 655345.44 | 2876428.9 | 4708430.12 | 631508.44 | 2993100.49 | 111583.79 | 313513.18 | 1635625.98 | 520444.02 | 4153954.79 | 722736.65 | 1040013.12 | 20362684.92
3. Construction | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [6 empty] | 19478 | 4784.68 | 3415.83 | 10247.49 | 6642.66 | 3415.83 | 47984.49
|  | Contract Total | [7 empty] | 19478 | 4784.68 | 3415.83 | 10247.49 | 6642.66 | 3415.83 | 47984.49
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [8 empty] | 19478 | 4784.68 | 3415.83 | 10247.49 | 6642.66 | 3415.83 | 47984.49
| Construction Management Services | Contract | Contract Entries <$50,000 | 101489.36 | 59619.22 | 145767.05 | 257.6 | 95156.79 | 2959.44 | 6412.5 | 257.6 | 6075 | 8671.85 | 21555 | 37242.95 | 485464.36
|  |  | UTILITY LINE MANAGEMENT SERVICES |  |  |  | 106705.04 | [8 empty] | 106705.04
|  | Contract Total |  | 101489.36 | 59619.22 | 145767.05 | 106962.64 | 95156.79 | 2959.44 | 6412.5 | 257.6 | 6075 | 8671.85 | 21555 | 37242.95 | 592169.4
| Construction Management Services Total |  |  | 101489.36 | 59619.22 | 145767.05 | 106962.64 | 95156.79 | 2959.44 | 6412.5 | 257.6 | 6075 | 8671.85 | 21555 | 37242.95 | 592169.4
| Construction Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -13859.34 | 13859.34 |  |  | 0
|  | Contract Total | [9 empty] | -13859.34 | 13859.34 |  |  | 0
| Construction Services - Correction Total | [10 empty] | -13859.34 | 13859.34 |  |  | 0
| Construction Services - Other | Contract | Contract Entries <$50,000 |  |  |  |  | 4500 |  |  | 4500 | 2500 | 5256.69 | 2000 | 2500 | 21256.69
|  | Contract Total | [5 empty] | 4500 |  |  | 4500 | 2500 | 5256.69 | 2000 | 2500 | 21256.69
| Construction Services - Other Total | [6 empty] | 4500 |  |  | 4500 | 2500 | 5256.69 | 2000 | 2500 | 21256.69
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | 2707.18 | 1497.88 | 678.94 | 1721.9 |  | 11542.99 | [6 empty] | 18148.89
|  | Contract Total |  | 2707.18 | 1497.88 | 678.94 | 1721.9 |  | 11542.99 | [6 empty] | 18148.89
| Construction, Civil/Structural Total |  |  | 2707.18 | 1497.88 | 678.94 | 1721.9 |  | 11542.99 | [6 empty] | 18148.89
| Construction, Earthwork | Contract | Contract Entries <$50,000 | -0.7 | 49000 |  |  |  | 27639 |  | 28028 |  |  | 6205.94 |  | 110872.24
|  |  | SOUTH WEST PUMP & DRILLING, INC. | [6 empty] | 176906.7 | [5 empty] | 176906.7
|  | Contract Total |  | -0.7 | 49000 |  |  |  | 27639 | 176906.7 | 28028 |  |  | 6205.94 |  | 287778.94
| Construction, Earthwork Total |  |  | -0.7 | 49000 |  |  |  | 27639 | 176906.7 | 28028 |  |  | 6205.94 |  | 287778.94
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 664.96 | 664.96
|  | Labor Total | [12 empty] | 664.96 | 664.96
| ELEC SYS PLANNING Total | [13 empty] | 664.96 | 664.96
| Electrical Construction | Contract | Contract Entries <$50,000 | [7 empty] | 37529 |  |  |  |  | 37529
|  |  | PAR ELECTRICAL CONTRACTORS INC |  | 883861.4 | 771796.44 | 780007.79 | 4154816.09 | 888872.78 |  | 4641580.5 | 56339 |  |  |  | 12177274
|  | Contract Total |  |  | 883861.4 | 771796.44 | 780007.79 | 4154816.09 | 888872.78 |  | 4679109.5 | 56339 |  |  |  | 12214803
| Electrical Construction Total |  |  |  | 883861.4 | 771796.44 | 780007.79 | 4154816.09 | 888872.78 |  | 4679109.5 | 56339 |  |  |  | 12214803
| Electrical Construction, Substations | Contract | Contract Entries <$50,000 | [11 empty] | 42922 | 42922
|  |  | WILSON UTILITY CONSTRUCTION | [7 empty] | 786842.85 |  | 2195922 | 5117494.03 | 3972093.61 | 12072352.49
|  | Contract Total | [8 empty] | 786842.85 |  | 2195922 | 5117494.03 | 4015015.61 | 12115274.49
| Electrical Construction, Substations Total | [9 empty] | 786842.85 |  | 2195922 | 5117494.03 | 4015015.61 | 12115274.49
| ENGINEERING | Labor | Labor Entries <$5,000 | 169.41 |  | 468.2 | 614.62 |  |  | 327.8 | 333.75 |  |  |  |  | 1913.78
|  | Labor Total |  | 169.41 |  | 468.2 | 614.62 |  |  | 327.8 | 333.75 |  |  |  |  | 1913.78
| ENGINEERING Total |  |  | 169.41 |  | 468.2 | 614.62 |  |  | 327.8 | 333.75 |  |  |  |  | 1913.78
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 2338.39 | 2338.39
|  | Labor Total | [12 empty] | 2338.39 | 2338.39
| GRID OPS Total | [13 empty] | 2338.39 | 2338.39
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 |  |  | 1397 | 7530.5 | 2500 | -2500 |  |  |  | 1397 |  |  | 10324.5
|  | Contract Total |  |  |  | 1397 | 7530.5 | 2500 | -2500 |  |  |  | 1397 |  |  | 10324.5
| Hauling / Industrial Moving Services Total |  |  |  |  | 1397 | 7530.5 | 2500 | -2500 |  |  |  | 1397 |  |  | 10324.5
| Labor - Other | Labor | Labor Entries <$5,000 | [5 empty] | 1718.73 | 787.21 | 1190.42 | 1248.74 | 2717.3 | 881.77 | 1129.02 | 9673.19
|  | Labor Total | [6 empty] | 1718.73 | 787.21 | 1190.42 | 1248.74 | 2717.3 | 881.77 | 1129.02 | 9673.19
| Labor - Other Total | [7 empty] | 1718.73 | 787.21 | 1190.42 | 1248.74 | 2717.3 | 881.77 | 1129.02 | 9673.19
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  | 27674 | 33660 |  |  | 14151 | 27734.29 | [5 empty] | 103219.29
|  |  | KINDNESS GENERAL CONTRACTORS INC | [7 empty] | 83798.48 | 84154.34 |  |  |  | 167952.82
|  | Contract Total |  |  | 27674 | 33660 |  |  | 14151 | 27734.29 | 83798.48 | 84154.34 |  |  |  | 271172.11
| Major Construction, Turnkey, Trans/Subs Total |  |  |  | 27674 | 33660 |  |  | 14151 | 27734.29 | 83798.48 | 84154.34 |  |  |  | 271172.11
| Material - Other | Material | Material - Other | [9 empty] | 8.97 |  |  | 8.97
|  | Material Total | [10 empty] | 8.97 |  |  | 8.97
| Material - Other Total | [11 empty] | 8.97 |  |  | 8.97
| Other | Other | Other | [5 empty] | 71.82 | 141.42 | 63.83 | 7089.34 | -7003.85 |  | 22.48 | 385.04
|  | Other Total | [6 empty] | 71.82 | 141.42 | 63.83 | 7089.34 | -7003.85 |  | 22.48 | 385.04
| Other Total | [7 empty] | 71.82 | 141.42 | 63.83 | 7089.34 | -7003.85 |  | 22.48 | 385.04
| SC&M | Labor | Labor Entries <$5,000 | 1867.67 | 810.36 | 2337 | 2469.52 | 1800.19 | 2203.71 | 1067.1 | 3234.28 | 1272.51 | 1736.87 | 2322.38 | 1953.79 | 23075.38
|  | Labor Total |  | 1867.67 | 810.36 | 2337 | 2469.52 | 1800.19 | 2203.71 | 1067.1 | 3234.28 | 1272.51 | 1736.87 | 2322.38 | 1953.79 | 23075.38
| SC&M Total |  |  | 1867.67 | 810.36 | 2337 | 2469.52 | 1800.19 | 2203.71 | 1067.1 | 3234.28 | 1272.51 | 1736.87 | 2322.38 | 1953.79 | 23075.38
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  | 171.84 |  |  | 124.63 | [5 empty] | 140.77 |  | 437.24
|  | Labor Total |  |  | 171.84 |  |  | 124.63 | [5 empty] | 140.77 |  | 437.24
| SCM HOME CENTER Total |  |  |  | 171.84 |  |  | 124.63 | [5 empty] | 140.77 |  | 437.24
| Security / Protection Services | Contract | Contract Entries <$50,000 | 33645.79 |  | 36847.15 | 37198.02 | 34980.99 | 36669.37 | 47688.09 | 69948.64 | 17500.19 | 1803.11 | 44504.79 | 1803.11 | 362589.25
|  |  | WACKENHUT CORPORATION (THE) |  | 50964.99 | [7 empty] | 60007.2 |  | 76556.57 | 187528.76
|  | Contract Total |  | 33645.79 | 50964.99 | 36847.15 | 37198.02 | 34980.99 | 36669.37 | 47688.09 | 69948.64 | 17500.19 | 61810.31 | 44504.79 | 78359.68 | 550118.01
| Security / Protection Services Total |  |  | 33645.79 | 50964.99 | 36847.15 | 37198.02 | 34980.99 | 36669.37 | 47688.09 | 69948.64 | 17500.19 | 61810.31 | 44504.79 | 78359.68 | 550118.01
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 15672.52 | 14308.23 | 54624.12 | 19203.49 | 26229.69 | 74365.15 | 33498.22 | 11423.94 | 33719.76 | 28812.97 | 21314.53 | 26444.42 | 359617.04
|  | Contract Total |  | 15672.52 | 14308.23 | 54624.12 | 19203.49 | 26229.69 | 74365.15 | 33498.22 | 11423.94 | 33719.76 | 28812.97 | 21314.53 | 26444.42 | 359617.04
| Short Term Equipment Rent Total |  |  | 15672.52 | 14308.23 | 54624.12 | 19203.49 | 26229.69 | 74365.15 | 33498.22 | 11423.94 | 33719.76 | 28812.97 | 21314.53 | 26444.42 | 359617.04
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 |  |  | 82 | 246 | [5 empty] | 82 |  |  | 410
|  | Labor Total |  |  |  | 82 | 246 | [5 empty] | 82 |  |  | 410
| TSD-HERC - Crane Svs Total |  |  |  |  | 82 | 246 | [5 empty] | 82 |  |  | 410
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 |  |  | 328 | 164 | 164 | 164 | 164 | 164 | 246 | 164 | 164 | 410 | 2132
|  | Labor Total |  |  |  | 328 | 164 | 164 | 164 | 164 | 164 | 246 | 164 | 164 | 410 | 2132
| TSD-HERC - Rental Total |  |  |  |  | 328 | 164 | 164 | 164 | 164 | 164 | 246 | 164 | 164 | 410 | 2132
3. Construction Total |  |  |  | 155551.23 | 1087907.92 | 1047985.9 | 956118.48 | 4320272.38 | 1057857.99 | 314205.33 | 5673679.97 | 199701.37 | 2323682.94 | 5223225.87 | 4169497.13 | 26529686.51
4. Allocated | Chargebacks | Chargeback | BR Reprographics / DWG MGMT REPRGRAPHC | [8 empty] | 7650.88 |  |  |  | 7650.88
|  |  | Chargeback Entries <$5,000 | 122515.13 | -66032.25 | -15048.15 | 568425.38 | -745803.42 | 243264.49 | -185911.66 | -708220.68 | -124809.39 | 48926.72 | 5827.17 | -88697.99 | -945564.65
|  |  | COLORADO RIVER SUB COST ALLOCATION | 7150.32 | 26727.62 | 131284.56 | 88675.41 | 150519.08 | 87315.83 | 171063.56 | 107700.96 | 12806.09 | 143582.53 | 124600.48 | 260313.08 | 1311739.52
|  |  | CRS Switchyard & Expansion Share Costs |  | 139976.17 |  |  | 592609.97 | 23757.95 |  | 863248.01 |  |  |  |  | 1619592.1
|  |  | DPV2/DCR Project Mgmt Home Office Cost |  | 17370.17 | 16172.02 | 20457.89 | 17860.43 | 16648.97 | 16763.81 | 21312.24 | 17765.57 | 18879.44 | 18419.31 | 18714.59 | 200364.44
|  |  | MATERIAL MANAGEM | 238454.25 |  | 178511.17 |  |  |  |  | 39977 | 41462.61 | 139626.87 | 18075.59 | 27129.08 | 683236.57
|  |  | PDP- Colorado Rvr Switchyd/Sub-MPO | 211733.21 | 316119.13 | 506463.43 | 499705.51 | 303342.28 | 112780.54 | 438239.5 | 76350.94 |  | 193136.86 | 120098.27 | 115791.9 | 2893761.57
|  |  | PDP-Colorado River Switchyard-MPO |  |  | 1720883.2 | 104037.37 | 189278.33 | 24596.75 | 158307.66 | 36046.26 |  | 58413.21 | 27829.97 | 41847.18 | 2361239.93
|  |  | PDP-DPV2 General Mtg Support-MPO |  | 74896.84 |  | 10110.79 | 27958.65 | 63649.86 | 63688.81 | 98400.65 |  | 111533.05 | 71806.5 | 39398.37 | 561443.52
|  |  | PROCUREMENT TDBU |  | 24717.14 | 30444.73 | 10096.11 | 46553.97 | 8366.03 |  | 46415.26 |  | 47510.27 | 38559.2 | 33381.47 | 286044.18
|  | Chargeback Total |  | 579852.91 | 533774.82 | 2568710.96 | 1301508.46 | 582319.29 | 580380.42 | 662151.68 | 581230.64 | -45124.24 | 761608.95 | 425216.49 | 447877.68 | 8979508.06
| Chargebacks Total |  |  | 579852.91 | 533774.82 | 2568710.96 | 1301508.46 | 582319.29 | 580380.42 | 662151.68 | 581230.64 | -45124.24 | 761608.95 | 425216.49 | 447877.68 | 8979508.06
| Labor - Other | Labor | Division Overhead | 73918.81 | 342177.29 | 410498.07 | 116179.33 | 488930.14 | 89929.37 | 42440.52 | 544739.51 |  | 686217.08 | 147463.96 | 191893.97 | 3134388.05
|  |  | Labor Entries <$5,000 | 10145.29 | 4270.09 | 5027.48 | 3579.24 | 4838.43 | 3758.1 | 7795.3 | -4985.28 | -97233.99 | 8202.24 | 6728.48 | 5388.46 | -42486.16
|  |  | Paid Absence |  | 5389.84 | [7 empty] | 10889.09 |  |  | 16278.93
|  | Labor Total |  | 84064.1 | 351837.22 | 415525.55 | 119758.57 | 493768.57 | 93687.47 | 50235.82 | 539754.23 | -97233.99 | 705308.41 | 154192.44 | 197282.43 | 3108180.82
| Labor - Other Total |  |  | 84064.1 | 351837.22 | 415525.55 | 119758.57 | 493768.57 | 93687.47 | 50235.82 | 539754.23 | -97233.99 | 705308.41 | 154192.44 | 197282.43 | 3108180.82
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -47369.31 | 47369.31 |  |  | 0
|  | Overhead Total | [9 empty] | -47369.31 | 47369.31 |  |  | 0
| Overhead Correction Total | [10 empty] | -47369.31 | 47369.31 |  |  | 0
4. Allocated Total |  |  |  | 663917.01 | 885612.04 | 2984236.51 | 1421267.03 | 1076087.86 | 674067.89 | 712387.5 | 1120984.87 | -189727.54 | 1514286.67 | 579408.93 | 645160.11 | 12087688.88
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 179936.7 | 13391.98 | [6 empty] | 417669.1 | 610997.78
|  |  | AFUDC - Debt/Equity |  |  | 129403.86 | -129403.86 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 84873.71 | 143901.05 | 312473.67 | 108491.02 | 701921.94 | 72806.82 | 48341.93 | 243878.07 | 38479.32 | 206002.4 | 176334.57 | 168261.37 | 2305765.87
|  |  | Capitalized Overhead - Inj & Damages | 1121.2 | 6357.37 | 7861.9 | 1332.76 | 27708.66 | 724.3 | 250.87 | 2404.96 | 2399.1 | 9328.6 | 1591.72 | 1352.01 | 62433.45
|  |  | Capitalized Overhead - P&B/Payroll Tax | 25402.21 | 53281.37 | 37801.41 | 46297.26 | 61972.83 | 46652.41 | 38070.24 | 6976.7 | -41901.65 | 43286.99 | 26655.5 | 93754.97 | 438250.24
|  |  | Corporate Overheads Correction |  |  |  |  | -175337.16 | [7 empty] | -175337.16
|  | Non Budgeted Total |  | 111397.12 | 203539.79 | 487540.84 | 206653.88 | 629658.25 | 120183.53 | 86663.04 | 253259.73 | -1023.23 | 258617.99 | 204581.79 | 681037.45 | 3242110.18
| Non Budget - Other Total |  |  | 111397.12 | 203539.79 | 487540.84 | 206653.88 | 629658.25 | 120183.53 | 86663.04 | 253259.73 | -1023.23 | 258617.99 | 204581.79 | 681037.45 | 3242110.18
5. Corporate Overhead Total |  |  |  | 111397.12 | 203539.79 | 487540.84 | 206653.88 | 629658.25 | 120183.53 | 86663.04 | 253259.73 | -1023.23 | 258617.99 | 204581.79 | 681037.45 | 3242110.18
Grand Total |  |  |  | 2639255.59 | 5285616.05 | 11421846.09 | 4497966.06 | 7209844.67 | 5506891.8 | -112945.72 | 4786997.8 | 4354697.6 | 9265892.99 | 5545708.93 | 3077629.69 | 63479401.55

## 800063033
Pin: 4847 | Project: DCR
Order: 800063033 | 800063033- I: DCR: DEVERS-Colorado River 500KV SERI
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  |  | 10.92 |  | 256.62 |  |  | 378.33 |  |  | 645.87
|  | Labor Total | [5 empty] | 10.92 |  | 256.62 |  |  | 378.33 |  |  | 645.87
| BP&FM Total | [6 empty] | 10.92 |  | 256.62 |  |  | 378.33 |  |  | 645.87
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 | [7 empty] | 344.5 | 689 | 159.12 | 318.24 | 689 | 2199.86
|  | Contract Total | [8 empty] | 344.5 | 689 | 159.12 | 318.24 | 689 | 2199.86
| Cleaning / Janitorial Services Total | [9 empty] | 344.5 | 689 | 159.12 | 318.24 | 689 | 2199.86
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  |  | 1305 |  | 612.15 | -612.15 |  |  |  |  | 1305
|  | Contract Total | [5 empty] | 1305 |  | 612.15 | -612.15 |  |  |  |  | 1305
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [6 empty] | 1305 |  | 612.15 | -612.15 |  |  |  |  | 1305
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 103044.36 |  |  | 103044.36
|  |  | Contract Entries <$50,000 | [8 empty] | -103044.36 |  |  |  | -103044.36
|  | Contract Total | [9 empty] | -103044.36 | 103044.36 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -103044.36 | 103044.36 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | [5 empty] | 8482.3 | 6454.76 | [5 empty] | 14937.06
|  | Contract Total | [6 empty] | 8482.3 | 6454.76 | [5 empty] | 14937.06
| Contract Consult/Contract Ord to Ord Total | [7 empty] | 8482.3 | 6454.76 | [5 empty] | 14937.06
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 |  | 210.66 | [9 empty] | 11518.8 | 11729.46
|  | Labor Total |  |  | 210.66 | [9 empty] | 11518.8 | 11729.46
| ELEC SYS PLANNING Total |  |  |  | 210.66 | [9 empty] | 11518.8 | 11729.46
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 160.74 |  |  | 48.46 | 63.34 | 527.58 | [5 empty] | 800.12
|  | Labor Total |  |  | 160.74 |  |  | 48.46 | 63.34 | 527.58 | [5 empty] | 800.12
| ENG ADVANCEMENT Total |  |  |  | 160.74 |  |  | 48.46 | 63.34 | 527.58 | [5 empty] | 800.12
| ENGINEERING | Labor | Engineer | [7 empty] | 6616.64 | 5034.4 |  |  |  | 11651.04
|  |  | Labor Entries <$5,000 | 6677.87 | 7685.05 | 8705.89 | 4321.35 | 3314.79 | 9050.46 | 9379.44 | 9236.26 | 7148.99 | 10964.11 | 12283.1 | 1282.33 | 90049.64
|  | Labor Total |  | 6677.87 | 7685.05 | 8705.89 | 4321.35 | 3314.79 | 9050.46 | 9379.44 | 15852.9 | 12183.39 | 10964.11 | 12283.1 | 1282.33 | 101700.68
| ENGINEERING Total |  |  | 6677.87 | 7685.05 | 8705.89 | 4321.35 | 3314.79 | 9050.46 | 9379.44 | 15852.9 | 12183.39 | 10964.11 | 12283.1 | 1282.33 | 101700.68
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 6629.03 | 14080 | 6323 | 0 | 3324 | 9380.5 | 4285.5 | 19385.9 | 688 | 20109.95 | 5043.4 | 31919.9 | 121169.18
|  | Contract Total |  | 6629.03 | 14080 | 6323 | 0 | 3324 | 9380.5 | 4285.5 | 19385.9 | 688 | 20109.95 | 5043.4 | 31919.9 | 121169.18
| Engineering/Technical Professional Servi Total |  |  | 6629.03 | 14080 | 6323 | 0 | 3324 | 9380.5 | 4285.5 | 19385.9 | 688 | 20109.95 | 5043.4 | 31919.9 | 121169.18
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 670 | 1087.5 | 884.21 | 330 |  | 3440.25 | 3749.69 | 4255 | 3789.23 | 2768.52 | 1384.95 | 3584.87 | 25944.22
|  |  | GENERAL ELECTRIC INTERNATIONAL INC | 89950 | [11 empty] | 89950
|  | Contract Total |  | 90620 | 1087.5 | 884.21 | 330 |  | 3440.25 | 3749.69 | 4255 | 3789.23 | 2768.52 | 1384.95 | 3584.87 | 115894.22
| Environmental/Safety Professional Servic Total |  |  | 90620 | 1087.5 | 884.21 | 330 |  | 3440.25 | 3749.69 | 4255 | 3789.23 | 2768.52 | 1384.95 | 3584.87 | 115894.22
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 4506.69 | 3693.43 | 4216.27 | 4024.69 | -1441.23 | 3227.73 | 2857.38 | 2242.51 | 289220.21 | -304342.81 | -13201.57 | -1147.88 | -6144.58
|  | IMM Correction Total |  | 4506.69 | 3693.43 | 4216.27 | 4024.69 | -1441.23 | 3227.73 | 2857.38 | 2242.51 | 289220.21 | -304342.81 | -13201.57 | -1147.88 | -6144.58
| IMM/Allocated - Correction Total |  |  | 4506.69 | 3693.43 | 4216.27 | 4024.69 | -1441.23 | 3227.73 | 2857.38 | 2242.51 | 289220.21 | -304342.81 | -13201.57 | -1147.88 | -6144.58
| Labor - Other | Labor | Labor Correction | [9 empty] | 15852.38 |  |  | 15852.38
|  |  | Labor Entries <$5,000 | -135.58 | 1613.33 | -1525.22 | 184.55 | 6035.88 | -1670.35 | -303.06 | 905.38 | 33202.79 | -46381.38 | -2125.87 | 3339.89 | -6859.64
|  | Labor Total |  | -135.58 | 1613.33 | -1525.22 | 184.55 | 6035.88 | -1670.35 | -303.06 | 905.38 | 33202.79 | -30529 | -2125.87 | 3339.89 | 8992.74
| Labor - Other Total |  |  | -135.58 | 1613.33 | -1525.22 | 184.55 | 6035.88 | -1670.35 | -303.06 | 905.38 | 33202.79 | -30529 | -2125.87 | 3339.89 | 8992.74
| Legal Professional Services (OC & Attys) | Contract | Contract Entries <$50,000 |  |  |  | 5073 |  |  | 30.9 | [5 empty] | 5103.9
|  | Contract Total |  |  |  |  | 5073 |  |  | 30.9 | [5 empty] | 5103.9
| Legal Professional Services (OC & Attys) Total | [5 empty] | 5073 |  |  | 30.9 | [5 empty] | 5103.9
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 1004.79 | 739.69 | 587.8 | 495.22 | 932.45 | 834.02 | 494.03 | 586.16 | 1595.54 | 2716.72 | 2165.6 | 833.47 | 12985.49
|  | Labor Total |  | 1004.79 | 739.69 | 587.8 | 495.22 | 932.45 | 834.02 | 494.03 | 586.16 | 1595.54 | 2716.72 | 2165.6 | 833.47 | 12985.49
| MAJOR PROJECT ORG Total |  |  | 1004.79 | 739.69 | 587.8 | 495.22 | 932.45 | 834.02 | 494.03 | 586.16 | 1595.54 | 2716.72 | 2165.6 | 833.47 | 12985.49
| Other | Other | Other | -473.5 | 27.75 | 1497.87 | -100.75 | -562.91 | 13050.64 | -3891.1 | -3354.36 | -159631.33 | 161086.59 | 229.03 | 34101.79 | 41979.72
|  | Other Total |  | -473.5 | 27.75 | 1497.87 | -100.75 | -562.91 | 13050.64 | -3891.1 | -3354.36 | -159631.33 | 161086.59 | 229.03 | 34101.79 | 41979.72
| Other Total |  |  | -473.5 | 27.75 | 1497.87 | -100.75 | -562.91 | 13050.64 | -3891.1 | -3354.36 | -159631.33 | 161086.59 | 229.03 | 34101.79 | 41979.72
| PLGHCC | Labor | Labor Entries <$5,000 | [11 empty] | 63.04 | 63.04
|  | Labor Total | [12 empty] | 63.04 | 63.04
| PLGHCC Total | [13 empty] | 63.04 | 63.04
| SC&M | Labor | Labor Entries <$5,000 |  | 1014.4 | 688 |  | 460.57 |  | 597.77 |  |  | 157.01 | 158.31 | 1781.23 | 4857.29
|  | Labor Total |  |  | 1014.4 | 688 |  | 460.57 |  | 597.77 |  |  | 157.01 | 158.31 | 1781.23 | 4857.29
| SC&M Total |  |  |  | 1014.4 | 688 |  | 460.57 |  | 597.77 |  |  | 157.01 | 158.31 | 1781.23 | 4857.29
| Software License Via Electronic Delivery | Contract | Contract Entries <$50,000 | [11 empty] | 7810.6 | 7810.6
|  | Contract Total | [12 empty] | 7810.6 | 7810.6
| Software License Via Electronic Delivery Total | [13 empty] | 7810.6 | 7810.6
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 | [5 empty] | 424.04 | [6 empty] | 424.04
|  | Labor Total | [6 empty] | 424.04 | [6 empty] | 424.04
| TEC SRVCS SUMMARY Total | [7 empty] | 424.04 | [6 empty] | 424.04
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -3715.34 | 3715.34 |  |  | 0
|  | Contract Total | [9 empty] | -3715.34 | 3715.34 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -3715.34 | 3715.34 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 2018.54 | [11 empty] | 2018.54
|  | Contract Total |  | 2018.54 | [11 empty] | 2018.54
| Temporary/Supplementary - Technical/Prof Total |  |  | 2018.54 | [11 empty] | 2018.54
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 13685.9 | 27139.94 | 18209.51 | 10153.25 | 10089.57 | 15394.58 | 9482.58 | 18273.44 | 20740.7 | 24428.9 | 18661.88 | 37684.5 | 223944.75
|  | Contract Total |  | 13685.9 | 27139.94 | 18209.51 | 10153.25 | 10089.57 | 15394.58 | 9482.58 | 18273.44 | 20740.7 | 24428.9 | 18661.88 | 37684.5 | 223944.75
| Temporary/Supplementary - Trade/Labor Total |  |  | 13685.9 | 27139.94 | 18209.51 | 10153.25 | 10089.57 | 15394.58 | 9482.58 | 18273.44 | 20740.7 | 24428.9 | 18661.88 | 37684.5 | 223944.75
1. Project Support Total |  |  |  | 124533.74 | 57452.49 | 39587.33 | 24481.31 | 23517.5 | 61677.51 | 34534.24 | 57879.28 | 95717.83 | -5342.86 | 24917.07 | 133461.54 | 672416.98
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 3582.65 | 3582.65
|  | Material - Direct Purchase Total | [12 empty] | 3582.65 | 3582.65
| Breakers - Circuit-DP Total | [13 empty] | 3582.65 | 3582.65
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp |  |  |  |  | 14424.43 |  | 5822.01 | [5 empty] | 20246.44
|  |  | JENSEN PRECAST | [6 empty] | 11657 | [5 empty] | 11657
|  |  | Material Entries <$5,000 |  |  |  | 52.77 | 147.27 | 26.74 |  | 1494.24 |  |  |  |  | 1721.02
|  | Material - Direct Purchase Total |  |  |  |  | 52.77 | 14571.7 | 26.74 | 17479.01 | 1494.24 |  |  |  |  | 33624.46
| Building, Shop & Industrial Products/Eqp Total | [5 empty] | 52.77 | 14571.7 | 26.74 | 17479.01 | 1494.24 |  |  |  |  | 33624.46
| Capacitors and Regulators-DP | Material - Direct Purchase | SIEMENS ENERGY, INC. | [9 empty] | 1756158 |  |  | 1756158
|  | Material - Direct Purchase Total | [10 empty] | 1756158 |  |  | 1756158
| Capacitors and Regulators-DP Total | [11 empty] | 1756158 |  |  | 1756158
| Communication Systems and Equipment -DP | Material - Direct Purchase | Communication Systems and Equipment -DP | [11 empty] | 21483 | 21483
|  | Material - Direct Purchase Total | [12 empty] | 21483 | 21483
| Communication Systems and Equipment -DP Total | [13 empty] | 21483 | 21483
| Electric Wiring and Components-DP | Material - Direct Purchase | Electric Wiring and Components-DP | [6 empty] | 8222.87 |  |  |  | 6205.75 |  | 14428.62
|  |  | Material Entries <$5,000 |  |  | 1711 | 3057.38 | 764.47 |  |  | 6242.75 | 387.35 |  |  |  | 12162.95
|  | Material - Direct Purchase Total |  |  |  | 1711 | 3057.38 | 764.47 |  | 8222.87 | 6242.75 | 387.35 |  | 6205.75 |  | 26591.57
| Electric Wiring and Components-DP Total |  |  |  |  | 1711 | 3057.38 | 764.47 |  | 8222.87 | 6242.75 | 387.35 |  | 6205.75 |  | 26591.57
| Insulators & Bushings-DP | Material - Direct Purchase | NGK-LOCKE, INC |  |  | 10353.39 | [9 empty] | 10353.39
|  | Material - Direct Purchase Total |  |  |  | 10353.39 | [9 empty] | 10353.39
| Insulators & Bushings-DP Total |  |  |  |  | 10353.39 | [9 empty] | 10353.39
| Line Switches & Switchgear-DP | Material - Direct Purchase | CORIMPEX USA, INC. |  |  |  |  | 135507 | [7 empty] | 135507
|  |  | Material Entries <$5,000 |  |  |  | 2676 | [8 empty] | 2676
|  |  | SOUTHERN STATES LLC |  |  |  | 289590 | [8 empty] | 289590
|  | Material - Direct Purchase Total |  |  |  |  | 292266 | 135507 | [7 empty] | 427773
| Line Switches & Switchgear-DP Total | [5 empty] | 292266 | 135507 | [7 empty] | 427773
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -95.7 | 95.7 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -95.7 | 95.7 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -95.7 | 95.7 |  |  | 0
| Material - Inventory | Material | Material - Inventory |  |  |  |  | 68752.5 |  | 142414.59 | 786.96 | -10.05 | 10.05 |  |  | 211954.05
|  | Material Total | [5 empty] | 68752.5 |  | 142414.59 | 786.96 | -10.05 | 10.05 |  |  | 211954.05
| Material - Inventory Total | [6 empty] | 68752.5 |  | 142414.59 | 786.96 | -10.05 | 10.05 |  |  | 211954.05
| Material - Other | Material | Material - Other | 0.06 | 0.02 | 3346.3 | 68413.36 | 17871.16 | 12933.32 | 35029.16 | 7246.49 | 907.67 | 1797.3 | 339.15 | 1117.4 | 149001.39
|  | Material Total |  | 0.06 | 0.02 | 3346.3 | 68413.36 | 17871.16 | 12933.32 | 35029.16 | 7246.49 | 907.67 | 1797.3 | 339.15 | 1117.4 | 149001.39
| Material - Other Total |  |  | 0.06 | 0.02 | 3346.3 | 68413.36 | 17871.16 | 12933.32 | 35029.16 | 7246.49 | 907.67 | 1797.3 | 339.15 | 1117.4 | 149001.39
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 2052.44 | 50 |  | 98.22 |  |  | 2200.66
|  | Material - Direct Purchase Total | [7 empty] | 2052.44 | 50 |  | 98.22 |  |  | 2200.66
| Metals & Fabricated Metal Products-DP Total | [8 empty] | 2052.44 | 50 |  | 98.22 |  |  | 2200.66
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 5.38 | [5 empty] | 5.38
|  | Material - Direct Purchase Total | [7 empty] | 5.38 | [5 empty] | 5.38
| Monitor Equipment, Gauges and Hoses-DP Total | [8 empty] | 5.38 | [5 empty] | 5.38
| Office & Office Support Products-DP | Material - Direct Purchase | Office & Office Support Products-DP | [6 empty] | 19783.06 | [5 empty] | 19783.06
|  | Material - Direct Purchase Total | [7 empty] | 19783.06 | [5 empty] | 19783.06
| Office & Office Support Products-DP Total | [8 empty] | 19783.06 | [5 empty] | 19783.06
| Other Consumables-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 349.65 | [5 empty] | 349.65
|  | Material - Direct Purchase Total | [7 empty] | 349.65 | [5 empty] | 349.65
| Other Consumables-DP Total | [8 empty] | 349.65 | [5 empty] | 349.65
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 1799.96 | 585.49 |  |  |  |  | 2385.45
|  | Material - Direct Purchase Total | [7 empty] | 1799.96 | 585.49 |  |  |  |  | 2385.45
| Pipe/Tubing, Fittings and Gaskets-DP Total | [8 empty] | 1799.96 | 585.49 |  |  |  |  | 2385.45
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 936.02 | 5544.07 |  |  |  |  | 6480.09
|  | Material - Direct Purchase Total | [7 empty] | 936.02 | 5544.07 |  |  |  |  | 6480.09
| Pole Line Hdwe & Connectors-DP Total | [8 empty] | 936.02 | 5544.07 |  |  |  |  | 6480.09
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO |  |  | 30647.4 | 560834.96 | [8 empty] | 591482.36
|  |  | Material Entries <$5,000 | [6 empty] | 970.95 | 393 | 57.6 |  |  |  | 1421.55
|  |  | PARCELL STEEL CO | [5 empty] | 31094.7 | [6 empty] | 31094.7
|  |  | WASHINGTON ORNAMENTAL |  |  |  | 22412.1 | [8 empty] | 22412.1
|  | Material - Direct Purchase Total |  |  |  | 30647.4 | 583247.06 |  | 31094.7 | 970.95 | 393 | 57.6 |  |  |  | 646410.71
| Steel / Fabricated / Structural-DP Total |  |  |  |  | 30647.4 | 583247.06 |  | 31094.7 | 970.95 | 393 | 57.6 |  |  |  | 646410.71
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 9494.23 | 1944.77 | 279.86 |  | 1162.81 | 766.08 | 241.43 |  | 102.74 | 13991.92
|  |  | Transportation & Mobile Equip-DP |  |  |  |  | 5609.6 | [7 empty] | 5609.6
|  | Material - Direct Purchase Total |  |  |  |  | 9494.23 | 7554.37 | 279.86 |  | 1162.81 | 766.08 | 241.43 |  | 102.74 | 19601.52
| Transportation & Mobile Equip-DP Total | [5 empty] | 9494.23 | 7554.37 | 279.86 |  | 1162.81 | 766.08 | 241.43 |  | 102.74 | 19601.52
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 424.82 | 424.82
|  | Material - Direct Purchase Total | [12 empty] | 424.82 | 424.82
| Wire, Cable & Bus Bar-DP Total | [13 empty] | 424.82 | 424.82
2. Material Total |  |  |  | 0.06 | 0.02 | 46058.09 | 956530.8 | 245021.2 | 44334.62 | 229043.09 | 23505.81 | 2012.95 | 1758400.7 | 6544.9 | 26710.61 | 3338162.85
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  | 1696.2 | 4901.04 | 2600 | 2340 | 10170.5 | 28412 | 3171.16 | 2760 | 17734.12 | 121576.44 | 75989.07 | 271350.53
|  | Contract Total |  |  | 1696.2 | 4901.04 | 2600 | 2340 | 10170.5 | 28412 | 3171.16 | 2760 | 17734.12 | 121576.44 | 75989.07 | 271350.53
| Construction Management Services Total |  |  |  | 1696.2 | 4901.04 | 2600 | 2340 | 10170.5 | 28412 | 3171.16 | 2760 | 17734.12 | 121576.44 | 75989.07 | 271350.53
| Construction Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -4002.9 | 4002.9 |  |  | 0
|  | Contract Total | [9 empty] | -4002.9 | 4002.9 |  |  | 0
| Construction Services - Correction Total | [10 empty] | -4002.9 | 4002.9 |  |  | 0
| Construction Services - Other | Contract | Contract Entries <$50,000 | [5 empty] | 1529.06 |  | 3600 | 2000 | 1600 | 1600 | 2000 | 12329.06
|  | Contract Total | [6 empty] | 1529.06 |  | 3600 | 2000 | 1600 | 1600 | 2000 | 12329.06
| Construction Services - Other Total | [7 empty] | 1529.06 |  | 3600 | 2000 | 1600 | 1600 | 2000 | 12329.06
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [5 empty] | 3437.18 | 3412.89 | 2582.55 | 494.15 | 7275.57 |  | 2231.35 | 19433.69
|  | Contract Total | [6 empty] | 3437.18 | 3412.89 | 2582.55 | 494.15 | 7275.57 |  | 2231.35 | 19433.69
| Construction, Civil/Structural Total | [7 empty] | 3437.18 | 3412.89 | 2582.55 | 494.15 | 7275.57 |  | 2231.35 | 19433.69
| Construction, Property/Building | Contract | Contract Entries <$50,000 | [11 empty] | 701.14 | 701.14
|  | Contract Total | [12 empty] | 701.14 | 701.14
| Construction, Property/Building Total | [13 empty] | 701.14 | 701.14
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 | [5 empty] | 2633 | [6 empty] | 2633
|  | Contract Total | [6 empty] | 2633 | [6 empty] | 2633
| Decontamination & Waste Disposal Service Total | [7 empty] | 2633 | [6 empty] | 2633
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 333.71 | 333.71
|  | Labor Total | [12 empty] | 333.71 | 333.71
| ELEC SYS PLANNING Total | [13 empty] | 333.71 | 333.71
| ENGINEERING | Labor | Labor Entries <$5,000 | 338.81 | 135.24 | 321.75 | 167.72 | 667.48 | 166.69 | 333.74 | 166.87 |  |  |  |  | 2298.3
|  | Labor Total |  | 338.81 | 135.24 | 321.75 | 167.72 | 667.48 | 166.69 | 333.74 | 166.87 |  |  |  |  | 2298.3
| ENGINEERING Total |  |  | 338.81 | 135.24 | 321.75 | 167.72 | 667.48 | 166.69 | 333.74 | 166.87 |  |  |  |  | 2298.3
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 2291.62 | 2291.62
|  | Labor Total | [12 empty] | 2291.62 | 2291.62
| GRID OPS Total | [13 empty] | 2291.62 | 2291.62
| Major Construction, Generation/Nuclear | Contract | SIEMENS ENERGY, INC. | [8 empty] | 1876099 |  |  | 1042119 | 2918218
|  | Contract Total | [9 empty] | 1876099 |  |  | 1042119 | 2918218
| Major Construction, Generation/Nuclear Total | [10 empty] | 1876099 |  |  | 1042119 | 2918218
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [8 empty] | 7652 | 43939 |  | 20876.57 | 72467.57
|  |  | PROFESSIONAL ELECTRICAL CONSTRUCTIO | [7 empty] | 923624 | 339211 |  |  |  | 1262835
|  | Contract Total | [8 empty] | 923624 | 346863 | 43939 |  | 20876.57 | 1335302.57
| Major Construction, Turnkey, Trans/Subs Total | [9 empty] | 923624 | 346863 | 43939 |  | 20876.57 | 1335302.57
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [5 empty] | 7631.36 |  | 2509.22 |  |  |  |  | 10140.58
|  | Labor Total | [6 empty] | 7631.36 |  | 2509.22 |  |  |  |  | 10140.58
| S/E SUBS MTCETST&APP Total | [7 empty] | 7631.36 |  | 2509.22 |  |  |  |  | 10140.58
| SC&M | Labor | Labor Entries <$5,000 | 435.96 | 864.74 | 351.05 | 175.48 | 569.54 | 1219.81 | 2134.99 | 2535.12 | 643.77 | 428.96 |  | 436.44 | 9795.86
|  | Labor Total |  | 435.96 | 864.74 | 351.05 | 175.48 | 569.54 | 1219.81 | 2134.99 | 2535.12 | 643.77 | 428.96 |  | 436.44 | 9795.86
| SC&M Total |  |  | 435.96 | 864.74 | 351.05 | 175.48 | 569.54 | 1219.81 | 2134.99 | 2535.12 | 643.77 | 428.96 |  | 436.44 | 9795.86
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  |  | 205.88 |  | 124.24 | [6 empty] | 330.12
|  | Labor Total |  |  |  |  | 205.88 |  | 124.24 | [6 empty] | 330.12
| SCM HOME CENTER Total | [5 empty] | 205.88 |  | 124.24 | [6 empty] | 330.12
| Security / Protection Services | Contract | ASHLAND INTEGRATED INC | [11 empty] | 152661.63 | 152661.63
|  |  | Contract Entries <$50,000 | [5 empty] | 17990.92 | 30109.42 | 18380.17 | 30452.74 | 14866.2 | 19130.52 | 39885.27 | 170815.24
|  | Contract Total | [6 empty] | 17990.92 | 30109.42 | 18380.17 | 30452.74 | 14866.2 | 19130.52 | 192546.9 | 323476.87
| Security / Protection Services Total | [7 empty] | 17990.92 | 30109.42 | 18380.17 | 30452.74 | 14866.2 | 19130.52 | 192546.9 | 323476.87
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [6 empty] | 7572.67 | 5951.63 | 3784.85 | 3369.35 | 3369.35 | 3611.79 | 27659.64
|  | Contract Total | [7 empty] | 7572.67 | 5951.63 | 3784.85 | 3369.35 | 3369.35 | 3611.79 | 27659.64
| Short Term Equipment Rent Total | [8 empty] | 7572.67 | 5951.63 | 3784.85 | 3369.35 | 3369.35 | 3611.79 | 27659.64
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | [6 empty] | 82 | [5 empty] | 82
|  | Labor Total | [7 empty] | 82 | [5 empty] | 82
| TSD-HERC - Rental Total | [8 empty] | 82 | [5 empty] | 82
3. Construction Total |  |  |  | 774.77 | 2696.18 | 5573.84 | 3149.08 | 3577.02 | 44902.76 | 72057.71 | 962520.72 | 2259094.61 | 93216.1 | 145676.31 | 1343137.59 | 4936376.69
4. Allocated | Chargebacks | Chargeback | Cal Capacitor Substation û ISAS Install | [11 empty] | 354983.48 | 354983.48
|  |  | Chargeback Entries <$5,000 | 11662.43 | 13399 | -53093.27 | 13572.29 | -8836.56 | 21963.88 | 3340.94 | 10824.15 | -58284.95 | 22625.06 | 376225.15 | -355612.86 | -2214.74
|  |  | MATERIAL MANAGEM |  |  |  |  | 13365.49 |  | 26631.53 | [5 empty] | 39997.02
|  |  | PDP-DPV2 General Mtg Support-MPO |  | 93621.05 |  | 18577.81 | 5308.6 | 8215.88 | 12092.81 | 18683.66 |  | 14096.13 | 11225.17 | 6371.9 | 188193.01
|  |  | PDP-Series Capacitor-MPO |  |  | 28288.5 |  | 10118.46 | 51267.61 | 84290 | 6030.66 |  | 89162.2 | 60283.73 | 58750.68 | 388191.84
|  |  | PROCUREMENT TDBU |  |  |  | 5947.92 |  |  |  | 6661.62 | 14354.53 | 13201.57 |  | 9528.72 | 49694.36
|  | Chargeback Total |  | 11662.43 | 107020.05 | -24804.77 | 38098.02 | 19955.99 | 81447.37 | 126355.28 | 42200.09 | -43930.42 | 139084.96 | 447734.05 | 74021.92 | 1018844.97
| Chargebacks Total |  |  | 11662.43 | 107020.05 | -24804.77 | 38098.02 | 19955.99 | 81447.37 | 126355.28 | 42200.09 | -43930.42 | 139084.96 | 447734.05 | 74021.92 | 1018844.97
| Labor - Other | Labor | Division Overhead |  |  |  | 63368.34 | 6713.45 |  | 9232.79 | 75304.75 | 141906.04 | 163319.87 |  | 50092.24 | 509937.48
|  |  | Labor Entries <$5,000 | 11740.56 | 7005.22 | 8586.35 | 6398.07 | 12309.23 | 11528.71 | 17248.45 | 7295.35 | -554.08 | 4460.14 | 7461.88 | 9072.3 | 102552.18
|  |  | Paid Absence | [9 empty] | 6419.99 |  |  | 6419.99
|  | Labor Total |  | 11740.56 | 7005.22 | 8586.35 | 69766.41 | 19022.68 | 11528.71 | 26481.24 | 82600.1 | 141351.96 | 174200 | 7461.88 | 59164.54 | 618909.65
| Labor - Other Total |  |  | 11740.56 | 7005.22 | 8586.35 | 69766.41 | 19022.68 | 11528.71 | 26481.24 | 82600.1 | 141351.96 | 174200 | 7461.88 | 59164.54 | 618909.65
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -2786.6 | 2786.6 |  |  | 0
|  | Overhead Total | [9 empty] | -2786.6 | 2786.6 |  |  | 0
| Overhead Correction Total | [10 empty] | -2786.6 | 2786.6 |  |  | 0
4. Allocated Total |  |  |  | 23402.99 | 114025.27 | -16218.42 | 107864.43 | 38978.67 | 92976.08 | 152836.52 | 124800.19 | 94634.94 | 316071.56 | 455195.93 | 133186.46 | 1637754.62
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 16410.88 | 1122.77 | [6 empty] | 73843.37 | 91377.02
|  |  | Capitalized Overhead - A&G | 8335.8 | 5102.63 | 2624.28 | 38955.98 | 25974.89 | 8249.95 | 17455.95 | 33164.29 | 109835.36 | 55868.09 | 16710.85 | 45000.52 | 367278.59
|  |  | Capitalized Overhead - Inj & Damages | 32.16 | 215.85 | 38.54 | 881.96 | 2474.69 | 183.2 | 328.94 | 218 | 251.33 | 5729.95 | 671.09 | -207.54 | 10818.17
|  |  | Capitalized Overhead - P&B/Payroll Tax | 7434.02 | 17717.25 | 12646.33 | 12469.7 | 21304.34 | 28194.3 | 21531.98 | 21953.82 | -3410.99 | 20426.33 | 14373.62 | 60796.18 | 235436.88
|  | Non Budgeted Total |  | 15801.98 | 23035.73 | 15309.15 | 68718.52 | 50876.69 | 36627.45 | 39316.87 | 55336.11 | 106675.7 | 82024.37 | 31755.56 | 179432.53 | 704910.66
| Non Budget - Other Total |  |  | 15801.98 | 23035.73 | 15309.15 | 68718.52 | 50876.69 | 36627.45 | 39316.87 | 55336.11 | 106675.7 | 82024.37 | 31755.56 | 179432.53 | 704910.66
5. Corporate Overhead Total |  |  |  | 15801.98 | 23035.73 | 15309.15 | 68718.52 | 50876.69 | 36627.45 | 39316.87 | 55336.11 | 106675.7 | 82024.37 | 31755.56 | 179432.53 | 704910.66
Grand Total |  |  |  | 164513.54 | 197209.69 | 90309.99 | 1160744.14 | 361971.08 | 280518.42 | 527788.43 | 1224042.11 | 2558136.03 | 2244369.87 | 664089.77 | 1815928.73 | 11289621.8

## 800062902
Pin: 4847 | Project: DCR
Order: 800062902 | 800062902- I: Valley: Equip line position 8X with t
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  |  | 10.92 |  | 163.31 | [5 empty] | 174.23
|  | Labor Total | [5 empty] | 10.92 |  | 163.31 | [5 empty] | 174.23
| BP&FM Total | [6 empty] | 10.92 |  | 163.31 | [5 empty] | 174.23
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -13793.1 | 13793.1 |  |  | 0
|  | Contract Total | [9 empty] | -13793.1 | 13793.1 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -13793.1 | 13793.1 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 210.59 | 210.59
|  | Labor Total | [12 empty] | 210.59 | 210.59
| ELEC SYS PLANNING Total | [13 empty] | 210.59 | 210.59
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 459.26 | 24.27 |  |  | 77.56 |  | 39.68 |  |  |  |  | 600.77
|  | Labor Total |  |  | 459.26 | 24.27 |  |  | 77.56 |  | 39.68 |  |  |  |  | 600.77
| ENG ADVANCEMENT Total |  |  |  | 459.26 | 24.27 |  |  | 77.56 |  | 39.68 |  |  |  |  | 600.77
| ENGINEERING | Labor | Labor Entries <$5,000 | 1981.51 | 5525.05 | 4472.93 | 5925.95 | 3494.91 | 6294.29 | 2400.31 | 4233.24 | 1283.33 | 2499.92 | 3640.24 | 2115.84 | 43867.52
|  | Labor Total |  | 1981.51 | 5525.05 | 4472.93 | 5925.95 | 3494.91 | 6294.29 | 2400.31 | 4233.24 | 1283.33 | 2499.92 | 3640.24 | 2115.84 | 43867.52
| ENGINEERING Total |  |  | 1981.51 | 5525.05 | 4472.93 | 5925.95 | 3494.91 | 6294.29 | 2400.31 | 4233.24 | 1283.33 | 2499.92 | 3640.24 | 2115.84 | 43867.52
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 10000 | 30728 | 15252 | 12960 | 569 | 9000 |  | 30738 | 1073 | 2096 |  |  | 112416
|  | Contract Total |  | 10000 | 30728 | 15252 | 12960 | 569 | 9000 |  | 30738 | 1073 | 2096 |  |  | 112416
| Engineering/Technical Professional Servi Total |  |  | 10000 | 30728 | 15252 | 12960 | 569 | 9000 |  | 30738 | 1073 | 2096 |  |  | 112416
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | [6 empty] | 11350.14 | 3083.25 | 4307.21 | 2821.03 | 2602.95 | 1951.57 | 26116.15
|  | Contract Total | [7 empty] | 11350.14 | 3083.25 | 4307.21 | 2821.03 | 2602.95 | 1951.57 | 26116.15
| Environmental/Safety Professional Servic Total | [8 empty] | 11350.14 | 3083.25 | 4307.21 | 2821.03 | 2602.95 | 1951.57 | 26116.15
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 1048.4 | 966.7 | 810.99 | -12.82 | -2318.25 | 709.56 | -6681.96 | 243.13 | 207149.51 | -210368.71 | -686.84 | -808.33 | -9948.62
|  | IMM Correction Total |  | 1048.4 | 966.7 | 810.99 | -12.82 | -2318.25 | 709.56 | -6681.96 | 243.13 | 207149.51 | -210368.71 | -686.84 | -808.33 | -9948.62
| IMM/Allocated - Correction Total |  |  | 1048.4 | 966.7 | 810.99 | -12.82 | -2318.25 | 709.56 | -6681.96 | 243.13 | 207149.51 | -210368.71 | -686.84 | -808.33 | -9948.62
| Labor - Other | Labor | Labor Correction | [9 empty] | 7600.62 |  |  | 7600.62
|  |  | Labor Entries <$5,000 | 21.86 | 1350.51 | -1208.7 | 94.88 | 1092.18 | -1381.84 | -36.39 | 897.69 | -4464.7 | 218.69 | -4267.22 | 975.97 | -6707.07
|  | Labor Total |  | 21.86 | 1350.51 | -1208.7 | 94.88 | 1092.18 | -1381.84 | -36.39 | 897.69 | -4464.7 | 7819.31 | -4267.22 | 975.97 | 893.55
| Labor - Other Total |  |  | 21.86 | 1350.51 | -1208.7 | 94.88 | 1092.18 | -1381.84 | -36.39 | 897.69 | -4464.7 | 7819.31 | -4267.22 | 975.97 | 893.55
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 |  | 92.46 |  |  |  | 92.67 |  | 431.91 | 494.07 | 246.66 | 528.8 |  | 1886.57
|  | Labor Total |  |  | 92.46 |  |  |  | 92.67 |  | 431.91 | 494.07 | 246.66 | 528.8 |  | 1886.57
| MAJOR PROJECT ORG Total |  |  |  | 92.46 |  |  |  | 92.67 |  | 431.91 | 494.07 | 246.66 | 528.8 |  | 1886.57
| Other | Other | Other | -520 | 3725 | 519734.16 | -523357.59 | 1603.15 | 10249.42 | -7431.59 | 107389.07 | -284257.66 | 251812.69 | -59576.08 | 6291.88 | 25662.45
|  | Other Total |  | -520 | 3725 | 519734.16 | -523357.59 | 1603.15 | 10249.42 | -7431.59 | 107389.07 | -284257.66 | 251812.69 | -59576.08 | 6291.88 | 25662.45
| Other Total |  |  | -520 | 3725 | 519734.16 | -523357.59 | 1603.15 | 10249.42 | -7431.59 | 107389.07 | -284257.66 | 251812.69 | -59576.08 | 6291.88 | 25662.45
| SC&M | Labor | Labor Entries <$5,000 |  |  |  | 347.79 | 1074.11 | 1435.31 |  | 1048.73 | 1543.02 | 452.56 | 838.07 | 554.74 | 7294.33
|  | Labor Total |  |  |  |  | 347.79 | 1074.11 | 1435.31 |  | 1048.73 | 1543.02 | 452.56 | 838.07 | 554.74 | 7294.33
| SC&M Total | [5 empty] | 347.79 | 1074.11 | 1435.31 |  | 1048.73 | 1543.02 | 452.56 | 838.07 | 554.74 | 7294.33
| SOUTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [10 empty] | 67.16 |  | 67.16
|  | Labor Total | [11 empty] | 67.16 |  | 67.16
| SOUTH GRIDMGMTCENTER Total | [12 empty] | 67.16 |  | 67.16
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 | [10 empty] | 416.11 |  | 416.11
|  | Labor Total | [11 empty] | 416.11 |  | 416.11
| TEC SRVCS SUMMARY Total | [12 empty] | 416.11 |  | 416.11
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -2609.21 | 2609.21 |  |  | 0
|  | Contract Total | [9 empty] | -2609.21 | 2609.21 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -2609.21 | 2609.21 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1347.02 | 682.83 | 884.69 | 2762.3 | 476.56 | 2485.07 | 253 | 1138.5 | 674.98 | 363.44 | 567.46 | 440.96 | 12076.81
|  | Contract Total |  | 1347.02 | 682.83 | 884.69 | 2762.3 | 476.56 | 2485.07 | 253 | 1138.5 | 674.98 | 363.44 | 567.46 | 440.96 | 12076.81
| Temporary/Supplementary - Trade/Labor Total |  |  | 1347.02 | 682.83 | 884.69 | 2762.3 | 476.56 | 2485.07 | 253 | 1138.5 | 674.98 | 363.44 | 567.46 | 440.96 | 12076.81
1. Project Support Total |  |  |  | 13878.79 | 43529.81 | 539970.34 | -501279.49 | 6002.58 | 28962.04 | 16.82 | 149243.2 | -88599.55 | 74145.21 | -55869.35 | 11733.22 | 221733.62
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 32.16 |  | 32.12 |  |  | 64.28
|  |  | MITSUBISHI ELECTRIC | [5 empty] | 954988 | [6 empty] | 954988
|  | Material - Direct Purchase Total | [6 empty] | 954988 |  | 32.16 |  | 32.12 |  |  | 955052.28
| Breakers - Circuit-DP Total | [7 empty] | 954988 |  | 32.16 |  | 32.12 |  |  | 955052.28
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 2069.08 | 923.04 |  | 1280.73 | 428.84 | 278.59 | 377.67 |  | 5357.95
|  | Material - Direct Purchase Total | [5 empty] | 2069.08 | 923.04 |  | 1280.73 | 428.84 | 278.59 | 377.67 |  | 5357.95
| Building, Shop & Industrial Products/Eqp Total | [6 empty] | 2069.08 | 923.04 |  | 1280.73 | 428.84 | 278.59 | 377.67 |  | 5357.95
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 879.59 |  | 133.28 |  |  | 1012.87
|  | Material - Direct Purchase Total | [8 empty] | 879.59 |  | 133.28 |  |  | 1012.87
| Cabinets, Panels and Switchboards-DP Total | [9 empty] | 879.59 |  | 133.28 |  |  | 1012.87
| Capacitors and Regulators-DP | Material - Direct Purchase | HAEFELY TRENCH LIMITED |  |  | 77475 | [9 empty] | 77475
|  | Material - Direct Purchase Total |  |  |  | 77475 | [9 empty] | 77475
| Capacitors and Regulators-DP Total |  |  |  |  | 77475 | [9 empty] | 77475
| Communication Systems and Equipment -DP | Material - Direct Purchase | DAQ ELECTRONICS INC |  |  | 49710 | [9 empty] | 49710
|  |  | Material Entries <$5,000 | [5 empty] | 3390 |  |  | 700 |  |  |  | 4090
|  | Material - Direct Purchase Total |  |  |  | 49710 |  |  | 3390 |  |  | 700 |  |  |  | 53800
| Communication Systems and Equipment -DP Total |  |  |  |  | 49710 |  |  | 3390 |  |  | 700 |  |  |  | 53800
| Electric Wiring and Components-DP | Material - Direct Purchase | ANIXTER INC | [9 empty] | 47034 |  |  | 47034
|  |  | Electric Wiring and Components-DP | [9 empty] | 12873.06 |  | 6831 | 19704.06
|  |  | Material Entries <$5,000 | [5 empty] | 7071.26 | 8770.28 | 4475.64 |  |  | 7409.83 |  | 27727.01
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [8 empty] | 6813.5 |  |  |  | 6813.5
|  |  | QUALITROL COMPANY LLC | [8 empty] | 76728 |  |  |  | 76728
|  |  | RFL ELECTRONICS INC | [6 empty] | 19880 | [5 empty] | 19880
|  |  | SOUTHWIRE COMPANY | [7 empty] | 9533 |  |  |  |  | 9533
|  | Material - Direct Purchase Total | [6 empty] | 7071.26 | 28650.28 | 14008.64 | 83541.5 | 59907.06 | 7409.83 | 6831 | 207419.57
| Electric Wiring and Components-DP Total | [7 empty] | 7071.26 | 28650.28 | 14008.64 | 83541.5 | 59907.06 | 7409.83 | 6831 | 207419.57
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 159.78 |  |  | 159.78
|  | Material - Direct Purchase Total | [10 empty] | 159.78 |  |  | 159.78
| Fuels, Chemicals & Petrochem-DP Total | [11 empty] | 159.78 |  |  | 159.78
| Line Switches & Switchgear-DP | Material - Direct Purchase | SOUTHERN STATES LLC |  |  |  | 481080 | [8 empty] | 481080
|  | Material - Direct Purchase Total |  |  |  |  | 481080 | [8 empty] | 481080
| Line Switches & Switchgear-DP Total | [5 empty] | 481080 | [8 empty] | 481080
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -26.12 | 26.12 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -26.12 | 26.12 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -26.12 | 26.12 |  |  | 0
| Material - Inventory | Material | Material - Inventory |  |  |  |  | 22428.7 |  | 1416.99 | 346920.3 | -3.02 | -4485.83 | 122537.19 |  | 488814.33
|  | Material Total | [5 empty] | 22428.7 |  | 1416.99 | 346920.3 | -3.02 | -4485.83 | 122537.19 |  | 488814.33
| Material - Inventory Total | [6 empty] | 22428.7 |  | 1416.99 | 346920.3 | -3.02 | -4485.83 | 122537.19 |  | 488814.33
| Material - Other | Material | Material - Other | 0.02 | 289.46 | 9975.09 | 37460.81 | 4877.4 | 90815.69 | 6120.05 | 40377.91 | 14099.41 | 8925.96 | 14915.7 | 1024.01 | 228881.51
|  | Material Total |  | 0.02 | 289.46 | 9975.09 | 37460.81 | 4877.4 | 90815.69 | 6120.05 | 40377.91 | 14099.41 | 8925.96 | 14915.7 | 1024.01 | 228881.51
| Material - Other Total |  |  | 0.02 | 289.46 | 9975.09 | 37460.81 | 4877.4 | 90815.69 | 6120.05 | 40377.91 | 14099.41 | 8925.96 | 14915.7 | 1024.01 | 228881.51
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 4720.39 | 12.5 | 195.5 | 450 |  | 5378.39
|  | Material - Direct Purchase Total | [8 empty] | 4720.39 | 12.5 | 195.5 | 450 |  | 5378.39
| Metals & Fabricated Metal Products-DP Total | [9 empty] | 4720.39 | 12.5 | 195.5 | 450 |  | 5378.39
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | QUALITROL COMPANY LLC | [6 empty] | 14528 | [5 empty] | 14528
|  | Material - Direct Purchase Total | [7 empty] | 14528 | [5 empty] | 14528
| Meters, Monitor and Warnings-DP Total | [8 empty] | 14528 | [5 empty] | 14528
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 10.77 |  |  |  |  | 10.77
|  | Material - Direct Purchase Total | [8 empty] | 10.77 |  |  |  |  | 10.77
| Monitor Equipment, Gauges and Hoses-DP Total | [9 empty] | 10.77 |  |  |  |  | 10.77
| Other Consumables-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 51.72 | 68.14 |  | 119.86
|  | Material - Direct Purchase Total | [10 empty] | 51.72 | 68.14 |  | 119.86
| Other Consumables-DP Total | [11 empty] | 51.72 | 68.14 |  | 119.86
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 32.16 |  | 614.36 | 31.7 |  | 678.22
|  | Material - Direct Purchase Total | [8 empty] | 32.16 |  | 614.36 | 31.7 |  | 678.22
| Pipe/Tubing, Fittings and Gaskets-DP Total | [9 empty] | 32.16 |  | 614.36 | 31.7 |  | 678.22
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 516.89 | 2198.89 | 3638.13 | 902.62 | 7256.53
|  |  | Pole Line Hdwe & Connectors-DP | [7 empty] | 40274.81 |  |  |  |  | 40274.81
|  | Material - Direct Purchase Total | [8 empty] | 40274.81 | 516.89 | 2198.89 | 3638.13 | 902.62 | 47531.34
| Pole Line Hdwe & Connectors-DP Total | [9 empty] | 40274.81 | 516.89 | 2198.89 | 3638.13 | 902.62 | 47531.34
| Protection and Test-DP | Material - Direct Purchase | GE CONSUMER AND INDUSTRIAL | [5 empty] | 34078.11 | [6 empty] | 34078.11
|  |  | Material Entries <$5,000 | [10 empty] | 412.34 |  | 412.34
|  |  | Protection and Test-DP | [7 empty] | 51143.91 |  |  |  |  | 51143.91
|  |  | SCHWEITZER ENGINEERING LABS INC | [5 empty] | 10620 | [6 empty] | 10620
|  | Material - Direct Purchase Total | [6 empty] | 44698.11 |  | 51143.91 |  |  | 412.34 |  | 96254.36
| Protection and Test-DP Total | [7 empty] | 44698.11 |  | 51143.91 |  |  | 412.34 |  | 96254.36
| Reactors and Line Traps-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 3650 | [10 empty] | 3650
|  | Material - Direct Purchase Total |  |  | 3650 | [10 empty] | 3650
| Reactors and Line Traps-DP Total |  |  |  | 3650 | [10 empty] | 3650
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 2498.88 |  | 2324 | 4822.88
|  |  | PARCELL STEEL CO | [5 empty] | 17613.84 | [6 empty] | 17613.84
|  |  | WASHINGTON ORNAMENTAL |  |  |  |  | 37769.2 | 89217.21 | [6 empty] | 126986.41
|  | Material - Direct Purchase Total | [5 empty] | 37769.2 | 106831.05 |  |  |  | 2498.88 |  | 2324 | 149423.13
| Steel / Fabricated / Structural-DP Total | [6 empty] | 37769.2 | 106831.05 |  |  |  | 2498.88 |  | 2324 | 149423.13
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 2840.75 |  |  |  |  | 2840.75
|  | Material - Direct Purchase Total | [8 empty] | 2840.75 |  |  |  |  | 2840.75
| Transformers CT/PT/INSTR-DP Total | [9 empty] | 2840.75 |  |  |  |  | 2840.75
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 2783.37 | 4840.73 | 3678.6 | 311.38 | 185.98 |  | 4583.8 | 63.63 | 1160.66 | 1430.44 | 19038.59
|  |  | Transportation & Mobile Equip-DP |  |  | 11090.74 | 5893.92 | [8 empty] | 16984.66
|  | Material - Direct Purchase Total |  |  |  | 13874.11 | 10734.65 | 3678.6 | 311.38 | 185.98 |  | 4583.8 | 63.63 | 1160.66 | 1430.44 | 36023.25
| Transportation & Mobile Equip-DP Total |  |  |  |  | 13874.11 | 10734.65 | 3678.6 | 311.38 | 185.98 |  | 4583.8 | 63.63 | 1160.66 | 1430.44 | 36023.25
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 4632 |  |  |  | 4632
|  |  | Wire, Cable & Bus Bar-DP | [7 empty] | 40346.45 |  |  |  |  | 40346.45
|  | Material - Direct Purchase Total | [8 empty] | 40346.45 | 4632 |  |  |  | 44978.45
| Wire, Cable & Bus Bar-DP Total | [9 empty] | 40346.45 | 4632 |  |  |  | 44978.45
2. Material Total |  |  |  | 0.02 | 3939.46 | 151034.2 | 529275.46 | 70822.98 | 1209028.53 | 50901.3 | 542868.57 | 108485.8 | 70600.06 | 151001.36 | 12512.07 | 2900469.81
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  | 910 | 3595 | 2561.04 | 2210 | 3455.1 | 15253.7 | 32413.5 | 3440 | 10419.28 | 71080.2 | 94475.04 | 239812.86
|  | Contract Total |  |  | 910 | 3595 | 2561.04 | 2210 | 3455.1 | 15253.7 | 32413.5 | 3440 | 10419.28 | 71080.2 | 94475.04 | 239812.86
| Construction Management Services Total |  |  |  | 910 | 3595 | 2561.04 | 2210 | 3455.1 | 15253.7 | 32413.5 | 3440 | 10419.28 | 71080.2 | 94475.04 | 239812.86
| Construction Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -2084.81 | 2084.81 |  |  | 0
|  | Contract Total | [9 empty] | -2084.81 | 2084.81 |  |  | 0
| Construction Services - Correction Total | [10 empty] | -2084.81 | 2084.81 |  |  | 0
| Construction Services - Other | Contract | Contract Entries <$50,000 | [8 empty] | 499.29 |  |  |  | 499.29
|  | Contract Total | [9 empty] | 499.29 |  |  |  | 499.29
| Construction Services - Other Total | [10 empty] | 499.29 |  |  |  | 499.29
| ENGINEERING | Labor | Labor Entries <$5,000 | 169.41 | 405.71 |  |  | 500.61 | 495.87 | 500.61 | [5 empty] | 2072.21
|  | Labor Total |  | 169.41 | 405.71 |  |  | 500.61 | 495.87 | 500.61 | [5 empty] | 2072.21
| ENGINEERING Total |  |  | 169.41 | 405.71 |  |  | 500.61 | 495.87 | 500.61 | [5 empty] | 2072.21
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 100.13 | 100.13
|  | Labor Total | [12 empty] | 100.13 | 100.13
| GRID OPS Total | [13 empty] | 100.13 | 100.13
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | [6 empty] | 1397 |  |  | 1397 |  |  | 2794
|  | Contract Total | [7 empty] | 1397 |  |  | 1397 |  |  | 2794
| Hauling / Industrial Moving Services Total | [8 empty] | 1397 |  |  | 1397 |  |  | 2794
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [10 empty] | 32817 | 6714 | 39531
|  |  | SUBSTATION SPECIALISTS | [8 empty] | 379000 |  |  |  | 379000
|  |  | V MAX ELECTRIC INC | [11 empty] | 632000 | 632000
|  | Contract Total | [9 empty] | 379000 |  | 32817 | 638714 | 1050531
| Major Construction, Turnkey, Trans/Subs Total | [10 empty] | 379000 |  | 32817 | 638714 | 1050531
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [6 empty] | 2665.47 | 12918.96 | 12712.72 | 17037.03 | 25682.64 | 520.64 | 71537.46
|  |  | Supervisor | [7 empty] | 6456.56 |  |  |  |  | 6456.56
|  | Labor Total | [7 empty] | 2665.47 | 19375.52 | 12712.72 | 17037.03 | 25682.64 | 520.64 | 77994.02
| S/E SUBS MTCETST&APP Total | [8 empty] | 2665.47 | 19375.52 | 12712.72 | 17037.03 | 25682.64 | 520.64 | 77994.02
| SC&M | Labor | Labor Entries <$5,000 |  |  | 109.7 |  | 1684.45 | 1257.45 | 479.11 | 6081.32 | 595.03 | 3649.05 | 7426.74 | 10744.22 | 32027.07
|  | Labor Total |  |  |  | 109.7 |  | 1684.45 | 1257.45 | 479.11 | 6081.32 | 595.03 | 3649.05 | 7426.74 | 10744.22 | 32027.07
| SC&M Total |  |  |  |  | 109.7 |  | 1684.45 | 1257.45 | 479.11 | 6081.32 | 595.03 | 3649.05 | 7426.74 | 10744.22 | 32027.07
| Security / Protection Services | Contract | Contract Entries <$50,000 | [7 empty] | 4947.9 | 1471.71 | 93.68 |  |  | 6513.29
|  | Contract Total | [8 empty] | 4947.9 | 1471.71 | 93.68 |  |  | 6513.29
| Security / Protection Services Total | [9 empty] | 4947.9 | 1471.71 | 93.68 |  |  | 6513.29
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [5 empty] | 669.3 | 604.03 | 604.03 | 1773.41 | 1838.68 | 1898.08 | 2365.68 | 9753.21
|  | Contract Total | [6 empty] | 669.3 | 604.03 | 604.03 | 1773.41 | 1838.68 | 1898.08 | 2365.68 | 9753.21
| Short Term Equipment Rent Total | [7 empty] | 669.3 | 604.03 | 604.03 | 1773.41 | 1838.68 | 1898.08 | 2365.68 | 9753.21
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | [6 empty] | 82 |  |  | 82 |  |  | 164
|  | Labor Total | [7 empty] | 82 |  |  | 82 |  |  | 164
| TSD-HERC - Crane Svs Total | [8 empty] | 82 |  |  | 82 |  |  | 164
3. Construction Total |  |  |  | 169.41 | 1315.71 | 3704.7 | 2561.04 | 4395.06 | 5877.72 | 20981.92 | 63422.27 | 397407.35 | 36601.53 | 138904.66 | 746919.71 | 1422261.08
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 4194.25 | 3311.33 | -15146.65 | 12818.38 | 8909.36 | 9884.89 | 11545.79 | 16832.57 | 6274.26 | 14941.19 | -8385.15 | -9098.03 | 56082.19
|  |  | MATERIAL MANAGEM | [7 empty] | 45273.1 |  |  | 20806.81 |  | 66079.91
|  |  | PDP-Devers Valley Sub (Xpan)-MPO |  |  | 147552.77 |  |  |  | 6771.05 | 7155.69 |  | 42434.73 | 35200.75 | 14406.59 | 253521.58
|  |  | PDP-DPV2 General Mtg Support-MPO |  | 28086.31 | [10 empty] | 28086.31
|  |  | PROCUREMENT TDBU | [5 empty] | 7493.42 | [6 empty] | 7493.42
|  | Chargeback Total |  | 4194.25 | 31397.64 | 132406.12 | 12818.38 | 8909.36 | 17378.31 | 18316.84 | 69261.36 | 6274.26 | 57375.92 | 47622.41 | 5308.56 | 411263.41
| Chargebacks Total |  |  | 4194.25 | 31397.64 | 132406.12 | 12818.38 | 8909.36 | 17378.31 | 18316.84 | 69261.36 | 6274.26 | 57375.92 | 47622.41 | 5308.56 | 411263.41
| Labor - Other | Labor | Division Overhead |  |  | 5306.46 | 35655.86 |  | 74751.12 |  | 39226.07 | 25305.62 |  |  | 13800.32 | 194045.45
|  |  | Labor Entries <$5,000 | 1603.83 | 4956.09 | 8036.24 | 4641.3 | 7325.48 | 2585.61 | 8054.83 | 8778.95 | 8312.27 | 14410.16 | 14482.32 | 18422.53 | 101609.61
|  |  | Paid Absence | [7 empty] | 5602.6 |  | 5817.35 |  |  | 11419.95
|  | Labor Total |  | 1603.83 | 4956.09 | 13342.7 | 40297.16 | 7325.48 | 77336.73 | 8054.83 | 53607.62 | 33617.89 | 20227.51 | 14482.32 | 32222.85 | 307075.01
| Labor - Other Total |  |  | 1603.83 | 4956.09 | 13342.7 | 40297.16 | 7325.48 | 77336.73 | 8054.83 | 53607.62 | 33617.89 | 20227.51 | 14482.32 | 32222.85 | 307075.01
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -788.82 | 788.82 |  |  | 0
|  | Overhead Total | [9 empty] | -788.82 | 788.82 |  |  | 0
| Overhead Correction Total | [10 empty] | -788.82 | 788.82 |  |  | 0
4. Allocated Total |  |  |  | 5798.08 | 36353.73 | 145748.82 | 53115.54 | 16234.84 | 94715.04 | 26371.67 | 122868.98 | 39103.33 | 78392.25 | 62104.73 | 37531.41 | 718338.42
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 10487.91 | 678.84 | [6 empty] | 37737.82 | 48904.57
|  |  | Capitalized Overhead - A&G | 1136.63 | 2385.11 | 11432.49 | 21650.28 | 7977.74 | 47487.6 | 3787.53 | 21849.06 | 25194.51 | 4908.37 | 9458.81 | 22660.02 | 179928.15
|  |  | Capitalized Overhead - Inj & Damages | 8.02 | 85.69 | 315.19 | 486.18 | 811.25 | 1692.3 | 63.09 | 909.9 | 171.6 | 411.45 | 346.75 | 57.55 | 5358.97
|  |  | Capitalized Overhead - P&B/Payroll Tax | 2488.29 | 10714.91 | 4402.52 | 9588.88 | 13027.78 | 12557.23 | 10544.91 | 27392.12 | 11114.41 | 18194.14 | 28805.38 | 36554.62 | 185385.19
|  | Non Budgeted Total |  | 3632.94 | 13185.71 | 16150.2 | 42213.25 | 22495.61 | 61737.13 | 14395.53 | 50151.08 | 36480.52 | 23513.96 | 38610.94 | 97010.01 | 419576.88
| Non Budget - Other Total |  |  | 3632.94 | 13185.71 | 16150.2 | 42213.25 | 22495.61 | 61737.13 | 14395.53 | 50151.08 | 36480.52 | 23513.96 | 38610.94 | 97010.01 | 419576.88
5. Corporate Overhead Total |  |  |  | 3632.94 | 13185.71 | 16150.2 | 42213.25 | 22495.61 | 61737.13 | 14395.53 | 50151.08 | 36480.52 | 23513.96 | 38610.94 | 97010.01 | 419576.88
Grand Total |  |  |  | 23479.24 | 98324.42 | 856608.26 | 125885.8 | 119951.07 | 1400320.46 | 112667.24 | 928554.1 | 492877.45 | 283253.01 | 334752.34 | 905706.42 | 5682379.81

## 800062856
Pin: 4847 | Project: DCR
Order: 800062856 | 800062856- I: DCR: Devers: Install 2 500kV Shunt Ca
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 |  | 2012 Total
SubCategory | Prime | Group | Details | 2 | 8
0. Conversion | Conversion | Conversion | Conversion |  | -2441.87 | -2441.87
|  | Conversion Total |  |  | -2441.87 | -2441.87
| Conversion Total |  |  |  | -2441.87 | -2441.87
0. Conversion Total |  |  |  |  | -2441.87 | -2441.87
1. Project Support | Other | Other | Other |  | -290 | -290
|  | Other Total |  |  | -290 | -290
| Other Total |  |  |  | -290 | -290
1. Project Support Total |  |  |  |  | -290 | -290
3. Construction | Short Term Equipment Rent | Contract | Contract Entries <$50,000 |  | -3192.06 | -3192.06
|  | Contract Total |  |  | -3192.06 | -3192.06
| Short Term Equipment Rent Total |  |  |  | -3192.06 | -3192.06
3. Construction Total |  |  |  |  | -3192.06 | -3192.06
4. Allocated | Labor - Other | Labor | Labor Entries <$5,000 |  | -252.83 | -252.83
|  | Labor Total |  |  | -252.83 | -252.83
| Labor - Other Total |  |  |  | -252.83 | -252.83
4. Allocated Total |  |  |  |  | -252.83 | -252.83
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G |  | -105.64 | -105.64
|  |  | Capitalized Overhead - Inj & Damages |  | -4.87 | -4.87
|  |  | Non-Budgeted WO Pstngs- WO/WBS Pstg - Co | -77.31 |  | -77.31
|  | Non Budgeted Total |  | -77.31 | -110.51 | -187.82
| Non Budget - Other Total |  |  | -77.31 | -110.51 | -187.82
5. Corporate Overhead Total |  |  |  | -77.31 | -110.51 | -187.82
Grand Total |  |  |  | -77.31 | -6287.27 | -6364.58

## 800062855
Pin: 4847 | Project: DCR
Order: 800062855 | 800062855- I: DCR: Devers: Install Line Pos for Dev
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | 2012 Total
SubCategory | Prime | Group | Details | 2
0. Conversion | Conversion | Conversion | Conversion | -5444.95 | -5444.95
|  | Conversion Total |  | -5444.95 | -5444.95
| Conversion Total |  |  | -5444.95 | -5444.95
0. Conversion Total |  |  |  | -5444.95 | -5444.95
1. Project Support | Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | -476 | -476
|  | Contract Total |  | -476 | -476
| Engineering/Technical Professional Servi Total |  |  | -476 | -476
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | -17.54 | -17.54
|  | IMM Correction Total |  | -17.54 | -17.54
| IMM/Allocated - Correction Total |  |  | -17.54 | -17.54
| Labor - Other | Labor | Labor Entries <$5,000 | -4674.28 | -4674.28
|  | Labor Total |  | -4674.28 | -4674.28
| Labor - Other Total |  |  | -4674.28 | -4674.28
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | -26213.57 | -26213.57
|  | Contract Total |  | -26213.57 | -26213.57
| Temporary/Supplementary - Technical/Prof Total |  |  | -26213.57 | -26213.57
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | -2569.16 | -2569.16
|  | Contract Total |  | -2569.16 | -2569.16
| Temporary/Supplementary - Trade/Labor Total |  |  | -2569.16 | -2569.16
1. Project Support Total |  |  |  | -33950.55 | -33950.55
2. Material | Material - Other | Material | Material - Other | -0.2 | -0.2
|  | Material Total |  | -0.2 | -0.2
| Material - Other Total |  |  | -0.2 | -0.2
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | -121.51 | -121.51
|  | Material - Direct Purchase Total |  | -121.51 | -121.51
| Transportation & Mobile Equip-DP Total |  |  | -121.51 | -121.51
2. Material Total |  |  |  | -121.71 | -121.71
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -580.93 | -580.93
|  | Chargeback Total |  | -580.93 | -580.93
| Chargebacks Total |  |  | -580.93 | -580.93
| Labor - Other | Labor | Labor Entries <$5,000 | -3515.34 | -3515.34
|  | Labor Total |  | -3515.34 | -3515.34
| Labor - Other Total |  |  | -3515.34 | -3515.34
4. Allocated Total |  |  |  | -4096.27 | -4096.27
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G | -1118.19 | -1118.19
|  |  | Capitalized Overhead - Inj & Damages | -15.38 | -15.38
|  |  | Capitalized Overhead - P&B/Payroll Tax | -5401.25 | -5401.25
|  |  | Non-Budgeted WO Pstngs- WO/WBS Pstg - Co | -3122.46 | -3122.46
|  | Non Budgeted Total |  | -9657.28 | -9657.28
| Non Budget - Other Total |  |  | -9657.28 | -9657.28
5. Corporate Overhead Total |  |  |  | -9657.28 | -9657.28
Grand Total |  |  |  | -53270.76 | -53270.76

## 800062850
Pin: 4847 | Project: DCR
Order: 800062850 | 800062850- I: DEVERS: Extend 500kV bus two position
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
0. Conversion | Conversion | Conversion | Conversion |  | 321346.13 | [5 empty] | 7091.82 |  |  |  |  | 328437.95
|  | Conversion Total |  |  | 321346.13 | [5 empty] | 7091.82 |  |  |  |  | 328437.95
| Conversion Total |  |  |  | 321346.13 | [5 empty] | 7091.82 |  |  |  |  | 328437.95
0. Conversion Total |  |  |  |  | 321346.13 | [5 empty] | 7091.82 |  |  |  |  | 328437.95
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  | 159.9 | 10.92 |  |  | 143.02 |  | 283.75 |  |  | 597.59
|  | Labor Total |  |  |  |  | 159.9 | 10.92 |  |  | 143.02 |  | 283.75 |  |  | 597.59
| BP&FM Total | [5 empty] | 159.9 | 10.92 |  |  | 143.02 |  | 283.75 |  |  | 597.59
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 | [6 empty] | 1140 | 570 |  | 1140 | 570 |  | 3420
|  | Contract Total | [7 empty] | 1140 | 570 |  | 1140 | 570 |  | 3420
| Cleaning / Janitorial Services Total | [8 empty] | 1140 | 570 |  | 1140 | 570 |  | 3420
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -38785.52 | 38785.52 |  |  | 0
|  | Contract Total | [9 empty] | -38785.52 | 38785.52 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -38785.52 | 38785.52 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | [7 empty] | 398.31 | 292.16 | 264 | 612.48 | 318.05 | 1885
|  | Contract Total | [8 empty] | 398.31 | 292.16 | 264 | 612.48 | 318.05 | 1885
| Contract Consult/Contract Ord to Ord Total | [9 empty] | 398.31 | 292.16 | 264 | 612.48 | 318.05 | 1885
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 |  |  |  | 88.4 |  | 1453.73 |  |  |  | 43.86 | 3373.09 | 328.97 | 5288.05
|  | Labor Total |  |  |  |  | 88.4 |  | 1453.73 |  |  |  | 43.86 | 3373.09 | 328.97 | 5288.05
| EAST GRID MGMTCENTER Total | [5 empty] | 88.4 |  | 1453.73 |  |  |  | 43.86 | 3373.09 | 328.97 | 5288.05
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 7129.2 | 7129.2
|  | Labor Total | [12 empty] | 7129.2 | 7129.2
| ELEC SYS PLANNING Total | [13 empty] | 7129.2 | 7129.2
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 666.8 |  | 182.96 |  |  | 351.72 | 142.76 |  |  |  |  | 1344.24
|  | Labor Total |  |  | 666.8 |  | 182.96 |  |  | 351.72 | 142.76 |  |  |  |  | 1344.24
| ENG ADVANCEMENT Total |  |  |  | 666.8 |  | 182.96 |  |  | 351.72 | 142.76 |  |  |  |  | 1344.24
| ENGINEERING | Labor | Engineer Sr |  | 5247.14 | [10 empty] | 5247.14
|  |  | Labor Entries <$5,000 | 7979.2 | 4583.53 | 11082.25 | 7960.96 | 7488.02 | 6088.85 | 5918.03 | 6721.86 | 5009.56 | 8111.19 | 6448.62 | 2049.75 | 79441.82
|  | Labor Total |  | 7979.2 | 9830.67 | 11082.25 | 7960.96 | 7488.02 | 6088.85 | 5918.03 | 6721.86 | 5009.56 | 8111.19 | 6448.62 | 2049.75 | 84688.96
| ENGINEERING Total |  |  | 7979.2 | 9830.67 | 11082.25 | 7960.96 | 7488.02 | 6088.85 | 5918.03 | 6721.86 | 5009.56 | 8111.19 | 6448.62 | 2049.75 | 84688.96
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  | 32729.08 |  |  |  |  | 27065.5 | 5162 | 11808 | 624 | 11405.92 | 55806.28 | 144600.78
|  |  | LOPEZ & ASSOCIATES ENGINEERS |  |  | 57113.22 | 64133.2 | [8 empty] | 121246.42
|  | Contract Total |  |  | 32729.08 | 57113.22 | 64133.2 |  |  | 27065.5 | 5162 | 11808 | 624 | 11405.92 | 55806.28 | 265847.2
| Engineering/Technical Professional Servi Total |  |  |  | 32729.08 | 57113.22 | 64133.2 |  |  | 27065.5 | 5162 | 11808 | 624 | 11405.92 | 55806.28 | 265847.2
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 5628.77 | 863 | 889.71 | 2129.19 | 5650.51 | 2025.79 | 4018.25 | 2200.5 | 5073.83 | 4835.5 | 4615.87 | 3826.49 | 41757.41
|  | Contract Total |  | 5628.77 | 863 | 889.71 | 2129.19 | 5650.51 | 2025.79 | 4018.25 | 2200.5 | 5073.83 | 4835.5 | 4615.87 | 3826.49 | 41757.41
| Environmental/Safety Professional Servic Total |  |  | 5628.77 | 863 | 889.71 | 2129.19 | 5650.51 | 2025.79 | 4018.25 | 2200.5 | 5073.83 | 4835.5 | 4615.87 | 3826.49 | 41757.41
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 2929.56 | -1091.39 | -7164.87 | 1623.81 | 2450.73 | -3162.49 | 2058.96 | 1193.41 | 293893.26 | -297231.86 | -1237.92 | -13411.37 | -19150.17
|  | IMM Correction Total |  | 2929.56 | -1091.39 | -7164.87 | 1623.81 | 2450.73 | -3162.49 | 2058.96 | 1193.41 | 293893.26 | -297231.86 | -1237.92 | -13411.37 | -19150.17
| IMM/Allocated - Correction Total |  |  | 2929.56 | -1091.39 | -7164.87 | 1623.81 | 2450.73 | -3162.49 | 2058.96 | 1193.41 | 293893.26 | -297231.86 | -1237.92 | -13411.37 | -19150.17
| Labor - Other | Labor | Labor Correction | [9 empty] | 17968.41 |  |  | 17968.41
|  |  | Labor Entries <$5,000 | -209.92 | 6704.49 | -1730.96 | 389.48 | 5304.51 | -2793.05 | -211.66 | 633.02 | 37704.29 | -48339.85 | -4346.83 | -2768.89 | -9665.37
|  |  | SUR/DEVERS 500 kV EXPANSION |  |  |  |  | 7484.57 | [7 empty] | 7484.57
|  | Labor Total |  | -209.92 | 6704.49 | -1730.96 | 389.48 | 12789.08 | -2793.05 | -211.66 | 633.02 | 37704.29 | -30371.44 | -4346.83 | -2768.89 | 15787.61
| Labor - Other Total |  |  | -209.92 | 6704.49 | -1730.96 | 389.48 | 12789.08 | -2793.05 | -211.66 | 633.02 | 37704.29 | -30371.44 | -4346.83 | -2768.89 | 15787.61
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 |  | 123.28 |  | 557.12 | 186.49 | 648.68 | 154.38 | 586.16 | 432.31 | 493.33 | 741.04 | 277.82 | 4200.61
|  | Labor Total |  |  | 123.28 |  | 557.12 | 186.49 | 648.68 | 154.38 | 586.16 | 432.31 | 493.33 | 741.04 | 277.82 | 4200.61
| MAJOR PROJECT ORG Total |  |  |  | 123.28 |  | 557.12 | 186.49 | 648.68 | 154.38 | 586.16 | 432.31 | 493.33 | 741.04 | 277.82 | 4200.61
| Other | Other | Other | -260 | 26.51 | 32.19 | 2556.13 | 9155.84 | 10060.66 | 95023.59 | -99642.05 | -158390.67 | 179162.69 | -1002.91 | 145604.65 | 182326.63
|  | Other Total |  | -260 | 26.51 | 32.19 | 2556.13 | 9155.84 | 10060.66 | 95023.59 | -99642.05 | -158390.67 | 179162.69 | -1002.91 | 145604.65 | 182326.63
| Other Total |  |  | -260 | 26.51 | 32.19 | 2556.13 | 9155.84 | 10060.66 | 95023.59 | -99642.05 | -158390.67 | 179162.69 | -1002.91 | 145604.65 | 182326.63
| SC&M | Labor | Labor Entries <$5,000 |  | 1539.38 | 1056.46 | 3681.5 | 1229.55 | 1602.26 | 1901.48 | 4075.77 | 6685.13 | 7045.48 | 3680.41 | 1487.9 | 33985.32
|  | Labor Total |  |  | 1539.38 | 1056.46 | 3681.5 | 1229.55 | 1602.26 | 1901.48 | 4075.77 | 6685.13 | 7045.48 | 3680.41 | 1487.9 | 33985.32
| SC&M Total |  |  |  | 1539.38 | 1056.46 | 3681.5 | 1229.55 | 1602.26 | 1901.48 | 4075.77 | 6685.13 | 7045.48 | 3680.41 | 1487.9 | 33985.32
| Software License Via Electronic Delivery | Contract | Contract Entries <$50,000 | [11 empty] | 7810.6 | 7810.6
|  | Contract Total | [12 empty] | 7810.6 | 7810.6
| Software License Via Electronic Delivery Total | [13 empty] | 7810.6 | 7810.6
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 | [8 empty] | 207.17 |  | 208.05 |  | 415.22
|  | Labor Total | [9 empty] | 207.17 |  | 208.05 |  | 415.22
| TEC SRVCS SUMMARY Total | [10 empty] | 207.17 |  | 208.05 |  | 415.22
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -2456.16 | 2456.16 |  |  | 0
|  | Contract Total | [9 empty] | -2456.16 | 2456.16 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -2456.16 | 2456.16 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 |  | 26213.57 | [10 empty] | 26213.57
|  | Contract Total |  |  | 26213.57 | [10 empty] | 26213.57
| Temporary/Supplementary - Technical/Prof Total |  |  |  | 26213.57 | [10 empty] | 26213.57
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 9215.04 | 13519.41 | 4416.4 | 1525.22 | 4185.17 | 9566 | 1741.46 | 428.68 |  | 298 | 447 | 2378.06 | 47720.44
|  | Contract Total |  | 9215.04 | 13519.41 | 4416.4 | 1525.22 | 4185.17 | 9566 | 1741.46 | 428.68 |  | 298 | 447 | 2378.06 | 47720.44
| Temporary/Supplementary - Trade/Labor Total |  |  | 9215.04 | 13519.41 | 4416.4 | 1525.22 | 4185.17 | 9566 | 1741.46 | 428.68 |  | 298 | 447 | 2378.06 | 47720.44
1. Project Support Total |  |  |  | 25282.65 | 91124.8 | 65694.4 | 84987.87 | 43146.31 | 25490.43 | 139161.71 | -77386.56 | 161473.36 | -84059.82 | 25514.82 | 210837.51 | 711267.48
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | Breakers - Circuit-DP | [8 empty] | 47374.68 |  |  |  | 47374.68
|  |  | Material Entries <$5,000 | [7 empty] | 128.66 |  |  |  |  | 128.66
|  |  | MITSUBISHI ELECTRIC | 524808 | 1432482 | [10 empty] | 1957290
|  | Material - Direct Purchase Total |  | 524808 | 1432482 | [5 empty] | 128.66 | 47374.68 |  |  |  | 2004793.34
| Breakers - Circuit-DP Total |  |  | 524808 | 1432482 | [5 empty] | 128.66 | 47374.68 |  |  |  | 2004793.34
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp | [8 empty] | 15702.78 |  |  |  | 15702.78
|  |  | JENSEN PRECAST | [8 empty] | 29859.2 |  |  |  | 29859.2
|  |  | Material Entries <$5,000 | [9 empty] | 3886.93 | 90.21 |  | 3977.14
|  | Material - Direct Purchase Total | [9 empty] | 45561.98 | 3886.93 | 90.21 |  | 49539.12
| Building, Shop & Industrial Products/Eqp Total | [10 empty] | 45561.98 | 3886.93 | 90.21 |  | 49539.12
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Material Entries <$5,000 | [5 empty] | 1572.45 |  | 1545.85 |  |  |  |  | 3118.3
|  | Material - Direct Purchase Total | [6 empty] | 1572.45 |  | 1545.85 |  |  |  |  | 3118.3
| Cabinets, Panels and Switchboards-DP Total | [7 empty] | 1572.45 |  | 1545.85 |  |  |  |  | 3118.3
| Capacitors and Regulators-DP | Material - Direct Purchase | HAEFELY TRENCH LIMITED | 21250 |  | 129125 | [9 empty] | 150375
|  | Material - Direct Purchase Total |  | 21250 |  | 129125 | [9 empty] | 150375
| Capacitors and Regulators-DP Total |  |  | 21250 |  | 129125 | [9 empty] | 150375
| Communication Systems and Equipment -DP | Material - Direct Purchase | Communication Systems and Equipment -DP | [11 empty] | 42966 | 42966
|  |  | CROSS BROTHERS INC | [6 empty] | 7475 | [5 empty] | 7475
|  | Material - Direct Purchase Total | [7 empty] | 7475 |  |  |  |  | 42966 | 50441
| Communication Systems and Equipment -DP Total | [8 empty] | 7475 |  |  |  |  | 42966 | 50441
| Electric Wiring and Components-DP | Material - Direct Purchase | ABB INC | [6 empty] | 12747.2 | [5 empty] | 12747.2
|  |  | CROSS BROTHERS INC | [10 empty] | 43700 |  | 43700
|  |  | Electric Wiring and Components-DP | [7 empty] | 10788 |  |  | 18779.48 | 6703.47 | 36270.95
|  |  | Material Entries <$5,000 |  |  |  |  | 4821.9 |  |  | 5836.88 | 3690.67 | 76.83 |  |  | 14426.28
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [5 empty] | 7074.13 | 12316.88 |  | 59872.25 | 68768.85 |  |  | 148032.11
|  |  | SOUTHWIRE COMPANY | [6 empty] | 14943 | 8064 | 15600 |  |  |  | 38607
|  | Material - Direct Purchase Total | [5 empty] | 4821.9 | 7074.13 | 40007.08 | 24688.88 | 79162.92 | 68845.68 | 62479.48 | 6703.47 | 293783.54
| Electric Wiring and Components-DP Total | [6 empty] | 4821.9 | 7074.13 | 40007.08 | 24688.88 | 79162.92 | 68845.68 | 62479.48 | 6703.47 | 293783.54
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 2712 | 200.03 |  | 2912.03
|  | Material - Direct Purchase Total | [10 empty] | 2712 | 200.03 |  | 2912.03
| Fuels, Chemicals & Petrochem-DP Total | [11 empty] | 2712 | 200.03 |  | 2912.03
| Line Switches & Switchgear-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 2036.67 |  | 2036.67
|  |  | SOUTHERN STATES LLC |  |  |  |  | 729612 | [7 empty] | 729612
|  | Material - Direct Purchase Total | [5 empty] | 729612 | [5 empty] | 2036.67 |  | 731648.67
| Line Switches & Switchgear-DP Total | [6 empty] | 729612 | [5 empty] | 2036.67 |  | 731648.67
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -25.81 | 25.81 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -25.81 | 25.81 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -25.81 | 25.81 |  |  | 0
| Material - Inventory | Material | Material - Inventory |  |  | 237211.59 |  |  | 1747.5 |  | 41851.2 | 774484.05 | 5576.88 |  |  | 1060871.22
|  | Material Total |  |  |  | 237211.59 |  |  | 1747.5 |  | 41851.2 | 774484.05 | 5576.88 |  |  | 1060871.22
| Material - Inventory Total |  |  |  |  | 237211.59 |  |  | 1747.5 |  | 41851.2 | 774484.05 | 5576.88 |  |  | 1060871.22
| Material - Other | Material | Material - Other | 41266.5 | 113884.97 | 28700.34 | 299.6 | 67479.51 | 827.86 | 7077.41 | 14037.97 | 144306.52 | 30045.05 | 21594.16 | 10974.74 | 480494.63
|  | Material Total |  | 41266.5 | 113884.97 | 28700.34 | 299.6 | 67479.51 | 827.86 | 7077.41 | 14037.97 | 144306.52 | 30045.05 | 21594.16 | 10974.74 | 480494.63
| Material - Other Total |  |  | 41266.5 | 113884.97 | 28700.34 | 299.6 | 67479.51 | 827.86 | 7077.41 | 14037.97 | 144306.52 | 30045.05 | 21594.16 | 10974.74 | 480494.63
| Material Handling Services | Contract | Contract Entries <$50,000 | [9 empty] | 96 | 64 |  | 160
|  | Contract Total | [10 empty] | 96 | 64 |  | 160
| Material Handling Services Total | [11 empty] | 96 | 64 |  | 160
| Mechanical Systems and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 2797 | 2797
|  | Material - Direct Purchase Total | [12 empty] | 2797 | 2797
| Mechanical Systems and Components-DP Total | [13 empty] | 2797 | 2797
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 422.61 | 3326.54 | 44.14 | 4131.1 | 22.03 | 7946.42
|  | Material - Direct Purchase Total | [8 empty] | 422.61 | 3326.54 | 44.14 | 4131.1 | 22.03 | 7946.42
| Metals & Fabricated Metal Products-DP Total | [9 empty] | 422.61 | 3326.54 | 44.14 | 4131.1 | 22.03 | 7946.42
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 1731.2 |  |  |  | 3672 | 5403.2
|  |  | QUALITROL COMPANY LLC | [6 empty] | 8154 | [5 empty] | 8154
|  | Material - Direct Purchase Total | [7 empty] | 8154 | 1731.2 |  |  |  | 3672 | 13557.2
| Meters, Monitor and Warnings-DP Total | [8 empty] | 8154 | 1731.2 |  |  |  | 3672 | 13557.2
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 16.96 |  |  | 650.44 | 667.4
|  |  | Pipe/Tubing, Fittings and Gaskets-DP | [10 empty] | 11019.09 |  | 11019.09
|  | Material - Direct Purchase Total | [9 empty] | 16.96 |  | 11019.09 | 650.44 | 11686.49
| Pipe/Tubing, Fittings and Gaskets-DP Total | [10 empty] | 16.96 |  | 11019.09 | 650.44 | 11686.49
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [5 empty] | 55.5 |  |  |  | 2495.72 |  |  | 2551.22
|  |  | Pole Line Hdwe & Connectors-DP | [8 empty] | 6062.08 |  | 21159.9 | 8770.11 | 35992.09
|  | Material - Direct Purchase Total | [6 empty] | 55.5 |  |  | 6062.08 | 2495.72 | 21159.9 | 8770.11 | 38543.31
| Pole Line Hdwe & Connectors-DP Total | [7 empty] | 55.5 |  |  | 6062.08 | 2495.72 | 21159.9 | 8770.11 | 38543.31
| Protection and Test-DP | Material - Direct Purchase | GE CONSUMER AND INDUSTRIAL | [7 empty] | 101456.46 |  |  |  |  | 101456.46
|  |  | Material Entries <$5,000 | [7 empty] | 1500 | 3173.28 | 692.72 | 393.4 | 404.29 | 6163.69
|  |  | SCHWEITZER ENGINEERING LABS INC | [6 empty] | 34093.2 | [5 empty] | 34093.2
|  | Material - Direct Purchase Total | [7 empty] | 34093.2 | 102956.46 | 3173.28 | 692.72 | 393.4 | 404.29 | 141713.35
| Protection and Test-DP Total | [8 empty] | 34093.2 | 102956.46 | 3173.28 | 692.72 | 393.4 | 404.29 | 141713.35
| Reactors and Line Traps-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 3650 | [10 empty] | 3650
|  | Material - Direct Purchase Total |  |  | 3650 | [10 empty] | 3650
| Reactors and Line Traps-DP Total |  |  |  | 3650 | [10 empty] | 3650
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 3712.76 |  | 3712.76
|  |  | PARCELL STEEL CO | [10 empty] | 46588.19 |  | 46588.19
|  |  | WASHINGTON ORNAMENTAL |  |  |  |  | 91261.84 |  |  |  | 771987.41 |  |  |  | 863249.25
|  | Material - Direct Purchase Total | [5 empty] | 91261.84 |  |  |  | 771987.41 |  | 50300.95 |  | 913550.2
| Steel / Fabricated / Structural-DP Total | [6 empty] | 91261.84 |  |  |  | 771987.41 |  | 50300.95 |  | 913550.2
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | AMERON INTERNATIONAL CORPORATION | [8 empty] | 5860 |  |  |  | 5860
|  | Material - Direct Purchase Total | [9 empty] | 5860 |  |  |  | 5860
| Towers/Poles, Steel & Concrete-DP Total | [10 empty] | 5860 |  |  |  | 5860
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | Transformers CT/PT/INSTR-DP | [7 empty] | 5689.03 |  |  |  |  | 5689.03
|  | Material - Direct Purchase Total | [8 empty] | 5689.03 |  |  |  |  | 5689.03
| Transformers CT/PT/INSTR-DP Total | [9 empty] | 5689.03 |  |  |  |  | 5689.03
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 121.51 |  |  | 9766.1 |  | 667.31 | 85.23 |  | 200.38 |  | 3174.02 | 14014.55
|  |  | Transportation & Mobile Equip-DP |  |  |  |  | 28358.29 | 5919.89 | [6 empty] | 34278.18
|  | Material - Direct Purchase Total |  |  | 121.51 |  |  | 38124.39 | 5919.89 | 667.31 | 85.23 |  | 200.38 |  | 3174.02 | 48292.73
| Transportation & Mobile Equip-DP Total |  |  |  | 121.51 |  |  | 38124.39 | 5919.89 | 667.31 | 85.23 |  | 200.38 |  | 3174.02 | 48292.73
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 48.7 |  | 266.35 | 13.3 | 328.35
|  |  | Wire, Cable & Bus Bar-DP |  |  |  |  | 33504.68 | [7 empty] | 33504.68
|  | Material - Direct Purchase Total | [5 empty] | 33504.68 |  |  |  | 48.7 |  | 266.35 | 13.3 | 33833.03
| Wire, Cable & Bus Bar-DP Total | [6 empty] | 33504.68 |  |  |  | 48.7 |  | 266.35 | 13.3 | 33833.03
2. Material Total |  |  |  | 587324.5 | 1550138.48 | 395036.93 | 299.6 | 964804.32 | 17197.33 | 97474 | 193137.09 | 1881339.31 | 114621.31 | 173735.34 | 80147.4 | 6055255.61
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  | 390 | 2600 | 2340 | 2210 | 4972.13 | 3922.5 |  | 3996.63 | 6603.16 | 88826.8 | 164794.83 | 280656.05
|  | Contract Total |  |  | 390 | 2600 | 2340 | 2210 | 4972.13 | 3922.5 |  | 3996.63 | 6603.16 | 88826.8 | 164794.83 | 280656.05
| Construction Management Services Total |  |  |  | 390 | 2600 | 2340 | 2210 | 4972.13 | 3922.5 |  | 3996.63 | 6603.16 | 88826.8 | 164794.83 | 280656.05
| Construction Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -2278.6 | 2278.6 |  |  | 0
|  | Contract Total | [9 empty] | -2278.6 | 2278.6 |  |  | 0
| Construction Services - Correction Total | [10 empty] | -2278.6 | 2278.6 |  |  | 0
| Construction Services - Other | Contract | Contract Entries <$50,000 | [11 empty] | 164.57 | 164.57
|  | Contract Total | [12 empty] | 164.57 | 164.57
| Construction Services - Other Total | [13 empty] | 164.57 | 164.57
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 |  |  |  |  | 352 | 408.32 | [6 empty] | 760.32
|  | Contract Total | [5 empty] | 352 | 408.32 | [6 empty] | 760.32
| Construction, Civil/Structural Total | [6 empty] | 352 | 408.32 | [6 empty] | 760.32
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 166.86 | 166.86
|  | Labor Total | [12 empty] | 166.86 | 166.86
| ELEC SYS PLANNING Total | [13 empty] | 166.86 | 166.86
| ENGINEERING | Labor | Labor Entries <$5,000 | 338.81 |  |  |  | 489.72 | 166.69 |  | 163.25 | 324.02 |  |  |  | 1482.49
|  | Labor Total |  | 338.81 |  |  |  | 489.72 | 166.69 |  | 163.25 | 324.02 |  |  |  | 1482.49
| ENGINEERING Total |  |  | 338.81 |  |  |  | 489.72 | 166.69 |  | 163.25 | 324.02 |  |  |  | 1482.49
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 |  | 19490.1 | 3696.6 | [6 empty] | 8833.05 |  |  | 32019.75
|  | Contract Total |  |  | 19490.1 | 3696.6 | [6 empty] | 8833.05 |  |  | 32019.75
| Hauling / Industrial Moving Services Total |  |  |  | 19490.1 | 3696.6 | [6 empty] | 8833.05 |  |  | 32019.75
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [9 empty] | 42473 |  |  | 42473
|  |  | KINDNESS GENERAL CONTRACTORS INC | [10 empty] | 1763735 |  | 1763735
|  |  | SUBSTATION SPECIALISTS | [11 empty] | 1923717 | 1923717
|  | Contract Total | [10 empty] | 42473 | 1763735 | 1923717 | 3729925
| Major Construction, Turnkey, Trans/Subs Total | [11 empty] | 42473 | 1763735 | 1923717 | 3729925
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 |  |  |  |  | 342.54 | 3680.88 | 2888.67 | 6156.37 | 4235.96 | 8784.46 | 34360.77 | 6484.87 | 66934.52
|  |  | Technician Test | [7 empty] | 5554.08 | 5987.99 |  |  |  | 11542.07
|  |  | Tst Spr Tech | [7 empty] | 5790.54 | 6009.51 | 5936.52 | 5255.28 |  | 22991.85
|  | Labor Total | [5 empty] | 342.54 | 3680.88 | 2888.67 | 17500.99 | 16233.46 | 14720.98 | 39616.05 | 6484.87 | 101468.44
| S/E SUBS MTCETST&APP Total | [6 empty] | 342.54 | 3680.88 | 2888.67 | 17500.99 | 16233.46 | 14720.98 | 39616.05 | 6484.87 | 101468.44
| SC&M | Labor | Labor Entries <$5,000 |  | 433.52 | 219.41 | 700.45 | 557.46 | 1693.98 | 827.55 | 1257.19 | 5639.43 | 14286.59 | 1665.45 | 11810.12 | 39091.15
|  | Labor Total |  |  | 433.52 | 219.41 | 700.45 | 557.46 | 1693.98 | 827.55 | 1257.19 | 5639.43 | 14286.59 | 1665.45 | 11810.12 | 39091.15
| SC&M Total |  |  |  | 433.52 | 219.41 | 700.45 | 557.46 | 1693.98 | 827.55 | 1257.19 | 5639.43 | 14286.59 | 1665.45 | 11810.12 | 39091.15
| SCM HOME CENTER | Labor | Labor Entries <$5,000 | [10 empty] | 46.92 |  | 46.92
|  | Labor Total | [11 empty] | 46.92 |  | 46.92
| SCM HOME CENTER Total | [12 empty] | 46.92 |  | 46.92
| Security / Protection Services | Contract | Contract Entries <$50,000 | [10 empty] | 9280 |  | 9280
|  | Contract Total | [11 empty] | 9280 |  | 9280
| Security / Protection Services Total | [12 empty] | 9280 |  | 9280
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [6 empty] | 1206.61 | 4048.67 | 3263.22 | 1934.11 | 2216.79 | 2216.79 | 14886.19
|  | Contract Total | [7 empty] | 1206.61 | 4048.67 | 3263.22 | 1934.11 | 2216.79 | 2216.79 | 14886.19
| Short Term Equipment Rent Total | [8 empty] | 1206.61 | 4048.67 | 3263.22 | 1934.11 | 2216.79 | 2216.79 | 14886.19
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 |  | 328 | 164 | [6 empty] | 164 |  |  | 656
|  | Labor Total |  |  | 328 | 164 | [6 empty] | 164 |  |  | 656
| TSD-HERC - Crane Svs Total |  |  |  | 328 | 164 | [6 empty] | 164 |  |  | 656
3. Construction Total |  |  |  | 338.81 | 20641.62 | 6680.01 | 3040.45 | 3951.72 | 10922 | 8845.33 | 22970.1 | 27178.16 | 91293.49 | 1905387.01 | 2109355.04 | 4210603.74
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 12310.15 | 3410.31 | 8263.93 | 9109.34 | -51336.96 | 15566.45 | 9559.48 | 27443.01 | 17490.1 | 2691.83 | 4733.87 | -13805.78 | 45435.73
|  |  | MATERIAL MANAGEM |  |  | 57808.46 |  |  |  |  | 5461.58 | 139949.27 |  |  |  | 203219.31
|  |  | PDP- Devers Sub (Xpansion)-MPO |  |  | 48061.03 | 36298.5 |  | 70703.66 | 31876.66 | 113102.1 |  | 120336.81 | 85655.11 | 62289.96 | 568323.83
|  |  | PDP-DPV2 General Mtg Support-MPO | [5 empty] | 5477.26 | 8061.87 |  |  | 9397.41 | 7483.45 |  | 30419.99
|  |  | PROCUREMENT TDBU |  | 10094.43 |  |  | 6007.83 |  |  |  | 6208.67 |  | 13411.37 | 14717.89 | 50440.19
|  |  | TDBU Vehicle Cost | [9 empty] | 6346.39 | 5048.28 |  | 11394.67
|  | Chargeback Total |  | 12310.15 | 13504.74 | 114133.42 | 45407.84 | -45329.13 | 91747.37 | 49498.01 | 146006.69 | 163648.04 | 138772.44 | 116332.08 | 63202.07 | 909233.72
| Chargebacks Total |  |  | 12310.15 | 13504.74 | 114133.42 | 45407.84 | -45329.13 | 91747.37 | 49498.01 | 146006.69 | 163648.04 | 138772.44 | 116332.08 | 63202.07 | 909233.72
| Labor - Other | Labor | Division Overhead | 39038.77 | 105840.37 | 20753.55 |  | 58005.89 |  |  | 6095.6 | 111912.54 | 6624.65 | 47016.54 | 77254.07 | 472541.98
|  |  | Labor Entries <$5,000 | 8048.83 | 6043.35 | 15759.96 | 9878.9 | 8548.44 | 6369.91 | 14068.6 | 13255.69 | 5854.52 | 22014.74 | 9464.97 | 12147.07 | 131454.98
|  |  | Paid Absence | [7 empty] | 5501.6 |  | 12101.55 | 5605.06 |  | 23208.21
|  | Labor Total |  | 47087.6 | 111883.72 | 36513.51 | 9878.9 | 66554.33 | 6369.91 | 14068.6 | 24852.89 | 117767.06 | 40740.94 | 62086.57 | 89401.14 | 627205.17
| Labor - Other Total |  |  | 47087.6 | 111883.72 | 36513.51 | 9878.9 | 66554.33 | 6369.91 | 14068.6 | 24852.89 | 117767.06 | 40740.94 | 62086.57 | 89401.14 | 627205.17
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -1539.82 | 1539.82 |  |  | 0
|  | Overhead Total | [9 empty] | -1539.82 | 1539.82 |  |  | 0
| Overhead Correction Total | [10 empty] | -1539.82 | 1539.82 |  |  | 0
4. Allocated Total |  |  |  | 59397.75 | 125388.46 | 150646.93 | 55286.74 | 21225.2 | 98117.28 | 63566.61 | 170859.58 | 279875.28 | 181053.2 | 178418.65 | 152603.21 | 1536438.89
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 26533.37 | 2016.96 | [6 empty] | 86802.31 | 115352.64
|  |  | Capitalized Overhead - A&G | 37537.71 | 52360.87 | 22030.47 | 5121.38 | 85349.78 | 5064.22 | 7534.84 | 11694 | 102284.4 | 9207.8 | 60420.78 | 67621.51 | 466227.76
|  |  | Capitalized Overhead - Inj & Damages | 614.76 | 2927.42 | 573.82 | 53.95 | 8964.67 | 148.03 | 146.47 | 524.21 | 2085.65 | 367.71 | 512.57 | 204.15 | 17123.41
|  |  | Capitalized Overhead - P&B/Payroll Tax | 7546.85 | 23882.56 | 14148.1 | 21809.79 | 36022.21 | 21309.79 | 20259.08 | 28818.05 | 20494.48 | 36780.8 | 42786.33 | 66577.7 | 340435.74
|  |  | Non-Budgeted WO Pstngs- WO/WBS Pstg - Co |  | 3199.77 | [9 empty] | 88617.53 | 91817.3
|  | Non Budgeted Total |  | 45699.32 | 82370.62 | 36752.39 | 53518.49 | 132353.62 | 26522.04 | 27940.39 | 41036.26 | 124864.53 | 46356.31 | 103719.68 | 309823.2 | 1030956.85
| Non Budget - Other Total |  |  | 45699.32 | 82370.62 | 36752.39 | 53518.49 | 132353.62 | 26522.04 | 27940.39 | 41036.26 | 124864.53 | 46356.31 | 103719.68 | 309823.2 | 1030956.85
5. Corporate Overhead Total |  |  |  | 45699.32 | 82370.62 | 36752.39 | 53518.49 | 132353.62 | 26522.04 | 27940.39 | 41036.26 | 124864.53 | 46356.31 | 103719.68 | 309823.2 | 1030956.85
Grand Total |  |  |  | 718043.03 | 2191010.11 | 654810.66 | 197133.15 | 1165481.17 | 178249.08 | 336988.04 | 357708.29 | 2474730.64 | 349264.49 | 2386775.5 | 2862766.36 | 13872960.52

## 800062846
Pin: 4847 | Project: DCR
Order: 800062846 | 800062846- I: DCR: Devers: Replace Eleven 230kV Cir
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [8 empty] | 2012 Total
SubCategory | Prime | Group | Details | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | [6 empty] | 39.67 |  |  | 39.67
|  | Labor Total | [7 empty] | 39.67 |  |  | 39.67
| ENG ADVANCEMENT Total | [8 empty] | 39.67 |  |  | 39.67
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 415.35 |  | 417.96 | 426.91 |  |  |  | 1260.22
|  | Labor Total |  |  |  | 415.35 |  | 417.96 | 426.91 |  |  |  | 1260.22
| ENGINEERING Total |  |  |  |  | 415.35 |  | 417.96 | 426.91 |  |  |  | 1260.22
| Engineering/Technical Professional Servi | Contract | Engineering/Technical Professional Servi | [8 empty] | 125554.36 | 125554.36
|  | Contract Total | [9 empty] | 125554.36 | 125554.36
| Engineering/Technical Professional Servi Total | [10 empty] | 125554.36 | 125554.36
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  |  |  | -0.88 |  |  |  |  | -0.88
|  | IMM Correction Total | [5 empty] | -0.88 |  |  |  |  | -0.88
| IMM/Allocated - Correction Total | [6 empty] | -0.88 |  |  |  |  | -0.88
| Labor - Other | Labor | Labor Entries <$5,000 |  |  | -45.36 | 45.36 | [5 empty] | 0
|  | Labor Total |  |  |  | -45.36 | 45.36 | [5 empty] | 0
| Labor - Other Total |  |  |  |  | -45.36 | 45.36 | [5 empty] | 0
| Other | Other | Other |  |  |  |  | 83.26 | 166.56 |  |  | 6619.77 | 6869.59
|  | Other Total | [5 empty] | 83.26 | 166.56 |  |  | 6619.77 | 6869.59
| Other Total | [6 empty] | 83.26 | 166.56 |  |  | 6619.77 | 6869.59
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  |  |  | 134.05 |  |  |  |  | 649.6 | 783.65
|  | Contract Total |  |  |  |  | 134.05 |  |  |  |  | 649.6 | 783.65
| Temporary/Supplementary - Trade/Labor Total | [5 empty] | 134.05 |  |  |  |  | 649.6 | 783.65
1. Project Support Total | [5 empty] | 369.99 | 179.41 | 500.34 | 593.47 | 39.67 |  | 132823.73 | 134506.61
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | Breakers - Circuit-DP | [8 empty] | 1525725.75 | 1525725.75
|  | Material - Direct Purchase Total | [9 empty] | 1525725.75 | 1525725.75
| Breakers - Circuit-DP Total | [10 empty] | 1525725.75 | 1525725.75
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 1238.32 | 1238.32
|  | Material - Direct Purchase Total | [9 empty] | 1238.32 | 1238.32
| Building, Shop & Industrial Products/Eqp Total | [10 empty] | 1238.32 | 1238.32
| Electric Wiring and Components-DP | Material - Direct Purchase | Electric Wiring and Components-DP | [8 empty] | 90984.03 | 90984.03
|  |  | Material Entries <$5,000 | [8 empty] | 27157.35 | 27157.35
|  | Material - Direct Purchase Total | [9 empty] | 118141.38 | 118141.38
| Electric Wiring and Components-DP Total | [10 empty] | 118141.38 | 118141.38
| Material - Inventory | Material | Material - Inventory | [7 empty] | 16951.19 | 117366.71 | 134317.9
|  | Material Total | [8 empty] | 16951.19 | 117366.71 | 134317.9
| Material - Inventory Total | [9 empty] | 16951.19 | 117366.71 | 134317.9
| Material - Other | Material | Material - Other | [7 empty] | 1319.58 | 18770.7 | 20090.28
|  | Material Total | [8 empty] | 1319.58 | 18770.7 | 20090.28
| Material - Other Total | [9 empty] | 1319.58 | 18770.7 | 20090.28
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 669.24 | 669.24
|  | Material - Direct Purchase Total | [9 empty] | 669.24 | 669.24
| Metals & Fabricated Metal Products-DP Total | [10 empty] | 669.24 | 669.24
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 6981.93 | 6981.93
|  | Material - Direct Purchase Total | [9 empty] | 6981.93 | 6981.93
| Pole Line Hdwe & Connectors-DP Total | [10 empty] | 6981.93 | 6981.93
| Protection and Test-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 95.52 | 95.52
|  | Material - Direct Purchase Total | [9 empty] | 95.52 | 95.52
| Protection and Test-DP Total | [10 empty] | 95.52 | 95.52
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 907.2 | 907.2
|  | Material - Direct Purchase Total | [9 empty] | 907.2 | 907.2
| Steel / Fabricated / Structural-DP Total | [10 empty] | 907.2 | 907.2
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 1861.6 | 1861.6
|  | Material - Direct Purchase Total | [9 empty] | 1861.6 | 1861.6
| Transformers CT/PT/INSTR-DP Total | [10 empty] | 1861.6 | 1861.6
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 3470.2 | 3470.2
|  | Material - Direct Purchase Total | [9 empty] | 3470.2 | 3470.2
| Transportation & Mobile Equip-DP Total | [10 empty] | 3470.2 | 3470.2
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 3929.16 | 3929.16
|  |  | Wire, Cable & Bus Bar-DP | [8 empty] | 5686.81 | 5686.81
|  | Material - Direct Purchase Total | [9 empty] | 9615.97 | 9615.97
| Wire, Cable & Bus Bar-DP Total | [10 empty] | 9615.97 | 9615.97
2. Material Total | [10 empty] | 18270.77 | 1804844.52 | 1823115.29
3. Construction | Construction Management Services | Contract | Construction Management Services | [8 empty] | 51552.06 | 51552.06
|  | Contract Total | [9 empty] | 51552.06 | 51552.06
| Construction Management Services Total | [10 empty] | 51552.06 | 51552.06
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [8 empty] | 408.32 | 408.32
|  | Contract Total | [9 empty] | 408.32 | 408.32
| Construction, Civil/Structural Total | [10 empty] | 408.32 | 408.32
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | [8 empty] | 12240.05 | 12240.05
|  | Contract Total | [9 empty] | 12240.05 | 12240.05
| Hauling / Industrial Moving Services Total | [10 empty] | 12240.05 | 12240.05
| Major Construction, Turnkey, Trans/Subs | Contract | Major Construction, Turnkey, Trans/Subs | [8 empty] | 621600 | 621600
|  | Contract Total | [9 empty] | 621600 | 621600
| Major Construction, Turnkey, Trans/Subs Total | [10 empty] | 621600 | 621600
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [8 empty] | 565.36 | 565.36
|  | Contract Total | [9 empty] | 565.36 | 565.36
| Short Term Equipment Rent Total | [10 empty] | 565.36 | 565.36
3. Construction Total | [11 empty] | 686365.79 | 686365.79
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 |  |  | 42.29 | 6.71 | 35.03 | 49.35 | 3.84 | 2878.31 |  | 3015.53
|  |  | MATERIAL MANAGEM | [8 empty] | 15762.35 | 15762.35
|  |  | PROCUREMENT TDBU | [8 empty] | 16388.06 | 16388.06
|  | Chargeback Total |  |  |  | 42.29 | 6.71 | 35.03 | 49.35 | 3.84 | 2878.31 | 32150.41 | 35165.94
| Chargebacks Total |  |  |  |  | 42.29 | 6.71 | 35.03 | 49.35 | 3.84 | 2878.31 | 32150.41 | 35165.94
| Labor - Other | Labor | Division Overhead | [8 empty] | 90137.37 | 90137.37
|  |  | Labor Entries <$5,000 |  |  | 115.65 | 25.36 | 142.73 | 143.88 | 13.46 | 428.86 | 4428.71 | 5298.65
|  | Labor Total |  |  |  | 115.65 | 25.36 | 142.73 | 143.88 | 13.46 | 428.86 | 94566.08 | 95436.02
| Labor - Other Total |  |  |  |  | 115.65 | 25.36 | 142.73 | 143.88 | 13.46 | 428.86 | 94566.08 | 95436.02
4. Allocated Total | [5 empty] | 157.94 | 32.07 | 177.76 | 193.23 | 17.3 | 3307.17 | 126716.49 | 130601.96
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax | 594.28 | 36.12 | [6 empty] | 17202.61 | 17833.01
|  |  | Capitalized Overhead - A&G |  |  | 18.84 | 7.42 | 19.18 | 35.25 | 1.47 | 570.25 | 77231.13 | 77883.54
|  |  | Capitalized Overhead - Inj & Damages |  |  | 0.68 | 0.07 | 0.88 | 0.71 | 0.18 | 35.48 | 2180.8 | 2218.8
|  |  | Capitalized Overhead - P&B/Payroll Tax |  |  | 495.26 | 58.75 | 339.77 | 611.67 | 19.38 |  |  | 1524.83
|  | Non Budgeted Total |  | 594.28 | 36.12 | 514.78 | 66.24 | 359.83 | 647.63 | 21.03 | 605.73 | 96614.54 | 99460.18
| Non Budget - Other Total |  |  | 594.28 | 36.12 | 514.78 | 66.24 | 359.83 | 647.63 | 21.03 | 605.73 | 96614.54 | 99460.18
5. Corporate Overhead Total |  |  |  | 594.28 | 36.12 | 514.78 | 66.24 | 359.83 | 647.63 | 21.03 | 605.73 | 96614.54 | 99460.18
Grand Total |  |  |  | 594.28 | 36.12 | 1042.71 | 277.72 | 1037.93 | 1434.33 | 78 | 22183.67 | 2847365.07 | 2874049.83

## 800062527
Pin: 4847 | Project: DCR
Order: 800062527 | 800062527- I: DCR: Devers - Valley #2 500kV T/L: BU
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  | 69.43 | 159.9 | 10.92 | 90.35 | 46.66 |  | 286.26 | 851.86 |  |  | 1515.38
|  | Labor Total |  |  |  | 69.43 | 159.9 | 10.92 | 90.35 | 46.66 |  | 286.26 | 851.86 |  |  | 1515.38
| BP&FM Total |  |  |  |  | 69.43 | 159.9 | 10.92 | 90.35 | 46.66 |  | 286.26 | 851.86 |  |  | 1515.38
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 | [8 empty] | 110.64 |  |  |  | 110.64
|  | Contract Total | [9 empty] | 110.64 |  |  |  | 110.64
| Building/Facility Repairs & Maintenance Total | [10 empty] | 110.64 |  |  |  | 110.64
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Con - Consults/Prof Srvcs/Out Ord to Ord | [8 empty] | 104709.45 |  |  |  | 104709.45
|  |  | Contract Entries <$50,000 | 42919.5 |  |  |  | 5818.5 | 25685.31 | 45511.06 | [5 empty] | 119934.37
|  | Contract Total |  | 42919.5 |  |  |  | 5818.5 | 25685.31 | 45511.06 |  | 104709.45 |  |  |  | 224643.82
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 42919.5 |  |  |  | 5818.5 | 25685.31 | 45511.06 |  | 104709.45 |  |  |  | 224643.82
| Consultants - Engineering/Technical | Contract | Contract Entries <$50,000 | [9 empty] | 3442.81 |  |  | 3442.81
|  | Contract Total | [10 empty] | 3442.81 |  |  | 3442.81
| Consultants - Engineering/Technical Total | [11 empty] | 3442.81 |  |  | 3442.81
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 4603651.68 |  |  | 4603651.68
|  |  | Contract Entries <$50,000 | [8 empty] | -4603651.68 |  |  |  | -4603651.68
|  | Contract Total | [9 empty] | -4603651.68 | 4603651.68 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -4603651.68 | 4603651.68 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | 12085.89 | 15554.03 |  | 23107.05 | 3505.97 | 7823.75 | [6 empty] | 62076.69
|  | Contract Total |  | 12085.89 | 15554.03 |  | 23107.05 | 3505.97 | 7823.75 | [6 empty] | 62076.69
| Contract Consult/Contract Ord to Ord Total |  |  | 12085.89 | 15554.03 |  | 23107.05 | 3505.97 | 7823.75 | [6 empty] | 62076.69
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 |  | 421.94 | 3192.37 |  |  |  | 2826.32 | 2143.45 | 1935.91 | 1789.74 | 343.62 | 21.35 | 12674.7
|  | Labor Total |  |  | 421.94 | 3192.37 |  |  |  | 2826.32 | 2143.45 | 1935.91 | 1789.74 | 343.62 | 21.35 | 12674.7
| EAST GRID MGMTCENTER Total |  |  |  | 421.94 | 3192.37 |  |  |  | 2826.32 | 2143.45 | 1935.91 | 1789.74 | 343.62 | 21.35 | 12674.7
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | 275.42 | [10 empty] | 11881.13 | 12156.55
|  | Labor Total |  | 275.42 | [10 empty] | 11881.13 | 12156.55
| ELEC SYS PLANNING Total |  |  | 275.42 | [10 empty] | 11881.13 | 12156.55
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 528.15 | 166.9 | 316 |  |  |  | 51.54 |  |  |  |  | 1062.59
|  | Labor Total |  |  | 528.15 | 166.9 | 316 |  |  |  | 51.54 |  |  |  |  | 1062.59
| ENG ADVANCEMENT Total |  |  |  | 528.15 | 166.9 | 316 |  |  |  | 51.54 |  |  |  |  | 1062.59
| ENGINEERING | Labor | Engineer | [7 empty] | 5760.51 |  |  |  |  | 5760.51
|  |  | Engineer Sr | [5 empty] | 6443.22 | [6 empty] | 6443.22
|  |  | Labor Entries <$5,000 | 13942.1 | 18397.24 | 21356.48 | 18940.84 | 19378.91 | 19775.56 | 16096.77 | 12618.85 | 14825.08 | 14582.7 | 15344.28 |  | 185258.81
|  | Labor Total |  | 13942.1 | 18397.24 | 21356.48 | 18940.84 | 19378.91 | 26218.78 | 16096.77 | 18379.36 | 14825.08 | 14582.7 | 15344.28 |  | 197462.54
| ENGINEERING Total |  |  | 13942.1 | 18397.24 | 21356.48 | 18940.84 | 19378.91 | 26218.78 | 16096.77 | 18379.36 | 14825.08 | 14582.7 | 15344.28 |  | 197462.54
| Engineering/Technical Professional Servi | Contract | BUREAU VERITAS NORTH AMERICA INC |  | 64202.9 |  | 87733 | [5 empty] | 116082 |  |  | 268017.9
|  |  | Contract Entries <$50,000 | 8300 | 12274.82 | 26920 | 21302.11 |  |  | 51521.5 | 10872 | 9272 | 54634.64 | 64346.28 | 81033.27 | 340476.62
|  |  | NINYO & MOORE | [10 empty] | 100850.22 | 378887.16 | 479737.38
|  | Contract Total |  | 8300 | 76477.72 | 26920 | 109035.11 |  |  | 51521.5 | 10872 | 9272 | 170716.64 | 165196.5 | 459920.43 | 1088231.9
| Engineering/Technical Professional Servi Total |  |  | 8300 | 76477.72 | 26920 | 109035.11 |  |  | 51521.5 | 10872 | 9272 | 170716.64 | 165196.5 | 459920.43 | 1088231.9
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 48133.6 | 13879.85 | 9095 | 30695.65 | 15612.66 | 22640.15 | 13384.14 | 15997.85 | 30277.4 | 39773.62 | 20172.92 | 13771.26 | 273434.1
|  |  | EL CAPITAN ENVIRONMENTAL | [11 empty] | 52561.77 | 52561.77
|  | Contract Total |  | 48133.6 | 13879.85 | 9095 | 30695.65 | 15612.66 | 22640.15 | 13384.14 | 15997.85 | 30277.4 | 39773.62 | 20172.92 | 66333.03 | 325995.87
| Environmental/Safety Professional Servic Total |  |  | 48133.6 | 13879.85 | 9095 | 30695.65 | 15612.66 | 22640.15 | 13384.14 | 15997.85 | 30277.4 | 39773.62 | 20172.92 | 66333.03 | 325995.87
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 44629.97 | 29604.53 | 35212.34 | 29748.9 | 26057.42 | 32450.48 | 23903.85 | -14126.45 | 10969054.5 | -10932871.29 | -55257.56 | -7119.69 | 181287
|  | IMM Correction Total |  | 44629.97 | 29604.53 | 35212.34 | 29748.9 | 26057.42 | 32450.48 | 23903.85 | -14126.45 | 10969054.5 | -10932871.29 | -55257.56 | -7119.69 | 181287
| IMM/Allocated - Correction Total |  |  | 44629.97 | 29604.53 | 35212.34 | 29748.9 | 26057.42 | 32450.48 | 23903.85 | -14126.45 | 10969054.5 | -10932871.29 | -55257.56 | -7119.69 | 181287
| Labor - Other | Labor | Labor - Other | [9 empty] | 15371.07 |  |  | 15371.07
|  |  | Labor Correction | [9 empty] | 76472.94 |  |  | 76472.94
|  |  | Labor Entries <$5,000 | 7399.12 | 8693.93 | -571.62 | -102.23 | 3647.43 | -4574.48 | 2109.05 | 1076.62 | 926951.9 | -1005759.84 | -4033.69 | 6354.49 | -58809.32
|  | Labor Total |  | 7399.12 | 8693.93 | -571.62 | -102.23 | 3647.43 | -4574.48 | 2109.05 | 1076.62 | 926951.9 | -913915.83 | -4033.69 | 6354.49 | 33034.69
| Labor - Other Total |  |  | 7399.12 | 8693.93 | -571.62 | -102.23 | 3647.43 | -4574.48 | 2109.05 | 1076.62 | 926951.9 | -913915.83 | -4033.69 | 6354.49 | 33034.69
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | [9 empty] | 1783.73 | 1384.99 |  | 3168.72
|  | Labor Total | [10 empty] | 1783.73 | 1384.99 |  | 3168.72
| MAJOR PROJECT ORG Total | [11 empty] | 1783.73 | 1384.99 |  | 3168.72
| Other | Other | Other | 439923.61 | 165893.95 | 1103424.57 | 2011164.08 | 1792356.24 | 1018596.39 | -2782176.38 | -1325677.96 | -3654716.68 | 8784638.07 | -1064726.47 | -2166989.73 | 4321709.69
|  | Other Total |  | 439923.61 | 165893.95 | 1103424.57 | 2011164.08 | 1792356.24 | 1018596.39 | -2782176.38 | -1325677.96 | -3654716.68 | 8784638.07 | -1064726.47 | -2166989.73 | 4321709.69
| Other Total |  |  | 439923.61 | 165893.95 | 1103424.57 | 2011164.08 | 1792356.24 | 1018596.39 | -2782176.38 | -1325677.96 | -3654716.68 | 8784638.07 | -1064726.47 | -2166989.73 | 4321709.69
| SOUTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  |  | 83.83 | [9 empty] | 83.83
|  | Labor Total |  |  |  | 83.83 | [9 empty] | 83.83
| SOUTH GRIDMGMTCENTER Total |  |  |  |  | 83.83 | [9 empty] | 83.83
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 |  | 207.47 |  | 424.97 | [8 empty] | 632.44
|  | Labor Total |  |  | 207.47 |  | 424.97 | [8 empty] | 632.44
| TEC SRVCS SUMMARY Total |  |  |  | 207.47 |  | 424.97 | [8 empty] | 632.44
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -25238.28 | 25238.28 |  |  | 0
|  | Contract Total | [9 empty] | -25238.28 | 25238.28 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -25238.28 | 25238.28 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 2834.95 | 7097.3 | 26255.34 | 67155.04 | 15548.09 | 21989.1 | 4861.3 |  |  |  | 15170.9 | 28327.5 | 189239.52
|  | Contract Total |  | 2834.95 | 7097.3 | 26255.34 | 67155.04 | 15548.09 | 21989.1 | 4861.3 |  |  |  | 15170.9 | 28327.5 | 189239.52
| Temporary/Supplementary - Technical/Prof Total |  |  | 2834.95 | 7097.3 | 26255.34 | 67155.04 | 15548.09 | 21989.1 | 4861.3 |  |  |  | 15170.9 | 28327.5 | 189239.52
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 678.86 | 433.52 | 271.04 | 298 |  |  |  | 146.08 | 98.02 | 465.08 | 784.08 | 2603.45 | 5778.13
|  | Contract Total |  | 678.86 | 433.52 | 271.04 | 298 |  |  |  | 146.08 | 98.02 | 465.08 | 784.08 | 2603.45 | 5778.13
| Temporary/Supplementary - Trade/Labor Total |  |  | 678.86 | 433.52 | 271.04 | 298 |  |  |  | 146.08 | 98.02 | 465.08 | 784.08 | 2603.45 | 5778.13
| TRANSMISSION | Labor | Labor Entries <$5,000 | 50.79 | 2686.19 | 4582.41 | 404.22 |  |  |  |  | 502.96 | 297.54 |  | 10761.33 | 19285.44
|  | Labor Total |  | 50.79 | 2686.19 | 4582.41 | 404.22 |  |  |  |  | 502.96 | 297.54 |  | 10761.33 | 19285.44
| TRANSMISSION Total |  |  | 50.79 | 2686.19 | 4582.41 | 404.22 |  |  |  |  | 502.96 | 297.54 |  | 10761.33 | 19285.44
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 10415.64 | 7850.85 | 8807.14 | 8424.71 | 13002.75 | 8606.52 | 13389.31 | 5871.45 | 13096.45 | 7774.36 | 13685.28 | 3475.76 | 114400.22
|  |  | Mgr-Prj/Prod |  | 12301.51 | 12187.27 | 5499 |  | 5034.3 |  | 11720.45 |  | 6079.89 |  |  | 52822.42
|  | Labor Total |  | 10415.64 | 20152.36 | 20994.41 | 13923.71 | 13002.75 | 13640.82 | 13389.31 | 17591.9 | 13096.45 | 13854.25 | 13685.28 | 3475.76 | 167222.64
| TRNS CAPITAL Total |  |  | 10415.64 | 20152.36 | 20994.41 | 13923.71 | 13002.75 | 13640.82 | 13389.31 | 17591.9 | 13096.45 | 13854.25 | 13685.28 | 3475.76 | 167222.64
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 |  |  |  | 2325.8 | 333 |  |  |  | 266.4 |  |  |  | 2925.2
|  | Labor Total |  |  |  |  | 2325.8 | 333 |  |  |  | 266.4 |  |  |  | 2925.2
| TSD-Aircraft - Fixed Total | [5 empty] | 2325.8 | 333 |  |  |  | 266.4 |  |  |  | 2925.2
1. Project Support Total |  |  |  | 631589.45 | 360028.18 | 1251052.5 | 2307597.04 | 1895271.89 | 1164560.65 | -2608526.42 | -1273545.61 | 3787780.33 | 1814298.88 | -891935.15 | -1584430.95 | 6853740.79
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 | 2980.8 | 1142.64 | [8 empty] | 129.2 |  | 4252.64
|  | Material - Direct Purchase Total |  | 2980.8 | 1142.64 | [8 empty] | 129.2 |  | 4252.64
| Building, Shop & Industrial Products/Eqp Total |  |  | 2980.8 | 1142.64 | [8 empty] | 129.2 |  | 4252.64
| Labor - Other | Labor | Labor Entries <$5,000 | [7 empty] | 164.12 |  |  |  |  | 164.12
|  | Labor Total | [8 empty] | 164.12 |  |  |  |  | 164.12
| Labor - Other Total | [9 empty] | 164.12 |  |  |  |  | 164.12
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -674.65 | 674.65 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -674.65 | 674.65 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -674.65 | 674.65 |  |  | 0
| Material - Inventory | Material | Material - Inventory | [8 empty] | -50.25 | 50.25 |  |  | 0
|  | Material Total | [9 empty] | -50.25 | 50.25 |  |  | 0
| Material - Inventory Total | [10 empty] | -50.25 | 50.25 |  |  | 0
| Material - Other | Material | Material - Other | 134612.63 | 97597.62 | 103081.8 | 102970.72 | -969.09 | 45266.63 | 61205.76 | 151740.65 | 24705.9 | 136.08 | 3018.29 | 39041.29 | 762408.28
|  | Material Total |  | 134612.63 | 97597.62 | 103081.8 | 102970.72 | -969.09 | 45266.63 | 61205.76 | 151740.65 | 24705.9 | 136.08 | 3018.29 | 39041.29 | 762408.28
| Material - Other Total |  |  | 134612.63 | 97597.62 | 103081.8 | 102970.72 | -969.09 | 45266.63 | 61205.76 | 151740.65 | 24705.9 | 136.08 | 3018.29 | 39041.29 | 762408.28
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 106.84 |  | 377.53 | 146.63 |  | 631
|  | Material - Direct Purchase Total | [8 empty] | 106.84 |  | 377.53 | 146.63 |  | 631
| Office & Office Support Products-DP Total | [9 empty] | 106.84 |  | 377.53 | 146.63 |  | 631
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | AGILE SOURCING PARTNERS INC | [11 empty] | 156484 | 156484
|  |  | Material Entries <$5,000 | 5602.88 | 1184 |  | 115.85 |  |  | 0 |  |  |  | 1519 |  | 8421.73
|  |  | ONE SOURCE DISTRIBUTORS INC | 125882.03 | 256749.3 | 531353.35 | 70501.5 | [8 empty] | 984486.18
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [11 empty] | 62289.73 | 62289.73
|  |  | Pole Line Hdwe & Connectors-DP | 21818.16 | [11 empty] | 21818.16
|  | Material - Direct Purchase Total |  | 153303.07 | 257933.3 | 531353.35 | 70617.35 |  |  | 0 |  |  |  | 1519 | 218773.73 | 1233499.8
| Pole Line Hdwe & Connectors-DP Total |  |  | 153303.07 | 257933.3 | 531353.35 | 70617.35 |  |  | 0 |  |  |  | 1519 | 218773.73 | 1233499.8
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | ON-RAMP WIRELESS, INC. | [7 empty] | 40880 |  |  | 10363.78 |  | 51243.78
|  | Material - Direct Purchase Total | [8 empty] | 40880 |  |  | 10363.78 |  | 51243.78
| Power Systems, Batteries and Light-DP Total | [9 empty] | 40880 |  |  | 10363.78 |  | 51243.78
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | [8 empty] | 13900 |  |  |  | 13900
|  |  | Material Entries <$5,000 | [8 empty] | 600 |  |  |  | 600
|  | Material - Direct Purchase Total | [9 empty] | 14500 |  |  |  | 14500
| Steel / Fabricated / Structural-DP Total | [10 empty] | 14500 |  |  |  | 14500
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | FORMET | 472705.17 | 372397.6 | 185564.86 | 105248.63 | 95757.06 | 286670.62 | 571800.88 | 780957.55 | 167736.02 |  | 21941.49 | 163392.56 | 3224172.44
|  |  | Material Entries <$5,000 | 0.92 |  | 4473.21 |  | -96577.92 |  | 1564.46 | -54918.14 |  |  |  |  | -145457.47
|  |  | SAE TOWERS | 343267.45 |  |  | 221244 | 8837.72 | 126519.76 | [6 empty] | 699868.93
|  | Material - Direct Purchase Total |  | 815973.54 | 372397.6 | 190038.07 | 326492.63 | 8016.86 | 413190.38 | 573365.34 | 726039.41 | 167736.02 |  | 21941.49 | 163392.56 | 3778583.9
| Steel Lattice Towers (T/S)-DP Total |  |  | 815973.54 | 372397.6 | 190038.07 | 326492.63 | 8016.86 | 413190.38 | 573365.34 | 726039.41 | 167736.02 |  | 21941.49 | 163392.56 | 3778583.9
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | SABRE COMMUNICATIONS CORPORATION |  |  |  |  | 10269 |  |  | 128474 |  |  |  |  | 138743
|  |  | VALMONT INDUSTRIES INC |  |  |  | 215530.74 | [8 empty] | 215530.74
|  | Material - Direct Purchase Total |  |  |  |  | 215530.74 | 10269 |  |  | 128474 |  |  |  |  | 354273.74
| Towers/Poles, Steel & Concrete-DP Total | [5 empty] | 215530.74 | 10269 |  |  | 128474 |  |  |  |  | 354273.74
| Transportation & Mobile Equip-DP | Material - Direct Purchase | CAZCOM, INC. | [6 empty] | 5524.37 | [5 empty] | 5524.37
|  |  | Material Entries <$5,000 | 1024.94 | 355.1 | 380.93 |  |  | 38.56 |  | 1774.77 |  |  | 790.17 | 433.5 | 4797.97
|  | Material - Direct Purchase Total |  | 1024.94 | 355.1 | 380.93 |  |  | 38.56 | 5524.37 | 1774.77 |  |  | 790.17 | 433.5 | 10322.34
| Transportation & Mobile Equip-DP Total |  |  | 1024.94 | 355.1 | 380.93 |  |  | 38.56 | 5524.37 | 1774.77 |  |  | 790.17 | 433.5 | 10322.34
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | AFL TELECOMMUNICATIONS LLC |  | 214964.7 | 188835.93 | 306879.9 | [8 empty] | 710680.53
|  |  | Material Entries <$5,000 |  | 560.35 | 875 | [9 empty] | 1435.35
|  |  | SOUTHWIRE COMPANY | 686569.38 | [11 empty] | 686569.38
|  | Material - Direct Purchase Total |  | 686569.38 | 215525.05 | 189710.93 | 306879.9 | [8 empty] | 1398685.26
| Wire, Cable & Bus Bar-DP Total |  |  | 686569.38 | 215525.05 | 189710.93 | 306879.9 | [8 empty] | 1398685.26
2. Material Total |  |  |  | 1794464.36 | 944951.31 | 1014565.08 | 1022491.34 | 17316.77 | 458495.57 | 640095.47 | 1049179.79 | 206217.02 | 1238.51 | 37908.56 | 421641.08 | 7608564.86
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 14083.6 | 51467.06 | 46451.52 | 80167.22 | 35254.82 | 58811.86 | 68595.62 | 64394.23 | 22910.54 | 37575.9 | 27470.88 | 113263.04 | 620446.29
|  |  | KENNY CONSTRUCTION COMPANY | 117550.91 | 150561.79 | 182744.02 | 252121.74 | 237546.21 | 242636.42 | 260431.48 | 298024.29 | 320942.39 | 370679.7 | 403832.73 | 414719.68 | 3251791.36
|  |  | UTILITY LINE MANAGEMENT SERVICES | [11 empty] | 131552.96 | 131552.96
|  | Contract Total |  | 131634.51 | 202028.85 | 229195.54 | 332288.96 | 272801.03 | 301448.28 | 329027.1 | 362418.52 | 343852.93 | 408255.6 | 431303.61 | 659535.68 | 4003790.61
| Construction Management Services Total |  |  | 131634.51 | 202028.85 | 229195.54 | 332288.96 | 272801.03 | 301448.28 | 329027.1 | 362418.52 | 343852.93 | 408255.6 | 431303.61 | 659535.68 | 4003790.61
| Construction Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -140864.06 | 32103.06 |  |  | -108761
|  | Contract Total | [9 empty] | -140864.06 | 32103.06 |  |  | -108761
| Construction Services - Correction Total | [10 empty] | -140864.06 | 32103.06 |  |  | -108761
| Construction Services - Other | Contract | Construction Services - Other |  |  |  |  | 199133.69 | 67891.05 |  | 56662.14 | 65954.64 |  |  |  | 389641.52
|  |  | Contract Entries <$50,000 | 4622.28 | 598.22 | 5248.11 | 4501.21 |  |  | 1088.35 |  |  | 33617.32 | 14501.97 | 8168.74 | 72346.2
|  | Contract Total |  | 4622.28 | 598.22 | 5248.11 | 4501.21 | 199133.69 | 67891.05 | 1088.35 | 56662.14 | 65954.64 | 33617.32 | 14501.97 | 8168.74 | 461987.72
| Construction Services - Other Total |  |  | 4622.28 | 598.22 | 5248.11 | 4501.21 | 199133.69 | 67891.05 | 1088.35 | 56662.14 | 65954.64 | 33617.32 | 14501.97 | 8168.74 | 461987.72
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | 616 | 1112.43 | 595.65 | [5 empty] | 1169 | 680 | 680 | 1360 | 6213.08
|  | Contract Total |  | 616 | 1112.43 | 595.65 | [5 empty] | 1169 | 680 | 680 | 1360 | 6213.08
| Construction, Civil/Structural Total |  |  | 616 | 1112.43 | 595.65 | [5 empty] | 1169 | 680 | 680 | 1360 | 6213.08
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  | 496.08 | [8 empty] | 496.08
|  | Contract Total |  |  |  |  | 496.08 | [8 empty] | 496.08
| Contract Consult/Contract Ord to Ord Total | [5 empty] | 496.08 | [8 empty] | 496.08
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 164.39 | 164.39
|  | Labor Total | [12 empty] | 164.39 | 164.39
| ELEC SYS PLANNING Total | [13 empty] | 164.39 | 164.39
| Electrical Construction | Contract | Contract Entries <$50,000 | 21312.51 | 66709.74 | 24238.98 | 22509.73 | 27599.26 |  | 22571.84 | 15924.24 | 10325.17 | 9482.83 | 8397.32 | 6503.32 | 235574.94
|  |  | KENNY CONSTRUCTION COMPANY | 208703.23 | 211222.08 | 245762.98 | 281938.73 | 187164.14 | 217252.27 | 201754.5 | 209621.83 | 179565.57 | 145690.36 | 159795.58 | 192848.29 | 2441319.56
|  |  | PAR ELECTRICAL CONTRACTORS INC |  |  | 775075.5 | 1045938.6 | 914720.4 | 567635.4 | 5646281.4 | 1787438.1 | 1515753.9 | 2897401.5 | 227847.15 | 16183424.75 | 31561516.7
|  | Contract Total |  | 230015.74 | 277931.82 | 1045077.46 | 1350387.06 | 1129483.8 | 784887.67 | 5870607.74 | 2012984.17 | 1705644.64 | 3052574.69 | 396040.05 | 16382776.36 | 34238411.2
| Electrical Construction Total |  |  | 230015.74 | 277931.82 | 1045077.46 | 1350387.06 | 1129483.8 | 784887.67 | 5870607.74 | 2012984.17 | 1705644.64 | 3052574.69 | 396040.05 | 16382776.36 | 34238411.2
| ENGINEERING | Labor | Labor Entries <$5,000 | [10 empty] | 162.87 |  | 162.87
|  | Labor Total | [11 empty] | 162.87 |  | 162.87
| ENGINEERING Total | [12 empty] | 162.87 |  | 162.87
| GRID OPS | Labor | Labor Entries <$5,000 |  |  | 66.19 | 202.9 |  | 66.34 |  | 238.21 |  |  |  | 380.87 | 954.51
|  | Labor Total |  |  |  | 66.19 | 202.9 |  | 66.34 |  | 238.21 |  |  |  | 380.87 | 954.51
| GRID OPS Total |  |  |  |  | 66.19 | 202.9 |  | 66.34 |  | 238.21 |  |  |  | 380.87 | 954.51
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 17299.06 | 13373.07 | 11583.17 | 2067 | 2067 | 4134 |  | 2067 |  | 0 |  |  | 52590.3
|  | Contract Total |  | 17299.06 | 13373.07 | 11583.17 | 2067 | 2067 | 4134 |  | 2067 |  | 0 |  |  | 52590.3
| Short Term Equipment Rent Total |  |  | 17299.06 | 13373.07 | 11583.17 | 2067 | 2067 | 4134 |  | 2067 |  | 0 |  |  | 52590.3
| TRANSMISSION | Labor | Labor Entries <$5,000 | 5604.04 | 298.05 | 540.46 | 157.46 |  |  |  | 328.61 | 178.3 | 75.11 | 279.68 | 109.94 | 7571.65
|  | Labor Total |  | 5604.04 | 298.05 | 540.46 | 157.46 |  |  |  | 328.61 | 178.3 | 75.11 | 279.68 | 109.94 | 7571.65
| TRANSMISSION Total |  |  | 5604.04 | 298.05 | 540.46 | 157.46 |  |  |  | 328.61 | 178.3 | 75.11 | 279.68 | 109.94 | 7571.65
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 4681.74 | 4502.93 | 5087.28 | 1297.83 | 1247.97 | 1492.37 | 1461.95 | 1499.54 | 1681.48 | 1034.92 | 661.54 |  | 24649.55
|  | Labor Total |  | 4681.74 | 4502.93 | 5087.28 | 1297.83 | 1247.97 | 1492.37 | 1461.95 | 1499.54 | 1681.48 | 1034.92 | 661.54 |  | 24649.55
| TRNS CAPITAL Total |  |  | 4681.74 | 4502.93 | 5087.28 | 1297.83 | 1247.97 | 1492.37 | 1461.95 | 1499.54 | 1681.48 | 1034.92 | 661.54 |  | 24649.55
3. Construction Total |  |  |  | 394473.37 | 499845.37 | 1297393.86 | 1691398.5 | 1604733.49 | 1159919.71 | 6202185.14 | 2436198.19 | 1977616.93 | 3528340.7 | 843629.72 | 17052495.98 | 38688230.96
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 23054.31 | 25392.68 | -343165.25 | 36713.67 | -24838.97 | 30976.56 | -612231.45 | 45020.79 | 222183.91 | -205278.16 | 32579.2 | -210155.32 | -979748.03
|  |  | DPV2/DCR Project Mgmt Home Office Cost | 39991.71 | 39989.77 | 30911.09 | 39103.06 | 34138.26 | 38030.35 | 32042.21 | 40736.09 | 33956.95 | 36086 | 35206.53 | 40941.53 | 441133.55
|  |  | DPV2/DCR Project OE T/L Work | 201284.71 | 177399.79 | 186975.91 | 170983.31 | 175873.48 | 222431.65 | 198922 | 157943.94 | 158612.37 | 153328.2 | 167296.99 | 152587.42 | 2123639.77
|  |  | PDP-2010 Devers to Valley 500kV-MPO | 692461.95 | 627897.24 | 3940961.52 | 953919.76 | 722953.38 | 1131696.59 | 1464016.48 | 1204881.57 |  | 2010286.51 | 1919769.74 | 1456580.78 | 16125425.52
|  |  | PDP-DPV2 General Mtg Support-MPO | 12101.09 | 489776.27 | 28737.16 | 99514.12 | 74157.61 | 129244.05 | 136921.83 | 196119.93 |  | 231358.91 | 159575.73 | 87993.59 | 1645500.29
|  |  | PROCUREMENT TDBU | 15025.44 | 9417.63 | 14881.07 | 18572.55 | 10896.44 | 10639.76 | 45205.91 | 22180.92 |  | 55257.56 | 7119.69 | 118745.44 | 327942.41
|  |  | TDBU Vehicle Cost | 11365.73 | 12581.21 | [7 empty] | 6202.81 |  |  | 30149.75
|  | Chargeback Total |  | 995284.94 | 1382454.59 | 3859301.5 | 1318806.47 | 993180.2 | 1563018.96 | 1264876.98 | 1666883.24 | 414753.23 | 2287241.83 | 2321547.88 | 1646693.44 | 19714043.26
| Chargebacks Total |  |  | 995284.94 | 1382454.59 | 3859301.5 | 1318806.47 | 993180.2 | 1563018.96 | 1264876.98 | 1666883.24 | 414753.23 | 2287241.83 | 2321547.88 | 1646693.44 | 19714043.26
| Labor - Other | Labor | Division Overhead | 122389.91 | 124987.95 | 82815.47 | 86254.2 | 72168.5 | 72224.6 | 285036.01 | 137992.1 |  | 434647.2 | 6600.71 | 241131.47 | 1666248.12
|  |  | Labor Entries <$5,000 | 4526.85 | 8081.08 | 3858.55 | 6486.24 | 2829.45 | 2945.18 | 2947.4 | 3026.92 | -88379.45 | 12323.96 | 9723.95 | 1307.28 | -30322.59
|  |  | Paid Absence | 5628.99 | 8071.48 | 7995.65 | 5609.47 | 6316.58 | 5989.18 | 5773.25 | 6562.3 |  | 21213.25 |  | 5689.09 | 78849.24
|  | Labor Total |  | 132545.75 | 141140.51 | 94669.67 | 98349.91 | 81314.53 | 81158.96 | 293756.66 | 147581.32 | -88379.45 | 468184.41 | 16324.66 | 248127.84 | 1714774.77
| Labor - Other Total |  |  | 132545.75 | 141140.51 | 94669.67 | 98349.91 | 81314.53 | 81158.96 | 293756.66 | 147581.32 | -88379.45 | 468184.41 | 16324.66 | 248127.84 | 1714774.77
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -104229.71 | 104229.71 |  |  | 0
|  | Overhead Total | [9 empty] | -104229.71 | 104229.71 |  |  | 0
| Overhead Correction Total | [10 empty] | -104229.71 | 104229.71 |  |  | 0
4. Allocated Total |  |  |  | 1127830.69 | 1523595.1 | 3953971.17 | 1417156.38 | 1074494.73 | 1644177.92 | 1558633.64 | 1814464.56 | 222144.07 | 2859655.95 | 2337872.54 | 1894821.28 | 21428818.03
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 363262.76 | 23237.28 | [6 empty] | 696453.17 | 1082953.21
|  |  | Capitalized Overhead - A&G | 196296.46 | 92786.48 | 228945.04 | 157986.93 | 233189.81 | 121769.2 | 301163.8 | 151587.08 | 167715.73 | 142874.65 | 89738.24 | 560260.74 | 2444314.16
|  |  | Capitalized Overhead - Inj & Damages | 2437.8 | 4097.46 | 4621.7 | 1516.1 | 3496.29 | 1315.03 | 522.91 | 3389.61 | 5524.11 | -15769.36 | 1561.06 | 895.87 | 13608.58
|  |  | Capitalized Overhead - P&B/Payroll Tax | 48936.01 | 100317.37 | 86273.65 | 90630.65 | 108787.69 | 86245.38 | 84470.92 | 67461.04 | -49672.92 | 85342.14 | 51870.15 | 149474.39 | 910136.47
|  |  | Corporate Overheads Correction |  |  |  |  | -1597575.92 | [7 empty] | -1597575.92
|  | Non Budgeted Total |  | 247670.27 | 197201.31 | 319840.39 | 613396.44 | -1228864.85 | 209329.61 | 386157.63 | 222437.73 | 123566.92 | 212447.43 | 143169.45 | 1407084.17 | 2853436.5
| Non Budget - Other Total |  |  | 247670.27 | 197201.31 | 319840.39 | 613396.44 | -1228864.85 | 209329.61 | 386157.63 | 222437.73 | 123566.92 | 212447.43 | 143169.45 | 1407084.17 | 2853436.5
5. Corporate Overhead Total |  |  |  | 247670.27 | 197201.31 | 319840.39 | 613396.44 | -1228864.85 | 209329.61 | 386157.63 | 222437.73 | 123566.92 | 212447.43 | 143169.45 | 1407084.17 | 2853436.5
Grand Total |  |  |  | 4196028.14 | 3525621.27 | 7836823 | 7052039.7 | 3362952.03 | 4636483.46 | 6178545.46 | 4248734.66 | 6317325.27 | 8415981.47 | 2470645.12 | 19191611.56 | 77432791.14

## 800062522
Pin: 4847 | Project: DCR
Order: 800062522 | 800062522- DCR: Preliminary Engineering, Licensing
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  |  | 10.92 | 90.35 | [6 empty] | 101.27
|  | Labor Total | [5 empty] | 10.92 | 90.35 | [6 empty] | 101.27
| BP&FM Total | [6 empty] | 10.92 | 90.35 | [6 empty] | 101.27
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 | [7 empty] | 415.01 |  |  |  |  | 415.01
|  | Contract Total | [8 empty] | 415.01 |  |  |  |  | 415.01
| Building/Facility Repairs & Maintenance Total | [9 empty] | 415.01 |  |  |  |  | 415.01
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  | -1397.74 | [9 empty] | -1397.74
|  | Contract Total |  |  |  | -1397.74 | [9 empty] | -1397.74
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  |  | -1397.74 | [9 empty] | -1397.74
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 101094.83 |  |  | 101094.83
|  |  | Contract Entries <$50,000 | [8 empty] | -101094.83 |  |  |  | -101094.83
|  | Contract Total | [9 empty] | -101094.83 | 101094.83 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -101094.83 | 101094.83 |  |  | 0
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | [8 empty] | 45 |  | 1885 |  | 1930
|  | Contract Total | [9 empty] | 45 |  | 1885 |  | 1930
| Environmental/Safety Professional Servic Total | [10 empty] | 45 |  | 1885 |  | 1930
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  |  | -13.97 | -812.15 |  |  |  | 101092.09 | -101094.83 | -667.23 | -58.81 | -1554.9
|  | IMM Correction Total |  |  |  |  | -13.97 | -812.15 |  |  |  | 101092.09 | -101094.83 | -667.23 | -58.81 | -1554.9
| IMM/Allocated - Correction Total | [5 empty] | -13.97 | -812.15 |  |  |  | 101092.09 | -101094.83 | -667.23 | -58.81 | -1554.9
| Labor - Other | Labor | Labor Entries <$5,000 |  |  |  |  | 3.85 | 49.8 | [6 empty] | 53.65
|  | Labor Total | [5 empty] | 3.85 | 49.8 | [6 empty] | 53.65
| Labor - Other Total | [6 empty] | 3.85 | 49.8 | [6 empty] | 53.65
| Other | Other | Other |  | 50669.16 | 43489.63 | 47023.07 |  |  | 251255.11 | 67131.67 |  | 282804.69 |  |  | 742373.33
|  | Other Total |  |  | 50669.16 | 43489.63 | 47023.07 |  |  | 251255.11 | 67131.67 |  | 282804.69 |  |  | 742373.33
| Other Total |  |  |  | 50669.16 | 43489.63 | 47023.07 |  |  | 251255.11 | 67131.67 |  | 282804.69 |  |  | 742373.33
| VRZN BUS TELECONF | Labor | Labor Entries <$5,000 | [5 empty] | 0 | [6 empty] | 0
|  | Labor Total | [6 empty] | 0 | [6 empty] | 0
| VRZN BUS TELECONF Total | [7 empty] | 0 | [6 empty] | 0
| WEBEX | Labor | Labor Entries <$5,000 | [5 empty] | 45.14 | [6 empty] | 45.14
|  | Labor Total | [6 empty] | 45.14 | [6 empty] | 45.14
| WEBEX Total | [7 empty] | 45.14 | [6 empty] | 45.14
1. Project Support Total |  |  |  |  | 50669.16 | 42091.89 | 47009.1 | -797.38 | 185.29 | 251255.11 | 67546.68 | 42.26 | 282804.69 | 1217.77 | -58.81 | 741965.76
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  | 781 | 994 | [8 empty] | 1775
|  |  | KENNY CONSTRUCTION COMPANY |  |  |  | 56906.36 | [8 empty] | 56906.36
|  | Contract Total |  |  |  | 781 | 57900.36 | [8 empty] | 58681.36
| Construction Management Services Total |  |  |  |  | 781 | 57900.36 | [8 empty] | 58681.36
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 |  |  | 560 | [9 empty] | 560
|  | Contract Total |  |  |  | 560 | [9 empty] | 560
| Decontamination & Waste Disposal Service Total |  |  |  |  | 560 | [9 empty] | 560
| Electrical Construction | Contract | Contract Entries <$50,000 |  |  |  | 1369.93 | [8 empty] | 1369.93
|  |  | KENNY CONSTRUCTION COMPANY |  |  |  | 61029.2 | [8 empty] | 61029.2
|  | Contract Total |  |  |  |  | 62399.13 | [8 empty] | 62399.13
| Electrical Construction Total | [5 empty] | 62399.13 | [8 empty] | 62399.13
| Electrical Constructioni | Contract | Contract Entries <$50,000 |  |  |  | 2752.91 | [8 empty] | 2752.91
|  | Contract Total |  |  |  |  | 2752.91 | [8 empty] | 2752.91
| Electrical Constructioni Total | [5 empty] | 2752.91 | [8 empty] | 2752.91
| Mechanical Services | Contract | Contract Entries <$50,000 |  |  | 775 | [7 empty] | 7025 |  | 7800
|  | Contract Total |  |  |  | 775 | [7 empty] | 7025 |  | 7800
| Mechanical Services Total |  |  |  |  | 775 | [7 empty] | 7025 |  | 7800
3. Construction Total | [5 empty] | 2116 | 123052.4 | [6 empty] | 7025 |  | 132193.4
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 |  |  | 4518.97 | 812.15 | 0.63 | 4.99 |  | 2.74 | -666.93 | 667.23 | 1169.88 | 4233.75 | 10743.41
|  |  | Law/TDBU-DPV2 Petition-Modify CEQA Issue | 26985.45 | 8755 |  | 7341.4 | 10140.48 | 10211 | 6587.5 | 26569 |  | 7835.2 | 29372.15 |  | 133797.18
|  | Chargeback Total |  | 26985.45 | 8755 | 4518.97 | 8153.55 | 10141.11 | 10215.99 | 6587.5 | 26571.74 | -666.93 | 8502.43 | 30542.03 | 4233.75 | 144540.59
| Chargebacks Total |  |  | 26985.45 | 8755 | 4518.97 | 8153.55 | 10141.11 | 10215.99 | 6587.5 | 26571.74 | -666.93 | 8502.43 | 30542.03 | 4233.75 | 144540.59
| Labor - Other | Labor | Labor Entries <$5,000 |  | 2.67 | 37.05 | 3949.98 | 4.06 | 25.46 |  | 17.01 | -3213.38 | 5246.82 | 95.34 |  | 6165.01
|  | Labor Total |  |  | 2.67 | 37.05 | 3949.98 | 4.06 | 25.46 |  | 17.01 | -3213.38 | 5246.82 | 95.34 |  | 6165.01
| Labor - Other Total |  |  |  | 2.67 | 37.05 | 3949.98 | 4.06 | 25.46 |  | 17.01 | -3213.38 | 5246.82 | 95.34 |  | 6165.01
4. Allocated Total |  |  |  | 26985.45 | 8757.67 | 4556.02 | 12103.53 | 10145.17 | 10241.45 | 6587.5 | 26588.75 | -3880.31 | 13749.25 | 30637.37 | 4233.75 | 150705.6
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 105001.27 | 6295.82 | [6 empty] | 111525.1 | 222822.19
|  |  | AFUDC - Debt/Equity |  | -398143 | -34771.17 | 34771.17 | [8 empty] | -398143
|  |  | Capitalized Overhead - A&G | 1506.05 | 1740.98 | 1738.17 | 6496.11 | 778.01 | 372.13 | 9053.6 | 2662.65 | -171.94 | 7662 | 1027.49 | 117.22 | 32982.47
|  |  | Capitalized Overhead - Inj & Damages |  | 87.5 | 45.94 | 42.92 | -7.07 | 0.21 | 229.82 | 87.51 | 88.05 | 592.82 | 0.98 | 0.4 | 1169.08
|  |  | Capitalized Overhead - P&B/Payroll Tax |  |  |  |  | 22.28 | 115.79 | [6 empty] | 138.07
|  |  | Corporate Overheads Correction |  |  |  |  | -290358.67 | [7 empty] | -290358.67
|  |  | Non-Budgeted WO Pstngs- WO/WBS Pstg - Co |  | 398143 | [10 empty] | 398143
|  | Non Budgeted Total |  | 1506.05 | 1828.48 | -32987.06 | 146311.47 | -283269.63 | 488.13 | 9283.42 | 2750.16 | -83.89 | 8254.82 | 1028.47 | 111642.72 | -33246.86
| Non Budget - Other Total |  |  | 1506.05 | 1828.48 | -32987.06 | 146311.47 | -283269.63 | 488.13 | 9283.42 | 2750.16 | -83.89 | 8254.82 | 1028.47 | 111642.72 | -33246.86
5. Corporate Overhead Total |  |  |  | 1506.05 | 1828.48 | -32987.06 | 146311.47 | -283269.63 | 488.13 | 9283.42 | 2750.16 | -83.89 | 8254.82 | 1028.47 | 111642.72 | -33246.86
Grand Total |  |  |  | 28491.5 | 61255.31 | 15776.85 | 328476.5 | -273921.84 | 10914.87 | 267126.03 | 96885.59 | -3921.94 | 304808.76 | 39908.61 | 115817.66 | 991617.9

## 800062494
Pin: 4847 | Project: DCR
Order: 800062494 | 800062494- I: Devers - Colorado River 500KV No.2 T/
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  | 92.58 | 365.5 | 10.92 | 161.29 | 349.94 | 806 | 3466.12 | 4827.45 | 2645.88 | 3241.54 | 15967.22
|  | Labor Total |  |  |  | 92.58 | 365.5 | 10.92 | 161.29 | 349.94 | 806 | 3466.12 | 4827.45 | 2645.88 | 3241.54 | 15967.22
| BP&FM Total |  |  |  |  | 92.58 | 365.5 | 10.92 | 161.29 | 349.94 | 806 | 3466.12 | 4827.45 | 2645.88 | 3241.54 | 15967.22
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 |  |  |  |  | 1432 | [7 empty] | 1432
|  | Contract Total | [5 empty] | 1432 | [7 empty] | 1432
| Building/Facility Repairs & Maintenance Total | [6 empty] | 1432 | [7 empty] | 1432
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Con - Consults/Prof Srvcs/Out Ord to Ord | 75847.83 |  |  |  |  | 76458.62 | 66520.02 | 71837.95 | 210851.62 |  |  | 760266.2 | 1261782.24
|  |  | Contract Entries <$50,000 |  |  | 32083.92 | [9 empty] | 32083.92
|  | Contract Total |  | 75847.83 |  | 32083.92 |  |  | 76458.62 | 66520.02 | 71837.95 | 210851.62 |  |  | 760266.2 | 1293866.16
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 75847.83 |  | 32083.92 |  |  | 76458.62 | 66520.02 | 71837.95 | 210851.62 |  |  | 760266.2 | 1293866.16
| Consultants - Engineering/Technical | Contract | Contract Entries <$50,000 | [9 empty] | 5164.21 |  |  | 5164.21
|  | Contract Total | [10 empty] | 5164.21 |  |  | 5164.21
| Consultants - Engineering/Technical Total | [11 empty] | 5164.21 |  |  | 5164.21
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 7487415.02 |  |  | 7487415.02
|  |  | Contract Entries <$50,000 | [8 empty] | -7487415.02 |  |  |  | -7487415.02
|  | Contract Total | [9 empty] | -7487415.02 | 7487415.02 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -7487415.02 | 7487415.02 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  | 8929.45 | 812.7 | 8169.02 | [8 empty] | 17911.17
|  | Contract Total |  |  | 8929.45 | 812.7 | 8169.02 | [8 empty] | 17911.17
| Contract Consult/Contract Ord to Ord Total |  |  |  | 8929.45 | 812.7 | 8169.02 | [8 empty] | 17911.17
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 |  | 62.06 | 325.8 | 341.7 | 544.85 | 1966.34 | 2772.76 | 1716.46 | 3133.95 | 3638.17 | 9770.11 | 405.63 | 24677.83
|  | Labor Total |  |  | 62.06 | 325.8 | 341.7 | 544.85 | 1966.34 | 2772.76 | 1716.46 | 3133.95 | 3638.17 | 9770.11 | 405.63 | 24677.83
| EAST GRID MGMTCENTER Total |  |  |  | 62.06 | 325.8 | 341.7 | 544.85 | 1966.34 | 2772.76 | 1716.46 | 3133.95 | 3638.17 | 9770.11 | 405.63 | 24677.83
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | 214.21 | 451.42 | [9 empty] | 9024.68 | 9690.31
|  | Labor Total |  | 214.21 | 451.42 | [9 empty] | 9024.68 | 9690.31
| ELEC SYS PLANNING Total |  |  | 214.21 | 451.42 | [9 empty] | 9024.68 | 9690.31
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 574.08 | 166.9 | 155.91 |  |  | 49.27 | 51.54 |  |  |  |  | 997.7
|  | Labor Total |  |  | 574.08 | 166.9 | 155.91 |  |  | 49.27 | 51.54 |  |  |  |  | 997.7
| ENG ADVANCEMENT Total |  |  |  | 574.08 | 166.9 | 155.91 |  |  | 49.27 | 51.54 |  |  |  |  | 997.7
| ENGINEERING | Labor | Engineer Sr | [9 empty] | 5078.4 | 6030.6 |  | 11109
|  |  | Labor Entries <$5,000 | 15470.19 | 13389.38 | 18401.04 | 18191.33 | 20365.5 | 20544.42 | 17723.48 | 25876.65 | 13585.11 | 8082.08 | 9979.74 |  | 181608.92
|  | Labor Total |  | 15470.19 | 13389.38 | 18401.04 | 18191.33 | 20365.5 | 20544.42 | 17723.48 | 25876.65 | 13585.11 | 13160.48 | 16010.34 |  | 192717.92
| ENGINEERING Total |  |  | 15470.19 | 13389.38 | 18401.04 | 18191.33 | 20365.5 | 20544.42 | 17723.48 | 25876.65 | 13585.11 | 13160.48 | 16010.34 |  | 192717.92
| Engineering/Technical Professional Servi | Contract | BUREAU VERITAS NORTH AMERICA INC |  | 77448.9 |  | 81565.3 |  |  | 132133 |  |  | 259726.5 | 89655 | 221866.5 | 862395.2
|  |  | Contract Entries <$50,000 | 1840 | 1990.12 |  | 46752.23 |  | 23014.78 | 166.5 | 12109.36 | 849.09 | 89581.53 | 29009.26 | 89573.24 | 294886.11
|  |  | MESA ASSOCIATES INC. |  | 63190.01 | [6 empty] | 58173.01 |  |  |  | 121363.02
|  |  | NINYO & MOORE | [11 empty] | 108917.89 | 108917.89
|  | Contract Total |  | 1840 | 142629.03 |  | 128317.53 |  | 23014.78 | 132299.5 | 12109.36 | 59022.1 | 349308.03 | 118664.26 | 420357.63 | 1387562.22
| Engineering/Technical Professional Servi Total |  |  | 1840 | 142629.03 |  | 128317.53 |  | 23014.78 | 132299.5 | 12109.36 | 59022.1 | 349308.03 | 118664.26 | 420357.63 | 1387562.22
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 18225.01 |  | 4748.78 |  | 2668.84 |  |  |  | 2974.52 | 44011.13 |  | 15067.39 | 87695.67
|  | Contract Total |  | 18225.01 |  | 4748.78 |  | 2668.84 |  |  |  | 2974.52 | 44011.13 |  | 15067.39 | 87695.67
| Environmental/Safety Professional Servic Total |  |  | 18225.01 |  | 4748.78 |  | 2668.84 |  |  |  | 2974.52 | 44011.13 |  | 15067.39 | 87695.67
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 63416.23 | 47741.19 | 50486.23 | 50622.85 | 46411.86 | 59469.64 | 7107.36 | -11848.94 | 20253324.22 | -20330803.08 | -142900.07 | -29016.56 | 64010.93
|  | IMM Correction Total |  | 63416.23 | 47741.19 | 50486.23 | 50622.85 | 46411.86 | 59469.64 | 7107.36 | -11848.94 | 20253324.22 | -20330803.08 | -142900.07 | -29016.56 | 64010.93
| IMM/Allocated - Correction Total |  |  | 63416.23 | 47741.19 | 50486.23 | 50622.85 | 46411.86 | 59469.64 | 7107.36 | -11848.94 | 20253324.22 | -20330803.08 | -142900.07 | -29016.56 | 64010.93
| ITBI (HCC) | Labor | Labor Entries <$5,000 |  |  |  | 216.93 | [8 empty] | 216.93
|  | Labor Total |  |  |  |  | 216.93 | [8 empty] | 216.93
| ITBI (HCC) Total | [5 empty] | 216.93 | [8 empty] | 216.93
| Labor - Other | Labor | Labor - Other | [9 empty] | 38330.04 |  |  | 38330.04
|  |  | Labor Correction | [9 empty] | 190696.49 |  |  | 190696.49
|  |  | Labor Entries <$5,000 | 1616.07 | 5608.17 | -2231.14 | 180.73 | 4400.01 | 1781.91 | 2107.53 | 4103.74 | 1682916.07 | -1903182.51 | -4860.3 | 4273.56 | -203286.16
|  | Labor Total |  | 1616.07 | 5608.17 | -2231.14 | 180.73 | 4400.01 | 1781.91 | 2107.53 | 4103.74 | 1682916.07 | -1674155.98 | -4860.3 | 4273.56 | 25740.37
| Labor - Other Total |  |  | 1616.07 | 5608.17 | -2231.14 | 180.73 | 4400.01 | 1781.91 | 2107.53 | 4103.74 | 1682916.07 | -1674155.98 | -4860.3 | 4273.56 | 25740.37
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | [8 empty] | 478.71 | 1459.42 | 1266.27 | 320.91 | 3525.31
|  | Labor Total | [9 empty] | 478.71 | 1459.42 | 1266.27 | 320.91 | 3525.31
| MAJOR PROJECT ORG Total | [10 empty] | 478.71 | 1459.42 | 1266.27 | 320.91 | 3525.31
| Other | Other | Other | 227016.97 | -885772.14 | 2561696.26 | -1938487.31 | 6051221.07 | -239339.99 | 4944071.15 | 3936717.59 | -9471511.13 | 15566888.59 | 1591328.8 | -5031630.85 | 17312199.01
|  | Other Total |  | 227016.97 | -885772.14 | 2561696.26 | -1938487.31 | 6051221.07 | -239339.99 | 4944071.15 | 3936717.59 | -9471511.13 | 15566888.59 | 1591328.8 | -5031630.85 | 17312199.01
| Other Total |  |  | 227016.97 | -885772.14 | 2561696.26 | -1938487.31 | 6051221.07 | -239339.99 | 4944071.15 | 3936717.59 | -9471511.13 | 15566888.59 | 1591328.8 | -5031630.85 | 17312199.01
| SOUTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [10 empty] | 1603.81 |  | 1603.81
|  | Labor Total | [11 empty] | 1603.81 |  | 1603.81
| SOUTH GRIDMGMTCENTER Total | [12 empty] | 1603.81 |  | 1603.81
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 |  | 207.47 |  | 424.97 | [8 empty] | 632.44
|  | Labor Total |  |  | 207.47 |  | 424.97 | [8 empty] | 632.44
| TEC SRVCS SUMMARY Total |  |  |  | 207.47 |  | 424.97 | [8 empty] | 632.44
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -42861.14 | 42861.14 |  |  | 0
|  | Contract Total | [9 empty] | -42861.14 | 42861.14 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -42861.14 | 42861.14 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 4628.29 | 16127.21 | 19702.16 | 18395.65 | 13093.01 | 30388.55 | 72289 | 22266.6 | 69144.98 | 46796.13 | 35995.72 | 10558.8 | 359386.1
|  | Contract Total |  | 4628.29 | 16127.21 | 19702.16 | 18395.65 | 13093.01 | 30388.55 | 72289 | 22266.6 | 69144.98 | 46796.13 | 35995.72 | 10558.8 | 359386.1
| Temporary/Supplementary - Technical/Prof Total |  |  | 4628.29 | 16127.21 | 19702.16 | 18395.65 | 13093.01 | 30388.55 | 72289 | 22266.6 | 69144.98 | 46796.13 | 35995.72 | 10558.8 | 359386.1
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 284.52 | 1328.56 |  | 298 | 265.15 | 310.42 | 298 | 146.08 | 829.47 | 3090.53 | 933.08 | 1920.99 | 9704.8
|  | Contract Total |  | 284.52 | 1328.56 |  | 298 | 265.15 | 310.42 | 298 | 146.08 | 829.47 | 3090.53 | 933.08 | 1920.99 | 9704.8
| Temporary/Supplementary - Trade/Labor Total |  |  | 284.52 | 1328.56 |  | 298 | 265.15 | 310.42 | 298 | 146.08 | 829.47 | 3090.53 | 933.08 | 1920.99 | 9704.8
| TRANSMISSION | Labor | Labor Entries <$5,000 | 46.84 |  |  | 595.01 | 188.9 | 71.19 | 71.16 | 71.27 |  |  | 71.75 | 7826.6 | 8942.72
|  |  | TRANSMISSION / Mgr-Prj/Prod | [11 empty] | 5807.32 | 5807.32
|  | Labor Total |  | 46.84 |  |  | 595.01 | 188.9 | 71.19 | 71.16 | 71.27 |  |  | 71.75 | 13633.92 | 14750.04
| TRANSMISSION Total |  |  | 46.84 |  |  | 595.01 | 188.9 | 71.19 | 71.16 | 71.27 |  |  | 71.75 | 13633.92 | 14750.04
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 4656.64 | 10242.47 | 7303.26 | 12871.57 | 10780.87 | 11562.33 | 11203.12 | 15662.47 | 9603.63 | 9008.29 | 5286.43 | 1903.2 | 110084.28
|  |  | Mgr-Prj/Prod |  |  | 13177.47 |  | 5227.94 | 5924.98 |  |  | 6583.42 | 5189.2 | 17335.65 |  | 53438.66
|  | Labor Total |  | 4656.64 | 10242.47 | 20480.73 | 12871.57 | 16008.81 | 17487.31 | 11203.12 | 15662.47 | 16187.05 | 14197.49 | 22622.08 | 1903.2 | 163522.94
| TRNS CAPITAL Total |  |  | 4656.64 | 10242.47 | 20480.73 | 12871.57 | 16008.81 | 17487.31 | 11203.12 | 15662.47 | 16187.05 | 14197.49 | 22622.08 | 1903.2 | 163522.94
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 |  | 1332 |  | 1051.4 |  |  |  | 4928.4 |  | 52 |  | 6327 | 13690.8
|  | Labor Total |  |  | 1332 |  | 1051.4 |  |  |  | 4928.4 |  | 52 |  | 6327 | 13690.8
| TSD-Aircraft - Fixed Total |  |  |  | 1332 |  | 1051.4 |  |  |  | 4928.4 |  | 52 |  | 6327 | 13690.8
1. Project Support Total |  |  |  | 413262.8 | -637149.65 | 2706765.96 | -1698289.21 | 6156610.92 | -7685.52 | 5256862.29 | 4084445.17 | 5314126.63 | 1577910.73 | 1653151.73 | -3813345.96 | 21006665.89
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 289.3 |  | 288.3 |  | 577.6
|  | Material - Direct Purchase Total | [9 empty] | 289.3 |  | 288.3 |  | 577.6
| Building, Shop & Industrial Products/Eqp Total | [10 empty] | 289.3 |  | 288.3 |  | 577.6
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -1240.49 | 1240.49 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -1240.49 | 1240.49 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -1240.49 | 1240.49 |  |  | 0
| Material - Inventory | Material | Material - Inventory |  |  |  | 0 |  |  |  |  | -100.5 | 100.5 |  |  | 0
|  | Material Total |  |  |  |  | 0 |  |  |  |  | -100.5 | 100.5 |  |  | 0
| Material - Inventory Total | [5 empty] | 0 |  |  |  |  | -100.5 | 100.5 |  |  | 0
| Material - Other | Material | Material - Other | 149658.28 | 91785.93 | 117852.23 | 74412.76 | -70497.88 | 134927.17 | 136657.07 | 164919.76 | 178498.21 | 174467.27 | 263503.48 | 63241.09 | 1479425.37
|  | Material Total |  | 149658.28 | 91785.93 | 117852.23 | 74412.76 | -70497.88 | 134927.17 | 136657.07 | 164919.76 | 178498.21 | 174467.27 | 263503.48 | 63241.09 | 1479425.37
| Material - Other Total |  |  | 149658.28 | 91785.93 | 117852.23 | 74412.76 | -70497.88 | 134927.17 | 136657.07 | 164919.76 | 178498.21 | 174467.27 | 263503.48 | 63241.09 | 1479425.37
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 129.29 | -1618.65 |  |  | 96.96 |  |  | 312.68 | 432.8 | -646.92
|  | Material - Direct Purchase Total |  |  |  |  | 129.29 | -1618.65 |  |  | 96.96 |  |  | 312.68 | 432.8 | -646.92
| Office & Office Support Products-DP Total | [5 empty] | 129.29 | -1618.65 |  |  | 96.96 |  |  | 312.68 | 432.8 | -646.92
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | 7146.69 | -1941.3 |  |  | 4945.02 |  |  | 1463 |  | 3797.5 |  | 3857 | 19267.91
|  |  | ONE SOURCE DISTRIBUTORS INC | 18487.05 | 577238.94 | 595438.19 | 46263 | [6 empty] | 34956 |  | 1272383.18
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [11 empty] | 84378.58 | 84378.58
|  | Material - Direct Purchase Total |  | 25633.74 | 575297.64 | 595438.19 | 46263 | 4945.02 |  |  | 1463 |  | 3797.5 | 34956 | 88235.58 | 1376029.67
| Pole Line Hdwe & Connectors-DP Total |  |  | 25633.74 | 575297.64 | 595438.19 | 46263 | 4945.02 |  |  | 1463 |  | 3797.5 | 34956 | 88235.58 | 1376029.67
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | ON-RAMP WIRELESS, INC. | [7 empty] | 115855 |  |  | 31746.92 |  | 147601.92
|  | Material - Direct Purchase Total | [8 empty] | 115855 |  |  | 31746.92 |  | 147601.92
| Power Systems, Batteries and Light-DP Total | [9 empty] | 115855 |  |  | 31746.92 |  | 147601.92
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | [8 empty] | 29400 |  |  |  | 29400
|  | Material - Direct Purchase Total | [9 empty] | 29400 |  |  |  | 29400
| Steel / Fabricated / Structural-DP Total | [10 empty] | 29400 |  |  |  | 29400
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | FORMET | [11 empty] | 9384.32 | 9384.32
|  |  | Material Entries <$5,000 | 2623 |  | -17984.55 | 6947.95 | -519272.32 |  | 1538.6 | -40751.1 |  |  |  | -113906.34 | -680804.76
|  |  | SAE TOWERS | 527575.32 | 139325.07 | 316374.07 | 382132.74 | 1385015.16 | 616176.18 | 1129545.91 | 1304529.03 | 1284608.59 | 1448762.2 | 2947722.71 | 634363.05 | 12116130.03
|  | Material - Direct Purchase Total |  | 530198.32 | 139325.07 | 298389.52 | 389080.69 | 865742.84 | 616176.18 | 1131084.51 | 1263777.93 | 1284608.59 | 1448762.2 | 2947722.71 | 529841.03 | 11444709.59
| Steel Lattice Towers (T/S)-DP Total |  |  | 530198.32 | 139325.07 | 298389.52 | 389080.69 | 865742.84 | 616176.18 | 1131084.51 | 1263777.93 | 1284608.59 | 1448762.2 | 2947722.71 | 529841.03 | 11444709.59
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | SABRE COMMUNICATIONS CORPORATION |  |  |  |  | 15051 |  |  | 149565 |  |  |  |  | 164616
|  | Material - Direct Purchase Total | [5 empty] | 15051 |  |  | 149565 |  |  |  |  | 164616
| Towers/Poles, Steel & Concrete-DP Total | [6 empty] | 15051 |  |  | 149565 |  |  |  |  | 164616
| Transportation & Mobile Equip-DP | Material - Direct Purchase | CAZCOM, INC. | [6 empty] | 5524.37 | [5 empty] | 5524.37
|  |  | Material Entries <$5,000 |  |  | 326.87 |  | 1353.2 | 2055.99 |  |  | 5.87 |  | 24.03 |  | 3765.96
|  | Material - Direct Purchase Total |  |  |  | 326.87 |  | 1353.2 | 2055.99 | 5524.37 |  | 5.87 |  | 24.03 |  | 9290.33
| Transportation & Mobile Equip-DP Total |  |  |  |  | 326.87 |  | 1353.2 | 2055.99 | 5524.37 |  | 5.87 |  | 24.03 |  | 9290.33
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | AFL TELECOMMUNICATIONS LLC |  |  | 151960.89 | 227561.57 | 463076.91 | 615479.3 | 155868.23 | 11801.39 |  |  |  |  | 1625748.29
|  |  | Material Entries <$5,000 |  | 800.5 |  |  |  |  | -2.13 | -27800 |  |  |  |  | -27001.63
|  |  | SOUTHWIRE COMPANY | 757948.21 | 79851.61 | [10 empty] | 837799.82
|  | Material - Direct Purchase Total |  | 757948.21 | 80652.11 | 151960.89 | 227561.57 | 463076.91 | 615479.3 | 155866.1 | -15998.61 |  |  |  |  | 2436546.48
| Wire, Cable & Bus Bar-DP Total |  |  | 757948.21 | 80652.11 | 151960.89 | 227561.57 | 463076.91 | 615479.3 | 155866.1 | -15998.61 |  |  |  |  | 2436546.48
2. Material Total |  |  |  | 1463438.55 | 887060.75 | 1163967.7 | 737447.31 | 1278052.44 | 1368638.64 | 1429132.05 | 1679679.04 | 1491460.98 | 1628367.96 | 3278554.12 | 681750.5 | 17087550.04
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 25126.51 | 76858.77 | 55197.72 | 93548.38 | 30568.4 | 61573.2 | 105394.61 | 92026.63 | 74426.85 | 89143.26 | 27045.64 | 26993.22 | 757903.19
|  |  | KENNY CONSTRUCTION COMPANY | 159577.36 | 208408.31 | 272811.43 | 331686.65 | 356347.2 | 359224.66 | 402094.59 | 484246.18 | 551862.23 | 579530.71 | 621478.28 | 606399.23 | 4933666.83
|  |  | UTILITY LINE MANAGEMENT SERVICES | [11 empty] | 129044.27 | 129044.27
|  | Contract Total |  | 184703.87 | 285267.08 | 328009.15 | 425235.03 | 386915.6 | 420797.86 | 507489.2 | 576272.81 | 626289.08 | 668673.97 | 648523.92 | 762436.72 | 5820614.29
| Construction Management Services Total |  |  | 184703.87 | 285267.08 | 328009.15 | 425235.03 | 386915.6 | 420797.86 | 507489.2 | 576272.81 | 626289.08 | 668673.97 | 648523.92 | 762436.72 | 5820614.29
| Construction Services - Correction | Contract | Construction Services - Correction | [9 empty] | 50288.37 |  |  | 50288.37
|  |  | Contract Entries <$50,000 | [8 empty] | -50288.37 |  |  |  | -50288.37
|  | Contract Total | [9 empty] | -50288.37 | 50288.37 |  |  | 0
| Construction Services - Correction Total | [10 empty] | -50288.37 | 50288.37 |  |  | 0
| Construction Services - Other | Contract | Construction Services - Other | [5 empty] | 54343.34 | 176810.08 | 73866.4 |  |  | 58964.91 |  | 363984.73
|  |  | Contract Entries <$50,000 | 1199.73 | 2648.71 | 5215.8 | 11548.37 | 28828.96 |  |  |  | 4658.7 | 12547.38 |  | 6783.91 | 73431.56
|  | Contract Total |  | 1199.73 | 2648.71 | 5215.8 | 11548.37 | 28828.96 | 54343.34 | 176810.08 | 73866.4 | 4658.7 | 12547.38 | 58964.91 | 6783.91 | 437416.29
| Construction Services - Other Total |  |  | 1199.73 | 2648.71 | 5215.8 | 11548.37 | 28828.96 | 54343.34 | 176810.08 | 73866.4 | 4658.7 | 12547.38 | 58964.91 | 6783.91 | 437416.29
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | 704 | 734.8 | 352 |  | -352 | [7 empty] | 1438.8
|  | Contract Total |  | 704 | 734.8 | 352 |  | -352 | [7 empty] | 1438.8
| Construction, Civil/Structural Total |  |  | 704 | 734.8 | 352 |  | -352 | [7 empty] | 1438.8
| Construction, Earthwork | Contract | Contract Entries <$50,000 |  |  |  |  | -2597906 | [7 empty] | -2597906
|  | Contract Total | [5 empty] | -2597906 | [7 empty] | -2597906
| Construction, Earthwork Total | [6 empty] | -2597906 | [7 empty] | -2597906
| Construction, Property/Building | Contract | Contract Entries <$50,000 |  |  |  |  | 7135.83 | [7 empty] | 7135.83
|  | Contract Total | [5 empty] | 7135.83 | [7 empty] | 7135.83
| Construction, Property/Building Total | [6 empty] | 7135.83 | [7 empty] | 7135.83
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 328.79 | 328.79
|  | Labor Total | [12 empty] | 328.79 | 328.79
| ELEC SYS PLANNING Total | [13 empty] | 328.79 | 328.79
| Electrical Construction | Contract | Contract Entries <$50,000 | 31968.75 | 38631.5 | 70924.78 | 33764.59 | 41398.89 |  | 33857.76 | 23890.86 | 15487.75 | 62375.42 | 12595.98 | 9754.98 | 374651.26
|  |  | KENNY CONSTRUCTION COMPANY | 619754.81 | 414374.74 | 463115.83 | 588700.77 | 464347.1 | 470269.53 | 395166.41 | 429782.13 | 466790.4 | 395570.54 | 505697.78 | 448496.16 | 5662066.2
|  |  | PAR ELECTRICAL CONTRACTORS INC |  | 259394.4 |  | 714136.5 | 625213.8 | 4127201.1 | 5875461 | 10335608.1 | 16338129.3 | 11028755.23 |  | 45690164.59 | 94994064.02
|  | Contract Total |  | 651723.56 | 712400.64 | 534040.61 | 1336601.86 | 1130959.79 | 4597470.63 | 6304485.17 | 10789281.09 | 16820407.45 | 11486701.19 | 518293.76 | 46148415.73 | 101030781.48
| Electrical Construction Total |  |  | 651723.56 | 712400.64 | 534040.61 | 1336601.86 | 1130959.79 | 4597470.63 | 6304485.17 | 10789281.09 | 16820407.45 | 11486701.19 | 518293.76 | 46148415.73 | 101030781.48
| ENGINEERING | Labor | Labor Entries <$5,000 | [10 empty] | 162.87 |  | 162.87
|  | Labor Total | [11 empty] | 162.87 |  | 162.87
| ENGINEERING Total | [12 empty] | 162.87 |  | 162.87
| GRID OPS | Labor | Labor Entries <$5,000 |  |  | 330.95 | 608.71 | 329.93 | 199.01 | 194.96 | 918.82 | 268.54 | 678.93 | 611.66 | 2931.96 | 7073.47
|  | Labor Total |  |  |  | 330.95 | 608.71 | 329.93 | 199.01 | 194.96 | 918.82 | 268.54 | 678.93 | 611.66 | 2931.96 | 7073.47
| GRID OPS Total |  |  |  |  | 330.95 | 608.71 | 329.93 | 199.01 | 194.96 | 918.82 | 268.54 | 678.93 | 611.66 | 2931.96 | 7073.47
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [5 empty] | 5466.56 | [6 empty] | 5466.56
|  | Labor Total | [6 empty] | 5466.56 | [6 empty] | 5466.56
| S/E SUBS MTCETST&APP Total | [7 empty] | 5466.56 | [6 empty] | 5466.56
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 12760.92 | 11101.04 | 10147.79 | 1378 |  | 1378 | 867.5 | 1378 |  |  |  |  | 39011.25
|  | Contract Total |  | 12760.92 | 11101.04 | 10147.79 | 1378 |  | 1378 | 867.5 | 1378 |  |  |  |  | 39011.25
| Short Term Equipment Rent Total |  |  | 12760.92 | 11101.04 | 10147.79 | 1378 |  | 1378 | 867.5 | 1378 |  |  |  |  | 39011.25
| TRANSMISSION | Labor | Labor Entries <$5,000 | 45.69 |  |  | 444.46 | 205.33 | 267.46 |  | 73.02 |  |  | 1448.61 | 1283.47 | 3768.04
|  | Labor Total |  | 45.69 |  |  | 444.46 | 205.33 | 267.46 |  | 73.02 |  |  | 1448.61 | 1283.47 | 3768.04
| TRANSMISSION Total |  |  | 45.69 |  |  | 444.46 | 205.33 | 267.46 |  | 73.02 |  |  | 1448.61 | 1283.47 | 3768.04
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 3385.85 | 4174.82 | 5290.28 | 1922.76 | 2008.57 | 1705.57 | 1949.27 | 1846.42 | 1041.75 | 2172.4 | 1465.26 |  | 26962.95
|  | Labor Total |  | 3385.85 | 4174.82 | 5290.28 | 1922.76 | 2008.57 | 1705.57 | 1949.27 | 1846.42 | 1041.75 | 2172.4 | 1465.26 |  | 26962.95
| TRNS CAPITAL Total |  |  | 3385.85 | 4174.82 | 5290.28 | 1922.76 | 2008.57 | 1705.57 | 1949.27 | 1846.42 | 1041.75 | 2172.4 | 1465.26 |  | 26962.95
3. Construction Total |  |  |  | 854523.62 | 1016327.09 | 883386.58 | 1777739.19 | -1041873.99 | 5081628.43 | 6991796.18 | 11443636.56 | 17402377.15 | 12221062.24 | 1229470.99 | 46922180.58 | 104782254.62
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 31555.82 | 27027.68 | -702183.48 | 23205.31 | -43728.29 | 37844.26 | -644269.55 | 26350.96 | -49834.46 | 88882.23 | -332051.46 | -794042.16 | -2331243.14
|  |  | DPV2/DCR Project Mgmt Home Office Cost | 53703.18 | 62644.24 | 50461.85 | 67533.88 | 53569.44 | 54023.27 | 45516.91 | 69549.27 | 54110.07 | 51261.22 | 55435.95 | 63419.07 | 681228.35
|  |  | DPV2/DCR Project OE T/L Work | 301927.09 | 265421.45 | 279749.06 | 261569.69 | 263137.89 | 338471.91 | 302994.71 | 236312.05 | 237312.2 | 229406.12 | 250305.85 | 228297.78 | 3194905.8
|  |  | PDP-2010 Colorado Rvr to Devers-MPO | 1195471.19 | 805202.65 | 6556491.48 | 1959344.91 | 2074925.56 | 1807065.47 | 2508866.4 | 2677247.51 |  | 4171518.82 | 2791825.9 | 2368118.31 | 28916078.2
|  |  | PDP-DPV2 General Mtg Support-MPO | 24202.2 | 987775.23 | 70012.36 | 211737.88 | 105343.08 | 183595 | 200323.77 | 291577.87 |  | 328652.25 | 226682.07 | 130363.85 | 2760265.56
|  |  | PROCUREMENT TDBU | 15675.04 | 12930 | 12793.38 | 17051.47 |  | 41976.82 | 56010.79 | 85725.62 | 74684.8 | 142900.07 | 29016.56 | 316695.45 | 805460
|  |  | TDBU Vehicle Cost | 7676.82 | 7900.09 | [7 empty] | 12812.64 |  |  | 28389.55
|  | Chargeback Total |  | 1630211.34 | 2168901.34 | 6267324.65 | 2540443.14 | 2453247.68 | 2462976.73 | 2469443.03 | 3386763.28 | 316272.61 | 5025433.35 | 3021214.87 | 2312852.3 | 34055084.32
| Chargebacks Total |  |  | 1630211.34 | 2168901.34 | 6267324.65 | 2540443.14 | 2453247.68 | 2462976.73 | 2469443.03 | 3386763.28 | 316272.61 | 5025433.35 | 3021214.87 | 2312852.3 | 34055084.32
| Labor - Other | Labor | Division Overhead | 127282.69 | 170706.4 | 71342.12 | 79188.66 | 5098.5 | 283881.89 | 353194.12 | 532771.16 | 359944.42 | 1136995.25 | 44452.8 | 652556.88 | 3817414.89
|  |  | ENG Colorado River Devers | [11 empty] | 5021.61 | 5021.61
|  |  | Labor Entries <$5,000 | 7043.9 | 4884.25 | 2853.27 | 6089.82 | 12450.84 | 4194.18 | 3104.61 | 3918.98 | -39293.02 | 7929.36 | 4411.6 | 1542.87 | 19130.66
|  |  | Paid Absence |  | 5147.59 | 6050.69 | 6270.8 | 7220.98 | 5866.53 | 5175.96 | 7779.94 |  | 45572.07 | 6003.18 | 6111.54 | 101199.28
|  | Labor Total |  | 134326.59 | 180738.24 | 80246.08 | 91549.28 | 24770.32 | 293942.6 | 361474.69 | 544470.08 | 320651.4 | 1190496.68 | 54867.58 | 665232.9 | 3942766.44
| Labor - Other Total |  |  | 134326.59 | 180738.24 | 80246.08 | 91549.28 | 24770.32 | 293942.6 | 361474.69 | 544470.08 | 320651.4 | 1190496.68 | 54867.58 | 665232.9 | 3942766.44
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -170981.11 | 170981.11 |  |  | 0
|  | Overhead Total | [9 empty] | -170981.11 | 170981.11 |  |  | 0
| Overhead Correction Total | [10 empty] | -170981.11 | 170981.11 |  |  | 0
4. Allocated Total |  |  |  | 1764537.93 | 2349639.58 | 6347570.73 | 2631992.42 | 2478018 | 2756919.33 | 2830917.72 | 3931233.36 | 465942.9 | 6386911.14 | 3076082.45 | 2978085.2 | 37997850.76
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 525705.71 | 34598.62 | [6 empty] | 1502998.25 | 2063302.58
|  |  | Capitalized Overhead - A&G | 238501.24 | 132056.13 | 304821.38 | 192228.15 | 234940.23 | 337021.04 | 406247.71 | 486712.05 | 977880.07 | 479838.21 | 202188.82 | 1474417.96 | 5466852.99
|  |  | Capitalized Overhead - Inj & Damages | 2500.42 | 5182.4 | 7049.89 | 2058.81 | 22451.75 | 3283.07 | 1367.2 | 6469.18 | 10311.9 | -18473.9 | 5303.83 | 1926.76 | 49431.31
|  |  | Capitalized Overhead - P&B/Payroll Tax | 58946.52 | 108624 | 103653.47 | 127369.6 | 152979.77 | 127397.97 | 111189.12 | 95630.38 | -217857.65 | 168011.56 | 88232.16 | 203969.35 | 1128146.25
|  |  | Corporate Overheads Correction |  |  |  |  | -1657424 | [7 empty] | -1657424
|  | Non Budgeted Total |  | 299948.18 | 245862.53 | 415524.74 | 847362.27 | -1212453.63 | 467702.08 | 518804.03 | 588811.61 | 770334.32 | 629375.87 | 295724.81 | 3183312.32 | 7050309.13
| Non Budget - Other Total |  |  | 299948.18 | 245862.53 | 415524.74 | 847362.27 | -1212453.63 | 467702.08 | 518804.03 | 588811.61 | 770334.32 | 629375.87 | 295724.81 | 3183312.32 | 7050309.13
5. Corporate Overhead Total |  |  |  | 299948.18 | 245862.53 | 415524.74 | 847362.27 | -1212453.63 | 467702.08 | 518804.03 | 588811.61 | 770334.32 | 629375.87 | 295724.81 | 3183312.32 | 7050309.13
Grand Total |  |  |  | 4795711.08 | 3861740.3 | 11517215.71 | 4296251.98 | 7658353.74 | 9667202.96 | 17027512.27 | 21727805.74 | 25444241.98 | 22443627.94 | 9532984.1 | 49951982.64 | 187924630.44

## 800051691
Pin: 4847 | Project: DCR
Order: 800051691 | 800051691- 9219-2080/Devers-Valley 500kV T/L
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [9 empty] | 2012 Total | Grand Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 11 | 12
1. Project Support | HRealProp | Labor | Labor Entries <$5,000 | 284.17 | 2450.95 | 773.23 | 28.73 | 311.24 | 241.53 | 43.77 |  | 24.21 |  | 4157.83 | 4157.83
|  | Labor Total |  | 284.17 | 2450.95 | 773.23 | 28.73 | 311.24 | 241.53 | 43.77 |  | 24.21 |  | 4157.83 | 4157.83
| HRealProp Total |  |  | 284.17 | 2450.95 | 773.23 | 28.73 | 311.24 | 241.53 | 43.77 |  | 24.21 |  | 4157.83 | 4157.83
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -0.05 | -1.49 | -3.97 | -0.05 | -24.73 | -0.06 | -0.23 |  |  | -30.58 | -30.58
|  | IMM Correction Total |  |  | -0.05 | -1.49 | -3.97 | -0.05 | -24.73 | -0.06 | -0.23 |  |  | -30.58 | -30.58
| IMM/Allocated - Correction Total |  |  |  | -0.05 | -1.49 | -3.97 | -0.05 | -24.73 | -0.06 | -0.23 |  |  | -30.58 | -30.58
| Information System Professional Services | Contract | Contract Entries <$50,000 |  |  | 58.5 | [7 empty] | 58.5 | 58.5
|  | Contract Total |  |  |  | 58.5 | [7 empty] | 58.5 | 58.5
| Information System Professional Services Total |  |  |  |  | 58.5 | [7 empty] | 58.5 | 58.5
| Labor - Other | Labor | Labor Entries <$5,000 | 1.81 | 329.51 | -331.32 | 2.16 | 95.08 | -116.69 | 21.2 | -1.75 | -3.77 | 3.77 | -3.5527e-15 | -3.5527e-15
|  | Labor Total |  | 1.81 | 329.51 | -331.32 | 2.16 | 95.08 | -116.69 | 21.2 | -1.75 | -3.77 | 3.77 | -3.5527e-15 | -3.5527e-15
| Labor - Other Total |  |  | 1.81 | 329.51 | -331.32 | 2.16 | 95.08 | -116.69 | 21.2 | -1.75 | -3.77 | 3.77 | -3.5527e-15 | -3.5527e-15
| Other | Other | Other | 7.11 | 28.5 |  | 14.13 | 3557.7 |  | 35.05 |  |  |  | 3642.49 | 3642.49
|  | Other Total |  | 7.11 | 28.5 |  | 14.13 | 3557.7 |  | 35.05 |  |  |  | 3642.49 | 3642.49
| Other Total |  |  | 7.11 | 28.5 |  | 14.13 | 3557.7 |  | 35.05 |  |  |  | 3642.49 | 3642.49
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  | 187.78 | 543.7 |  | 180.56 | [5 empty] | 912.04 | 912.04
|  | Contract Total |  |  | 187.78 | 543.7 |  | 180.56 | [5 empty] | 912.04 | 912.04
| Temporary/Supplementary - Trade/Labor Total |  |  |  | 187.78 | 543.7 |  | 180.56 | [5 empty] | 912.04 | 912.04
1. Project Support Total |  |  |  | 293.09 | 2996.69 | 1042.62 | 41.05 | 4144.53 | 100.11 | 99.96 | -1.98 | 20.44 | 3.77 | 8740.28 | 8740.28
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 8.81 |  |  | 9.05 | 9.05 |  |  |  |  | 26.91 | 26.91
|  | Material - Direct Purchase Total |  |  | 8.81 |  |  | 9.05 | 9.05 |  |  |  |  | 26.91 | 26.91
| Transportation & Mobile Equip-DP Total |  |  |  | 8.81 |  |  | 9.05 | 9.05 |  |  |  |  | 26.91 | 26.91
2. Material Total |  |  |  |  | 8.81 |  |  | 9.05 | 9.05 |  |  |  |  | 26.91 | 26.91
3. Construction | HRealProp | Labor | Labor Entries <$5,000 |  |  | 1283.81 | [7 empty] | 1283.81 | 1283.81
|  | Labor Total |  |  |  | 1283.81 | [7 empty] | 1283.81 | 1283.81
| HRealProp Total |  |  |  |  | 1283.81 | [7 empty] | 1283.81 | 1283.81
3. Construction Total | [5 empty] | 1283.81 | [7 empty] | 1283.81 | 1283.81
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 0.05 | 1.49 | 3.97 | 0.05 | 24.73 | 0.06 | 0.23 |  |  |  | 30.58 | 30.58
|  | Chargeback Total |  | 0.05 | 1.49 | 3.97 | 0.05 | 24.73 | 0.06 | 0.23 |  |  |  | 30.58 | 30.58
| Chargebacks Total |  |  | 0.05 | 1.49 | 3.97 | 0.05 | 24.73 | 0.06 | 0.23 |  |  |  | 30.58 | 30.58
| Labor - Other | Labor | Labor Entries <$5,000 | 65.04 | 357.67 | 398.08 | 7.05 | 173.05 | 28.04 | 15.26 | -0.39 | 5.13 | 0.98 | 1049.91 | 1049.91
|  | Labor Total |  | 65.04 | 357.67 | 398.08 | 7.05 | 173.05 | 28.04 | 15.26 | -0.39 | 5.13 | 0.98 | 1049.91 | 1049.91
| Labor - Other Total |  |  | 65.04 | 357.67 | 398.08 | 7.05 | 173.05 | 28.04 | 15.26 | -0.39 | 5.13 | 0.98 | 1049.91 | 1049.91
4. Allocated Total |  |  |  | 65.09 | 359.16 | 402.05 | 7.1 | 197.78 | 28.1 | 15.49 | -0.39 | 5.13 | 0.98 | 1080.49 | 1080.49
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 12642.83 | 769.84 |  |  |  |  | 13117.51 | 26530.18 | 26530.18
|  | Non Budgeted Total |  |  |  |  | 12642.83 | 769.84 |  |  |  |  | 13117.51 | 26530.18 | 26530.18
| Non Budget - Other Total | [5 empty] | 12642.83 | 769.84 |  |  |  |  | 13117.51 | 26530.18 | 26530.18
5. Corporate Overhead Total | [6 empty] | 12642.83 | 769.84 |  |  |  |  | 13117.51 | 26530.18 | 26530.18
Grand Total |  |  |  | 358.18 | 3364.66 | 2728.48 | 12690.98 | 5121.2 | 137.26 | 115.45 | -2.37 | 25.57 | 13122.26 | 37661.67 | 37661.67

## 800051690
Pin: 4847 | Project: DCR
Order: 800051690 | 800051690- 9219-2079/FERC-DEVERS-PALO VERDE ACQ
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | HRealProp | Labor | Labor Entries <$5,000 | 2280.16 | 300.11 | 2030.69 | 293.32 | 736.88 | 681.92 | 1001.69 | 763.83 | 1687.79 | 837.76 | 203 | 146.63 | 10963.78
|  | Labor Total |  | 2280.16 | 300.11 | 2030.69 | 293.32 | 736.88 | 681.92 | 1001.69 | 763.83 | 1687.79 | 837.76 | 203 | 146.63 | 10963.78
| HRealProp Total |  |  | 2280.16 | 300.11 | 2030.69 | 293.32 | 736.88 | 681.92 | 1001.69 | 763.83 | 1687.79 | 837.76 | 203 | 146.63 | 10963.78
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -9 |  | -6.5 | -0.08 | -0.49 |  | -3.3 | -0.1 | -5.16 | -0.18 |  | -24.81
|  | IMM Correction Total |  |  | -9 |  | -6.5 | -0.08 | -0.49 |  | -3.3 | -0.1 | -5.16 | -0.18 |  | -24.81
| IMM/Allocated - Correction Total |  |  |  | -9 |  | -6.5 | -0.08 | -0.49 |  | -3.3 | -0.1 | -5.16 | -0.18 |  | -24.81
| Information System Professional Services | Contract | Contract Entries <$50,000 | [8 empty] | 6.38 |  |  |  | 6.38
|  | Contract Total | [9 empty] | 6.38 |  |  |  | 6.38
| Information System Professional Services Total | [10 empty] | 6.38 |  |  |  | 6.38
| Labor - Other | Labor | Labor Entries <$5,000 | -66.24 | 106.87 | -57.4 | 16.77 | 200.65 | -289.14 | 67.45 | 55.88 | 17.66 | 134.6 | -97.51 | 23.62 | 113.21
|  | Labor Total |  | -66.24 | 106.87 | -57.4 | 16.77 | 200.65 | -289.14 | 67.45 | 55.88 | 17.66 | 134.6 | -97.51 | 23.62 | 113.21
| Labor - Other Total |  |  | -66.24 | 106.87 | -57.4 | 16.77 | 200.65 | -289.14 | 67.45 | 55.88 | 17.66 | 134.6 | -97.51 | 23.62 | 113.21
| Other | Other | Other | 12265 | -912 | 1059.58 |  | 73.9 |  | 4708 | 4491.2 | 4500 | 2040 |  | 26003 | 54228.68
|  | Other Total |  | 12265 | -912 | 1059.58 |  | 73.9 |  | 4708 | 4491.2 | 4500 | 2040 |  | 26003 | 54228.68
| Other Total |  |  | 12265 | -912 | 1059.58 |  | 73.9 |  | 4708 | 4491.2 | 4500 | 2040 |  | 26003 | 54228.68
| RURALS | Labor | Labor Entries <$5,000 | [7 empty] | 139.42 |  |  |  |  | 139.42
|  | Labor Total | [8 empty] | 139.42 |  |  |  |  | 139.42
| RURALS Total | [9 empty] | 139.42 |  |  |  |  | 139.42
1. Project Support Total |  |  |  | 14478.92 | -514.02 | 3032.87 | 303.59 | 1011.35 | 392.29 | 5777.14 | 5447.03 | 6211.73 | 3007.2 | 105.31 | 26173.25 | 65426.66
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 11.99 |  |  |  |  | 25.11 | 26.63 |  |  | 63.73
|  | Material - Direct Purchase Total |  |  |  |  | 11.99 |  |  |  |  | 25.11 | 26.63 |  |  | 63.73
| Transportation & Mobile Equip-DP Total | [5 empty] | 11.99 |  |  |  |  | 25.11 | 26.63 |  |  | 63.73
2. Material Total | [6 empty] | 11.99 |  |  |  |  | 25.11 | 26.63 |  |  | 63.73
3. Construction | HRealProp | Labor | Labor Entries <$5,000 | 568.83 | [11 empty] | 568.83
|  | Labor Total |  | 568.83 | [11 empty] | 568.83
| HRealProp Total |  |  | 568.83 | [11 empty] | 568.83
3. Construction Total |  |  |  | 568.83 | [11 empty] | 568.83
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 9 |  | 6.5 | 0.08 | 0.49 |  | 3.3 | 0.1 | 5.16 | 0.18 |  | 12.14 | 36.95
|  | Chargeback Total |  | 9 |  | 6.5 | 0.08 | 0.49 |  | 3.3 | 0.1 | 5.16 | 0.18 |  | 12.14 | 36.95
| Chargebacks Total |  |  | 9 |  | 6.5 | 0.08 | 0.49 |  | 3.3 | 0.1 | 5.16 | 0.18 |  | 12.14 | 36.95
| Labor - Other | Labor | Labor Entries <$5,000 | 663.37 | 90.75 | 461.7 | 69.42 | 210.69 | 87.59 | 238.49 | 207.94 | 399.09 | 242.07 | 23.71 | 83.46 | 2778.28
|  | Labor Total |  | 663.37 | 90.75 | 461.7 | 69.42 | 210.69 | 87.59 | 238.49 | 207.94 | 399.09 | 242.07 | 23.71 | 83.46 | 2778.28
| Labor - Other Total |  |  | 663.37 | 90.75 | 461.7 | 69.42 | 210.69 | 87.59 | 238.49 | 207.94 | 399.09 | 242.07 | 23.71 | 83.46 | 2778.28
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -30.41 | -30.41
|  | Overhead Total | [12 empty] | -30.41 | -30.41
| Overhead Correction Total | [13 empty] | -30.41 | -30.41
4. Allocated Total |  |  |  | 672.37 | 90.75 | 468.2 | 69.5 | 211.18 | 87.59 | 241.79 | 208.04 | 404.25 | 242.25 | 23.71 | 65.19 | 2784.82
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 5765.42 | 350.8 | [6 empty] | 6263.41 | 12379.63
|  | Non Budgeted Total |  |  |  |  | 5765.42 | 350.8 | [6 empty] | 6263.41 | 12379.63
| Non Budget - Other Total | [5 empty] | 5765.42 | 350.8 | [6 empty] | 6263.41 | 12379.63
5. Corporate Overhead Total | [6 empty] | 5765.42 | 350.8 | [6 empty] | 6263.41 | 12379.63
Grand Total |  |  |  | 15720.12 | -423.27 | 3501.07 | 6150.5 | 1573.33 | 479.88 | 6018.93 | 5655.07 | 6641.09 | 3276.08 | 129.02 | 32501.85 | 81223.67

## TRTP Seg 3B
WO | SumOfYTD2012 | Order | Project
900604086- TRTP Segment 3B: Highwind-Windhub: Insta | 9616089.22 | 900604086 | TRTP Segment 3B
800452215- ACQ- SEGMENT 3B 220 | 122511.46 | 800452215 | TRTP Segment 3B
800063658- I: TRTP 3B: Highwind SS Work: Grade and | 7119964.28 | 800063658 | TRTP Segment 3B
800062547- I: TRTP 3B: Windhub to Highwind 230 kV T | 21126094.72 | 800062547 | TRTP Segment 3B

## 900604086
Pin: 7183 | Project: TRTP Segment 3B
Order: 900604086 | 900604086- TRTP Segment 3B: Highwind-Windhub: Insta
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 87.81 |  | 722.2 | 515.32 | 737.22 | 1127.98 | 1131.56 | 1077.19 | 727.82 | 1164.51 | 1018.93 | 1455.64 | 9766.18
|  | Labor Total |  | 87.81 |  | 722.2 | 515.32 | 737.22 | 1127.98 | 1131.56 | 1077.19 | 727.82 | 1164.51 | 1018.93 | 1455.64 | 9766.18
| BP&FM Total |  |  | 87.81 |  | 722.2 | 515.32 | 737.22 | 1127.98 | 1131.56 | 1077.19 | 727.82 | 1164.51 | 1018.93 | 1455.64 | 9766.18
| Consultants - Engineering/Technical | Contract | Consultants - Engineering/Technical |  |  | 183000 | [9 empty] | 183000
|  | Contract Total |  |  |  | 183000 | [9 empty] | 183000
| Consultants - Engineering/Technical Total |  |  |  |  | 183000 | [9 empty] | 183000
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 56728.03 |  |  | 56728.03
|  |  | Contract Entries <$50,000 | [8 empty] | -56728.03 |  |  |  | -56728.03
|  | Contract Total | [9 empty] | -56728.03 | 56728.03 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -56728.03 | 56728.03 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 2089.23 | 2089.23
|  | Labor Total | [12 empty] | 2089.23 | 2089.23
| ELEC SYS PLANNING Total | [13 empty] | 2089.23 | 2089.23
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  |  | 531.49 |  |  | 529.88 | 1631 | 573.13 |  | 1125.37 |  | 4390.87
|  | Labor Total |  |  |  |  | 531.49 |  |  | 529.88 | 1631 | 573.13 |  | 1125.37 |  | 4390.87
| ENGINEERING Total | [5 empty] | 531.49 |  |  | 529.88 | 1631 | 573.13 |  | 1125.37 |  | 4390.87
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  |  | 30916.38 | 72823.34 |  | 58530.08 | 121656.8 | 6495.5 | 55196.13 | 44485.04 | 83439.67 | 73536.37 | 547079.31
|  |  | ELK ENGINEERING ASSOC INC | [11 empty] | 197169.44 | 197169.44
|  |  | Engineering/Technical Professional Servi |  |  |  |  | 134904.6 | [7 empty] | 134904.6
|  | Contract Total |  |  |  | 30916.38 | 72823.34 | 134904.6 | 58530.08 | 121656.8 | 6495.5 | 55196.13 | 44485.04 | 83439.67 | 270705.81 | 879153.35
| Engineering/Technical Professional Servi Total |  |  |  |  | 30916.38 | 72823.34 | 134904.6 | 58530.08 | 121656.8 | 6495.5 | 55196.13 | 44485.04 | 83439.67 | 270705.81 | 879153.35
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 86692.92 | -86692.92 |  |  | 0
|  | IMM Correction Total | [9 empty] | 86692.92 | -86692.92 |  |  | 0
| IMM/Allocated - Correction Total | [10 empty] | 86692.92 | -86692.92 |  |  | 0
| Labor - Other | Labor | Labor Correction | [9 empty] | 20107.57 |  |  | 20107.57
|  |  | Labor Entries <$5,000 |  |  | 12.85 | -13.43 | 151.98 | -181.79 | 1982.27 | 4005.32 | -23846.93 | 11048.76 | -5140.43 | 578.78 | -11402.62
|  | Labor Total |  |  |  | 12.85 | -13.43 | 151.98 | -181.79 | 1982.27 | 4005.32 | -23846.93 | 31156.33 | -5140.43 | 578.78 | 8704.95
| Labor - Other Total |  |  |  |  | 12.85 | -13.43 | 151.98 | -181.79 | 1982.27 | 4005.32 | -23846.93 | 31156.33 | -5140.43 | 578.78 | 8704.95
| Other | Other | Other |  |  | 3125.44 | 128.98 | 841.38 |  | 10537.89 | 99.88 | 18746.99 | 361162.52 | -299195.9 | 2761746.02 | 2857193.2
|  | Other Total |  |  |  | 3125.44 | 128.98 | 841.38 |  | 10537.89 | 99.88 | 18746.99 | 361162.52 | -299195.9 | 2761746.02 | 2857193.2
| Other Total |  |  |  |  | 3125.44 | 128.98 | 841.38 |  | 10537.89 | 99.88 | 18746.99 | 361162.52 | -299195.9 | 2761746.02 | 2857193.2
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -1676.1 | 1676.1 |  |  | 0
|  | Contract Total | [9 empty] | -1676.1 | 1676.1 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -1676.1 | 1676.1 |  |  | 0
| TRANSMISSION | Labor | Labor Entries <$5,000 | [9 empty] | 20752.6 | 6967.88 | 9207.88 | 36928.36
|  |  | TRANSMISSION / Opr R/W Eq | [10 empty] | 5012.7 |  | 5012.7
|  |  | TRANSMISSION / Supr road R/W | [9 empty] | 5131.81 | 11271.39 |  | 16403.2
|  | Labor Total | [10 empty] | 25884.41 | 23251.97 | 9207.88 | 58344.26
| TRANSMISSION Total | [11 empty] | 25884.41 | 23251.97 | 9207.88 | 58344.26
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | [5 empty] | 1029.94 | 308.61 | 565.14 |  |  |  |  | 1903.69
|  | Labor Total | [6 empty] | 1029.94 | 308.61 | 565.14 |  |  |  |  | 1903.69
| TRNS CAPITAL Total | [7 empty] | 1029.94 | 308.61 | 565.14 |  |  |  |  | 1903.69
1. Project Support Total |  |  |  | 87.81 |  | 217776.87 | 73985.7 | 136635.18 | 60506.21 | 136147.01 | 13874.03 | 79685.93 | 435564.02 | -195500.39 | 3045783.36 | 4004545.73
2. Material | Material - Other | Material | Material - Other | 2.24 | [8 empty] | 1160.95 |  |  | 1163.19
|  | Material Total |  | 2.24 | [8 empty] | 1160.95 |  |  | 1163.19
| Material - Other Total |  |  | 2.24 | [8 empty] | 1160.95 |  |  | 1163.19
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 66.39 | [11 empty] | 66.39
|  | Material - Direct Purchase Total |  | 66.39 | [11 empty] | 66.39
| Transportation & Mobile Equip-DP Total |  |  | 66.39 | [11 empty] | 66.39
2. Material Total |  |  |  | 68.63 | [8 empty] | 1160.95 |  |  | 1229.58
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [9 empty] | 4864 | 1216 | 7752 | 13832
|  | Contract Total | [10 empty] | 4864 | 1216 | 7752 | 13832
| Construction Management Services Total | [11 empty] | 4864 | 1216 | 7752 | 13832
| Construction Services - Other | Contract | Construction Services - Other | [10 empty] | 2373814.39 |  | 2373814.39
|  |  | Contract Entries <$50,000 | [9 empty] | 33462.89 | 31379.54 | 55265.93 | 120108.36
|  |  | RJ ALLEN INC | [10 empty] | 74393.07 |  | 74393.07
|  | Contract Total | [10 empty] | 33462.89 | 2479587 | 55265.93 | 2568315.82
| Construction Services - Other Total | [11 empty] | 33462.89 | 2479587 | 55265.93 | 2568315.82
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [11 empty] | 12588.96 | 12588.96
|  | Contract Total | [12 empty] | 12588.96 | 12588.96
| Construction, Civil/Structural Total | [13 empty] | 12588.96 | 12588.96
| Construction, Earthwork | Contract | Contract Entries <$50,000 | [9 empty] | 6078.65 |  |  | 6078.65
|  | Contract Total | [10 empty] | 6078.65 |  |  | 6078.65
| Construction, Earthwork Total | [11 empty] | 6078.65 |  |  | 6078.65
| Construction, Envrmntl Contamination | Contract | Contract Entries <$50,000 | [10 empty] | 1424.49 |  | 1424.49
|  | Contract Total | [11 empty] | 1424.49 |  | 1424.49
| Construction, Envrmntl Contamination Total | [12 empty] | 1424.49 |  | 1424.49
| Electrical Services | Contract | ACCURATE CORROSION CONTROL, INC. | [10 empty] | 1839157 |  | 1839157
|  |  | Contract Entries <$50,000 | [11 empty] | 44190 | 44190
|  | Contract Total | [11 empty] | 1839157 | 44190 | 1883347
| Electrical Services Total | [12 empty] | 1839157 | 44190 | 1883347
| Material - Inventory | Labor | Labor Entries <$5,000 | [10 empty] | 162.87 |  | 162.87
|  | Labor Total | [11 empty] | 162.87 |  | 162.87
| Material - Inventory Total | [12 empty] | 162.87 |  | 162.87
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [10 empty] | 280.15 | 16311.18 | 16591.33
|  | Contract Total | [11 empty] | 280.15 | 16311.18 | 16591.33
| Short Term Equipment Rent Total | [12 empty] | 280.15 | 16311.18 | 16591.33
| TRANSMISSION | Labor | Labor Entries <$5,000 | [9 empty] | 4721.55 | -158.25 |  | 4563.3
|  |  | TRANSMISSION / Supervisor | [9 empty] | 5761.8 | 17751 |  | 23512.8
|  | Labor Total | [10 empty] | 10483.35 | 17592.75 |  | 28076.1
| TRANSMISSION Total | [11 empty] | 10483.35 | 17592.75 |  | 28076.1
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | [11 empty] | 164 | 164
|  | Labor Total | [12 empty] | 164 | 164
| TSD-HERC - Rental Total | [13 empty] | 164 | 164
3. Construction Total | [12 empty] | 54888.89 | 4339420.26 | 136272.07 | 4530581.22
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 300.67 | 125.54 | 2404.14 | 1511.71 | 4264.19 | 4614 | 6117.99 | 3589.97 | 6468.35 | 6420.35 | 7009.43 | 4917.63 | 47743.97
|  |  | PROCUREMENT TDBU | [10 empty] | 29072.06 |  | 29072.06
|  |  | TRTP-3B Component - TRTP | [5 empty] | 13250.06 | 20015.7 | 35821.03 |  | 70822.39 | 206534.1 | 164746.31 | 511189.59
|  | Chargeback Total |  | 300.67 | 125.54 | 2404.14 | 1511.71 | 4264.19 | 17864.06 | 26133.69 | 39411 | 6468.35 | 77242.74 | 242615.59 | 169663.94 | 588005.62
| Chargebacks Total |  |  | 300.67 | 125.54 | 2404.14 | 1511.71 | 4264.19 | 17864.06 | 26133.69 | 39411 | 6468.35 | 77242.74 | 242615.59 | 169663.94 | 588005.62
| Labor - Other | Labor | Division Overhead |  |  | 21584.16 | [7 empty] | 44512.18 |  | 66096.34
|  |  | Labor Entries <$5,000 | 30.18 |  | 8105.72 | 2601.77 | 6126.54 | 3126.43 | 5571.48 | 1117.24 | -4874.86 | 15344.76 | 8258.59 | 9685.85 | 55093.7
|  |  | Paid Absence | [9 empty] | 8772.65 |  |  | 8772.65
|  | Labor Total |  | 30.18 |  | 29689.88 | 2601.77 | 6126.54 | 3126.43 | 5571.48 | 1117.24 | -4874.86 | 24117.41 | 52770.77 | 9685.85 | 129962.69
| Labor - Other Total |  |  | 30.18 |  | 29689.88 | 2601.77 | 6126.54 | 3126.43 | 5571.48 | 1117.24 | -4874.86 | 24117.41 | 52770.77 | 9685.85 | 129962.69
| Overhead - Correction | Overhead | Overhead - Correction | [8 empty] | -1727.26 | 1727.26 |  |  | 0
|  | Overhead Total | [9 empty] | -1727.26 | 1727.26 |  |  | 0
| Overhead - Correction Total | [10 empty] | -1727.26 | 1727.26 |  |  | 0
4. Allocated Total |  |  |  | 330.85 | 125.54 | 32094.02 | 4113.48 | 10390.73 | 20990.49 | 31705.17 | 40528.24 | -133.77 | 103087.41 | 295386.36 | 179349.79 | 717968.31
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 2123.97 | 178.46 | [7 empty] | 2302.43
|  |  | AFUDC - Debt/Equity | 137.69 | 141.23 | 979.41 | 2021.61 | 2725.69 | 4073.63 | 4631.53 | 5478.18 | 5900.67 | 8192.91 | 25355.99 | 25853.33 | 85491.87
|  |  | Capitalized Overhead - A&G | 27.2 | 3.68 | 8906.56 | 2785.06 | 12236.89 | 2908.64 | 5893.78 | 1538.79 | 3563.84 | 6401.62 | 125284.34 | 16944.34 | 186494.74
|  |  | Capitalized Overhead - Inj & Damages | 0.46 | 0.22 | 37.94 | 4 | 97.76 | 21.56 | 23.95 | 22.57 | 74.96 | 117.8 | 228.75 | 53.59 | 683.56
|  |  | Capitalized Overhead - P&B/Payroll Tax | 211.09 | 118.76 | 1426.56 | 1809.33 | 3968.47 | 11937.94 | 9465.52 | 10497.72 | -31385.09 | 36281.81 | 30838.07 | 34915.25 | 110085.43
|  |  | Corporate Overheads Correction |  |  |  |  | -23293.65 | [7 empty] | -23293.65
|  | Non Budgeted Total |  | 376.44 | 263.89 | 11350.47 | 8743.97 | -4086.38 | 18941.77 | 20014.78 | 17537.26 | -21845.62 | 50994.14 | 181707.15 | 77766.51 | 361764.38
| Non Budget - Other Total |  |  | 376.44 | 263.89 | 11350.47 | 8743.97 | -4086.38 | 18941.77 | 20014.78 | 17537.26 | -21845.62 | 50994.14 | 181707.15 | 77766.51 | 361764.38
5. Corporate Overhead Total |  |  |  | 376.44 | 263.89 | 11350.47 | 8743.97 | -4086.38 | 18941.77 | 20014.78 | 17537.26 | -21845.62 | 50994.14 | 181707.15 | 77766.51 | 361764.38
Grand Total |  |  |  | 863.73 | 389.43 | 261221.36 | 86843.15 | 142939.53 | 100438.47 | 187866.96 | 71939.53 | 57706.54 | 645695.41 | 4621013.38 | 3439171.73 | 9616089.22

## 800452215
Pin: 7183 | Project: TRTP Segment 3B
Order: 800452215 | 800452215- ACQ- SEGMENT 3B 220
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | HRealProp | Labor | Labor Entries <$5,000 | 175.76 |  |  |  |  | 389.24 | 1438.02 | 389.73 |  |  |  |  | 2392.75
|  | Labor Total |  | 175.76 |  |  |  |  | 389.24 | 1438.02 | 389.73 |  |  |  |  | 2392.75
| HRealProp Total |  |  | 175.76 |  |  |  |  | 389.24 | 1438.02 | 389.73 |  |  |  |  | 2392.75
| Information System Professional Services | Contract | Contract Entries <$50,000 |  |  |  |  | 95.7 | [7 empty] | 95.7
|  | Contract Total | [5 empty] | 95.7 | [7 empty] | 95.7
| Information System Professional Services Total | [6 empty] | 95.7 | [7 empty] | 95.7
| Labor - Other | Labor | Labor Entries <$5,000 | -3.43 | 3.43 |  |  | 729.86 |  | -20.48 | 59.1 | 10.45 |  |  |  | 778.93
|  | Labor Total |  | -3.43 | 3.43 |  |  | 729.86 |  | -20.48 | 59.1 | 10.45 |  |  |  | 778.93
| Labor - Other Total |  |  | -3.43 | 3.43 |  |  | 729.86 |  | -20.48 | 59.1 | 10.45 |  |  |  | 778.93
| Other | Other | Other |  |  |  | 9750 | 3639 | 4609 | 8281.9 | 1002.82 |  |  |  | 2933.88 | 30216.6
|  | Other Total |  |  |  |  | 9750 | 3639 | 4609 | 8281.9 | 1002.82 |  |  |  | 2933.88 | 30216.6
| Other Total | [5 empty] | 9750 | 3639 | 4609 | 8281.9 | 1002.82 |  |  |  | 2933.88 | 30216.6
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 3255.51 | 427.13 | 248.64 | 4333.15 | 20193.24 | 7029.54 | 1584.84 | 1563.14 | 2760.58 | 2687.52 | 1789.15 | 1982.98 | 47855.42
|  | Contract Total |  | 3255.51 | 427.13 | 248.64 | 4333.15 | 20193.24 | 7029.54 | 1584.84 | 1563.14 | 2760.58 | 2687.52 | 1789.15 | 1982.98 | 47855.42
| Temporary/Supplementary - Trade/Labor Total |  |  | 3255.51 | 427.13 | 248.64 | 4333.15 | 20193.24 | 7029.54 | 1584.84 | 1563.14 | 2760.58 | 2687.52 | 1789.15 | 1982.98 | 47855.42
1. Project Support Total |  |  |  | 3427.84 | 430.56 | 248.64 | 14083.15 | 24657.8 | 12027.78 | 11284.28 | 3014.79 | 2771.03 | 2687.52 | 1789.15 | 4916.86 | 81339.4
2. Material | Material - Other | Material | Material - Other |  | 33.63 | [10 empty] | 33.63
|  | Material Total |  |  | 33.63 | [10 empty] | 33.63
| Material - Other Total |  |  |  | 33.63 | [10 empty] | 33.63
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 12.42 |  |  | 20.17 |  | 39.46 |  | 29.12 | 8.81 |  |  |  | 109.98
|  | Material - Direct Purchase Total |  | 12.42 |  |  | 20.17 |  | 39.46 |  | 29.12 | 8.81 |  |  |  | 109.98
| Transportation & Mobile Equip-DP Total |  |  | 12.42 |  |  | 20.17 |  | 39.46 |  | 29.12 | 8.81 |  |  |  | 109.98
2. Material Total |  |  |  | 12.42 | 33.63 |  | 20.17 |  | 39.46 |  | 29.12 | 8.81 |  |  |  | 143.61
3. Construction | HRealProp | Labor | Labor Entries <$5,000 |  | 196.09 | [10 empty] | 196.09
|  | Labor Total |  |  | 196.09 | [10 empty] | 196.09
| HRealProp Total |  |  |  | 196.09 | [10 empty] | 196.09
3. Construction Total |  |  |  |  | 196.09 | [10 empty] | 196.09
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 23.53 | 2.82 | 1.64 | 28.73 | 134.82 | 77.07 | 32.12 | 10.51 | 18.28 | 17.74 | 11.81 | 32.45 | 391.52
|  | Chargeback Total |  | 23.53 | 2.82 | 1.64 | 28.73 | 134.82 | 77.07 | 32.12 | 10.51 | 18.28 | 17.74 | 11.81 | 32.45 | 391.52
| Chargebacks Total |  |  | 23.53 | 2.82 | 1.64 | 28.73 | 134.82 | 77.07 | 32.12 | 10.51 | 18.28 | 17.74 | 11.81 | 32.45 | 391.52
| Labor - Other | Labor | Labor Entries <$5,000 | 123.4 | 54.11 | 5.47 | 95.77 | 612.17 | 343.72 | 423.18 | 126.5 | 60.93 | 134.38 | 89.46 | 108.17 | 2177.26
|  | Labor Total |  | 123.4 | 54.11 | 5.47 | 95.77 | 612.17 | 343.72 | 423.18 | 126.5 | 60.93 | 134.38 | 89.46 | 108.17 | 2177.26
| Labor - Other Total |  |  | 123.4 | 54.11 | 5.47 | 95.77 | 612.17 | 343.72 | 423.18 | 126.5 | 60.93 | 134.38 | 89.46 | 108.17 | 2177.26
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -126.03 | -126.03
|  | Overhead Total | [12 empty] | -126.03 | -126.03
| Overhead Correction Total | [13 empty] | -126.03 | -126.03
4. Allocated Total |  |  |  | 146.93 | 56.93 | 7.11 | 124.5 | 746.99 | 420.79 | 455.3 | 137.01 | 79.21 | 152.12 | 101.27 | 14.59 | 2442.75
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 18125.58 | 1110.36 | [6 empty] | 19153.67 | 38389.61
|  | Non Budgeted Total |  |  |  |  | 18125.58 | 1110.36 | [6 empty] | 19153.67 | 38389.61
| Non Budget - Other Total | [5 empty] | 18125.58 | 1110.36 | [6 empty] | 19153.67 | 38389.61
5. Corporate Overhead Total | [6 empty] | 18125.58 | 1110.36 | [6 empty] | 19153.67 | 38389.61
Grand Total |  |  |  | 3587.19 | 717.21 | 255.75 | 32353.4 | 26515.15 | 12488.03 | 11739.58 | 3180.92 | 2859.05 | 2839.64 | 1890.42 | 24085.12 | 122511.46

## 800063658
Pin: 7183 | Project: TRTP Segment 3B
Order: 800063658 | 800063658- I: TRTP 3B: Highwind SS Work: Grade and
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 1237.19 | 1310.55 | 1386.62 | 1030.64 | 1361.01 | 1272.59 | 1102.55 | 1222.75 | 1164.51 | 960.72 | 1164.49 | 1280.96 | 14494.58
|  | Labor Total |  | 1237.19 | 1310.55 | 1386.62 | 1030.64 | 1361.01 | 1272.59 | 1102.55 | 1222.75 | 1164.51 | 960.72 | 1164.49 | 1280.96 | 14494.58
| BP&FM Total |  |  | 1237.19 | 1310.55 | 1386.62 | 1030.64 | 1361.01 | 1272.59 | 1102.55 | 1222.75 | 1164.51 | 960.72 | 1164.49 | 1280.96 | 14494.58
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  |  | 69.3 | [7 empty] | 69.3
|  | Contract Total | [5 empty] | 69.3 | [7 empty] | 69.3
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [6 empty] | 69.3 | [7 empty] | 69.3
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 561351.82 |  |  | 561351.82
|  |  | Contract Entries <$50,000 | [8 empty] | -561351.82 |  |  |  | -561351.82
|  | Contract Total | [9 empty] | -561351.82 | 561351.82 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -561351.82 | 561351.82 |  |  | 0
| CORP COMM SVP | Labor | Labor Entries <$5,000 | [5 empty] | 241.77 |  |  |  | 123.24 |  | 122.12 | 487.13
|  | Labor Total | [6 empty] | 241.77 |  |  |  | 123.24 |  | 122.12 | 487.13
| CORP COMM SVP Total | [7 empty] | 241.77 |  |  |  | 123.24 |  | 122.12 | 487.13
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 1785.95 | 1785.95
|  | Labor Total | [12 empty] | 1785.95 | 1785.95
| ELEC SYS PLANNING Total | [13 empty] | 1785.95 | 1785.95
| ENGINEERING | Labor | Labor Entries <$5,000 | 1734.43 | 1801.4 | 2253.89 | 3455.85 | 6394.22 | 9989.71 | 6702.71 | 9075.67 | 7039.44 | 4318.45 | 4689 |  | 57454.77
|  | Labor Total |  | 1734.43 | 1801.4 | 2253.89 | 3455.85 | 6394.22 | 9989.71 | 6702.71 | 9075.67 | 7039.44 | 4318.45 | 4689 |  | 57454.77
| ENGINEERING Total |  |  | 1734.43 | 1801.4 | 2253.89 | 3455.85 | 6394.22 | 9989.71 | 6702.71 | 9075.67 | 7039.44 | 4318.45 | 4689 |  | 57454.77
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 8613.38 | 559.81 | 200 | 7148.99 |  | 3505.25 | 42073.86 | 362.5 |  | 16394.47 | 2739.56 | 59429.6 | 141027.42
|  | Contract Total |  | 8613.38 | 559.81 | 200 | 7148.99 |  | 3505.25 | 42073.86 | 362.5 |  | 16394.47 | 2739.56 | 59429.6 | 141027.42
| Engineering/Technical Professional Servi Total |  |  | 8613.38 | 559.81 | 200 | 7148.99 |  | 3505.25 | 42073.86 | 362.5 |  | 16394.47 | 2739.56 | 59429.6 | 141027.42
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 150 | 451.5 | 1722 | 422.85 | 2083.72 | 2454.17 | 1049 | 1585.75 | 3248.61 | 1600.75 | 3778.79 | 18547.14
|  | Contract Total |  |  | 150 | 451.5 | 1722 | 422.85 | 2083.72 | 2454.17 | 1049 | 1585.75 | 3248.61 | 1600.75 | 3778.79 | 18547.14
| Environmental/Safety Professional Servic Total |  |  |  | 150 | 451.5 | 1722 | 422.85 | 2083.72 | 2454.17 | 1049 | 1585.75 | 3248.61 | 1600.75 | 3778.79 | 18547.14
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 594490.4 | -594490.4 |  |  | 0
|  | IMM Correction Total | [9 empty] | 594490.4 | -594490.4 |  |  | 0
| IMM/Allocated - Correction Total | [10 empty] | 594490.4 | -594490.4 |  |  | 0
| Labor - Other | Labor | Labor Correction | [9 empty] | 10869.59 |  |  | 10869.59
|  |  | Labor Entries <$5,000 | 38.08 | 4711.2 | 171.72 | 280.92 | 7608.75 | -3308.1 | -625.18 | 990.56 | -11077.74 | 2980.07 | -388.73 | 5065.39 | 6446.94
|  | Labor Total |  | 38.08 | 4711.2 | 171.72 | 280.92 | 7608.75 | -3308.1 | -625.18 | 990.56 | -11077.74 | 13849.66 | -388.73 | 5065.39 | 17316.53
| Labor - Other Total |  |  | 38.08 | 4711.2 | 171.72 | 280.92 | 7608.75 | -3308.1 | -625.18 | 990.56 | -11077.74 | 13849.66 | -388.73 | 5065.39 | 17316.53
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 |  |  | 160.47 | 460.46 | 588.28 | 367.35 | [6 empty] | 1576.56
|  | Labor Total |  |  |  | 160.47 | 460.46 | 588.28 | 367.35 | [6 empty] | 1576.56
| MAJOR PROJECT ORG Total |  |  |  |  | 160.47 | 460.46 | 588.28 | 367.35 | [6 empty] | 1576.56
| Other | Other | Other |  | 1126.48 | 6729.43 | 109.64 | 49756.05 | -46737.49 | 434053.29 | -223564.15 | -34554.94 | -131249.15 | 42544.03 | 573577.55 | 671790.74
|  | Other Total |  |  | 1126.48 | 6729.43 | 109.64 | 49756.05 | -46737.49 | 434053.29 | -223564.15 | -34554.94 | -131249.15 | 42544.03 | 573577.55 | 671790.74
| Other Total |  |  |  | 1126.48 | 6729.43 | 109.64 | 49756.05 | -46737.49 | 434053.29 | -223564.15 | -34554.94 | -131249.15 | 42544.03 | 573577.55 | 671790.74
| SC&M | Labor | Labor Entries <$5,000 | 261.62 | 506.56 | 261.42 | 1041.55 | 785.56 | 1296.55 | 1465.39 | 1049.27 | 736.78 | 3815.63 | 619.58 | 391.56 | 12231.47
|  | Labor Total |  | 261.62 | 506.56 | 261.42 | 1041.55 | 785.56 | 1296.55 | 1465.39 | 1049.27 | 736.78 | 3815.63 | 619.58 | 391.56 | 12231.47
| SC&M Total |  |  | 261.62 | 506.56 | 261.42 | 1041.55 | 785.56 | 1296.55 | 1465.39 | 1049.27 | 736.78 | 3815.63 | 619.58 | 391.56 | 12231.47
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  | 136.28 | 352.24 | 704.65 | 1181.79 | 1409.29 | 1166.85 | 1056.97 | 352.32 | 445.82 | 841.37 | 7647.58
|  | Labor Total |  |  |  | 136.28 | 352.24 | 704.65 | 1181.79 | 1409.29 | 1166.85 | 1056.97 | 352.32 | 445.82 | 841.37 | 7647.58
| SCM HOME CENTER Total |  |  |  |  | 136.28 | 352.24 | 704.65 | 1181.79 | 1409.29 | 1166.85 | 1056.97 | 352.32 | 445.82 | 841.37 | 7647.58
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -1864.74 | 1864.74 |  |  | 0
|  | Contract Total | [9 empty] | -1864.74 | 1864.74 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -1864.74 | 1864.74 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 9788 | 9048.6 | 6329.09 | 7287.27 | 4444.36 | 6799.06 | 6390.98 | 2660.14 |  |  |  |  | 52747.5
|  | Contract Total |  | 9788 | 9048.6 | 6329.09 | 7287.27 | 4444.36 | 6799.06 | 6390.98 | 2660.14 |  |  |  |  | 52747.5
| Temporary/Supplementary - Trade/Labor Total |  |  | 9788 | 9048.6 | 6329.09 | 7287.27 | 4444.36 | 6799.06 | 6390.98 | 2660.14 |  |  |  |  | 52747.5
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 | [5 empty] | 77 | 2664 |  | 865.8 |  | 999 |  | 4605.8
|  | Labor Total | [6 empty] | 77 | 2664 |  | 865.8 |  | 999 |  | 4605.8
| TSD-Aircraft - Fixed Total | [7 empty] | 77 | 2664 |  | 865.8 |  | 999 |  | 4605.8
1. Project Support Total |  |  |  | 21672.7 | 19214.6 | 18080.42 | 22889.56 | 72135.03 | -23230.8 | 497691.06 | -205987.41 | -1909.59 | -119459.89 | 54413.5 | 646273.29 | 1001782.47
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp |  |  |  |  | 6175.42 | [7 empty] | 6175.42
|  |  | JENSEN PRECAST | [7 empty] | 17405.8 |  |  |  |  | 17405.8
|  |  | Material Entries <$5,000 | [5 empty] | 213.45 | 651.84 | 84.35 | 3878.99 | 16.23 |  |  | 4844.86
|  | Material - Direct Purchase Total | [5 empty] | 6175.42 | 213.45 | 651.84 | 17490.15 | 3878.99 | 16.23 |  |  | 28426.08
| Building, Shop & Industrial Products/Eqp Total | [6 empty] | 6175.42 | 213.45 | 651.84 | 17490.15 | 3878.99 | 16.23 |  |  | 28426.08
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 83.33 |  |  | 83.33
|  | Material - Direct Purchase Total | [10 empty] | 83.33 |  |  | 83.33
| Cabinets, Panels and Switchboards-DP Total | [11 empty] | 83.33 |  |  | 83.33
| Capacitors and Regulators-DP | Material - Direct Purchase | ALSTOM GRID INC, | 61470 | [11 empty] | 61470
|  |  | Material Entries <$5,000 | [6 empty] | -30735 | [5 empty] | -30735
|  | Material - Direct Purchase Total |  | 61470 | [5 empty] | -30735 | [5 empty] | 30735
| Capacitors and Regulators-DP Total |  |  | 61470 | [5 empty] | -30735 | [5 empty] | 30735
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 344.4 |  |  | 95.2 |  | 2326.48 | 1551.18 | 684 | -6411.93 | -1410.67
|  | Material - Direct Purchase Total |  |  |  |  | 344.4 |  |  | 95.2 |  | 2326.48 | 1551.18 | 684 | -6411.93 | -1410.67
| Electric Wiring and Components-DP Total | [5 empty] | 344.4 |  |  | 95.2 |  | 2326.48 | 1551.18 | 684 | -6411.93 | -1410.67
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 79.46 |  |  |  | 79.46
|  | Material - Direct Purchase Total | [9 empty] | 79.46 |  |  |  | 79.46
| Fuels, Chemicals & Petrochem-DP Total | [10 empty] | 79.46 |  |  |  | 79.46
| Insulators & Bushings-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 381.96 | [5 empty] | 381.96
|  | Material - Direct Purchase Total | [7 empty] | 381.96 | [5 empty] | 381.96
| Insulators & Bushings-DP Total | [8 empty] | 381.96 | [5 empty] | 381.96
| Line Switches & Switchgear-DP | Material - Direct Purchase | Line Switches & Switchgear-DP | [11 empty] | 113535 | 113535
|  |  | Material Entries <$5,000 | [6 empty] | -113535 | [5 empty] | -113535
|  |  | SOUTHERN STATES LLC |  |  |  |  | 47904 | 74558 | [6 empty] | 122462
|  | Material - Direct Purchase Total | [5 empty] | 47904 | 74558 | -113535 |  |  |  |  | 113535 | 122462
| Line Switches & Switchgear-DP Total | [6 empty] | 47904 | 74558 | -113535 |  |  |  |  | 113535 | 122462
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -46.68 | 46.68 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -46.68 | 46.68 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -46.68 | 46.68 |  |  | 0
| Material - Inventory | Material | Material - Inventory |  |  |  |  | 77656.44 |  | 114219.98 | -1184.85 |  |  |  | -6000 | 184691.57
|  | Material Total | [5 empty] | 77656.44 |  | 114219.98 | -1184.85 |  |  |  | -6000 | 184691.57
| Material - Inventory Total | [6 empty] | 77656.44 |  | 114219.98 | -1184.85 |  |  |  | -6000 | 184691.57
| Material - Other | Material | Material - Other | 7599.63 | 303.55 | 0.1 | 31.56 | 11675.67 | 11259.27 | 43947.06 | 7728.98 | 2612.84 | 411.48 | 49.92 | 785.86 | 86405.92
|  | Material Total |  | 7599.63 | 303.55 | 0.1 | 31.56 | 11675.67 | 11259.27 | 43947.06 | 7728.98 | 2612.84 | 411.48 | 49.92 | 785.86 | 86405.92
| Material - Other Total |  |  | 7599.63 | 303.55 | 0.1 | 31.56 | 11675.67 | 11259.27 | 43947.06 | 7728.98 | 2612.84 | 411.48 | 49.92 | 785.86 | 86405.92
| Material Handling Services | Contract | Contract Entries <$50,000 | [7 empty] | 1344 |  |  |  |  | 1344
|  | Contract Total | [8 empty] | 1344 |  |  |  |  | 1344
| Material Handling Services Total | [9 empty] | 1344 |  |  |  |  | 1344
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 841.84 |  | 109.34 |  |  |  | 951.18
|  |  | OLSON WAGNER CONSTRUCTION INC | [6 empty] | 390210 | [5 empty] | 390210
|  | Material - Direct Purchase Total | [7 empty] | 391051.84 |  | 109.34 |  |  |  | 391161.18
| Metals & Fabricated Metal Products-DP Total | [8 empty] | 391051.84 |  | 109.34 |  |  |  | 391161.18
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 890 | [7 empty] | 890
|  | Material - Direct Purchase Total | [5 empty] | 890 | [7 empty] | 890
| Meters, Monitor and Warnings-DP Total | [6 empty] | 890 | [7 empty] | 890
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [5 empty] | 61.29 | 32.61 |  | 98.6 | 450.29 |  |  | 642.79
|  | Material - Direct Purchase Total | [6 empty] | 61.29 | 32.61 |  | 98.6 | 450.29 |  |  | 642.79
| Pipe/Tubing, Fittings and Gaskets-DP Total | [7 empty] | 61.29 | 32.61 |  | 98.6 | 450.29 |  |  | 642.79
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 502.45 |  | 1605.87 | 1948.49 |  |  |  | -4921.05 | -864.24
|  |  | Pole Line Hdwe & Connectors-DP | [8 empty] | 5807.01 |  |  |  | 5807.01
|  | Material - Direct Purchase Total | [5 empty] | 502.45 |  | 1605.87 | 1948.49 | 5807.01 |  |  | -4921.05 | 4942.77
| Pole Line Hdwe & Connectors-DP Total | [6 empty] | 502.45 |  | 1605.87 | 1948.49 | 5807.01 |  |  | -4921.05 | 4942.77
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | BENNING POWER ELECTRONICS INC | 8222 | [11 empty] | 8222
|  |  | ENERSYS DELAWARE INC | 33584 | [11 empty] | 33584
|  |  | Material Entries <$5,000 | [6 empty] | 44.35 | [5 empty] | 44.35
|  |  | Power Systems, Batteries and Light-DP | [11 empty] | 6670 | 6670
|  | Material - Direct Purchase Total |  | 41806 | [5 empty] | 44.35 |  |  |  |  | 6670 | 48520.35
| Power Systems, Batteries and Light-DP Total |  |  | 41806 | [5 empty] | 44.35 |  |  |  |  | 6670 | 48520.35
| Protection and Test-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 948.12 | [5 empty] | 948.12
|  | Material - Direct Purchase Total | [7 empty] | 948.12 | [5 empty] | 948.12
| Protection and Test-DP Total | [8 empty] | 948.12 | [5 empty] | 948.12
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO |  |  |  |  | 6429.92 |  | 7075 | [5 empty] | 13504.92
|  |  | Material Entries <$5,000 | [7 empty] | 2085.6 | 1328 | 441 |  | -69640 | -65785.4
|  |  | PARCELL STEEL CO |  |  |  |  | 9009.6 | 6558.84 | [6 empty] | 15568.44
|  | Material - Direct Purchase Total | [5 empty] | 15439.52 | 6558.84 | 7075 | 2085.6 | 1328 | 441 |  | -69640 | -36712.04
| Steel / Fabricated / Structural-DP Total | [6 empty] | 15439.52 | 6558.84 | 7075 | 2085.6 | 1328 | 441 |  | -69640 | -36712.04
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 2367.54 | 128.17 |  |  |  |  | 386.67 | 226.5 | 489.69 | 304.61 | 706.76 | 4609.94
|  |  | Transportation & Mobile Equip-DP | [5 empty] | 5305.84 | [6 empty] | 5305.84
|  | Material - Direct Purchase Total |  |  | 2367.54 | 128.17 |  |  | 5305.84 |  | 386.67 | 226.5 | 489.69 | 304.61 | 706.76 | 9915.78
| Transportation & Mobile Equip-DP Total |  |  |  | 2367.54 | 128.17 |  |  | 5305.84 |  | 386.67 | 226.5 | 489.69 | 304.61 | 706.76 | 9915.78
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 7680 | 22.21 | [7 empty] | 7702.21
|  |  | Wire, Cable & Bus Bar-DP |  |  |  | 11610 | [8 empty] | 11610
|  | Material - Direct Purchase Total |  |  |  |  | 19290 | 22.21 | [7 empty] | 19312.21
| Wire, Cable & Bus Bar-DP Total | [5 empty] | 19290 | 22.21 | [7 empty] | 19312.21
2. Material Total |  |  |  | 110875.63 | 2671.09 | 128.27 | 19665.96 | 160265.71 | 97956.69 | 415783.83 | 29799.04 | 16420.54 | 3489.88 | 1038.53 | 34724.64 | 892819.81
3. Construction | Construction Management Services | Contract | CIRCLE WOOD SERVICES, INC | [10 empty] | 52497.04 |  | 52497.04
|  |  | Contract Entries <$50,000 |  |  | 4267.9 |  | 9353.32 | 17511.87 | 43973.38 | 44798.19 | 15334 | 44487.98 | 144345.48 | 229968.57 | 554040.69
|  | Contract Total |  |  |  | 4267.9 |  | 9353.32 | 17511.87 | 43973.38 | 44798.19 | 15334 | 44487.98 | 196842.52 | 229968.57 | 606537.73
| Construction Management Services Total |  |  |  |  | 4267.9 |  | 9353.32 | 17511.87 | 43973.38 | 44798.19 | 15334 | 44487.98 | 196842.52 | 229968.57 | 606537.73
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [9 empty] | 32180 |  |  | 32180
|  |  | OLSON WAGNER CONSTRUCTION INC | [8 empty] | 247683 | 50885 |  |  | 298568
|  | Contract Total | [9 empty] | 247683 | 83065 |  |  | 330748
| Construction, Civil/Structural Total | [10 empty] | 247683 | 83065 |  |  | 330748
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 | [5 empty] | 1175 | [6 empty] | 1175
|  | Contract Total | [6 empty] | 1175 | [6 empty] | 1175
| Decontamination & Waste Disposal Service Total | [7 empty] | 1175 | [6 empty] | 1175
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 166.86 | 166.86
|  | Labor Total | [12 empty] | 166.86 | 166.86
| ELEC SYS PLANNING Total | [13 empty] | 166.86 | 166.86
| Electrical Construction, Substations | Contract | Contract Entries <$50,000 | [6 empty] | 38139 | [5 empty] | 38139
|  |  | ELEMENTAL ENERGY INC. | [5 empty] | 610313 | 395588 | 258212 | 415959 | 217640 | 424656 | 324972 | 2647340
|  | Contract Total | [6 empty] | 610313 | 433727 | 258212 | 415959 | 217640 | 424656 | 324972 | 2685479
| Electrical Construction, Substations Total | [7 empty] | 610313 | 433727 | 258212 | 415959 | 217640 | 424656 | 324972 | 2685479
| Electrical Services | Contract | Contract Entries <$50,000 | [7 empty] | 25800 |  | 21000 |  |  | 46800
|  | Contract Total | [8 empty] | 25800 |  | 21000 |  |  | 46800
| Electrical Services Total | [9 empty] | 25800 |  | 21000 |  |  | 46800
| ENGINEERING | Labor | Labor Entries <$5,000 |  | 270.47 | 165.68 | 167.72 | 166.87 | 666.77 |  | 333.75 |  |  |  |  | 1771.26
|  | Labor Total |  |  | 270.47 | 165.68 | 167.72 | 166.87 | 666.77 |  | 333.75 |  |  |  |  | 1771.26
| ENGINEERING Total |  |  |  | 270.47 | 165.68 | 167.72 | 166.87 | 666.77 |  | 333.75 |  |  |  |  | 1771.26
| GRID OPS | Labor | Labor Entries <$5,000 | [5 empty] | 232.18 |  |  | 234.97 | 543.15 |  |  | 1010.3
|  | Labor Total | [6 empty] | 232.18 |  |  | 234.97 | 543.15 |  |  | 1010.3
| GRID OPS Total | [7 empty] | 232.18 |  |  | 234.97 | 543.15 |  |  | 1010.3
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | [6 empty] | 1397 | [5 empty] | 1397
|  | Contract Total | [7 empty] | 1397 | [5 empty] | 1397
| Hauling / Industrial Moving Services Total | [8 empty] | 1397 | [5 empty] | 1397
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [6 empty] | 4523.6 |  |  |  |  | -182490.12 | -177966.52
|  | Contract Total | [7 empty] | 4523.6 |  |  |  |  | -182490.12 | -177966.52
| Major Construction, Turnkey, Trans/Subs Total | [8 empty] | 4523.6 |  |  |  |  | -182490.12 | -177966.52
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | [9 empty] | 188.18 | 3252.56 |  | 3440.74
|  | Labor Total | [10 empty] | 188.18 | 3252.56 |  | 3440.74
| N/W SUBSMTCETEST&APP Total | [11 empty] | 188.18 | 3252.56 |  | 3440.74
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [10 empty] | 353.65 |  | 353.65
|  | Labor Total | [11 empty] | 353.65 |  | 353.65
| S/E SUBS MTCETST&APP Total | [12 empty] | 353.65 |  | 353.65
| SC&M | Labor | Labor Entries <$5,000 |  | 433.52 | 433.26 |  |  | 434.93 |  | 862.29 |  | 1544.6 |  | 1125.36 | 4833.96
|  | Labor Total |  |  | 433.52 | 433.26 |  |  | 434.93 |  | 862.29 |  | 1544.6 |  | 1125.36 | 4833.96
| SC&M Total |  |  |  | 433.52 | 433.26 |  |  | 434.93 |  | 862.29 |  | 1544.6 |  | 1125.36 | 4833.96
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  |  |  | 207.72 | 82.82 | 207.07 | [5 empty] | 497.61
|  | Labor Total | [5 empty] | 207.72 | 82.82 | 207.07 | [5 empty] | 497.61
| SCM HOME CENTER Total | [6 empty] | 207.72 | 82.82 | 207.07 | [5 empty] | 497.61
| Security / Protection Services | Contract | Contract Entries <$50,000 |  |  | 1180.5 | 6468.51 | 6985.84 | 5979.35 | 5423.32 | 5253.44 | 5042.08 | 7658.51 | 5149.54 | 8136.17 | 57277.26
|  | Contract Total |  |  |  | 1180.5 | 6468.51 | 6985.84 | 5979.35 | 5423.32 | 5253.44 | 5042.08 | 7658.51 | 5149.54 | 8136.17 | 57277.26
| Security / Protection Services Total |  |  |  |  | 1180.5 | 6468.51 | 6985.84 | 5979.35 | 5423.32 | 5253.44 | 5042.08 | 7658.51 | 5149.54 | 8136.17 | 57277.26
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [5 empty] | 1683.55 | 2849.5 |  | 5651.49 | 5493.91 | 5925.78 | 15762.4 | 37366.63
|  | Contract Total | [6 empty] | 1683.55 | 2849.5 |  | 5651.49 | 5493.91 | 5925.78 | 15762.4 | 37366.63
| Short Term Equipment Rent Total | [7 empty] | 1683.55 | 2849.5 |  | 5651.49 | 5493.91 | 5925.78 | 15762.4 | 37366.63
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | [6 empty] | 82 | [5 empty] | 82
|  | Labor Total | [7 empty] | 82 | [5 empty] | 82
| TSD-HERC - Crane Svs Total | [8 empty] | 82 | [5 empty] | 82
3. Construction Total |  |  |  |  | 703.99 | 6047.34 | 6636.23 | 16713.75 | 638079.47 | 492182.87 | 335259.67 | 689904.54 | 381621.33 | 636180.05 | 397641.24 | 3600970.48
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 1666.38 | 1864.17 | 2856.72 | 4158.05 | 9094.46 | 16721.81 | 8726.79 | 9893.9 | 7968.77 | 1255.77 | 9358.86 | 1298 | 74863.68
|  |  | MATERIAL MANAGEM |  |  |  |  | 15096.41 |  | 21359.14 | [5 empty] | 36455.55
|  |  | PROCUREMENT TDBU | [6 empty] | 5264.03 |  |  | 6334.9 |  |  | 11598.93
|  |  | TRTP-2010 Segment 3B Highwind Sub-TDBU |  | 8094.96 | 32597.49 | 15760.21 | 245743.2 |  | 150852.23 | 109919.04 |  | 196478.17 | 8843.09 |  | 768288.39
|  | Chargeback Total |  | 1666.38 | 9959.13 | 35454.21 | 19918.26 | 269934.07 | 16721.81 | 186202.19 | 119812.94 | 7968.77 | 204068.84 | 18201.95 | 1298 | 891206.55
| Chargebacks Total |  |  | 1666.38 | 9959.13 | 35454.21 | 19918.26 | 269934.07 | 16721.81 | 186202.19 | 119812.94 | 7968.77 | 204068.84 | 18201.95 | 1298 | 891206.55
| Labor - Other | Labor | Division Overhead | [5 empty] | 44460.51 | 70374.07 | 16718.04 |  | 78724.24 | 8761.28 | 9030.98 | 228069.12
|  |  | Labor Entries <$5,000 | 10722.2 | 2387.46 | 2413.72 | 5371.81 | 15495.22 | 8215.66 | 3398.53 | 14840.91 | 8994.17 | 8015.97 | 9614.64 | 11174.8 | 100645.09
|  | Labor Total |  | 10722.2 | 2387.46 | 2413.72 | 5371.81 | 15495.22 | 52676.17 | 73772.6 | 31558.95 | 8994.17 | 86740.21 | 18375.92 | 20205.78 | 328714.21
| Labor - Other Total |  |  | 10722.2 | 2387.46 | 2413.72 | 5371.81 | 15495.22 | 52676.17 | 73772.6 | 31558.95 | 8994.17 | 86740.21 | 18375.92 | 20205.78 | 328714.21
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -13031.84 | 13031.84 |  |  | 0
|  | Overhead Total | [9 empty] | -13031.84 | 13031.84 |  |  | 0
| Overhead Correction Total | [10 empty] | -13031.84 | 13031.84 |  |  | 0
4. Allocated Total |  |  |  | 12388.58 | 12346.59 | 37867.93 | 25290.07 | 285429.29 | 69397.98 | 259974.79 | 151371.89 | 3931.1 | 303840.89 | 36577.87 | 21503.78 | 1219920.76
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 17309.64 | 1262.17 | [7 empty] | 18571.81
|  |  | Capitalized Overhead - A&G | 8088.86 | 1023.5 | 2201.03 | 2669.43 | 40570.49 | 29597.73 | 44001.49 | 15129.33 | 33746.61 | 18411.21 | 18172.34 | 14791.07 | 228403.09
|  |  | Capitalized Overhead - Inj & Damages | 118.35 | 27.53 | 17.64 | 30.24 | 1991.65 | 230.29 | 514.35 | 111.27 | 571.42 | -1343.64 | 78.01 | 91.63 | 2438.74
|  |  | Capitalized Overhead - P&B/Payroll Tax | 2456.35 | 8878.51 | 5869.13 | 11349.86 | 27604.4 | 19454.97 | 15668.35 | 13698.24 | -3242.64 | 16146.09 | 10461.13 | 26712.73 | 155057.12
|  | Non Budgeted Total |  | 10663.56 | 9929.54 | 8087.8 | 31359.17 | 71428.71 | 49282.99 | 60184.19 | 28938.84 | 31075.39 | 33213.66 | 28711.48 | 41595.43 | 404470.76
| Non Budget - Other Total |  |  | 10663.56 | 9929.54 | 8087.8 | 31359.17 | 71428.71 | 49282.99 | 60184.19 | 28938.84 | 31075.39 | 33213.66 | 28711.48 | 41595.43 | 404470.76
5. Corporate Overhead Total |  |  |  | 10663.56 | 9929.54 | 8087.8 | 31359.17 | 71428.71 | 49282.99 | 60184.19 | 28938.84 | 31075.39 | 33213.66 | 28711.48 | 41595.43 | 404470.76
Grand Total |  |  |  | 155600.47 | 44865.81 | 70211.76 | 105840.99 | 605972.49 | 831486.33 | 1725816.74 | 339382.03 | 739421.98 | 602705.87 | 756921.43 | 1141738.38 | 7119964.28

## 800062547
Pin: 7183 | Project: TRTP Segment 3B
Order: 800062547 | 800062547- I: TRTP 3B: Windhub to Highwind 230 kV T
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 2253.71 | 1737.9 | 2657.69 | 1717.73 | 2154.94 | 2664.45 | 1914.95 | 2495.92 | 1804.99 | 1601.2 | 1950.51 | 2154.34 | 25108.33
|  | Labor Total |  | 2253.71 | 1737.9 | 2657.69 | 1717.73 | 2154.94 | 2664.45 | 1914.95 | 2495.92 | 1804.99 | 1601.2 | 1950.51 | 2154.34 | 25108.33
| BP&FM Total |  |  | 2253.71 | 1737.9 | 2657.69 | 1717.73 | 2154.94 | 2664.45 | 1914.95 | 2495.92 | 1804.99 | 1601.2 | 1950.51 | 2154.34 | 25108.33
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  | 460.38 | 1357.66 | 732.73 | 5872.5 |  | 5872.5 | 1169.99 |  |  |  | 15465.76
|  | Contract Total |  |  |  | 460.38 | 1357.66 | 732.73 | 5872.5 |  | 5872.5 | 1169.99 |  |  |  | 15465.76
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  |  | 460.38 | 1357.66 | 732.73 | 5872.5 |  | 5872.5 | 1169.99 |  |  |  | 15465.76
| Consultants - Strategic Planning/Develop | Contract | Contract Entries <$50,000 | [11 empty] | 393.75 | 393.75
|  | Contract Total | [12 empty] | 393.75 | 393.75
| Consultants - Strategic Planning/Develop Total | [13 empty] | 393.75 | 393.75
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 1399805.44 |  |  | 1399805.44
|  |  | Contract Entries <$50,000 | [8 empty] | -1399805.44 |  |  |  | -1399805.44
|  | Contract Total | [9 empty] | -1399805.44 | 1399805.44 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -1399805.44 | 1399805.44 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  | 276.82 |  |  | 6850.67 | [7 empty] | 7127.49
|  | Contract Total |  |  | 276.82 |  |  | 6850.67 | [7 empty] | 7127.49
| Contract Consult/Contract Ord to Ord Total |  |  |  | 276.82 |  |  | 6850.67 | [7 empty] | 7127.49
| CORP COMM SVP | Labor | Labor Entries <$5,000 | [9 empty] | 246.48 | 144.49 |  | 390.97
|  | Labor Total | [10 empty] | 246.48 | 144.49 |  | 390.97
| CORP COMM SVP Total | [11 empty] | 246.48 | 144.49 |  | 390.97
| Device MAC | Labor | Labor Entries <$5,000 | [6 empty] | 170 | [5 empty] | 170
|  | Labor Total | [7 empty] | 170 | [5 empty] | 170
| Device MAC Total | [8 empty] | 170 | [5 empty] | 170
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 4109.17 | 4109.17
|  | Labor Total | [12 empty] | 4109.17 | 4109.17
| ELEC SYS PLANNING Total | [13 empty] | 4109.17 | 4109.17
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 488.41 | [11 empty] | 488.41
|  | Labor Total |  | 488.41 | [11 empty] | 488.41
| ENG ADVANCEMENT Total |  |  | 488.41 | [11 empty] | 488.41
| ENGINEERING | Labor | Engineer |  |  | 8702.64 | [9 empty] | 8702.64
|  |  | Engineer Sr | 5027.2 |  | 8043.52 | 6094.08 | [8 empty] | 19164.8
|  |  | Labor Entries <$5,000 | 2911.86 | 6790.2 | 5426.18 | 10740.93 | 9212.54 | 11375.08 | 6392.91 | 3250.84 | 3641.17 | 3614.21 | 4694 |  | 68049.92
|  | Labor Total |  | 7939.06 | 6790.2 | 22172.34 | 16835.01 | 9212.54 | 11375.08 | 6392.91 | 3250.84 | 3641.17 | 3614.21 | 4694 |  | 95917.36
| ENGINEERING Total |  |  | 7939.06 | 6790.2 | 22172.34 | 16835.01 | 9212.54 | 11375.08 | 6392.91 | 3250.84 | 3641.17 | 3614.21 | 4694 |  | 95917.36
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC |  |  |  | 51607.48 | [8 empty] | 51607.48
|  |  | Contract Entries <$50,000 | 21122.48 | -57780.51 | 21427.6 | 49695.03 | 20264.5 | 48359 | 141704.66 | 54034.6 | 12913.9 | 34515.97 | 50476.07 | 29833.72 | 426567.02
|  | Contract Total |  | 21122.48 | -57780.51 | 21427.6 | 101302.51 | 20264.5 | 48359 | 141704.66 | 54034.6 | 12913.9 | 34515.97 | 50476.07 | 29833.72 | 478174.5
| Engineering/Technical Professional Servi Total |  |  | 21122.48 | -57780.51 | 21427.6 | 101302.51 | 20264.5 | 48359 | 141704.66 | 54034.6 | 12913.9 | 34515.97 | 50476.07 | 29833.72 | 478174.5
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 27397.47 | 7308.27 | 4272.66 | 28050.91 | 40657.56 |  | 36613.28 | 39171.22 | 30158.31 | 31315.9 | 42144.39 | 287089.97
|  |  | SHAW ENVIRONMENTAL INC. | [6 empty] | 55995.95 | [5 empty] | 55995.95
|  | Contract Total |  |  | 27397.47 | 7308.27 | 4272.66 | 28050.91 | 40657.56 | 55995.95 | 36613.28 | 39171.22 | 30158.31 | 31315.9 | 42144.39 | 343085.92
| Environmental/Safety Professional Servic Total |  |  |  | 27397.47 | 7308.27 | 4272.66 | 28050.91 | 40657.56 | 55995.95 | 36613.28 | 39171.22 | 30158.31 | 31315.9 | 42144.39 | 343085.92
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [5 empty] | 335.21 |  |  | 1532608.27 | -1532608.27 |  |  | 335.21
|  | IMM Correction Total | [6 empty] | 335.21 |  |  | 1532608.27 | -1532608.27 |  |  | 335.21
| IMM/Allocated - Correction Total | [7 empty] | 335.21 |  |  | 1532608.27 | -1532608.27 |  |  | 335.21
| ITBI (HCC) | Labor | Labor Entries <$5,000 |  |  | 1549.95 | [9 empty] | 1549.95
|  | Labor Total |  |  |  | 1549.95 | [9 empty] | 1549.95
| ITBI (HCC) Total |  |  |  |  | 1549.95 | [9 empty] | 1549.95
| Labor - Other | Labor | Labor - Other | [9 empty] | 22530.23 |  |  | 22530.23
|  |  | Labor Correction | [9 empty] | 112090.66 |  |  | 112090.66
|  |  | Labor Entries <$5,000 | 2450.71 | 1843.79 | 8072.22 | 15672.16 | 53923.17 | -36073.68 | -22954.25 | 26703.61 | -119338.73 | 55936.25 | -72075.72 | -2396.86 | -88237.33
|  |  | SUR-TRTP Seg 3B-58 |  |  | 44932.23 | 44403.8 | 48981.38 | 30951.42 | 16697.88 | 6011.95 |  |  |  |  | 191978.66
|  | Labor Total |  | 2450.71 | 1843.79 | 53004.45 | 60075.96 | 102904.55 | -5122.26 | -6256.37 | 32715.56 | -119338.73 | 190557.14 | -72075.72 | -2396.86 | 238362.22
| Labor - Other Total |  |  | 2450.71 | 1843.79 | 53004.45 | 60075.96 | 102904.55 | -5122.26 | -6256.37 | 32715.56 | -119338.73 | 190557.14 | -72075.72 | -2396.86 | 238362.22
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 |  |  | 160.47 | [9 empty] | 160.47
|  | Labor Total |  |  |  | 160.47 | [9 empty] | 160.47
| MAJOR PROJECT ORG Total |  |  |  |  | 160.47 | [9 empty] | 160.47
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  |  | 283.15 |  |  | 149.78 |  | 341.5 |  | 692.54 | 176.47 |  | 1643.44
|  | Labor Total |  |  |  | 283.15 |  |  | 149.78 |  | 341.5 |  | 692.54 | 176.47 |  | 1643.44
| NORTH GRIDMGMTCENTER Total |  |  |  |  | 283.15 |  |  | 149.78 |  | 341.5 |  | 692.54 | 176.47 |  | 1643.44
| Other | Other | Other | -407017.57 | 153083.58 | -50509.09 | 118978.38 | 332243.63 | -79241.44 | 45020.86 | 194914.57 | 215759.33 | 114290.3 | 41459.08 | 668780.51 | 1347762.14
|  | Other Total |  | -407017.57 | 153083.58 | -50509.09 | 118978.38 | 332243.63 | -79241.44 | 45020.86 | 194914.57 | 215759.33 | 114290.3 | 41459.08 | 668780.51 | 1347762.14
| Other Total |  |  | -407017.57 | 153083.58 | -50509.09 | 118978.38 | 332243.63 | -79241.44 | 45020.86 | 194914.57 | 215759.33 | 114290.3 | 41459.08 | 668780.51 | 1347762.14
| SC&M | Labor | Labor Entries <$5,000 |  | 1713.09 | 64603.3 | 59353.8 | 32150.18 | 62576.72 | 33673.48 | 41028.59 | 34565.05 | 469.84 |  |  | 330134.05
|  |  | SC&M / Apr Strt Mech |  |  |  |  | 26598.89 | 15975.9 |  | 10053.82 |  |  |  |  | 52628.61
|  |  | SC&M / Civil/Structural-Union |  |  |  |  | 5581.09 |  |  | 5042.72 |  |  |  |  | 10623.81
|  |  | SC&M / Cvl/Strc Union(PT) |  |  |  |  | 5563.38 | [7 empty] | 5563.38
|  |  | SC&M / Frm Wrk CFF |  |  | 5197.35 | 5868.9 | 12744.78 | 6096.24 |  | 6085.23 |  |  |  |  | 35992.5
|  |  | SC&M / Mech Structural |  |  |  | 5344.77 | 30365.56 | 17677.99 |  | 5846.63 |  |  |  |  | 59234.95
|  | Labor Total |  |  | 1713.09 | 69800.65 | 70567.47 | 113003.88 | 102326.85 | 33673.48 | 68056.99 | 34565.05 | 469.84 |  |  | 494177.3
| SC&M Total |  |  |  | 1713.09 | 69800.65 | 70567.47 | 113003.88 | 102326.85 | 33673.48 | 68056.99 | 34565.05 | 469.84 |  |  | 494177.3
| Subcontracting Services | Contract | Contract Entries <$50,000 | [8 empty] | 97.02 |  |  |  | 97.02
|  | Contract Total | [9 empty] | 97.02 |  |  |  | 97.02
| Subcontracting Services Total | [10 empty] | 97.02 |  |  |  | 97.02
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -10692.3 | 10692.3 |  |  | 0
|  | Contract Total | [9 empty] | -10692.3 | 10692.3 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -10692.3 | 10692.3 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 15585.83 | 839 | 27652.94 | 49249.8 | 17058.18 | 35787.82 | 83652.28 | 21335.97 | 18084.25 | 1636.58 | 1591.9 | 4511.36 | 276985.91
|  | Contract Total |  | 15585.83 | 839 | 27652.94 | 49249.8 | 17058.18 | 35787.82 | 83652.28 | 21335.97 | 18084.25 | 1636.58 | 1591.9 | 4511.36 | 276985.91
| Temporary/Supplementary - Technical/Prof Total |  |  | 15585.83 | 839 | 27652.94 | 49249.8 | 17058.18 | 35787.82 | 83652.28 | 21335.97 | 18084.25 | 1636.58 | 1591.9 | 4511.36 | 276985.91
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 4127.86 | 9452.31 | 5844.53 | 3251.19 | 261.91 | 459.76 | 1280.35 | 2928.17 | 106.25 |  | 146.08 | 599.83 | 28458.24
|  | Contract Total |  | 4127.86 | 9452.31 | 5844.53 | 3251.19 | 261.91 | 459.76 | 1280.35 | 2928.17 | 106.25 |  | 146.08 | 599.83 | 28458.24
| Temporary/Supplementary - Trade/Labor Total |  |  | 4127.86 | 9452.31 | 5844.53 | 3251.19 | 261.91 | 459.76 | 1280.35 | 2928.17 | 106.25 |  | 146.08 | 599.83 | 28458.24
| TRANSMISSION | Labor | Labor Entries <$5,000 | 1341.08 | 5763.11 | 27311.7 | 35811.7 | 28808.01 | 87198.88 | 77240.6 | 91939.05 | 159739.27 | 275321.82 | 106680.75 | 3157.58 | 900313.55
|  |  | TRANSMISSION / Driver Lght Duty | [5 empty] | 6013.44 |  | 5261.76 |  |  |  |  | 11275.2
|  |  | TRANSMISSION / Lineman Rbr Trn | [7 empty] | 115740.37 | 69922.22 | 76383.6 |  |  | 262046.19
|  |  | TRANSMISSION / Supr road R/W |  |  |  | 18940.38 | 28263.33 | 32137.33 | 10421.6 | 5437.2 | 12664.72 |  |  |  | 107864.56
|  | Labor Total |  | 1341.08 | 5763.11 | 27311.7 | 54752.08 | 57071.34 | 125349.65 | 87662.2 | 218378.38 | 242326.21 | 351705.42 | 106680.75 | 3157.58 | 1281499.5
| TRANSMISSION Total |  |  | 1341.08 | 5763.11 | 27311.7 | 54752.08 | 57071.34 | 125349.65 | 87662.2 | 218378.38 | 242326.21 | 351705.42 | 106680.75 | 3157.58 | 1281499.5
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 3593.4 | 8464.79 | 15005.88 | 10746.81 | 9507.69 | 5432.01 | 3477.77 | 9790 | 8228.83 | 12586.45 | 7938.39 |  | 94772.02
|  |  | Mgr-Prj/Prod |  |  | 5560.41 | 19401.05 | 14121.52 | 21143.71 | 5770.03 | 7357.82 | 12856.5 |  |  |  | 86211.04
|  | Labor Total |  | 3593.4 | 8464.79 | 20566.29 | 30147.86 | 23629.21 | 26575.72 | 9247.8 | 17147.82 | 21085.33 | 12586.45 | 7938.39 |  | 180983.06
| TRNS CAPITAL Total |  |  | 3593.4 | 8464.79 | 20566.29 | 30147.86 | 23629.21 | 26575.72 | 9247.8 | 17147.82 | 21085.33 | 12586.45 | 7938.39 |  | 180983.06
| TSD Fleet | Labor | Labor Entries <$5,000 |  | 111.58 | 6857.12 | 3872.74 | 6287.89 | 7589.96 | 8975.53 | 25334.01 | 26730.25 | 17740.56 | 9218.02 |  | 112717.66
|  |  | TSD Fleet / Foreman |  |  |  | 5832.69 |  |  |  | 8724.16 |  |  |  |  | 14556.85
|  | Labor Total |  |  | 111.58 | 6857.12 | 9705.43 | 6287.89 | 7589.96 | 8975.53 | 34058.17 | 26730.25 | 17740.56 | 9218.02 |  | 127274.51
| TSD Fleet Total |  |  |  | 111.58 | 6857.12 | 9705.43 | 6287.89 | 7589.96 | 8975.53 | 34058.17 | 26730.25 | 17740.56 | 9218.02 |  | 127274.51
1. Project Support Total |  |  |  | -348115.03 | 159693.13 | 216548.44 | 522213.74 | 719726.88 | 323139.64 | 469434.6 | 692144.27 | 620226.76 | 637704.47 | 183715.94 | 753287.79 | 4949720.63
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | HOLLIDAY ROCK |  |  |  | 87948 | 64434 | 226812 | 6720 | 50796 | 32760 | 19740 |  |  | 489210
|  |  | HUB CONSTRUCTION SPECIALTIES, INC. |  |  |  | 8004.6 | [8 empty] | 8004.6
|  |  | Material Entries <$5,000 | 333 | 428.55 | 50.58 | 7570.76 | 5309 | 8051 | 3884.78 |  | 4041.16 | 759 |  |  | 30427.83
|  |  | SHAMROCK VALCAT INC |  |  |  | 8350 | [8 empty] | 8350
|  | Material - Direct Purchase Total |  | 333 | 428.55 | 50.58 | 111873.36 | 69743 | 234863 | 10604.78 | 50796 | 36801.16 | 20499 |  |  | 535992.43
| Building, Shop & Industrial Products/Eqp Total |  |  | 333 | 428.55 | 50.58 | 111873.36 | 69743 | 234863 | 10604.78 | 50796 | 36801.16 | 20499 |  |  | 535992.43
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 11.85 |  | 1634.92 | 356.4 |  |  | 1039.5 |  |  |  | 3042.67
|  | Material - Direct Purchase Total |  |  |  | 11.85 |  | 1634.92 | 356.4 |  |  | 1039.5 |  |  |  | 3042.67
| Fuels, Chemicals & Petrochem-DP Total |  |  |  |  | 11.85 |  | 1634.92 | 356.4 |  |  | 1039.5 |  |  |  | 3042.67
| Labor - Other | Labor | Labor Entries <$5,000 |  |  |  |  | 613.51 | [7 empty] | 613.51
|  | Labor Total | [5 empty] | 613.51 | [7 empty] | 613.51
| Labor - Other Total | [6 empty] | 613.51 | [7 empty] | 613.51
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -366.63 | 366.63 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -366.63 | 366.63 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -366.63 | 366.63 |  |  | 0
| Material - Inventory | Material | Material - Inventory | [6 empty] | -22104.53 |  | -3117.03 | 3117.03 |  |  | -22104.53
|  | Material Total | [7 empty] | -22104.53 |  | -3117.03 | 3117.03 |  |  | -22104.53
| Material - Inventory Total | [8 empty] | -22104.53 |  | -3117.03 | 3117.03 |  |  | -22104.53
| Material - Other | Material | Material - Other | 31150.86 | 30756.99 | 58611.05 | 81366.17 | 28854.22 | 61963.56 | 20357.18 | 8945.14 | 9435.38 | 5841.36 | 245.55 | 6571.42 | 344098.88
|  | Material Total |  | 31150.86 | 30756.99 | 58611.05 | 81366.17 | 28854.22 | 61963.56 | 20357.18 | 8945.14 | 9435.38 | 5841.36 | 245.55 | 6571.42 | 344098.88
| Material - Other Total |  |  | 31150.86 | 30756.99 | 58611.05 | 81366.17 | 28854.22 | 61963.56 | 20357.18 | 8945.14 | 9435.38 | 5841.36 | 245.55 | 6571.42 | 344098.88
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | PHILLIPS STEEL COMPANY |  | 21636.54 |  |  |  | 5596.72 | [6 empty] | 27233.26
|  | Material - Direct Purchase Total |  |  | 21636.54 |  |  |  | 5596.72 | [6 empty] | 27233.26
| Metals & Fabricated Metal Products-DP Total |  |  |  | 21636.54 |  |  |  | 5596.72 | [6 empty] | 27233.26
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 141.6 |  |  |  | 294.89 |  | 35.02 |  | 89.64 |  | 561.15
|  |  | ONE SOURCE DISTRIBUTORS INC | 6371.96 | [11 empty] | 6371.96
|  | Material - Direct Purchase Total |  | 6371.96 |  | 141.6 |  |  |  | 294.89 |  | 35.02 |  | 89.64 |  | 6933.11
| Office & Office Support Products-DP Total |  |  | 6371.96 |  | 141.6 |  |  |  | 294.89 |  | 35.02 |  | 89.64 |  | 6933.11
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | W E HALL CO INC |  |  |  | 61000.4 | [8 empty] | 61000.4
|  | Material - Direct Purchase Total |  |  |  |  | 61000.4 | [8 empty] | 61000.4
| Pipe/Tubing, Fittings and Gaskets-DP Total | [5 empty] | 61000.4 | [8 empty] | 61000.4
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | AGILE SOURCING PARTNERS INC |  |  |  | 6125 | [8 empty] | 6125
|  |  | CUNNINGHAM-DAVIS CORP | [8 empty] | 5280 |  |  |  | 5280
|  |  | Material Entries <$5,000 | 4001.6 | -261771 | 2709.99 | 800 | 1925.97 | 304.81 | 899.35 |  | 114 |  | 2700.45 |  | -248314.83
|  |  | ONE SOURCE DISTRIBUTORS INC | 236649.53 | 325430.29 | 122932.33 | 82555.28 | [8 empty] | 767567.43
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC |  |  |  |  | 56192.39 | 5300.75 | [6 empty] | 61493.14
|  | Material - Direct Purchase Total |  | 240651.13 | 63659.29 | 125642.32 | 89480.28 | 58118.36 | 5605.56 | 899.35 |  | 5394 |  | 2700.45 |  | 592150.74
| Pole Line Hdwe & Connectors-DP Total |  |  | 240651.13 | 63659.29 | 125642.32 | 89480.28 | 58118.36 | 5605.56 | 899.35 |  | 5394 |  | 2700.45 |  | 592150.74
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | 603 |  | 1090.42 |  | 4909.45 |  |  |  |  | 460 |  |  | 7062.87
|  |  | PARCELL STEEL CO |  |  | 114291.45 | 171411.5 | 195752.7 | 52492.7 | [6 empty] | 533948.35
|  | Material - Direct Purchase Total |  | 603 |  | 115381.87 | 171411.5 | 200662.15 | 52492.7 |  |  |  | 460 |  |  | 541011.22
| Steel / Fabricated / Structural-DP Total |  |  | 603 |  | 115381.87 | 171411.5 | 200662.15 | 52492.7 |  |  |  | 460 |  |  | 541011.22
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | -0.09 |  |  | -0.09
|  | Material - Direct Purchase Total | [10 empty] | -0.09 |  |  | -0.09
| Towers/Poles, Steel & Concrete-DP Total | [11 empty] | -0.09 |  |  | -0.09
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 719.85 | 117.79 | 1692.97 | 7105.58 | 4454.56 | 2413.49 | 2375.62 | 9219.65 | 101.17 |  | 189.55 |  | 28390.23
|  |  | Transportation & Mobile Equip-DP | [5 empty] | 5978.05 | [6 empty] | 5978.05
|  | Material - Direct Purchase Total |  | 719.85 | 117.79 | 1692.97 | 7105.58 | 4454.56 | 8391.54 | 2375.62 | 9219.65 | 101.17 |  | 189.55 |  | 34368.28
| Transportation & Mobile Equip-DP Total |  |  | 719.85 | 117.79 | 1692.97 | 7105.58 | 4454.56 | 8391.54 | 2375.62 | 9219.65 | 101.17 |  | 189.55 |  | 34368.28
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 |  | -19566.12 | 897.4 |  | 350 |  |  |  |  | 24210 |  |  | 5891.28
|  | Material - Direct Purchase Total |  |  | -19566.12 | 897.4 |  | 350 |  |  |  |  | 24210 |  |  | 5891.28
| Wire, Cable & Bus Bar-DP Total |  |  |  | -19566.12 | 897.4 |  | 350 |  |  |  |  | 24210 |  |  | 5891.28
2. Material Total |  |  |  | 279829.8 | 97033.04 | 302429.64 | 522237.29 | 364430.72 | 369269.48 | 12427.29 | 68960.79 | 49322.57 | 54493.93 | 3225.19 | 6571.42 | 2130231.16
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 4145.8 | 8446.8 | 2805 | 13132.16 | 42775.74 | 73002.25 | 157260.41 | 123564.55 | 70953.11 | 120330.29 | 33992.41 | 153049.97 | 803458.49
|  | Contract Total |  | 4145.8 | 8446.8 | 2805 | 13132.16 | 42775.74 | 73002.25 | 157260.41 | 123564.55 | 70953.11 | 120330.29 | 33992.41 | 153049.97 | 803458.49
| Construction Management Services Total |  |  | 4145.8 | 8446.8 | 2805 | 13132.16 | 42775.74 | 73002.25 | 157260.41 | 123564.55 | 70953.11 | 120330.29 | 33992.41 | 153049.97 | 803458.49
| Construction Services - Other | Contract | Construction Services - Other | [7 empty] | 278068.9 |  | 86984.3 |  |  | 365053.2
|  |  | Contract Entries <$50,000 | 7595.2 | 2063.75 | 2416.84 | 22257.04 | 37665.22 | 50635.41 | 13484.69 | 32512.39 | 117453.93 | 64179.74 | 4236.47 | 7763.34 | 362264.02
|  |  | RJ ALLEN INC |  |  |  | 273249.98 | 430406.99 | 394325.65 | 340934.39 | 155638.18 | 116611.78 | 96456.4 |  |  | 1807623.37
|  | Contract Total |  | 7595.2 | 2063.75 | 2416.84 | 295507.02 | 468072.21 | 444961.06 | 354419.08 | 466219.47 | 234065.71 | 247620.44 | 4236.47 | 7763.34 | 2534940.59
| Construction Services - Other Total |  |  | 7595.2 | 2063.75 | 2416.84 | 295507.02 | 468072.21 | 444961.06 | 354419.08 | 466219.47 | 234065.71 | 247620.44 | 4236.47 | 7763.34 | 2534940.59
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 |  | 981.64 | 817.83 | 5101.08 | 1021.1 | 903.1 | 1971.2 | 903.1 | 903.1 | 16261.58 | 8613.7 | 3843.86 | 41321.29
|  |  | CUNNINGHAM-DAVIS CORP | [11 empty] | 93629.47 | 93629.47
|  | Contract Total |  |  | 981.64 | 817.83 | 5101.08 | 1021.1 | 903.1 | 1971.2 | 903.1 | 903.1 | 16261.58 | 8613.7 | 97473.33 | 134950.76
| Construction, Civil/Structural Total |  |  |  | 981.64 | 817.83 | 5101.08 | 1021.1 | 903.1 | 1971.2 | 903.1 | 903.1 | 16261.58 | 8613.7 | 97473.33 | 134950.76
| Construction, Concrete/Masonry | Contract | Contract Entries <$50,000 | [7 empty] | 665 |  |  |  |  | 665
|  | Contract Total | [8 empty] | 665 |  |  |  |  | 665
| Construction, Concrete/Masonry Total | [9 empty] | 665 |  |  |  |  | 665
| Construction, Earthwork | Contract | Contract Entries <$50,000 | [11 empty] | 6763.53 | 6763.53
|  | Contract Total | [12 empty] | 6763.53 | 6763.53
| Construction, Earthwork Total | [13 empty] | 6763.53 | 6763.53
| Construction, Envrmntl Contamination | Contract | Contract Entries <$50,000 | [8 empty] | 1324.1 |  |  |  | 1324.1
|  | Contract Total | [9 empty] | 1324.1 |  |  |  | 1324.1
| Construction, Envrmntl Contamination Total | [10 empty] | 1324.1 |  |  |  | 1324.1
| Construction, Paving/Fencing | Contract | Contract Entries <$50,000 | [6 empty] | 53.61 | [5 empty] | 53.61
|  | Contract Total | [7 empty] | 53.61 | [5 empty] | 53.61
| Construction, Paving/Fencing Total | [8 empty] | 53.61 | [5 empty] | 53.61
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 | [5 empty] | 659 | 1468 |  |  |  |  | 1168.88 | 3295.88
|  | Contract Total | [6 empty] | 659 | 1468 |  |  |  |  | 1168.88 | 3295.88
| Decontamination & Waste Disposal Service Total | [7 empty] | 659 | 1468 |  |  |  |  | 1168.88 | 3295.88
| Electrical Construction, Substations | Contract | Contract Entries <$50,000 |  |  |  | -857.26 | [8 empty] | -857.26
|  | Contract Total |  |  |  |  | -857.26 | [8 empty] | -857.26
| Electrical Construction, Substations Total | [5 empty] | -857.26 | [8 empty] | -857.26
| Electrical Construction, Transmission Li | Contract | DICK HOWELLS HOLE DRILLING |  |  |  | 144638.5 | 109265 | 91595.41 | 57280.04 | 110078.06 | 97899.13 |  |  |  | 610756.14
|  | Contract Total |  |  |  |  | 144638.5 | 109265 | 91595.41 | 57280.04 | 110078.06 | 97899.13 |  |  |  | 610756.14
| Electrical Construction, Transmission Li Total | [5 empty] | 144638.5 | 109265 | 91595.41 | 57280.04 | 110078.06 | 97899.13 |  |  |  | 610756.14
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 2577.98 | 2577.98
|  | Labor Total | [12 empty] | 2577.98 | 2577.98
| GRID OPS Total | [13 empty] | 2577.98 | 2577.98
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 |  |  | 4795 |  | 17334.94 | 10399.07 | 37704.88 | 0 |  |  | 4860.78 | 4890.36 | 79985.03
|  |  | OFFSHORE CRANE & SERVICE CO | [5 empty] | 188660.71 |  | 206828.6 | 65774.45 | 60431.04 |  |  | 521694.8
|  | Contract Total |  |  |  | 4795 |  | 17334.94 | 199059.78 | 37704.88 | 206828.6 | 65774.45 | 60431.04 | 4860.78 | 4890.36 | 601679.83
| Hauling / Industrial Moving Services Total |  |  |  |  | 4795 |  | 17334.94 | 199059.78 | 37704.88 | 206828.6 | 65774.45 | 60431.04 | 4860.78 | 4890.36 | 601679.83
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [5 empty] | 7044.34 | [6 empty] | 7044.34
|  |  | PAR ELECTRICAL CONTRACTORS INC | 328200 | [11 empty] | 328200
|  | Contract Total |  | 328200 |  |  |  |  | 7044.34 | [6 empty] | 335244.34
| Major Construction, Turnkey, Trans/Subs Total |  |  | 328200 |  |  |  |  | 7044.34 | [6 empty] | 335244.34
| SC&M | Labor | Labor Entries <$5,000 |  | 598.45 | 16772.8 | 16253.73 | 32026.75 | 26246.27 | 3194.76 | 2138.96 | 1119.24 |  |  |  | 98350.96
|  | Labor Total |  |  | 598.45 | 16772.8 | 16253.73 | 32026.75 | 26246.27 | 3194.76 | 2138.96 | 1119.24 |  |  |  | 98350.96
| SC&M Total |  |  |  | 598.45 | 16772.8 | 16253.73 | 32026.75 | 26246.27 | 3194.76 | 2138.96 | 1119.24 |  |  |  | 98350.96
| Security / Protection Services | Contract | Contract Entries <$50,000 |  |  | 1180.5 | 6468.52 | 9735.94 | 33980.23 | 26281.95 | 34824.9 | 44369.36 | 88654.9 | 47278 | 81224.54 | 373998.84
|  | Contract Total |  |  |  | 1180.5 | 6468.52 | 9735.94 | 33980.23 | 26281.95 | 34824.9 | 44369.36 | 88654.9 | 47278 | 81224.54 | 373998.84
| Security / Protection Services Total |  |  |  |  | 1180.5 | 6468.52 | 9735.94 | 33980.23 | 26281.95 | 34824.9 | 44369.36 | 88654.9 | 47278 | 81224.54 | 373998.84
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 5043.27 | 19941.06 | 14080.11 | 63191.85 | 104171.78 | 126436.75 | 115990.53 | 165098.55 | 206153.67 | 88614.94 | 158120.63 | 105608.28 | 1172451.42
|  |  | CUNNINGHAM-DAVIS CORP | [9 empty] | 65959.68 |  |  | 65959.68
|  | Contract Total |  | 5043.27 | 19941.06 | 14080.11 | 63191.85 | 104171.78 | 126436.75 | 115990.53 | 165098.55 | 206153.67 | 154574.62 | 158120.63 | 105608.28 | 1238411.1
| Short Term Equipment Rent Total |  |  | 5043.27 | 19941.06 | 14080.11 | 63191.85 | 104171.78 | 126436.75 | 115990.53 | 165098.55 | 206153.67 | 154574.62 | 158120.63 | 105608.28 | 1238411.1
| TRANSMISSION | Labor | Labor Entries <$5,000 | 3961.38 | 6105.48 | 9763.73 | 52052.45 | 40280.86 | 106735.33 | 77961.15 | 178589.31 | 148121.56 | 169197.88 | 59920.6 | 1078.79 | 853768.52
|  |  | TRANSMISSION / Lineman Apr | [7 empty] | 50687.35 | 40092.14 | 26447.25 |  |  | 117226.74
|  |  | TRANSMISSION / Lineman Rbr Trn | [9 empty] | 5641.2 |  |  | 5641.2
|  |  | TRANSMISSION / Patroman Sr | [7 empty] | 18442.15 | 15740.21 |  |  |  | 34182.36
|  |  | TRANSMISSION / Supervisor |  |  |  | 24036.6 | 29434.65 | 32475.6 | 23367.3 | 80243.25 | 91126.65 | 54111.45 | 15481.2 |  | 350276.7
|  | Labor Total |  | 3961.38 | 6105.48 | 9763.73 | 76089.05 | 69715.51 | 139210.93 | 101328.45 | 327962.06 | 295080.56 | 255397.78 | 75401.8 | 1078.79 | 1361095.52
| TRANSMISSION Total |  |  | 3961.38 | 6105.48 | 9763.73 | 76089.05 | 69715.51 | 139210.93 | 101328.45 | 327962.06 | 295080.56 | 255397.78 | 75401.8 | 1078.79 | 1361095.52
| TRNS CAPITAL | Labor | Cnst/Mtrl Cndtr |  |  |  | 6406.56 | 5338.8 | [7 empty] | 11745.36
|  |  | Labor Entries <$5,000 | 1401.61 | 1033.35 | 1461.54 | 1092.66 | 4644.63 | 11084.83 | 5007.96 | 2301.63 | 4161.19 | 1681.48 | 1657.97 |  | 35528.85
|  | Labor Total |  | 1401.61 | 1033.35 | 1461.54 | 7499.22 | 9983.43 | 11084.83 | 5007.96 | 2301.63 | 4161.19 | 1681.48 | 1657.97 |  | 47274.21
| TRNS CAPITAL Total |  |  | 1401.61 | 1033.35 | 1461.54 | 7499.22 | 9983.43 | 11084.83 | 5007.96 | 2301.63 | 4161.19 | 1681.48 | 1657.97 |  | 47274.21
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | [11 empty] | 164 | 164
|  |  | TSD-HERC - Crane Svs / Cranes |  |  | 60801.5 | 141308.9 | 181275.63 | 278599.13 | 112000.7 | 299846.4 | 172478.2 | 117671.6 | 5938.35 |  | 1369920.41
|  | Labor Total |  |  |  | 60801.5 | 141308.9 | 181275.63 | 278599.13 | 112000.7 | 299846.4 | 172478.2 | 117671.6 | 5938.35 | 164 | 1370084.41
| TSD-HERC - Crane Svs Total |  |  |  |  | 60801.5 | 141308.9 | 181275.63 | 278599.13 | 112000.7 | 299846.4 | 172478.2 | 117671.6 | 5938.35 | 164 | 1370084.41
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | 82 | 246 | 328 | 656 | 1476 | 1230 | 1230 | 1640 | 2214 | 2542 | 1312 | 1312 | 14268
|  | Labor Total |  | 82 | 246 | 328 | 656 | 1476 | 1230 | 1230 | 1640 | 2214 | 2542 | 1312 | 1312 | 14268
| TSD-HERC - Rental Total |  |  | 82 | 246 | 328 | 656 | 1476 | 1230 | 1230 | 1640 | 2214 | 2542 | 1312 | 1312 | 14268
| Weed Abatement / Line Clearing | Contract | Contract Entries <$50,000 |  |  |  |  | 3165.8 |  | 7524.38 |  | 16687.4 |  |  |  | 27377.58
|  |  | CPM INC | [11 empty] | 61104.82 | 61104.82
|  | Contract Total | [5 empty] | 3165.8 |  | 7524.38 |  | 16687.4 |  |  | 61104.82 | 88482.4
| Weed Abatement / Line Clearing Total | [6 empty] | 3165.8 |  | 7524.38 |  | 16687.4 |  |  | 61104.82 | 88482.4
3. Construction Total |  |  |  | 350429.26 | 39416.53 | 115222.85 | 768988.77 | 1050019.83 | 1434013.08 | 982715.95 | 1742071.28 | 1213183.22 | 1065165.73 | 341412.11 | 524179.82 | 9626818.43
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -69663.44 | 4324.48 | 12552.34 | 11701.12 | 9991.69 | 8425.79 | 3995.82 | 13348.53 | 7751.15 | 3765.7 | 9409.17 | 2905.83 | 18508.18
|  |  | PROCUREMENT TDBU |  |  |  | 7024.71 | 6997.52 | 8510.57 | 6276.61 | 7467.18 |  | 13694.64 |  |  | 49971.23
|  |  | TDBU Vehicle Cost | 6904.84 | 8153.25 | 8996.37 | 15091.12 | 15118.66 | 22374.4 | 16540.83 | 28989.49 | 32281.52 | 43252.09 | 9257.5 |  | 206960.07
|  |  | TRTP-2010 Segment 3B - TDBU | 72431.39 | 29248.88 | 84397.98 | 161765 | 312088.21 | 98266.3 | 647441.77 | 157634.11 |  | 216716.95 | 52630.71 | 165229.93 | 1997851.23
|  | Chargeback Total |  | 9672.79 | 41726.61 | 105946.69 | 195581.95 | 344196.08 | 137577.06 | 674255.03 | 207439.31 | 40032.67 | 277429.38 | 71297.38 | 168135.76 | 2273290.71
| Chargebacks Total |  |  | 9672.79 | 41726.61 | 105946.69 | 195581.95 | 344196.08 | 137577.06 | 674255.03 | 207439.31 | 40032.67 | 277429.38 | 71297.38 | 168135.76 | 2273290.71
| Labor - Other | Labor | Division Overhead | 28364.16 |  | 5146.37 | 48310.95 | 79594.13 | 94471.32 | 54262.51 | 106384.04 | 26098.78 | 195378.88 |  | 5269.09 | 643280.23
|  |  | Labor Entries <$5,000 | 14486.91 | 13169.7 | 21416.65 | 4977.56 | 3530 | 3755.68 | 14904.88 | 38.76 | -11050.23 |  | 11491.82 | 8495.47 | 85217.2
|  |  | OH Tool Expenses |  |  | 5028.64 | 10985.19 | 12307.36 | 13776.35 | 10434 | 16509.51 | 18408.91 | 19663.55 | 6997.98 |  | 114111.49
|  |  | Paid Absence |  | 5617.23 | 22706.5 | 33580.2 | 44389.22 | 34876.34 | 23255.14 | 59608.47 | 35604.98 | 77153.6 | 5953.55 |  | 342745.23
|  |  | TOOL EXPENSE |  |  |  | 5942.42 | 6612.86 | 9248.72 |  | 14454.39 | 15702.69 | 19918.85 |  |  | 71879.93
|  | Labor Total |  | 42851.07 | 18786.93 | 54298.16 | 103796.32 | 146433.57 | 156128.41 | 102856.53 | 196995.17 | 84765.13 | 312114.88 | 24443.35 | 13764.56 | 1257234.08
| Labor - Other Total |  |  | 42851.07 | 18786.93 | 54298.16 | 103796.32 | 146433.57 | 156128.41 | 102856.53 | 196995.17 | 84765.13 | 312114.88 | 24443.35 | 13764.56 | 1257234.08
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -33756.27 | 33756.27 |  |  | 0
|  | Overhead Total | [9 empty] | -33756.27 | 33756.27 |  |  | 0
| Overhead Correction Total | [10 empty] | -33756.27 | 33756.27 |  |  | 0
4. Allocated Total |  |  |  | 52523.86 | 60513.54 | 160244.85 | 299378.27 | 490629.65 | 293705.47 | 777111.56 | 404434.48 | 91041.53 | 623300.53 | 95740.73 | 181900.32 | 3530524.79
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 149896.48 | 10147.58 | [7 empty] | 160044.06
|  |  | Capitalized Overhead - A&G | 41409.9 | 6193.53 | 31377.88 | 73163.96 | 201594.41 | -1117855.36 | 82363.09 | 80516.87 | 85958.47 | 62542.98 | 17720.85 | 28748.07 | -406265.35
|  |  | Capitalized Overhead - Inj & Damages | 283.59 | 350.31 | 782.78 | 1059.62 | 12464.48 | -56494.05 | 723.58 | 2104.77 | 2448.35 | 603.13 | 702.41 | 521.48 | -34449.55
|  |  | Capitalized Overhead - P&B/Payroll Tax | 25173.35 | 55016.55 | 231540.2 | 422959.62 | 612575.44 | -1727202.48 | 310369.32 | 526663.88 | 677031.71 | 367775.24 | 102724.15 | 30346.86 | 1634973.84
|  |  | Corporate Overheads Correction |  |  |  |  | -465503.29 | [7 empty] | -465503.29
|  | Non Budgeted Total |  | 66866.84 | 61560.39 | 263700.86 | 647079.68 | 371278.62 | -2901551.89 | 393455.99 | 609285.52 | 765438.53 | 430921.35 | 121147.41 | 59616.41 | 888799.71
| Non Budget - Other Total |  |  | 66866.84 | 61560.39 | 263700.86 | 647079.68 | 371278.62 | -2901551.89 | 393455.99 | 609285.52 | 765438.53 | 430921.35 | 121147.41 | 59616.41 | 888799.71
5. Corporate Overhead Total |  |  |  | 66866.84 | 61560.39 | 263700.86 | 647079.68 | 371278.62 | -2901551.89 | 393455.99 | 609285.52 | 765438.53 | 430921.35 | 121147.41 | 59616.41 | 888799.71
Grand Total |  |  |  | 401534.73 | 418216.63 | 1058146.64 | 2759897.75 | 2996085.7 | -481424.22 | 2635145.39 | 3516896.34 | 2739212.61 | 2811586.01 | 745241.38 | 1525555.76 | 21126094.72

## TRTP Seg 3C
WO | SumOfYTD2012 | Order | Project
900692988- Magunden: Install protective relays whic | 39325.12 | 900692988 | TRTP Segment 3C
800219631- I: TRTP 3C-3: VINCENT 500KV - EQUIP ONE | -53793.29 | 800219631 | TRTP Segment 3C
800219567- I: TRTP 3C-6: ANTELOPE SUBSTATION - 500K | -96.21 | 800219567 | TRTP Segment 3C
800219505- SC MP/SH I: TRTP 3C-5: ANTELOPE SUBSTATI | 5832334.9 | 800219505 | TRTP Segment 3C
800219436- I: TRTP Segment 3C: Windhub Sub: Install | 30489687.41 | 800219436 | TRTP Segment 3C
800219424- I: TRTP 3C-1: WINDHUB 500KV UPGRADE PIN | 3399475.26 | 800219424 | TRTP Segment 3C
800051827- 9219-2303--FERC-ANTELOPE TRANSMISSION | -664580.27 | 800051827 | TRTP Segment 3C

## 900692988
Pin: 7014 | Project: TRTP Segment 3C
Order: 900692988 | 900692988- Magunden: Install protective relays whic
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [9 empty] | 2012 Total | Grand Total
SubCategory | Prime | Group | Details | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [9 empty] | 1125.84 | 1125.84 | 1125.84
|  | Labor Total | [10 empty] | 1125.84 | 1125.84 | 1125.84
| ELEC SYS PLANNING Total | [11 empty] | 1125.84 | 1125.84 | 1125.84
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  |  | 87.9 | [7 empty] | 87.9 | 87.9
|  | Labor Total |  |  |  | 87.9 | [7 empty] | 87.9 | 87.9
| ENG ADVANCEMENT Total |  |  |  |  | 87.9 | [7 empty] | 87.9 | 87.9
| ENGINEERING | Labor | Labor Entries <$5,000 | 234.58 |  | 2346.8 | 2690.44 |  | 543.67 |  |  | 1013.34 |  | 6828.83 | 6828.83
|  | Labor Total |  | 234.58 |  | 2346.8 | 2690.44 |  | 543.67 |  |  | 1013.34 |  | 6828.83 | 6828.83
| ENGINEERING Total |  |  | 234.58 |  | 2346.8 | 2690.44 |  | 543.67 |  |  | 1013.34 |  | 6828.83 | 6828.83
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  |  |  |  | 200 | [5 empty] | 200 | 200
|  | Contract Total | [5 empty] | 200 | [5 empty] | 200 | 200
| Engineering/Technical Professional Servi Total | [6 empty] | 200 | [5 empty] | 200 | 200
| Labor - Other | Labor | Labor Entries <$5,000 | 5.67 | -5.67 | 307.39 | -454.82 | 147.43 |  |  |  |  | 190.51 | 190.51 | 190.51
|  | Labor Total |  | 5.67 | -5.67 | 307.39 | -454.82 | 147.43 |  |  |  |  | 190.51 | 190.51 | 190.51
| Labor - Other Total |  |  | 5.67 | -5.67 | 307.39 | -454.82 | 147.43 |  |  |  |  | 190.51 | 190.51 | 190.51
| Other | Other | Other |  |  | 10577.19 | -10577.19 | [6 empty] | 0 | 0
|  | Other Total |  |  |  | 10577.19 | -10577.19 | [6 empty] | 0 | 0
| Other Total |  |  |  |  | 10577.19 | -10577.19 | [6 empty] | 0 | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  | 759 | 189.75 | 379.5 |  | 97.06 |  |  |  |  | 1425.31 | 1425.31
|  | Contract Total |  |  | 759 | 189.75 | 379.5 |  | 97.06 |  |  |  |  | 1425.31 | 1425.31
| Temporary/Supplementary - Trade/Labor Total |  |  |  | 759 | 189.75 | 379.5 |  | 97.06 |  |  |  |  | 1425.31 | 1425.31
1. Project Support Total |  |  |  | 240.25 | 753.33 | 13509.03 | -7962.07 | 347.43 | 640.73 |  |  | 1013.34 | 1316.35 | 9858.39 | 9858.39
2. Material | Material - Other | Material | Material - Other |  |  | 0.05 | 711.77 |  |  |  | 0.16 |  |  | 711.98 | 711.98
|  | Material Total |  |  |  | 0.05 | 711.77 |  |  |  | 0.16 |  |  | 711.98 | 711.98
| Material - Other Total |  |  |  |  | 0.05 | 711.77 |  |  |  | 0.16 |  |  | 711.98 | 711.98
| Protection and Test-DP | Material - Direct Purchase | GE CONSUMER AND INDUSTRIAL |  |  |  | 9668.24 | [6 empty] | 9668.24 | 9668.24
|  | Material - Direct Purchase Total |  |  |  |  | 9668.24 | [6 empty] | 9668.24 | 9668.24
| Protection and Test-DP Total | [5 empty] | 9668.24 | [6 empty] | 9668.24 | 9668.24
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 64.74 |  |  |  |  | 214.96 |  |  | 279.7 | 279.7
|  | Material - Direct Purchase Total |  |  |  | 64.74 |  |  |  |  | 214.96 |  |  | 279.7 | 279.7
| Transportation & Mobile Equip-DP Total |  |  |  |  | 64.74 |  |  |  |  | 214.96 |  |  | 279.7 | 279.7
2. Material Total | [5 empty] | 64.79 | 10380.01 |  |  |  | 215.12 |  |  | 10659.92 | 10659.92
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  |  |  | 257.6 | [5 empty] | 257.6 | 257.6
|  | Contract Total | [5 empty] | 257.6 | [5 empty] | 257.6 | 257.6
| Construction Management Services Total | [6 empty] | 257.6 | [5 empty] | 257.6 | 257.6
| SCM HOME CENTER | Labor | Labor Entries <$5,000 | [5 empty] | 97.89 | 296.67 |  |  |  | 394.56 | 394.56
|  | Labor Total | [6 empty] | 97.89 | 296.67 |  |  |  | 394.56 | 394.56
| SCM HOME CENTER Total | [7 empty] | 97.89 | 296.67 |  |  |  | 394.56 | 394.56
3. Construction Total | [7 empty] | 257.6 | 97.89 | 296.67 |  |  |  | 652.16 | 652.16
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 21.42 | 4.48 | 249.84 | 354.11 | 130.83 | 101.41 | 34.3 | 1.42 | 105.07 | 119.79 | 1122.67 | 1122.67
|  | Chargeback Total |  | 21.42 | 4.48 | 249.84 | 354.11 | 130.83 | 101.41 | 34.3 | 1.42 | 105.07 | 119.79 | 1122.67 | 1122.67
| Chargebacks Total |  |  | 21.42 | 4.48 | 249.84 | 354.11 | 130.83 | 101.41 | 34.3 | 1.42 | 105.07 | 119.79 | 1122.67 | 1122.67
| Labor - Other | Labor | Labor Entries <$5,000 | 79.3 | 54.99 | 890.37 | 1359.99 | 84.1 | 216.79 | 92.45 | 17.53 | 247.45 | 396.89 | 3439.86 | 3439.86
|  | Labor Total |  | 79.3 | 54.99 | 890.37 | 1359.99 | 84.1 | 216.79 | 92.45 | 17.53 | 247.45 | 396.89 | 3439.86 | 3439.86
| Labor - Other Total |  |  | 79.3 | 54.99 | 890.37 | 1359.99 | 84.1 | 216.79 | 92.45 | 17.53 | 247.45 | 396.89 | 3439.86 | 3439.86
4. Allocated Total |  |  |  | 100.72 | 59.47 | 1140.21 | 1714.1 | 214.93 | 318.2 | 126.75 | 18.95 | 352.52 | 516.68 | 4562.53 | 4562.53
5. Corporate Overhead | Non Budget - Other | Non Budgeted | AFUDC - Debt/Equity | 1.84 | -1.84 | [8 empty] | 0 | 0
|  |  | Capitalized Overhead - A&G | 12.15 | 28.98 | 344.31 | 524.98 | 28.79 | 29.89 | 18.97 | 6.05 | 36.1 | 51.46 | 1081.68 | 1081.68
|  |  | Capitalized Overhead - Inj & Damages | 0.36 | 0.04 | 35.23 | 18.51 | 0.33 | 1.25 | 0.38 | 0.74 | 2.25 | 2.06 | 61.15 | 61.15
|  |  | Capitalized Overhead - P&B/Payroll Tax | 246.34 | -7.29 | 4136.9 | 2992.55 | 190.92 | 521.54 | 425.06 |  | 864.38 | 3078.89 | 12449.29 | 12449.29
|  | Non Budgeted Total |  | 260.69 | 19.89 | 4516.44 | 3536.04 | 220.04 | 552.68 | 444.41 | 6.79 | 902.73 | 3132.41 | 13592.12 | 13592.12
| Non Budget - Other Total |  |  | 260.69 | 19.89 | 4516.44 | 3536.04 | 220.04 | 552.68 | 444.41 | 6.79 | 902.73 | 3132.41 | 13592.12 | 13592.12
5. Corporate Overhead Total |  |  |  | 260.69 | 19.89 | 4516.44 | 3536.04 | 220.04 | 552.68 | 444.41 | 6.79 | 902.73 | 3132.41 | 13592.12 | 13592.12
Grand Total |  |  |  | 601.66 | 832.69 | 19230.47 | 7668.08 | 1040 | 1609.5 | 867.83 | 240.86 | 2268.59 | 4965.44 | 39325.12 | 39325.12

## 800219631
Pin: 7014 | Project: TRTP Segment 3C
Order: 800219631 | 800219631- I: TRTP 3C-3: VINCENT 500KV - EQUIP ONE
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [10 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 175.61 | 170.94 |  | 245.79 | 770.5 | -591.2 | [5 empty] | 771.64
|  | Labor Total |  | 175.61 | 170.94 |  | 245.79 | 770.5 | -591.2 | [5 empty] | 771.64
| BP&FM Total |  |  | 175.61 | 170.94 |  | 245.79 | 770.5 | -591.2 | [5 empty] | 771.64
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  |  |  | 161.07 | [7 empty] | 161.07
|  | Labor Total |  |  |  |  | 161.07 | [7 empty] | 161.07
| ENG ADVANCEMENT Total | [5 empty] | 161.07 | [7 empty] | 161.07
| ENGINEERING | Labor | Labor Entries <$5,000 | [5 empty] | 181.72 |  | 5523.37 | 3729.12 |  |  | 9434.21
|  | Labor Total | [6 empty] | 181.72 |  | 5523.37 | 3729.12 |  |  | 9434.21
| ENGINEERING Total | [7 empty] | 181.72 |  | 5523.37 | 3729.12 |  |  | 9434.21
| Labor - Other | Labor | Labor Entries <$5,000 | 5.68 | -5.68 | 49.5 | -49.5 | 66.84 | -86.28 | 19.44 | -95.17 | 178.19 | -83.02 |  | 0
|  | Labor Total |  | 5.68 | -5.68 | 49.5 | -49.5 | 66.84 | -86.28 | 19.44 | -95.17 | 178.19 | -83.02 |  | 0
| Labor - Other Total |  |  | 5.68 | -5.68 | 49.5 | -49.5 | 66.84 | -86.28 | 19.44 | -95.17 | 178.19 | -83.02 |  | 0
| Other | Other | Other | 4706.49 | [10 empty] | 4706.49
|  | Other Total |  | 4706.49 | [10 empty] | 4706.49
| Other Total |  |  | 4706.49 | [10 empty] | 4706.49
1. Project Support Total |  |  |  | 4887.78 | 165.26 | 49.5 | 357.36 | 837.34 | -495.76 | 19.44 | 5428.2 | 3907.31 | -83.02 |  | 15073.41
2. Material | Material - Other | Material | Material - Other | 33.21 | [10 empty] | 33.21
|  | Material Total |  | 33.21 | [10 empty] | 33.21
| Material - Other Total |  |  | 33.21 | [10 empty] | 33.21
2. Material Total |  |  |  | 33.21 | [10 empty] | 33.21
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [10 empty] | 542.8 | 542.8
|  | Contract Total | [11 empty] | 542.8 | 542.8
| Construction Management Services Total | [12 empty] | 542.8 | 542.8
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 |  |  | 2631.02 | [8 empty] | 2631.02
|  | Labor Total |  |  |  | 2631.02 | [8 empty] | 2631.02
| N/W SUBSMTCETEST&APP Total |  |  |  |  | 2631.02 | [8 empty] | 2631.02
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | -380.72 | [10 empty] | -380.72
|  | Contract Total |  | -380.72 | [10 empty] | -380.72
| Short Term Equipment Rent Total |  |  | -380.72 | [10 empty] | -380.72
3. Construction Total |  |  |  | -380.72 |  | 2631.02 | [7 empty] | 542.8 | 2793.1
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 20.22 | 14.12 | 239.11 | 33.91 | 75.79 | -56.67 | 2.5 | 627.99 | 519.71 | -8.6 | 141.97 | 1610.05
|  | Chargeback Total |  | 20.22 | 14.12 | 239.11 | 33.91 | 75.79 | -56.67 | 2.5 | 627.99 | 519.71 | -8.6 | 141.97 | 1610.05
| Chargebacks Total |  |  | 20.22 | 14.12 | 239.11 | 33.91 | 75.79 | -56.67 | 2.5 | 627.99 | 519.71 | -8.6 | 141.97 | 1610.05
| Labor - Other | Labor | Labor Entries <$5,000 | 29.24 | 58.78 | 639.17 | 117.32 | 266.53 | -154.98 | 6.45 | 1691.43 | 1326.93 | -20.26 | 19.69 | 3980.3
|  | Labor Total |  | 29.24 | 58.78 | 639.17 | 117.32 | 266.53 | -154.98 | 6.45 | 1691.43 | 1326.93 | -20.26 | 19.69 | 3980.3
| Labor - Other Total |  |  | 29.24 | 58.78 | 639.17 | 117.32 | 266.53 | -154.98 | 6.45 | 1691.43 | 1326.93 | -20.26 | 19.69 | 3980.3
4. Allocated Total |  |  |  | 49.46 | 72.9 | 878.28 | 151.23 | 342.32 | -211.65 | 8.95 | 2319.42 | 1846.64 | -28.86 | 161.66 | 5590.35
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G | 256.15 | 6.98 | 126.85 | 18.13 | 98.18 | -25.25 | 1 | 347.08 | 148.66 | -2.96 | 19.78 | 994.6
|  |  | Capitalized Overhead - Inj & Damages | 4.29 | 0.41 | 3.75 | 0.42 | 10.53 | -0.92 | 0.03 | 7.02 | 17.77 | -0.18 | 0.03 | 43.15
|  |  | Capitalized Overhead - P&B/Payroll Tax | 123.64 | 191.2 | 2414.69 | 459.23 | 1263.28 | -663.62 | 25.18 | 7777.37 | 1909.69 | -70.82 |  | 13429.84
|  |  | Corporate Overheads Correction |  |  |  |  | -91750.95 | [6 empty] | -91750.95
|  | Non Budgeted Total |  | 384.08 | 198.59 | 2545.29 | 477.78 | -90378.96 | -689.79 | 26.21 | 8131.47 | 2076.12 | -73.96 | 19.81 | -77283.36
| Non Budget - Other Total |  |  | 384.08 | 198.59 | 2545.29 | 477.78 | -90378.96 | -689.79 | 26.21 | 8131.47 | 2076.12 | -73.96 | 19.81 | -77283.36
5. Corporate Overhead Total |  |  |  | 384.08 | 198.59 | 2545.29 | 477.78 | -90378.96 | -689.79 | 26.21 | 8131.47 | 2076.12 | -73.96 | 19.81 | -77283.36
Grand Total |  |  |  | 4973.81 | 436.75 | 6104.09 | 986.37 | -89199.3 | -1397.2 | 54.6 | 15879.09 | 7830.07 | -185.84 | 724.27 | -53793.29

## 800219567
Pin: 7014 | Project: TRTP Segment 3C
Order: 800219567 | 800219567- I: TRTP 3C-6: ANTELOPE SUBSTATION - 500K
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 |  | 2012 Total
SubCategory | Prime | Group | Details | 5 | 7
1. Project Support | Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  | 0 | 0
|  | Contract Total |  |  | 0 | 0
| Engineering/Technical Professional Servi Total |  |  |  | 0 | 0
1. Project Support Total |  |  |  |  | 0 | 0
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Corporate Overheads Correction | -96.21 |  | -96.21
|  | Non Budgeted Total |  | -96.21 |  | -96.21
| Non Budget - Other Total |  |  | -96.21 |  | -96.21
5. Corporate Overhead Total |  |  |  | -96.21 |  | -96.21
Grand Total |  |  |  | -96.21 | 0 | -96.21

## 800219505
Pin: 7014 | Project: TRTP Segment 3C
Order: 800219505 | 800219505- SC MP/SH I: TRTP 3C-5: ANTELOPE SUBSTATI
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 1756.13 | 3589.77 | 6817.54 | 1975.39 | 1928.1 | 2487.33 | 1741.69 | 1863.24 | 1193.62 | 1193.62 | 1280.93 | 1251.85 | 27079.21
|  | Labor Total |  | 1756.13 | 3589.77 | 6817.54 | 1975.39 | 1928.1 | 2487.33 | 1741.69 | 1863.24 | 1193.62 | 1193.62 | 1280.93 | 1251.85 | 27079.21
| BP&FM Total |  |  | 1756.13 | 3589.77 | 6817.54 | 1975.39 | 1928.1 | 2487.33 | 1741.69 | 1863.24 | 1193.62 | 1193.62 | 1280.93 | 1251.85 | 27079.21
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 55572.94 |  |  | 55572.94
|  |  | Contract Entries <$50,000 | [8 empty] | -55572.94 |  |  |  | -55572.94
|  | Contract Total | [9 empty] | -55572.94 | 55572.94 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -55572.94 | 55572.94 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  | 1364 |  |  | 2637.93 |  |  | 660 |  |  |  |  | 4661.93
|  | Contract Total |  |  | 1364 |  |  | 2637.93 |  |  | 660 |  |  |  |  | 4661.93
| Contract Consult/Contract Ord to Ord Total |  |  |  | 1364 |  |  | 2637.93 |  |  | 660 |  |  |  |  | 4661.93
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 2211.21 | 2211.21
|  | Labor Total | [12 empty] | 2211.21 | 2211.21
| ELEC SYS PLANNING Total | [13 empty] | 2211.21 | 2211.21
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  |  | 2513.51 | 2598.49 |  |  | 263.79 | [5 empty] | 5375.79
|  | Labor Total |  |  |  | 2513.51 | 2598.49 |  |  | 263.79 | [5 empty] | 5375.79
| ENG ADVANCEMENT Total |  |  |  |  | 2513.51 | 2598.49 |  |  | 263.79 | [5 empty] | 5375.79
| ENGINEERING | Labor | Engineer |  | 5007.36 | [10 empty] | 5007.36
|  |  | Labor Entries <$5,000 | 3580.85 | 3722.69 | 7192.64 | 3918.32 | 5977.55 | 6657.83 | 7398.36 | 9147.45 | 1654.28 | 5648.93 | 5064.01 |  | 59962.91
|  | Labor Total |  | 3580.85 | 8730.05 | 7192.64 | 3918.32 | 5977.55 | 6657.83 | 7398.36 | 9147.45 | 1654.28 | 5648.93 | 5064.01 |  | 64970.27
| ENGINEERING Total |  |  | 3580.85 | 8730.05 | 7192.64 | 3918.32 | 5977.55 | 6657.83 | 7398.36 | 9147.45 | 1654.28 | 5648.93 | 5064.01 |  | 64970.27
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 8013.05 | 10362.17 | 0 | 42929.03 | 5512 | 416 | 3522.15 | 416 |  | 208 |  |  | 71378.4
|  | Contract Total |  | 8013.05 | 10362.17 | 0 | 42929.03 | 5512 | 416 | 3522.15 | 416 |  | 208 |  |  | 71378.4
| Engineering/Technical Professional Servi Total |  |  | 8013.05 | 10362.17 | 0 | 42929.03 | 5512 | 416 | 3522.15 | 416 |  | 208 |  |  | 71378.4
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  |  |  |  | 712 | 2640 |  |  | 60 |  |  |  | 3412
|  | Contract Total | [5 empty] | 712 | 2640 |  |  | 60 |  |  |  | 3412
| Environmental/Safety Professional Servic Total | [6 empty] | 712 | 2640 |  |  | 60 |  |  |  | 3412
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 64130.61 | -64130.61 |  |  | 0
|  | IMM Correction Total | [9 empty] | 64130.61 | -64130.61 |  |  | 0
| IMM/Allocated - Correction Total | [10 empty] | 64130.61 | -64130.61 |  |  | 0
| Labor - Other | Labor | Labor Correction | [9 empty] | 18317.25 |  |  | 18317.25
|  |  | Labor Entries <$5,000 | 3725.37 | 7839.07 | -5821.67 | 1655.54 | 5144.92 | -2457.07 | 1553.2 | 1500.69 | -22214.46 | 6137.66 | 1151.84 | 3071.51 | 1286.6
|  |  | Sub Order for Antelope Substation Phasin |  | 19514.58 | [10 empty] | 19514.58
|  | Labor Total |  | 3725.37 | 27353.65 | -5821.67 | 1655.54 | 5144.92 | -2457.07 | 1553.2 | 1500.69 | -22214.46 | 24454.91 | 1151.84 | 3071.51 | 39118.43
| Labor - Other Total |  |  | 3725.37 | 27353.65 | -5821.67 | 1655.54 | 5144.92 | -2457.07 | 1553.2 | 1500.69 | -22214.46 | 24454.91 | 1151.84 | 3071.51 | 39118.43
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | 667.96 |  | 2112.25 | 7185.81 | 5662.48 | 12599.96 | 270.04 | 1755.02 |  | 1340.46 | 4599.63 | 457.99 | 36651.6
|  | Labor Total |  | 667.96 |  | 2112.25 | 7185.81 | 5662.48 | 12599.96 | 270.04 | 1755.02 |  | 1340.46 | 4599.63 | 457.99 | 36651.6
| NORTH GRIDMGMTCENTER Total |  |  | 667.96 |  | 2112.25 | 7185.81 | 5662.48 | 12599.96 | 270.04 | 1755.02 |  | 1340.46 | 4599.63 | 457.99 | 36651.6
| Other | Other | Other | -1947055.1 | 57125.05 | 182487.02 | 590880.14 | -360063.54 | -207100.8 | -126824.29 | 85907.63 | -152344.62 | -30542.72 | -1284.51 | 40491.74 | -1868324
|  | Other Total |  | -1947055.1 | 57125.05 | 182487.02 | 590880.14 | -360063.54 | -207100.8 | -126824.29 | 85907.63 | -152344.62 | -30542.72 | -1284.51 | 40491.74 | -1868324
| Other Total |  |  | -1947055.1 | 57125.05 | 182487.02 | 590880.14 | -360063.54 | -207100.8 | -126824.29 | 85907.63 | -152344.62 | -30542.72 | -1284.51 | 40491.74 | -1868324
| PLGHCC | Labor | Labor Entries <$5,000 | [10 empty] | 31.7 | 141.84 | 173.54
|  | Labor Total | [11 empty] | 31.7 | 141.84 | 173.54
| PLGHCC Total | [12 empty] | 31.7 | 141.84 | 173.54
| SC&M | Labor | Labor Entries <$5,000 | 3763.55 | 14454.46 | 4177.99 | 4688.69 | 5113.88 | 5464.69 | 2366.89 | 3823.25 | 2975.21 | 4426.18 | 3960.83 | 2420.96 | 57636.58
|  | Labor Total |  | 3763.55 | 14454.46 | 4177.99 | 4688.69 | 5113.88 | 5464.69 | 2366.89 | 3823.25 | 2975.21 | 4426.18 | 3960.83 | 2420.96 | 57636.58
| SC&M Total |  |  | 3763.55 | 14454.46 | 4177.99 | 4688.69 | 5113.88 | 5464.69 | 2366.89 | 3823.25 | 2975.21 | 4426.18 | 3960.83 | 2420.96 | 57636.58
| SHOP SERVICES &INSTR | Labor | Labor Entries <$5,000 |  | 757.12 | [10 empty] | 757.12
|  | Labor Total |  |  | 757.12 | [10 empty] | 757.12
| SHOP SERVICES &INSTR Total |  |  |  | 757.12 | [10 empty] | 757.12
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -10384.17 | 10384.17 |  |  | 0
|  | Contract Total | [9 empty] | -10384.17 | 10384.17 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -10384.17 | 10384.17 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 2644.8 | 2548 | 1970 | 4308 | 1540 | 880 | 440 | [5 empty] | 14330.8
|  | Contract Total |  | 2644.8 | 2548 | 1970 | 4308 | 1540 | 880 | 440 | [5 empty] | 14330.8
| Temporary/Supplementary - Technical/Prof Total |  |  | 2644.8 | 2548 | 1970 | 4308 | 1540 | 880 | 440 | [5 empty] | 14330.8
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 10572.3 | 13882.53 | 8517.82 | 5255.4 | 4121.99 | 8976.43 | 7609.88 | 1099.89 |  | 253 | 253 | 920.34 | 61462.58
|  | Contract Total |  | 10572.3 | 13882.53 | 8517.82 | 5255.4 | 4121.99 | 8976.43 | 7609.88 | 1099.89 |  | 253 | 253 | 920.34 | 61462.58
| Temporary/Supplementary - Trade/Labor Total |  |  | 10572.3 | 13882.53 | 8517.82 | 5255.4 | 4121.99 | 8976.43 | 7609.88 | 1099.89 |  | 253 | 253 | 920.34 | 61462.58
| TRANSMISSION | Labor | Labor Entries <$5,000 |  | 0 | [10 empty] | 0
|  | Labor Total |  |  | 0 | [10 empty] | 0
| TRANSMISSION Total |  |  |  | 0 | [10 empty] | 0
1. Project Support Total |  |  |  | -1912331.09 | 140166.8 | 209967.1 | 665394.81 | -321712.69 | -169435.63 | -101658.29 | 106173.17 | -170502.47 | 8808.88 | 15057.43 | 50967.44 | -1479104.54
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 3248.85 | [9 empty] | 3248.85
|  | Material - Direct Purchase Total |  |  |  | 3248.85 | [9 empty] | 3248.85
| Breakers - Circuit-DP Total |  |  |  |  | 3248.85 | [9 empty] | 3248.85
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 | 426.39 | 2244.31 | [10 empty] | 2670.7
|  |  | SHAMROCK VALCAT INC | 9864 | [11 empty] | 9864
|  | Material - Direct Purchase Total |  | 10290.39 | 2244.31 | [10 empty] | 12534.7
| Building, Shop & Industrial Products/Eqp Total |  |  | 10290.39 | 2244.31 | [10 empty] | 12534.7
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 3254.6 |  | 268.12 |  |  |  | 1296.71 | 866.58 |  | 1220.83 |  | 6906.84
|  | Material - Direct Purchase Total |  |  | 3254.6 |  | 268.12 |  |  |  | 1296.71 | 866.58 |  | 1220.83 |  | 6906.84
| Electric Wiring and Components-DP Total |  |  |  | 3254.6 |  | 268.12 |  |  |  | 1296.71 | 866.58 |  | 1220.83 |  | 6906.84
| Labor - Other | Labor | Labor Entries <$5,000 | [8 empty] | 1.28 | -1.28 |  |  | 0
|  | Labor Total | [9 empty] | 1.28 | -1.28 |  |  | 0
| Labor - Other Total | [10 empty] | 1.28 | -1.28 |  |  | 0
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 |  |  | 84.08 | [5 empty] | -61.64 | 61.64 |  |  | 84.08
|  | Material - Direct Purchase Total |  |  |  | 84.08 | [5 empty] | -61.64 | 61.64 |  |  | 84.08
| Material - Direct Purchase - Correction Total |  |  |  |  | 84.08 | [5 empty] | -61.64 | 61.64 |  |  | 84.08
| Material - Inventory | Material | Material - Inventory | -58246.9 | -6534.73 | -64822.36 | -77899.48 | -50540.04 | -41580.67 | -6115.23 | -13296.89 | -9962.77 | -19118.49 | -742.17 | 110.01 | -348749.72
|  | Material Total |  | -58246.9 | -6534.73 | -64822.36 | -77899.48 | -50540.04 | -41580.67 | -6115.23 | -13296.89 | -9962.77 | -19118.49 | -742.17 | 110.01 | -348749.72
| Material - Inventory Total |  |  | -58246.9 | -6534.73 | -64822.36 | -77899.48 | -50540.04 | -41580.67 | -6115.23 | -13296.89 | -9962.77 | -19118.49 | -742.17 | 110.01 | -348749.72
| Material - Other | Material | Material - Other | -3718.94 | 2215.72 | -5232.37 | -3505.47 | -3322.44 | -2804.31 | 4632.58 | 1442.03 | -55.45 | -849.71 | 454.11 | 9.77 | -10734.48
|  | Material Total |  | -3718.94 | 2215.72 | -5232.37 | -3505.47 | -3322.44 | -2804.31 | 4632.58 | 1442.03 | -55.45 | -849.71 | 454.11 | 9.77 | -10734.48
| Material - Other Total |  |  | -3718.94 | 2215.72 | -5232.37 | -3505.47 | -3322.44 | -2804.31 | 4632.58 | 1442.03 | -55.45 | -849.71 | 454.11 | 9.77 | -10734.48
| Mechanical Systems and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | 2200 | [11 empty] | 2200
|  | Material - Direct Purchase Total |  | 2200 | [11 empty] | 2200
| Mechanical Systems and Components-DP Total |  |  | 2200 | [11 empty] | 2200
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | 528.86 | 48.6 | [6 empty] | 1763.2 |  |  |  | 2340.66
|  | Material - Direct Purchase Total |  | 528.86 | 48.6 | [6 empty] | 1763.2 |  |  |  | 2340.66
| Metals & Fabricated Metal Products-DP Total |  |  | 528.86 | 48.6 | [6 empty] | 1763.2 |  |  |  | 2340.66
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 4210 | [10 empty] | 4210
|  | Material - Direct Purchase Total |  |  | 4210 | [10 empty] | 4210
| Meters, Monitor and Warnings-DP Total |  |  |  | 4210 | [10 empty] | 4210
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | 267.84 |  |  | 1148.9 | 1858.5 | [7 empty] | 3275.24
|  | Material - Direct Purchase Total |  | 267.84 |  |  | 1148.9 | 1858.5 | [7 empty] | 3275.24
| Office & Office Support Products-DP Total |  |  | 267.84 |  |  | 1148.9 | 1858.5 | [7 empty] | 3275.24
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | 686.09 | 1079.53 | [5 empty] | 225.75 |  |  |  |  | 1991.37
|  | Material - Direct Purchase Total |  | 686.09 | 1079.53 | [5 empty] | 225.75 |  |  |  |  | 1991.37
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  | 686.09 | 1079.53 | [5 empty] | 225.75 |  |  |  |  | 1991.37
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 155.37 |  | -6827.86 |  |  |  | 631.57 |  |  |  |  | -6040.92
|  | Material - Direct Purchase Total |  |  | 155.37 |  | -6827.86 |  |  |  | 631.57 |  |  |  |  | -6040.92
| Pole Line Hdwe & Connectors-DP Total |  |  |  | 155.37 |  | -6827.86 |  |  |  | 631.57 |  |  |  |  | -6040.92
| Protection and Test-DP | Material - Direct Purchase | Protection and Test-DP |  |  |  |  | 5416.67 | [7 empty] | 5416.67
|  | Material - Direct Purchase Total | [5 empty] | 5416.67 | [7 empty] | 5416.67
| Protection and Test-DP Total | [6 empty] | 5416.67 | [7 empty] | 5416.67
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | [6 empty] | 31269 | [5 empty] | 31269
|  |  | Material Entries <$5,000 | 1485 | [11 empty] | 1485
|  |  | WASHINGTON ORNAMENTAL | [5 empty] | 9912 | [6 empty] | 9912
|  | Material - Direct Purchase Total |  | 1485 |  |  |  |  | 9912 | 31269 | [5 empty] | 42666
| Steel / Fabricated / Structural-DP Total |  |  | 1485 |  |  |  |  | 9912 | 31269 | [5 empty] | 42666
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 1127.52 | 743.28 | 2174.09 | 85.31 | 337.19 | 2498.2 | 127.94 | 169.55 |  | 175.98 | 237.24 |  | 7676.3
|  |  | Transportation & Mobile Equip-DP |  |  |  |  | 14339.68 | [7 empty] | 14339.68
|  | Material - Direct Purchase Total |  | 1127.52 | 743.28 | 2174.09 | 85.31 | 14676.87 | 2498.2 | 127.94 | 169.55 |  | 175.98 | 237.24 |  | 22015.98
| Transportation & Mobile Equip-DP Total |  |  | 1127.52 | 743.28 | 2174.09 | 85.31 | 14676.87 | 2498.2 | 127.94 | 169.55 |  | 175.98 | 237.24 |  | 22015.98
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | 733.8 | [11 empty] | 733.8
|  |  | Wire, Cable & Bus Bar-DP | [9 empty] | 9437.5 |  |  | 9437.5
|  | Material - Direct Purchase Total |  | 733.8 | [8 empty] | 9437.5 |  |  | 10171.3
| Wire, Cable & Bus Bar-DP Total |  |  | 733.8 | [8 empty] | 9437.5 |  |  | 10171.3
2. Material Total |  |  |  | -44646.34 | 7416.68 | -64547.71 | -86730.48 | -31910.44 | -31974.78 | 29914.29 | -9531.28 | -7448.8 | -10294.36 | 1170.01 | 119.78 | -248463.43
3. Construction | Construction Management Services | Contract | CIRCLE WOOD SERVICES, INC | [10 empty] | 59558.97 |  | 59558.97
|  |  | Contract Entries <$50,000 | 100927.31 | 1859.04 | 97958.99 | 119559.28 | 127044.06 | 144430.59 | 135504.99 | 149959.95 | 3300 | 57523.95 | 63749.73 | 237128.19 | 1238946.08
|  | Contract Total |  | 100927.31 | 1859.04 | 97958.99 | 119559.28 | 127044.06 | 144430.59 | 135504.99 | 149959.95 | 3300 | 57523.95 | 123308.7 | 237128.19 | 1298505.05
| Construction Management Services Total |  |  | 100927.31 | 1859.04 | 97958.99 | 119559.28 | 127044.06 | 144430.59 | 135504.99 | 149959.95 | 3300 | 57523.95 | 123308.7 | 237128.19 | 1298505.05
| Construction Services - Other | Contract | Contract Entries <$50,000 | 568.5 | 1458.6 | 6535.66 | 568.5 | 1023.3 | 16598.28 | [6 empty] | 26752.84
|  |  | RJ ALLEN INC | [5 empty] | 54833.33 | [6 empty] | 54833.33
|  | Contract Total |  | 568.5 | 1458.6 | 6535.66 | 568.5 | 1023.3 | 71431.61 | [6 empty] | 81586.17
| Construction Services - Other Total |  |  | 568.5 | 1458.6 | 6535.66 | 568.5 | 1023.3 | 71431.61 | [6 empty] | 81586.17
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 |  | 762.6 |  |  | 32.84 | 4093.28 | 1789.98 | [5 empty] | 6678.7
|  | Contract Total |  |  | 762.6 |  |  | 32.84 | 4093.28 | 1789.98 | [5 empty] | 6678.7
| Construction, Civil/Structural Total |  |  |  | 762.6 |  |  | 32.84 | 4093.28 | 1789.98 | [5 empty] | 6678.7
| Construction, Earthwork | Contract | Contract Entries <$50,000 | -11038.13 | [11 empty] | -11038.13
|  | Contract Total |  | -11038.13 | [11 empty] | -11038.13
| Construction, Earthwork Total |  |  | -11038.13 | [11 empty] | -11038.13
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 |  |  |  | 7426.55 |  | 1672.25 | 40228.76 | [5 empty] | 49327.56
|  | Contract Total |  |  |  |  | 7426.55 |  | 1672.25 | 40228.76 | [5 empty] | 49327.56
| Decontamination & Waste Disposal Service Total | [5 empty] | 7426.55 |  | 1672.25 | 40228.76 | [5 empty] | 49327.56
| Electrical Construction, Substations | Contract | Contract Entries <$50,000 |  | -182348.33 | [10 empty] | -182348.33
|  |  | NRG POWER INC | 1134760 | 172000.78 | [10 empty] | 1306760.78
|  | Contract Total |  | 1134760 | -10347.55 | [10 empty] | 1124412.45
| Electrical Construction, Substations Total |  |  | 1134760 | -10347.55 | [10 empty] | 1124412.45
| ENGINEERING | Labor | Labor Entries <$5,000 | 508.22 | 642.37 | 897.39 | 422.55 | 545.93 | 568.7 | 327.8 | 163.25 | 324.02 | 566.34 | 773.62 |  | 5740.19
|  | Labor Total |  | 508.22 | 642.37 | 897.39 | 422.55 | 545.93 | 568.7 | 327.8 | 163.25 | 324.02 | 566.34 | 773.62 |  | 5740.19
| ENGINEERING Total |  |  | 508.22 | 642.37 | 897.39 | 422.55 | 545.93 | 568.7 | 327.8 | 163.25 | 324.02 | 566.34 | 773.62 |  | 5740.19
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 142.54 | 142.54
|  | Labor Total | [12 empty] | 142.54 | 142.54
| GRID OPS Total | [13 empty] | 142.54 | 142.54
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 |  |  | 241.77 |  |  | 4077.84 | [6 empty] | 4319.61
|  | Contract Total |  |  |  | 241.77 |  |  | 4077.84 | [6 empty] | 4319.61
| Hauling / Industrial Moving Services Total |  |  |  |  | 241.77 |  |  | 4077.84 | [6 empty] | 4319.61
| Major Construction, Turnkey, Trans/Subs | Contract | CAROB VALLEY ELECTRIC INC | 209757.88 | 338458.48 | 205041 | 334112.31 |  | 113477.47 | 93585.01 | 85846.25 | 170626.51 |  | 95130.5 | 279001.5 | 1925036.91
|  |  | Contract Entries <$50,000 | 93650.69 |  | 27872.08 | 100131.53 | 60117 | 159213.85 | 14348.34 | 13840 | 6671.93 |  | 10870.46 | 58524.68 | 545240.56
|  |  | KINDNESS GENERAL CONTRACTORS INC |  | 113692.82 |  |  | 164994 | [7 empty] | 278686.82
|  |  | MISSION PAVING AND SEALING INC |  |  |  | 470364.12 | 665424.37 | [7 empty] | 1135788.49
|  | Contract Total |  | 303408.57 | 452151.3 | 232913.08 | 904607.96 | 890535.37 | 272691.32 | 107933.35 | 99686.25 | 177298.44 |  | 106000.96 | 337526.18 | 3884752.78
| Major Construction, Turnkey, Trans/Subs Total |  |  | 303408.57 | 452151.3 | 232913.08 | 904607.96 | 890535.37 | 272691.32 | 107933.35 | 99686.25 | 177298.44 |  | 106000.96 | 337526.18 | 3884752.78
| Mechanical Services | Contract | Contract Entries <$50,000 |  |  |  |  | 14525 | [7 empty] | 14525
|  | Contract Total | [5 empty] | 14525 | [7 empty] | 14525
| Mechanical Services Total | [6 empty] | 14525 | [7 empty] | 14525
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | 8260.45 | 16322.01 | 10591.49 | 27138.41 | 11834.35 | 9739.47 | 3228.18 | 8439.18 | 2161.52 | 1145.54 | 2498.85 |  | 101359.45
|  | Labor Total |  | 8260.45 | 16322.01 | 10591.49 | 27138.41 | 11834.35 | 9739.47 | 3228.18 | 8439.18 | 2161.52 | 1145.54 | 2498.85 |  | 101359.45
| N/W SUBSMTCETEST&APP Total |  |  | 8260.45 | 16322.01 | 10591.49 | 27138.41 | 11834.35 | 9739.47 | 3228.18 | 8439.18 | 2161.52 | 1145.54 | 2498.85 |  | 101359.45
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [10 empty] | 205.52 |  | 205.52
|  | Labor Total | [11 empty] | 205.52 |  | 205.52
| S/E SUBS MTCETST&APP Total | [12 empty] | 205.52 |  | 205.52
| SC&M | Labor | Labor Entries <$5,000 | 540.47 | 1772.83 |  | 1856.81 | 663.07 | 1691.96 | 217.78 | 352.9 |  |  |  |  | 7095.82
|  | Labor Total |  | 540.47 | 1772.83 |  | 1856.81 | 663.07 | 1691.96 | 217.78 | 352.9 |  |  |  |  | 7095.82
| SC&M Total |  |  | 540.47 | 1772.83 |  | 1856.81 | 663.07 | 1691.96 | 217.78 | 352.9 |  |  |  |  | 7095.82
| Security / Protection Services | Contract | Contract Entries <$50,000 | 38261.52 |  | 37467.89 | 37465.75 | 37333.95 | 12404.86 | 2113.72 | [5 empty] | 165047.69
|  |  | WACKENHUT CORPORATION (THE) |  | 55976.96 | [10 empty] | 55976.96
|  | Contract Total |  | 38261.52 | 55976.96 | 37467.89 | 37465.75 | 37333.95 | 12404.86 | 2113.72 | [5 empty] | 221024.65
| Security / Protection Services Total |  |  | 38261.52 | 55976.96 | 37467.89 | 37465.75 | 37333.95 | 12404.86 | 2113.72 | [5 empty] | 221024.65
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 32206.08 | 36751.81 | 17124.24 | 44909.79 | 40983.85 | 23395.05 | 19842.35 | 4648.22 | 17661.47 | 6854.06 | 5454.03 | 22141.95 | 271972.9
|  | Contract Total |  | 32206.08 | 36751.81 | 17124.24 | 44909.79 | 40983.85 | 23395.05 | 19842.35 | 4648.22 | 17661.47 | 6854.06 | 5454.03 | 22141.95 | 271972.9
| Short Term Equipment Rent Total |  |  | 32206.08 | 36751.81 | 17124.24 | 44909.79 | 40983.85 | 23395.05 | 19842.35 | 4648.22 | 17661.47 | 6854.06 | 5454.03 | 22141.95 | 271972.9
| TRANSMISSION | Labor | Labor Entries <$5,000 |  | 0 | [10 empty] | 0
|  | Labor Total |  |  | 0 | [10 empty] | 0
| TRANSMISSION Total |  |  |  | 0 | [10 empty] | 0
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | 82 | [11 empty] | 82
|  | Labor Total |  | 82 | [11 empty] | 82
| TSD-HERC - Crane Svs Total |  |  | 82 | [11 empty] | 82
3. Construction Total |  |  |  | 1608484.99 | 557349.97 | 403730.51 | 1143955.6 | 1124521.72 | 546196.93 | 311186.91 | 263249.75 | 200745.45 | 66089.89 | 238241.68 | 596938.86 | 7060692.26
4. Allocated | Chargebacks | Chargeback | Antelope Sub-Gradng Op Field Tstng & Dep | [6 empty] | 5189.59 | [5 empty] | 5189.59
|  |  | Chargeback Entries <$5,000 | -44084.91 | 12913.73 | -1680.05 | -739.39 | -497.77 | 7560.57 | 10368.01 | 8822.99 | 12515.07 | -2574.92 | 8446.29 | 12513.93 | 23563.55
|  |  | PROCUREMENT TDBU | 11579.01 |  |  | 7371.29 | 7288.59 | [7 empty] | 26238.89
|  |  | TDBU/TOFEE ANTELOPE 2OCBs,12 BUSH,9XFRMR | [9 empty] | 13053.2 |  |  | 13053.2
|  |  | TRTP-2010 SEG03C Antelope 500Kv-TDBU |  |  | 5827.16 |  | 23648.4 | [7 empty] | 29475.56
|  | Chargeback Total |  | -32505.9 | 12913.73 | 4147.11 | 6631.9 | 30439.22 | 7560.57 | 15557.6 | 8822.99 | 12515.07 | 10478.28 | 8446.29 | 12513.93 | 97520.79
| Chargebacks Total |  |  | -32505.9 | 12913.73 | 4147.11 | 6631.9 | 30439.22 | 7560.57 | 15557.6 | 8822.99 | 12515.07 | 10478.28 | 8446.29 | 12513.93 | 97520.79
| Labor - Other | Labor | Division Overhead | 153498.06 | 43616.12 | 16564.01 | 81206.98 | 75600.44 | 26863.84 | 16798.99 | 7793.9 |  |  |  | 10943.4 | 432885.74
|  |  | Labor Entries <$5,000 | 11192.03 | 26091.57 | 18021.98 | 10153.28 | 5829.36 | 16017.26 | 14763.23 | 18972.83 | 5088.7 | 14818.12 | 9782.28 | 13109.98 | 163840.62
|  |  | Paid Absence |  | 8401.84 |  | 7386.43 | 5736.63 |  |  |  |  | 6475.84 |  |  | 28000.74
|  | Labor Total |  | 164690.09 | 78109.53 | 34585.99 | 98746.69 | 87166.43 | 42881.1 | 31562.22 | 26766.73 | 5088.7 | 21293.96 | 9782.28 | 24053.38 | 624727.1
| Labor - Other Total |  |  | 164690.09 | 78109.53 | 34585.99 | 98746.69 | 87166.43 | 42881.1 | 31562.22 | 26766.73 | 5088.7 | 21293.96 | 9782.28 | 24053.38 | 624727.1
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -3881.72 | 3881.72 |  |  | 0
|  | Overhead Total | [9 empty] | -3881.72 | 3881.72 |  |  | 0
| Overhead Correction Total | [10 empty] | -3881.72 | 3881.72 |  |  | 0
4. Allocated Total |  |  |  | 132184.19 | 91023.26 | 38733.1 | 105378.59 | 117605.65 | 50441.67 | 47119.82 | 35589.72 | 13722.05 | 35653.96 | 18228.57 | 36567.31 | 722247.89
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 574939.14 | 34544.02 | [7 empty] | 609483.16
|  |  | AFUDC - Debt/Equity |  |  | 596736.72 | -596736.72 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 97812.56 | 21807.1 | 14880.55 | 44130.63 | 104039.92 | 21592.89 | 14883.95 | 8788.28 | 9741.18 | 2655.35 | 7241.92 | 18089.61 | 365663.94
|  |  | Capitalized Overhead - Inj & Damages | 149.83 | 365.62 | 19.72 | 90.01 | 1214.71 | 97.78 | 107.01 | 73.44 | 93.05 | -78.07 | 67.71 | 73.33 | 2274.14
|  |  | Capitalized Overhead - P&B/Payroll Tax | 16170.98 | 80954.67 | 30527.85 | 66230.04 | 56741.11 | 47770.01 | 23746.16 | 24681.93 | -19126.57 | 23716.68 | 16926.31 | 24699.32 | 393038.49
|  |  | Corporate Overheads Correction |  |  |  |  | -1593497.01 | [7 empty] | -1593497.01
|  | Non Budgeted Total |  | 114133.37 | 103127.39 | 642164.84 | 88653.1 | -1396957.25 | 69460.68 | 38737.12 | 33543.65 | -9292.34 | 26293.96 | 24235.94 | 42862.26 | -223037.28
| Non Budget - Other Total |  |  | 114133.37 | 103127.39 | 642164.84 | 88653.1 | -1396957.25 | 69460.68 | 38737.12 | 33543.65 | -9292.34 | 26293.96 | 24235.94 | 42862.26 | -223037.28
5. Corporate Overhead Total |  |  |  | 114133.37 | 103127.39 | 642164.84 | 88653.1 | -1396957.25 | 69460.68 | 38737.12 | 33543.65 | -9292.34 | 26293.96 | 24235.94 | 42862.26 | -223037.28
Grand Total |  |  |  | -102174.88 | 899084.1 | 1230047.84 | 1916651.62 | -508453.01 | 464688.87 | 325299.85 | 429025.01 | 27223.89 | 126552.33 | 296933.63 | 727455.65 | 5832334.9

## 800219436
Pin: 7014 | Project: TRTP Segment 3C
Order: 800219436 | 800219436- I: TRTP Segment 3C: Windhub Sub: Install
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 819.53 | 1424.51 | 1068.85 | 830.24 | 946.62 | 983.36 | 1045.35 | 960.74 | 1106.28 | 1601.2 | 2037.85 | 2445.47 | 15270
|  | Labor Total |  | 819.53 | 1424.51 | 1068.85 | 830.24 | 946.62 | 983.36 | 1045.35 | 960.74 | 1106.28 | 1601.2 | 2037.85 | 2445.47 | 15270
| BP&FM Total |  |  | 819.53 | 1424.51 | 1068.85 | 830.24 | 946.62 | 983.36 | 1045.35 | 960.74 | 1106.28 | 1601.2 | 2037.85 | 2445.47 | 15270
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 | [9 empty] | 175 |  | 350 | 525
|  | Contract Total | [10 empty] | 175 |  | 350 | 525
| Cleaning / Janitorial Services Total | [11 empty] | 175 |  | 350 | 525
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [11 empty] | 0 | 0
|  | Contract Total | [12 empty] | 0 | 0
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [13 empty] | 0 | 0
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -2083.84 | 2083.84 |  |  | 0
|  | Contract Total | [9 empty] | -2083.84 | 2083.84 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -2083.84 | 2083.84 |  |  | 0
| Data Collection Services | Contract | Contract Entries <$50,000 |  |  | -31.32 |  |  | -30.59 | [6 empty] | -61.91
|  | Contract Total |  |  |  | -31.32 |  |  | -30.59 | [6 empty] | -61.91
| Data Collection Services Total |  |  |  |  | -31.32 |  |  | -30.59 | [6 empty] | -61.91
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 3449.02 | 3449.02
|  | Labor Total | [12 empty] | 3449.02 | 3449.02
| ELEC SYS PLANNING Total | [13 empty] | 3449.02 | 3449.02
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | [6 empty] | 40.27 | 792.3 |  |  |  |  | 832.57
|  | Labor Total | [7 empty] | 40.27 | 792.3 |  |  |  |  | 832.57
| ENG ADVANCEMENT Total | [8 empty] | 40.27 | 792.3 |  |  |  |  | 832.57
| ENGINEERING | Labor | Labor Entries <$5,000 | 3006.07 | 2227.67 | 6359.42 | 4586.43 | 3326.57 | 6890.98 | 3014.1 | 2625.39 | 3962.03 | 3530.18 | 5249.04 |  | 44777.88
|  | Labor Total |  | 3006.07 | 2227.67 | 6359.42 | 4586.43 | 3326.57 | 6890.98 | 3014.1 | 2625.39 | 3962.03 | 3530.18 | 5249.04 |  | 44777.88
| ENGINEERING Total |  |  | 3006.07 | 2227.67 | 6359.42 | 4586.43 | 3326.57 | 6890.98 | 3014.1 | 2625.39 | 3962.03 | 3530.18 | 5249.04 |  | 44777.88
| Engineering/Technical Professional Servi | Contract | BLACK & VEATCH CORPORATION | 55974.1 |  |  | 59119.66 | [8 empty] | 115093.76
|  |  | Contract Entries <$50,000 | 4475.19 | 4746.17 |  | 17469.88 | 37140.44 | 54684.33 | 26039.88 | 6663.32 | 2874.78 | 2206.81 | 3586.31 | 4807.23 | 164694.34
|  |  | MITSUBISHI ELECTRIC | [10 empty] | 97600 |  | 97600
|  | Contract Total |  | 60449.29 | 4746.17 |  | 76589.54 | 37140.44 | 54684.33 | 26039.88 | 6663.32 | 2874.78 | 2206.81 | 101186.31 | 4807.23 | 377388.1
| Engineering/Technical Professional Servi Total |  |  | 60449.29 | 4746.17 |  | 76589.54 | 37140.44 | 54684.33 | 26039.88 | 6663.32 | 2874.78 | 2206.81 | 101186.31 | 4807.23 | 377388.1
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | [7 empty] | 2474.06 | 2267.93 | 4651.37 | 1077.37 | 7241.36 | 17712.09
|  | Contract Total | [8 empty] | 2474.06 | 2267.93 | 4651.37 | 1077.37 | 7241.36 | 17712.09
| Environmental/Safety Professional Servic Total | [9 empty] | 2474.06 | 2267.93 | 4651.37 | 1077.37 | 7241.36 | 17712.09
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  |  | 8388.8 |  |  |  |  | 9161.46 | -9161.46 |  |  | 8388.8
|  | IMM Correction Total |  |  |  |  | 8388.8 |  |  |  |  | 9161.46 | -9161.46 |  |  | 8388.8
| IMM/Allocated - Correction Total | [5 empty] | 8388.8 |  |  |  |  | 9161.46 | -9161.46 |  |  | 8388.8
| Labor - Other | Labor | ALH Sub Order for:TRTP Segment 3C: Windh | [11 empty] | 1002067.24 | 1002067.24
|  |  | Labor Accrual - SCE | [9 empty] | 5378.55 |  | 9116.38 | 14494.93
|  |  | Labor Entries <$5,000 | 525.2 | 496.2 | -632.81 | 15.03 | 4472.17 | -2422.3 | 311.94 | 438.12 | -5683.4 | 10034.14 | -9040.81 | -1001356.08 | -1002842.6
|  | Labor Total |  | 525.2 | 496.2 | -632.81 | 15.03 | 4472.17 | -2422.3 | 311.94 | 438.12 | -5683.4 | 15412.69 | -9040.81 | 9827.54 | 13719.57
| Labor - Other Total |  |  | 525.2 | 496.2 | -632.81 | 15.03 | 4472.17 | -2422.3 | 311.94 | 438.12 | -5683.4 | 15412.69 | -9040.81 | 9827.54 | 13719.57
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [10 empty] | 1365.24 | 148.21 | 1513.45
|  | Labor Total | [11 empty] | 1365.24 | 148.21 | 1513.45
| NORTH GRIDMGMTCENTER Total | [12 empty] | 1365.24 | 148.21 | 1513.45
| Other | Other | Other | -640219.3 | 350583.32 | -264165.12 | 129320.77 | -107810.35 | 4474165.96 | -4504296.84 | 448675.72 | 102944.37 | -520028.04 | 1911.02 | 1207019.88 | 678101.39
|  | Other Total |  | -640219.3 | 350583.32 | -264165.12 | 129320.77 | -107810.35 | 4474165.96 | -4504296.84 | 448675.72 | 102944.37 | -520028.04 | 1911.02 | 1207019.88 | 678101.39
| Other Total |  |  | -640219.3 | 350583.32 | -264165.12 | 129320.77 | -107810.35 | 4474165.96 | -4504296.84 | 448675.72 | 102944.37 | -520028.04 | 1911.02 | 1207019.88 | 678101.39
| PLGHCC | Labor | Labor Entries <$5,000 | [11 empty] | 378.23 | 378.23
|  | Labor Total | [12 empty] | 378.23 | 378.23
| PLGHCC Total | [13 empty] | 378.23 | 378.23
| SC&M | Labor | Labor Entries <$5,000 | 994.14 | 2425.73 | 1708.32 | 1825.87 | 1790.18 | 1542.07 | 535.53 | 514.12 | 343.82 | 1884.28 | 785.04 | 3037.92 | 17387.02
|  |  | SC&M / Planner |  |  | 5199.52 | [9 empty] | 5199.52
|  | Labor Total |  | 994.14 | 2425.73 | 6907.84 | 1825.87 | 1790.18 | 1542.07 | 535.53 | 514.12 | 343.82 | 1884.28 | 785.04 | 3037.92 | 22586.54
| SC&M Total |  |  | 994.14 | 2425.73 | 6907.84 | 1825.87 | 1790.18 | 1542.07 | 535.53 | 514.12 | 343.82 | 1884.28 | 785.04 | 3037.92 | 22586.54
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  | 953.96 | 1144.79 | 836.77 | 131.31 | 352.32 | 993.98 | 1453.33 | 1717.58 | 1515.78 | 841.37 | 9941.19
|  | Labor Total |  |  |  | 953.96 | 1144.79 | 836.77 | 131.31 | 352.32 | 993.98 | 1453.33 | 1717.58 | 1515.78 | 841.37 | 9941.19
| SCM HOME CENTER Total |  |  |  |  | 953.96 | 1144.79 | 836.77 | 131.31 | 352.32 | 993.98 | 1453.33 | 1717.58 | 1515.78 | 841.37 | 9941.19
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -816.09 | 816.09 |  |  | 0
|  | Contract Total | [9 empty] | -816.09 | 816.09 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -816.09 | 816.09 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 4400 | 3300 | 3740 |  | 2640 | 3520 | 7370 | 4180 |  | 6270 | 5060 | 6050 | 46530
|  | Contract Total |  | 4400 | 3300 | 3740 |  | 2640 | 3520 | 7370 | 4180 |  | 6270 | 5060 | 6050 | 46530
| Temporary/Supplementary - Technical/Prof Total |  |  | 4400 | 3300 | 3740 |  | 2640 | 3520 | 7370 | 4180 |  | 6270 | 5060 | 6050 | 46530
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 7580.47 | 10362.62 | 8046.52 | 9927.09 |  | 3455.34 | 2318.41 |  | 1303.68 |  |  | 553.28 | 43547.41
|  | Contract Total |  | 7580.47 | 10362.62 | 8046.52 | 9927.09 |  | 3455.34 | 2318.41 |  | 1303.68 |  |  | 553.28 | 43547.41
| Temporary/Supplementary - Trade/Labor Total |  |  | 7580.47 | 10362.62 | 8046.52 | 9927.09 |  | 3455.34 | 2318.41 |  | 1303.68 |  |  | 553.28 | 43547.41
1. Project Support Total |  |  |  | -562444.6 | 375566.22 | -237752.66 | 232628.56 | -56657.6 | 4542920.46 | -4463269.04 | 468317.75 | 116834.35 | -488840.46 | 111146.84 | 1246149.51 | 1284599.33
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | ABB INC |  | 48510 | [7 empty] | 135720 |  |  | 184230
|  | Material - Direct Purchase Total |  |  | 48510 | [7 empty] | 135720 |  |  | 184230
| Breakers - Circuit-DP Total |  |  |  | 48510 | [7 empty] | 135720 |  |  | 184230
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp | 8992.2 | [6 empty] | 9052.71 | 8355.42 | 12695.99 |  | 22154.88 | 61251.2
|  |  | COMPOSITE SUPPORT & SOLUTIONS |  |  |  |  | 239267 |  | 239267 |  | 239267 | 239267 |  |  | 957068
|  |  | Material Entries <$5,000 |  |  |  | 393.01 | 2426.47 | 526.09 |  |  |  |  | 4421.67 |  | 7767.24
|  | Material - Direct Purchase Total |  | 8992.2 |  |  | 393.01 | 241693.47 | 526.09 | 239267 | 9052.71 | 247622.42 | 251962.99 | 4421.67 | 22154.88 | 1026086.44
| Building, Shop & Industrial Products/Eqp Total |  |  | 8992.2 |  |  | 393.01 | 241693.47 | 526.09 | 239267 | 9052.71 | 247622.42 | 251962.99 | 4421.67 | 22154.88 | 1026086.44
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | ELECTRICAL POWER PRODUCTS INC |  |  |  |  | 96889 | [7 empty] | 96889
|  |  | Material Entries <$5,000 |  |  | 915 | 3248.85 | 2200 | [5 empty] | 449.95 | 1799.8 | 8613.6
|  |  | NORTON & NORTON ELECTRIC CO LTD |  |  | 36030 | [9 empty] | 36030
|  | Material - Direct Purchase Total |  |  |  | 36945 | 3248.85 | 99089 | [5 empty] | 449.95 | 1799.8 | 141532.6
| Cabinets, Panels and Switchboards-DP Total |  |  |  |  | 36945 | 3248.85 | 99089 | [5 empty] | 449.95 | 1799.8 | 141532.6
| Capacitors and Regulators-DP | Material - Direct Purchase | HAEFELY TRENCH LIMITED |  |  | 91500 | [9 empty] | 91500
|  | Material - Direct Purchase Total |  |  |  | 91500 | [9 empty] | 91500
| Capacitors and Regulators-DP Total |  |  |  |  | 91500 | [9 empty] | 91500
| Communication Systems and Equipment -DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 1429.2 | 299.4 | 1728.6
|  | Material - Direct Purchase Total | [11 empty] | 1429.2 | 299.4 | 1728.6
| Communication Systems and Equipment -DP Total | [12 empty] | 1429.2 | 299.4 | 1728.6
| Electric Wiring and Components-DP | Material - Direct Purchase | ABB INC |  |  | 13288 | [9 empty] | 13288
|  |  | Electric Wiring and Components-DP |  |  |  | 6905.55 |  |  |  |  | 74627.86 | 25037.05 | 10815.99 |  | 117386.45
|  |  | ELECTROSWITCH CORPORATION |  |  |  | 7749.54 | [8 empty] | 7749.54
|  |  | GUND CO | [10 empty] | 11865.5 |  | 11865.5
|  |  | JSB ENGINEERING |  | 7584 | [10 empty] | 7584
|  |  | Material Entries <$5,000 | 3575.55 |  | 625 | 723.4 | [5 empty] | 113.09 | 1750.71 | 7987.64 | 14775.39
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC |  |  | 14264.6 |  |  |  |  | 7000.84 |  |  |  |  | 21265.44
|  |  | PHILATRON INTERNATIONAL | [9 empty] | 36571.55 | 22020 |  | 58591.55
|  |  | R B CLAPP CO INC |  |  |  | 7253.44 | [8 empty] | 7253.44
|  |  | WALKER AND ASSOCIATES INC | [8 empty] | 7725.6 |  |  |  | 7725.6
|  | Material - Direct Purchase Total |  | 3575.55 | 7584 | 28177.6 | 22631.93 |  |  |  | 7000.84 | 82353.46 | 61721.69 | 46452.2 | 7987.64 | 267484.91
| Electric Wiring and Components-DP Total |  |  | 3575.55 | 7584 | 28177.6 | 22631.93 |  |  |  | 7000.84 | 82353.46 | 61721.69 | 46452.2 | 7987.64 | 267484.91
| Engines, Gearing and Bearings-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 376.67 | 376.67
|  | Material - Direct Purchase Total | [12 empty] | 376.67 | 376.67
| Engines, Gearing and Bearings-DP Total | [13 empty] | 376.67 | 376.67
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 675.81 |  |  |  | 675.81
|  | Material - Direct Purchase Total | [9 empty] | 675.81 |  |  |  | 675.81
| Fuels, Chemicals & Petrochem-DP Total | [10 empty] | 675.81 |  |  |  | 675.81
| Insulators & Bushings-DP | Material - Direct Purchase | Insulators & Bushings-DP | [8 empty] | 192145.53 | 28514.46 |  | 78409 | 299068.99
|  |  | Material Entries <$5,000 | [7 empty] | 2938.98 |  |  |  |  | 2938.98
|  | Material - Direct Purchase Total | [8 empty] | 2938.98 | 192145.53 | 28514.46 |  | 78409 | 302007.97
| Insulators & Bushings-DP Total | [9 empty] | 2938.98 | 192145.53 | 28514.46 |  | 78409 | 302007.97
| Labor - Other | Labor | Labor Entries <$5,000 | [11 empty] | 0 | 0
|  | Labor Total | [12 empty] | 0 | 0
| Labor - Other Total | [13 empty] | 0 | 0
| Line Switches & Switchgear-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 773.84 |  | 1432 |  | 2205.84
|  |  | SOUTHERN STATES LLC |  |  | 365172 | [9 empty] | 365172
|  | Material - Direct Purchase Total |  |  |  | 365172 | [5 empty] | 773.84 |  | 1432 |  | 367377.84
| Line Switches & Switchgear-DP Total |  |  |  |  | 365172 | [5 empty] | 773.84 |  | 1432 |  | 367377.84
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -0.19 | 0.19 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -0.19 | 0.19 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -0.19 | 0.19 |  |  | 0
| Material - Inventory | Material | Material - Inventory |  | 1738.32 | 7173.39 | 4597.28 | 1476.3 | 1092649.53 |  |  |  |  | 5159.36 | 274.85 | 1113069.03
|  | Material Total |  |  | 1738.32 | 7173.39 | 4597.28 | 1476.3 | 1092649.53 |  |  |  |  | 5159.36 | 274.85 | 1113069.03
| Material - Inventory Total |  |  |  | 1738.32 | 7173.39 | 4597.28 | 1476.3 | 1092649.53 |  |  |  |  | 5159.36 | 274.85 | 1113069.03
| Material - Other | Material | Material - Other | 72305.95 | 12623.14 | 109449.24 | 23783.08 | 43384.16 | 394426.18 | 529014.59 | 7560.72 | 50572.82 | 85807.9 | 90411.31 | -65553.8 | 1353785.29
|  | Material Total |  | 72305.95 | 12623.14 | 109449.24 | 23783.08 | 43384.16 | 394426.18 | 529014.59 | 7560.72 | 50572.82 | 85807.9 | 90411.31 | -65553.8 | 1353785.29
| Material - Other Total |  |  | 72305.95 | 12623.14 | 109449.24 | 23783.08 | 43384.16 | 394426.18 | 529014.59 | 7560.72 | 50572.82 | 85807.9 | 90411.31 | -65553.8 | 1353785.29
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | CROSS BROTHERS INC |  |  |  |  | 70473 | [7 empty] | 70473
|  |  | Material Entries <$5,000 | [8 empty] | 2552.27 | 437.24 |  | 102.22 | 3091.73
|  |  | Metals & Fabricated Metal Products-DP | [5 empty] | 5278.58 | [6 empty] | 5278.58
|  | Material - Direct Purchase Total | [5 empty] | 70473 | 5278.58 |  |  | 2552.27 | 437.24 |  | 102.22 | 78843.31
| Metals & Fabricated Metal Products-DP Total | [6 empty] | 70473 | 5278.58 |  |  | 2552.27 | 437.24 |  | 102.22 | 78843.31
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 1564 | [10 empty] | 1564
|  | Material - Direct Purchase Total |  |  | 1564 | [10 empty] | 1564
| Meters, Monitor and Warnings-DP Total |  |  |  | 1564 | [10 empty] | 1564
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 | [5 empty] | 11.11 | [6 empty] | 11.11
|  | Material - Direct Purchase Total | [6 empty] | 11.11 | [6 empty] | 11.11
| Monitor Equipment, Gauges and Hoses-DP Total | [7 empty] | 11.11 | [6 empty] | 11.11
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 40.13 | 5 | 523 |  |  | 568.13
|  | Material - Direct Purchase Total | [8 empty] | 40.13 | 5 | 523 |  |  | 568.13
| Office & Office Support Products-DP Total | [9 empty] | 40.13 | 5 | 523 |  |  | 568.13
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 396.65 | 1442.9 | 2740.89 | 798.14 | 5378.58
|  |  | Pipe/Tubing, Fittings and Gaskets-DP | [5 empty] | 5418.57 |  | 12208.42 |  |  |  |  | 17626.99
|  | Material - Direct Purchase Total | [6 empty] | 5418.57 |  | 12208.42 | 396.65 | 1442.9 | 2740.89 | 798.14 | 23005.57
| Pipe/Tubing, Fittings and Gaskets-DP Total | [7 empty] | 5418.57 |  | 12208.42 | 396.65 | 1442.9 | 2740.89 | 798.14 | 23005.57
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | M & M POWER PRODUCTS | 277034.48 | [11 empty] | 277034.48
|  |  | Material Entries <$5,000 |  |  |  |  | 273.16 | 4685.12 |  |  |  | 3607.83 |  |  | 8566.11
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [8 empty] | 5592.21 |  |  |  | 5592.21
|  |  | Pole Line Hdwe & Connectors-DP | [7 empty] | 5102.72 | 30204.95 |  | 5967.39 | 28248.26 | 69523.32
|  | Material - Direct Purchase Total |  | 277034.48 |  |  |  | 273.16 | 4685.12 |  | 5102.72 | 35797.16 | 3607.83 | 5967.39 | 28248.26 | 360716.12
| Pole Line Hdwe & Connectors-DP Total |  |  | 277034.48 |  |  |  | 273.16 | 4685.12 |  | 5102.72 | 35797.16 | 3607.83 | 5967.39 | 28248.26 | 360716.12
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | Power Systems, Batteries and Light-DP | 58159.5 | [11 empty] | 58159.5
|  | Material - Direct Purchase Total |  | 58159.5 | [11 empty] | 58159.5
| Power Systems, Batteries and Light-DP Total |  |  | 58159.5 | [11 empty] | 58159.5
| Protection and Test-DP | Material - Direct Purchase | GE MULTILIN |  |  | 112923.12 | [9 empty] | 112923.12
|  |  | Material Entries <$5,000 | [5 empty] | 1918.98 | [6 empty] | 1918.98
|  | Material - Direct Purchase Total |  |  |  | 112923.12 |  |  | 1918.98 | [6 empty] | 114842.1
| Protection and Test-DP Total |  |  |  |  | 112923.12 |  |  | 1918.98 | [6 empty] | 114842.1
| Reactors and Line Traps-DP | Material - Direct Purchase | HAEFELY TRENCH LIMITED |  | 481800 | 1000500 | [9 empty] | 1482300
|  | Material - Direct Purchase Total |  |  | 481800 | 1000500 | [9 empty] | 1482300
| Reactors and Line Traps-DP Total |  |  |  | 481800 | 1000500 | [9 empty] | 1482300
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | [8 empty] | 17938.52 |  |  |  | 17938.52
|  |  | Material Entries <$5,000 |  | 417.9 | [6 empty] | 431.8 | 1821.95 | 800 | 1285.2 | 4756.85
|  |  | WASHINGTON ORNAMENTAL | 428349.25 |  | 537951.28 |  | 171787 | 9912 | [6 empty] | 1147999.53
|  |  | WESTMONT INDUSTRIES | [9 empty] | 32984.6 |  |  | 32984.6
|  | Material - Direct Purchase Total |  | 428349.25 | 417.9 | 537951.28 |  | 171787 | 9912 |  |  | 18370.32 | 34806.55 | 800 | 1285.2 | 1203679.5
| Steel / Fabricated / Structural-DP Total |  |  | 428349.25 | 417.9 | 537951.28 |  | 171787 | 9912 |  |  | 18370.32 | 34806.55 | 800 | 1285.2 | 1203679.5
| Transformers - Distribution-DP | Material - Direct Purchase | POWER PARTNERS INC | [9 empty] | 5874 |  |  | 5874
|  | Material - Direct Purchase Total | [10 empty] | 5874 |  |  | 5874
| Transformers - Distribution-DP Total | [11 empty] | 5874 |  |  | 5874
| Transformers - Power Substation-DP | Material - Direct Purchase | MITSUBISHI ELECTRIC | [5 empty] | 4078800 | 6774670 |  |  | 628670 | 312186.99 |  | 11794326.99
|  | Material - Direct Purchase Total | [6 empty] | 4078800 | 6774670 |  |  | 628670 | 312186.99 |  | 11794326.99
| Transformers - Power Substation-DP Total | [7 empty] | 4078800 | 6774670 |  |  | 628670 | 312186.99 |  | 11794326.99
| Transformers Components/Parts-DP | Material - Direct Purchase | Transformers Components/Parts-DP | [11 empty] | 18501 | 18501
|  | Material - Direct Purchase Total | [12 empty] | 18501 | 18501
| Transformers Components/Parts-DP Total | [13 empty] | 18501 | 18501
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | ABB INC | 125982 | [11 empty] | 125982
|  |  | Material Entries <$5,000 |  | 4960 | [10 empty] | 4960
|  | Material - Direct Purchase Total |  | 125982 | 4960 | [10 empty] | 130942
| Transformers CT/PT/INSTR-DP Total |  |  | 125982 | 4960 | [10 empty] | 130942
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 2399.4 | 9922.76 | 4816 | 161.16 | 17.13 |  |  |  | 264.25 | 3126.87 | 3084.16 | 2633.25 | 26424.98
|  |  | Transportation & Mobile Equip-DP | 27919.39 |  | 10955.8 |  | 5708.8 | [7 empty] | 44583.99
|  | Material - Direct Purchase Total |  | 30318.79 | 9922.76 | 15771.8 | 161.16 | 5725.93 |  |  |  | 264.25 | 3126.87 | 3084.16 | 2633.25 | 71008.97
| Transportation & Mobile Equip-DP Total |  |  | 30318.79 | 9922.76 | 15771.8 | 161.16 | 5725.93 |  |  |  | 264.25 | 3126.87 | 3084.16 | 2633.25 | 71008.97
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 4860 | [9 empty] | 2.22 | 4862.22
|  |  | SOUTHWIRE COMPANY |  |  | 45853.86 | [9 empty] | 45853.86
|  |  | Wire, Cable & Bus Bar-DP | [7 empty] | 6721.28 |  |  |  |  | 6721.28
|  | Material - Direct Purchase Total |  |  | 4860 | 45853.86 |  |  |  |  | 6721.28 |  |  |  | 2.22 | 57437.36
| Wire, Cable & Bus Bar-DP Total |  |  |  | 4860 | 45853.86 |  |  |  |  | 6721.28 |  |  |  | 2.22 | 57437.36
2. Material Total |  |  |  | 1004717.72 | 573980.12 | 2351417.29 | 54815.31 | 633902.02 | 5593626.16 | 7542951.59 | 50625.8 | 631529.34 | 1242215.62 | 474535.12 | 97318.73 | 20251634.82
3. Construction | Construction Management Services | Contract | CIRCLE WOOD SERVICES, INC | [10 empty] | 79240.5 | 55260.4 | 134500.9
|  |  | Contract Entries <$50,000 | 4448 | 348 | 7056.5 | 5702 | 14320.83 | 10910 | 73094.16 | 35330.5 | 5541 | 86004.81 | 202689.18 | 317472.87 | 762917.85
|  |  | UTILITY LINE MANAGEMENT SERVICES | [6 empty] | 122727.49 | 218445.89 |  |  |  | 50866.57 | 392039.95
|  | Contract Total |  | 4448 | 348 | 7056.5 | 5702 | 14320.83 | 10910 | 195821.65 | 253776.39 | 5541 | 86004.81 | 281929.68 | 423599.84 | 1289458.7
| Construction Management Services Total |  |  | 4448 | 348 | 7056.5 | 5702 | 14320.83 | 10910 | 195821.65 | 253776.39 | 5541 | 86004.81 | 281929.68 | 423599.84 | 1289458.7
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [7 empty] | 1165.02 |  |  |  |  | 1165.02
|  | Contract Total | [8 empty] | 1165.02 |  |  |  |  | 1165.02
| Construction, Civil/Structural Total | [9 empty] | 1165.02 |  |  |  |  | 1165.02
| Construction, Earthwork | Contract | Contract Entries <$50,000 | [7 empty] | 6420 | 3260 | 1700 |  |  | 11380
|  | Contract Total | [8 empty] | 6420 | 3260 | 1700 |  |  | 11380
| Construction, Earthwork Total | [9 empty] | 6420 | 3260 | 1700 |  |  | 11380
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 166.86 | 166.86
|  | Labor Total | [12 empty] | 166.86 | 166.86
| ELEC SYS PLANNING Total | [13 empty] | 166.86 | 166.86
| Electrical Construction, Substations | Contract | Contract Entries <$50,000 | [10 empty] | 7949 |  | 7949
|  |  | PROFESSIONAL ELECTRICAL CONSTRUCTIO | [8 empty] | 318340 | 225971 | 628527 | 239984 | 1412822
|  | Contract Total | [9 empty] | 318340 | 225971 | 636476 | 239984 | 1420771
| Electrical Construction, Substations Total | [10 empty] | 318340 | 225971 | 636476 | 239984 | 1420771
| Electrical Services | Contract | ABB INC | [9 empty] | 135720 |  |  | 135720
|  | Contract Total | [10 empty] | 135720 |  |  | 135720
| Electrical Services Total | [11 empty] | 135720 |  |  | 135720
| ENGINEERING | Labor | Labor Entries <$5,000 | 508.22 | 135.24 | 156.07 |  |  |  | 166.87 |  |  | 328.68 |  |  | 1295.08
|  | Labor Total |  | 508.22 | 135.24 | 156.07 |  |  |  | 166.87 |  |  | 328.68 |  |  | 1295.08
| ENGINEERING Total |  |  | 508.22 | 135.24 | 156.07 |  |  |  | 166.87 |  |  | 328.68 |  |  | 1295.08
| GRID OPS | Labor | Labor Entries <$5,000 | [9 empty] | 543.15 |  | 254.96 | 798.11
|  | Labor Total | [10 empty] | 543.15 |  | 254.96 | 798.11
| GRID OPS Total | [11 empty] | 543.15 |  | 254.96 | 798.11
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | 11852.8 | 4404.56 | 1752.66 | 14234.33 |  |  |  | 2849.06 |  |  |  |  | 35093.41
|  | Contract Total |  | 11852.8 | 4404.56 | 1752.66 | 14234.33 |  |  |  | 2849.06 |  |  |  |  | 35093.41
| Hauling / Industrial Moving Services Total |  |  | 11852.8 | 4404.56 | 1752.66 | 14234.33 |  |  |  | 2849.06 |  |  |  |  | 35093.41
| Major Construction, Turnkey, Trans/Subs | Contract | CANUS CORPORATION | [11 empty] | 117809.3 | 117809.3
|  |  | Contract Entries <$50,000 | [5 empty] | 588 | [5 empty] | 80143.92 | 80731.92
|  |  | KINDNESS GENERAL CONTRACTORS INC | [5 empty] | 69947.67 | 64455.19 | 65148.4 |  |  | 61096.96 | 151993.75 | 412641.97
|  |  | Major Construction, Turnkey, Trans/Subs | [11 empty] | 173505.88 | 173505.88
|  |  | MISSION PAVING AND SEALING INC | [9 empty] | 900026.5 |  |  | 900026.5
|  |  | TRIMAX SYSTEMS, INC. | [6 empty] | 65240 | [5 empty] | 65240
|  | Contract Total | [6 empty] | 70535.67 | 129695.19 | 65148.4 |  | 900026.5 | 61096.96 | 523452.85 | 1749955.57
| Major Construction, Turnkey, Trans/Subs Total | [7 empty] | 70535.67 | 129695.19 | 65148.4 |  | 900026.5 | 61096.96 | 523452.85 | 1749955.57
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | 3959.1 | 3756.21 | 11314.48 | 2608.08 | 15440.82 |  | 1164.01 | 9610.57 | 1695.19 | 19301.33 | 15518.31 | -548.9 | 83819.2
|  |  | Sub Stn Elect | [9 empty] | 10623.69 |  |  | 10623.69
|  |  | Tst Spr Tech | [10 empty] | 17517.75 |  | 17517.75
|  | Labor Total |  | 3959.1 | 3756.21 | 11314.48 | 2608.08 | 15440.82 |  | 1164.01 | 9610.57 | 1695.19 | 29925.02 | 33036.06 | -548.9 | 111960.64
| N/W SUBSMTCETEST&APP Total |  |  | 3959.1 | 3756.21 | 11314.48 | 2608.08 | 15440.82 |  | 1164.01 | 9610.57 | 1695.19 | 29925.02 | 33036.06 | -548.9 | 111960.64
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [8 empty] | 1163.24 | 7481.41 | 966.7 | 1505.42 | 11116.77
|  |  | Technician Test | [10 empty] | 16575.67 |  | 16575.67
|  |  | Tst Spr Tech | [9 empty] | 14135.89 | 21187.96 |  | 35323.85
|  | Labor Total | [9 empty] | 1163.24 | 21617.3 | 38730.33 | 1505.42 | 63016.29
| S/E SUBS MTCETST&APP Total | [10 empty] | 1163.24 | 21617.3 | 38730.33 | 1505.42 | 63016.29
| SC&M | Labor | Labor Entries <$5,000 | 435.96 |  | 1769.82 | 438.7 | 214.41 |  |  | 683.04 | 1075.99 | 754.41 |  | 22954.11 | 28326.44
|  |  | SC&M / Tst Spr Tech | [11 empty] | 18892.38 | 18892.38
|  | Labor Total |  | 435.96 |  | 1769.82 | 438.7 | 214.41 |  |  | 683.04 | 1075.99 | 754.41 |  | 41846.49 | 47218.82
| SC&M Total |  |  | 435.96 |  | 1769.82 | 438.7 | 214.41 |  |  | 683.04 | 1075.99 | 754.41 |  | 41846.49 | 47218.82
| Security / Protection Services | Contract | Contract Entries <$50,000 | [6 empty] | 19018.02 | 26787.29 | 18805.02 | 18803.74 | 18915.72 | 27087.5 | 129417.29
|  | Contract Total | [7 empty] | 19018.02 | 26787.29 | 18805.02 | 18803.74 | 18915.72 | 27087.5 | 129417.29
| Security / Protection Services Total | [8 empty] | 19018.02 | 26787.29 | 18805.02 | 18803.74 | 18915.72 | 27087.5 | 129417.29
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 |  | 1917.5 |  |  |  | 4586.92 | 18050.74 | 7556.21 | 32520.56 | 22945.42 | 22214.94 | 31755.67 | 141547.96
|  | Contract Total |  |  | 1917.5 |  |  |  | 4586.92 | 18050.74 | 7556.21 | 32520.56 | 22945.42 | 22214.94 | 31755.67 | 141547.96
| Short Term Equipment Rent Total |  |  |  | 1917.5 |  |  |  | 4586.92 | 18050.74 | 7556.21 | 32520.56 | 22945.42 | 22214.94 | 31755.67 | 141547.96
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | 574 | 82 | 164 | 328 |  |  |  | 82 |  |  |  |  | 1230
|  | Labor Total |  | 574 | 82 | 164 | 328 |  |  |  | 82 |  |  |  |  | 1230
| TSD-HERC - Crane Svs Total |  |  | 574 | 82 | 164 | 328 |  |  |  | 82 |  |  |  |  | 1230
3. Construction Total |  |  |  | 21778.08 | 10643.51 | 22213.53 | 23311.11 | 29976.06 | 86032.59 | 363916.48 | 374077.98 | 382401 | 1444340.03 | 1092399.69 | 1289104.69 | 5140194.75
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 1136.23 | 8208.31 | 5363.8 | 3681.24 | 9105.05 | 336.73 | 8812.14 | 7727.43 | 3411.29 | 3646.29 | 5576.61 | 3995.52 | 61000.64
|  |  | MATERIAL MANAGEM | [5 empty] | 194054.56 | [6 empty] | 194054.56
|  |  | PGSP-TRTP 3C-TRTP | [11 empty] | 5347.74 | 5347.74
|  |  | PROCUREMENT TDBU | 7352.22 |  | 14885.37 |  |  | 28048.01 | 48801.72 |  | 6146.34 | 16777.11 | 9854.07 | 9242.05 | 141106.89
|  |  | TDBU Vehicle Cost | [9 empty] | 6740.56 | 7784.09 | 5555.33 | 20079.98
|  |  | TRTP 9 Windhub New Substation | [11 empty] | 7487.1 | 7487.1
|  | Chargeback Total |  | 8488.45 | 8208.31 | 20249.17 | 3681.24 | 9105.05 | 222439.3 | 57613.86 | 7727.43 | 9557.63 | 27163.96 | 23214.77 | 31627.74 | 429076.91
| Chargebacks Total |  |  | 8488.45 | 8208.31 | 20249.17 | 3681.24 | 9105.05 | 222439.3 | 57613.86 | 7727.43 | 9557.63 | 27163.96 | 23214.77 | 31627.74 | 429076.91
| Labor - Other | Labor | ALH Sub Order for:TRTP Segment 3C: Windh | [11 empty] | 19625.96 | 19625.96
|  |  | Division Overhead | 78606.21 | 31667.53 | 172040.02 |  | 41062.24 | 351838.2 | 570059.98 | 19492.54 | 59181.35 | 209093.93 | 35121.59 | 49748.22 | 1617911.81
|  |  | Labor Entries <$5,000 | 6384.84 | 12226.26 | 9039.25 | 14140.94 | 11868.31 | 1363.95 | 2222.24 | 17113.05 | 5536.81 | 13868.11 | 14238.93 | -6563.04 | 101439.65
|  |  | Paid Absence | [9 empty] | 8892.87 | 6868.02 | 9521.43 | 25282.32
|  | Labor Total |  | 84991.05 | 43893.79 | 181079.27 | 14140.94 | 52930.55 | 353202.15 | 572282.22 | 36605.59 | 64718.16 | 231854.91 | 56228.54 | 72332.57 | 1764259.74
| Labor - Other Total |  |  | 84991.05 | 43893.79 | 181079.27 | 14140.94 | 52930.55 | 353202.15 | 572282.22 | 36605.59 | 64718.16 | 231854.91 | 56228.54 | 72332.57 | 1764259.74
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -670.37 | 670.37 |  |  | 0
|  | Overhead Total | [9 empty] | -670.37 | 670.37 |  |  | 0
| Overhead Correction Total | [10 empty] | -670.37 | 670.37 |  |  | 0
4. Allocated Total |  |  |  | 93479.5 | 52102.1 | 201328.44 | 17822.18 | 62035.6 | 575641.45 | 629896.08 | 44333.02 | 73605.42 | 259689.24 | 79443.31 | 103960.31 | 2193336.65
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 186845.85 | 11626.03 | [7 empty] | 198471.88
|  |  | Capitalized Overhead - A&G | 67202.49 | 19385.54 | 92766.06 | 7107.54 | 64674.84 | 225715.29 | 301217.64 | 13848.47 | 49381.63 | 77082.93 | 46947.41 | 43377.23 | 1008707.07
|  |  | Capitalized Overhead - Inj & Damages | 1043.21 | 1102.6 | 2724.18 | 76.99 | 6452.55 | 7986.19 | 7496.91 | 154.46 | 681.09 | 5040 | 1085.12 | 338.55 | 34181.85
|  |  | Capitalized Overhead - P&B/Payroll Tax | 6896.01 | 11859.01 | 28182.92 | 14838.09 | 39179.78 | 8680.65 | 10655.76 | 14924.21 | 8071.84 | 36062.57 | 58199.82 | 141010.4 | 378561.06
|  | Non Budgeted Total |  | 75141.71 | 32347.15 | 123673.16 | 208868.47 | 121933.2 | 242382.13 | 319370.31 | 28927.14 | 58134.56 | 118185.5 | 106232.35 | 184726.18 | 1619921.86
| Non Budget - Other Total |  |  | 75141.71 | 32347.15 | 123673.16 | 208868.47 | 121933.2 | 242382.13 | 319370.31 | 28927.14 | 58134.56 | 118185.5 | 106232.35 | 184726.18 | 1619921.86
5. Corporate Overhead Total |  |  |  | 75141.71 | 32347.15 | 123673.16 | 208868.47 | 121933.2 | 242382.13 | 319370.31 | 28927.14 | 58134.56 | 118185.5 | 106232.35 | 184726.18 | 1619921.86
Grand Total |  |  |  | 632672.41 | 1044639.1 | 2460879.76 | 537445.63 | 791189.28 | 11040602.79 | 4392865.42 | 966281.69 | 1262504.67 | 2575589.93 | 1863757.31 | 2921259.42 | 30489687.41

## 800219424
Pin: 7014 | Project: TRTP Segment 3C
Order: 800219424 | 800219424- I: TRTP 3C-1: WINDHUB 500KV UPGRADE PIN
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 2078.09 | 1823.37 | 2715.46 | 1832.24 | 1910.67 | 2140.26 | 1683.66 | 1863.24 | 524.03 |  |  |  | 16571.02
|  | Labor Total |  | 2078.09 | 1823.37 | 2715.46 | 1832.24 | 1910.67 | 2140.26 | 1683.66 | 1863.24 | 524.03 |  |  |  | 16571.02
| BP&FM Total |  |  | 2078.09 | 1823.37 | 2715.46 | 1832.24 | 1910.67 | 2140.26 | 1683.66 | 1863.24 | 524.03 |  |  |  | 16571.02
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 |  | 175 | 350 |  | 175 | 175 | 175 | 0 | 350 |  | 175 |  | 1575
|  | Contract Total |  |  | 175 | 350 |  | 175 | 175 | 175 | 0 | 350 |  | 175 |  | 1575
| Cleaning / Janitorial Services Total |  |  |  | 175 | 350 |  | 175 | 175 | 175 | 0 | 350 |  | 175 |  | 1575
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [7 empty] | 5596.28 |  |  |  |  | 5596.28
|  | Contract Total | [8 empty] | 5596.28 |  |  |  |  | 5596.28
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [9 empty] | 5596.28 |  |  |  |  | 5596.28
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -45063.24 | 45063.24 |  |  | 0
|  | Contract Total | [9 empty] | -45063.24 | 45063.24 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -45063.24 | 45063.24 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  | 337.7 |  | 975.81 | [6 empty] | 1313.51
|  | Contract Total |  |  |  |  | 337.7 |  | 975.81 | [6 empty] | 1313.51
| Contract Consult/Contract Ord to Ord Total | [5 empty] | 337.7 |  | 975.81 | [6 empty] | 1313.51
| CORP COMM SVP | Labor | Labor Entries <$5,000 | [7 empty] | 93.58 |  |  |  |  | 93.58
|  | Labor Total | [8 empty] | 93.58 |  |  |  |  | 93.58
| CORP COMM SVP Total | [9 empty] | 93.58 |  |  |  |  | 93.58
| ENGINEERING | Labor | Labor Entries <$5,000 | 2495.05 | 523.4 | 3478.24 | 531.49 | 2055.71 | 2359.97 | 529.88 |  |  |  | 674.12 |  | 12647.86
|  | Labor Total |  | 2495.05 | 523.4 | 3478.24 | 531.49 | 2055.71 | 2359.97 | 529.88 |  |  |  | 674.12 |  | 12647.86
| ENGINEERING Total |  |  | 2495.05 | 523.4 | 3478.24 | 531.49 | 2055.71 | 2359.97 | 529.88 |  |  |  | 674.12 |  | 12647.86
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 11038.17 | 19014.94 | 0 | 39634.19 | 8393 | 1778 | 1144 | 416 |  | 208 |  |  | 81626.3
|  | Contract Total |  | 11038.17 | 19014.94 | 0 | 39634.19 | 8393 | 1778 | 1144 | 416 |  | 208 |  |  | 81626.3
| Engineering/Technical Professional Servi Total |  |  | 11038.17 | 19014.94 | 0 | 39634.19 | 8393 | 1778 | 1144 | 416 |  | 208 |  |  | 81626.3
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 6162.1 | 2857.6 | 2454.18 | 1625.16 | 1236.99 | 2286.52 | 0 |  |  |  |  | 16622.55
|  | Contract Total |  |  | 6162.1 | 2857.6 | 2454.18 | 1625.16 | 1236.99 | 2286.52 | 0 |  |  |  |  | 16622.55
| Environmental/Safety Professional Servic Total |  |  |  | 6162.1 | 2857.6 | 2454.18 | 1625.16 | 1236.99 | 2286.52 | 0 |  |  |  |  | 16622.55
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 43547.92 | -43547.92 |  |  | 0
|  | IMM Correction Total | [9 empty] | 43547.92 | -43547.92 |  |  | 0
| IMM/Allocated - Correction Total | [10 empty] | 43547.92 | -43547.92 |  |  | 0
| Labor - Other | Labor | Labor Correction | [9 empty] | 11335.09 |  |  | 11335.09
|  |  | Labor Entries <$5,000 | 55.05 | 519.84 | -615.49 | 2126.13 | 2909.13 | -1872.52 | -73.08 | 235.27 | -13647.05 | 2317.9 | -56.24 | -78.63 | -8179.69
|  |  | U_SUBORDER*WINDHUB 500KV UPGRADE |  |  |  | 7239.66 | [8 empty] | 7239.66
|  | Labor Total |  | 55.05 | 519.84 | -615.49 | 9365.79 | 2909.13 | -1872.52 | -73.08 | 235.27 | -13647.05 | 13652.99 | -56.24 | -78.63 | 10395.06
| Labor - Other Total |  |  | 55.05 | 519.84 | -615.49 | 9365.79 | 2909.13 | -1872.52 | -73.08 | 235.27 | -13647.05 | 13652.99 | -56.24 | -78.63 | 10395.06
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  | 582.79 | 303.42 | 587.8 | 1733.73 | 7469.32 |  |  | 1079.78 |  |  |  | 11756.84
|  | Labor Total |  |  | 582.79 | 303.42 | 587.8 | 1733.73 | 7469.32 |  |  | 1079.78 |  |  |  | 11756.84
| NORTH GRIDMGMTCENTER Total |  |  |  | 582.79 | 303.42 | 587.8 | 1733.73 | 7469.32 |  |  | 1079.78 |  |  |  | 11756.84
| Other | Other | Other | -489834.82 | 273688.64 | -241912.52 | 65679.03 | -103050.1 | 212.82 | 1678.09 | -59689.11 | 21869.46 | -20247.82 | 198189.52 | -195940.92 | -549357.73
|  | Other Total |  | -489834.82 | 273688.64 | -241912.52 | 65679.03 | -103050.1 | 212.82 | 1678.09 | -59689.11 | 21869.46 | -20247.82 | 198189.52 | -195940.92 | -549357.73
| Other Total |  |  | -489834.82 | 273688.64 | -241912.52 | 65679.03 | -103050.1 | 212.82 | 1678.09 | -59689.11 | 21869.46 | -20247.82 | 198189.52 | -195940.92 | -549357.73
| SC&M | Labor | Labor Entries <$5,000 | 995.14 | 1886.68 | 1813.77 | 1977.72 | 990.24 | 682.27 | 354.63 | 341.13 |  |  |  | 207.09 | 9248.67
|  | Labor Total |  | 995.14 | 1886.68 | 1813.77 | 1977.72 | 990.24 | 682.27 | 354.63 | 341.13 |  |  |  | 207.09 | 9248.67
| SC&M Total |  |  | 995.14 | 1886.68 | 1813.77 | 1977.72 | 990.24 | 682.27 | 354.63 | 341.13 |  |  |  | 207.09 | 9248.67
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -3908.57 | 3908.57 |  |  | 0
|  | Contract Total | [9 empty] | -3908.57 | 3908.57 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -3908.57 | 3908.57 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 788 | 788 | 1970 | 788 | [8 empty] | 4334
|  | Contract Total |  | 788 | 788 | 1970 | 788 | [8 empty] | 4334
| Temporary/Supplementary - Technical/Prof Total |  |  | 788 | 788 | 1970 | 788 | [8 empty] | 4334
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 5012.67 | 7450 | 13882.35 | -0.53 | 1448.3 | 335.04 | 2092 | 1568 |  |  |  |  | 31787.83
|  | Contract Total |  | 5012.67 | 7450 | 13882.35 | -0.53 | 1448.3 | 335.04 | 2092 | 1568 |  |  |  |  | 31787.83
| Temporary/Supplementary - Trade/Labor Total |  |  | 5012.67 | 7450 | 13882.35 | -0.53 | 1448.3 | 335.04 | 2092 | 1568 |  |  |  |  | 31787.83
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 | [5 empty] | 77 | 932.4 | [5 empty] | 1009.4
|  | Labor Total | [6 empty] | 77 | 932.4 | [5 empty] | 1009.4
| TSD-Aircraft - Fixed Total | [7 empty] | 77 | 932.4 | [5 empty] | 1009.4
1. Project Support Total |  |  |  | -467372.65 | 312614.76 | -215157.17 | 123187.61 | -81809.16 | 15569.96 | 10803.1 | -49575.61 | 4752.33 | -962.94 | 198982.4 | -195812.46 | -344779.83
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 3683.55 | [9 empty] | 3683.55
|  |  | MITSUBISHI ELECTRIC | [5 empty] | 9000 | [6 empty] | 9000
|  | Material - Direct Purchase Total |  |  |  | 3683.55 |  |  | 9000 | [6 empty] | 12683.55
| Breakers - Circuit-DP Total |  |  |  |  | 3683.55 |  |  | 9000 | [6 empty] | 12683.55
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | COMPOSITE SUPPORT & SOLUTIONS |  |  | 97994 | [9 empty] | 97994
|  |  | Material Entries <$5,000 | 326.27 | 2352.82 | 156.98 | [9 empty] | 2836.07
|  | Material - Direct Purchase Total |  | 326.27 | 2352.82 | 98150.98 | [9 empty] | 100830.07
| Building, Shop & Industrial Products/Eqp Total |  |  | 326.27 | 2352.82 | 98150.98 | [9 empty] | 100830.07
| Capacitors and Regulators-DP | Material - Direct Purchase | GENERAL ELECTRIC COMPANY |  |  | 11200 | [9 empty] | 11200
|  |  | Material Entries <$5,000 | [11 empty] | -66264 | -66264
|  | Material - Direct Purchase Total |  |  |  | 11200 | [8 empty] | -66264 | -55064
| Capacitors and Regulators-DP Total |  |  |  |  | 11200 | [8 empty] | -66264 | -55064
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | 151.32 | 4113.18 | -6534 | [9 empty] | -2269.5
|  |  | SOUTHWIRE COMPANY | 5910 | 251839.25 | [10 empty] | 257749.25
|  | Material - Direct Purchase Total |  | 6061.32 | 255952.43 | -6534 | [9 empty] | 255479.75
| Electric Wiring and Components-DP Total |  |  | 6061.32 | 255952.43 | -6534 | [9 empty] | 255479.75
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 | 77.7 | [11 empty] | 77.7
|  | Material - Direct Purchase Total |  | 77.7 | [11 empty] | 77.7
| Fuels, Chemicals & Petrochem-DP Total |  |  | 77.7 | [11 empty] | 77.7
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -70.46 | 70.46 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -70.46 | 70.46 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -70.46 | 70.46 |  |  | 0
| Material - Inventory | Material | Material - Inventory | -9866.78 |  | -279760.71 | -3319.66 |  |  | -30841.66 | -27877.86 | -1.1 | -4471.81 |  |  | -356139.58
|  | Material Total |  | -9866.78 |  | -279760.71 | -3319.66 |  |  | -30841.66 | -27877.86 | -1.1 | -4471.81 |  |  | -356139.58
| Material - Inventory Total |  |  | -9866.78 |  | -279760.71 | -3319.66 |  |  | -30841.66 | -27877.86 | -1.1 | -4471.81 |  |  | -356139.58
| Material - Other | Material | Material - Other | 1184.11 | 19691.59 | 51197.54 | 6196.03 | 32085.47 | 278.14 | -2277.92 | -2529.3 | -6.75 | -321.21 |  | -198.33 | 105299.37
|  | Material Total |  | 1184.11 | 19691.59 | 51197.54 | 6196.03 | 32085.47 | 278.14 | -2277.92 | -2529.3 | -6.75 | -321.21 |  | -198.33 | 105299.37
| Material - Other Total |  |  | 1184.11 | 19691.59 | 51197.54 | 6196.03 | 32085.47 | 278.14 | -2277.92 | -2529.3 | -6.75 | -321.21 |  | -198.33 | 105299.37
| Mechanical Systems and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | 1100 | [11 empty] | 1100
|  | Material - Direct Purchase Total |  | 1100 | [11 empty] | 1100
| Mechanical Systems and Components-DP Total |  |  | 1100 | [11 empty] | 1100
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | 183.38 | [11 empty] | 183.38
|  | Material - Direct Purchase Total |  | 183.38 | [11 empty] | 183.38
| Metals & Fabricated Metal Products-DP Total |  |  | 183.38 | [11 empty] | 183.38
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | 119.66 | 689.71 |  | -11.94 |  | 3642.66 |  | 169.69 |  |  |  |  | 4609.78
|  | Material - Direct Purchase Total |  | 119.66 | 689.71 |  | -11.94 |  | 3642.66 |  | 169.69 |  |  |  |  | 4609.78
| Office & Office Support Products-DP Total |  |  | 119.66 | 689.71 |  | -11.94 |  | 3642.66 |  | 169.69 |  |  |  |  | 4609.78
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | 194.02 | [11 empty] | 194.02
|  | Material - Direct Purchase Total |  | 194.02 | [11 empty] | 194.02
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  | 194.02 | [11 empty] | 194.02
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 483 | -1362.9 | [7 empty] | -15000 | -15879.9
|  | Material - Direct Purchase Total |  |  |  | 483 | -1362.9 | [7 empty] | -15000 | -15879.9
| Pole Line Hdwe & Connectors-DP Total |  |  |  |  | 483 | -1362.9 | [7 empty] | -15000 | -15879.9
| Protection and Test-DP | Material - Direct Purchase | GE CONSUMER AND INDUSTRIAL |  |  |  | 11398.56 | [8 empty] | 11398.56
|  |  | Material Entries <$5,000 | [11 empty] | -11399 | -11399
|  | Material - Direct Purchase Total |  |  |  |  | 11398.56 | [7 empty] | -11399 | -0.44
| Protection and Test-DP Total | [5 empty] | 11398.56 | [7 empty] | -11399 | -0.44
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | 150 |  | 795 | 125 | [7 empty] | -70000 | -68930
|  | Material - Direct Purchase Total |  | 150 |  | 795 | 125 | [7 empty] | -70000 | -68930
| Steel / Fabricated / Structural-DP Total |  |  | 150 |  | 795 | 125 | [7 empty] | -70000 | -68930
| Transformers Components/Parts-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -36.4 |  |  |  | -36.4
|  | Material - Direct Purchase Total | [9 empty] | -36.4 |  |  |  | -36.4
| Transformers Components/Parts-DP Total | [10 empty] | -36.4 |  |  |  | -36.4
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 698.28 | 132.11 | 502.41 | 526.04 |  | 561.43 | [6 empty] | 2420.27
|  | Material - Direct Purchase Total |  | 698.28 | 132.11 | 502.41 | 526.04 |  | 561.43 | [6 empty] | 2420.27
| Transportation & Mobile Equip-DP Total |  |  | 698.28 | 132.11 | 502.41 | 526.04 |  | 561.43 | [6 empty] | 2420.27
2. Material Total |  |  |  | 227.96 | 278818.66 | -120282.23 | 13551.13 | 32085.47 | 13482.23 | -33119.58 | -30237.47 | -114.71 | -4722.56 |  | -162861.33 | -13172.43
3. Construction | Construction Management Services | Contract | CIRCLE WOOD SERVICES, INC |  |  | 53971.28 |  |  | 57635.56 | [6 empty] | 111606.84
|  |  | Contract Entries <$50,000 | 80453.52 | 16721.65 | 66035.05 | 97232.25 | 137225.74 | 67268.99 | 6507 | 1180.54 |  | 3783.9 | 0 | 1800 | 478208.64
|  |  | UTILITY LINE MANAGEMENT SERVICES | [5 empty] | 54894.62 | [6 empty] | 54894.62
|  | Contract Total |  | 80453.52 | 16721.65 | 120006.33 | 97232.25 | 137225.74 | 179799.17 | 6507 | 1180.54 |  | 3783.9 | 0 | 1800 | 644710.1
| Construction Management Services Total |  |  | 80453.52 | 16721.65 | 120006.33 | 97232.25 | 137225.74 | 179799.17 | 6507 | 1180.54 |  | 3783.9 | 0 | 1800 | 644710.1
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 |  |  |  |  | 488.7 |  |  | 2887.53 |  |  |  |  | 3376.23
|  | Contract Total | [5 empty] | 488.7 |  |  | 2887.53 |  |  |  |  | 3376.23
| Construction, Civil/Structural Total | [6 empty] | 488.7 |  |  | 2887.53 |  |  |  |  | 3376.23
| Construction, Earthwork | Contract | Contract Entries <$50,000 |  |  | 34000 |  | 3400 | [7 empty] | 37400
|  | Contract Total |  |  |  | 34000 |  | 3400 | [7 empty] | 37400
| Construction, Earthwork Total |  |  |  |  | 34000 |  | 3400 | [7 empty] | 37400
| ECS HOME | Labor | Labor Entries <$5,000 |  | 2040.56 |  |  |  | 695.16 | [6 empty] | 2735.72
|  | Labor Total |  |  | 2040.56 |  |  |  | 695.16 | [6 empty] | 2735.72
| ECS HOME Total |  |  |  | 2040.56 |  |  |  | 695.16 | [6 empty] | 2735.72
| Electrical Services | Contract | Contract Entries <$50,000 |  |  | 30000 | [9 empty] | 30000
|  | Contract Total |  |  |  | 30000 | [9 empty] | 30000
| Electrical Services Total |  |  |  |  | 30000 | [9 empty] | 30000
| ENGINEERING | Labor | Labor Entries <$5,000 | 169.41 |  | 370.66 | 614.62 | 545.93 | 893.67 | [6 empty] | 2594.29
|  | Labor Total |  | 169.41 |  | 370.66 | 614.62 | 545.93 | 893.67 | [6 empty] | 2594.29
| ENGINEERING Total |  |  | 169.41 |  | 370.66 | 614.62 | 545.93 | 893.67 | [6 empty] | 2594.29
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | 2477.01 |  | 2483.18 | 3562.55 | [8 empty] | 8522.74
|  | Contract Total |  | 2477.01 |  | 2483.18 | 3562.55 | [8 empty] | 8522.74
| Hauling / Industrial Moving Services Total |  |  | 2477.01 |  | 2483.18 | 3562.55 | [8 empty] | 8522.74
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | 21184 | 40164 | 15744 | 3453 | 29193.92 |  |  | 10000 |  |  |  | -333505.88 | -213766.96
|  |  | KINDNESS GENERAL CONTRACTORS INC | 190602.63 | 165500.7 | 82606.19 | 355211.54 |  | 52322.5 | [5 empty] | 173505.88 | 1019749.44
|  |  | PROFESSIONAL ELECTRICAL CONSTRUCTIO |  | 217236 | 147272.5 | 125098.14 |  |  | 300517.33 | [5 empty] | 790123.97
|  | Contract Total |  | 211786.63 | 422900.7 | 245622.69 | 483762.68 | 29193.92 | 52322.5 | 300517.33 | 10000 |  |  |  | -160000 | 1596106.45
| Major Construction, Turnkey, Trans/Subs Total |  |  | 211786.63 | 422900.7 | 245622.69 | 483762.68 | 29193.92 | 52322.5 | 300517.33 | 10000 |  |  |  | -160000 | 1596106.45
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 |  |  |  |  | 1530.05 | 6877.77 | 106.59 |  | 2565.48 |  |  |  | 11079.89
|  | Labor Total | [5 empty] | 1530.05 | 6877.77 | 106.59 |  | 2565.48 |  |  |  | 11079.89
| N/W SUBSMTCETEST&APP Total | [6 empty] | 1530.05 | 6877.77 | 106.59 |  | 2565.48 |  |  |  | 11079.89
| SC&M | Labor | Labor Entries <$5,000 | 92.3 |  | 1674.5 | 87.74 |  | 185.98 |  | 496.24 |  |  |  |  | 2536.76
|  | Labor Total |  | 92.3 |  | 1674.5 | 87.74 |  | 185.98 |  | 496.24 |  |  |  |  | 2536.76
| SC&M Total |  |  | 92.3 |  | 1674.5 | 87.74 |  | 185.98 |  | 496.24 |  |  |  |  | 2536.76
| Security / Protection Services | Contract | Contract Entries <$50,000 | 79150.58 | 2948.78 | 19391.25 | 18945.74 | 19024.21 | 19444.02 | [6 empty] | 158904.58
|  |  | WACKENHUT CORPORATION (THE) |  | 55442.12 | [10 empty] | 55442.12
|  | Contract Total |  | 79150.58 | 58390.9 | 19391.25 | 18945.74 | 19024.21 | 19444.02 | [6 empty] | 214346.7
| Security / Protection Services Total |  |  | 79150.58 | 58390.9 | 19391.25 | 18945.74 | 19024.21 | 19444.02 | [6 empty] | 214346.7
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 29270.81 | 36675.52 | 21600.97 | 24822.72 | 16334.86 | 11789.7 | 7659.91 | 990.55 | 0 | -1207.55 | 1631.25 | -423.7 | 149145.04
|  | Contract Total |  | 29270.81 | 36675.52 | 21600.97 | 24822.72 | 16334.86 | 11789.7 | 7659.91 | 990.55 | 0 | -1207.55 | 1631.25 | -423.7 | 149145.04
| Short Term Equipment Rent Total |  |  | 29270.81 | 36675.52 | 21600.97 | 24822.72 | 16334.86 | 11789.7 | 7659.91 | 990.55 | 0 | -1207.55 | 1631.25 | -423.7 | 149145.04
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 |  | 82 | 82 | 82 | [8 empty] | 246
|  | Labor Total |  |  | 82 | 82 | 82 | [8 empty] | 246
| TSD-HERC - Crane Svs Total |  |  |  | 82 | 82 | 82 | [8 empty] | 246
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | [5 empty] | 82 | 82 | 82 | 82 |  |  |  | 328
|  | Labor Total | [6 empty] | 82 | 82 | 82 | 82 |  |  |  | 328
| TSD-HERC - Rental Total | [7 empty] | 82 | 82 | 82 | 82 |  |  |  | 328
3. Construction Total |  |  |  | 403400.26 | 536811.33 | 475231.58 | 629110.3 | 207743.41 | 272089.97 | 314872.83 | 15636.86 | 2647.48 | 2576.35 | 1631.25 | -158623.7 | 2703127.92
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -18504.18 | 3445.78 | -57522.84 | 10695.61 | 8061.5 | 7522 | -2115.23 | -2442.65 | -838.44 | 925.17 | 65.23 | -2108.32 | -52816.37
|  |  | PROCUREMENT TDBU |  | 5224.09 | [10 empty] | 5224.09
|  |  | TRTP 9 Windhub New Substation | 9579.03 | [11 empty] | 9579.03
|  |  | TRTP-2010 SEG03C Windhub 500Kv-TDBU |  |  | 5827.23 |  | 23648.42 | [7 empty] | 29475.65
|  |  | Windhub Construct 500KV- Segment 9 | [6 empty] | 5105.6 | [5 empty] | 5105.6
|  | Chargeback Total |  | -8925.15 | 8669.87 | -51695.61 | 10695.61 | 31709.92 | 7522 | 2990.37 | -2442.65 | -838.44 | 925.17 | 65.23 | -2108.32 | -3432
| Chargebacks Total |  |  | -8925.15 | 8669.87 | -51695.61 | 10695.61 | 31709.92 | 7522 | 2990.37 | -2442.65 | -838.44 | 925.17 | 65.23 | -2108.32 | -3432
| Labor - Other | Labor | Division Overhead | 37844.23 | 75413.76 | 10693.46 | 47598.73 | 6057.44 | 7175.61 | 9353.97 | [5 empty] | 194137.2
|  |  | Labor Entries <$5,000 | 6170.04 | 2514.43 | 16864.41 | 8568.83 | 12592.38 | 16292.67 | 13774.2 | 137.12 | -5560.1 | 7679.44 | 200.55 | -11620.47 | 67613.5
|  | Labor Total |  | 44014.27 | 77928.19 | 27557.87 | 56167.56 | 18649.82 | 23468.28 | 23128.17 | 137.12 | -5560.1 | 7679.44 | 200.55 | -11620.47 | 261750.7
| Labor - Other Total |  |  | 44014.27 | 77928.19 | 27557.87 | 56167.56 | 18649.82 | 23468.28 | 23128.17 | 137.12 | -5560.1 | 7679.44 | 200.55 | -11620.47 | 261750.7
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -1730.23 | 1730.23 |  |  | 0
|  | Overhead Total | [9 empty] | -1730.23 | 1730.23 |  |  | 0
| Overhead Correction Total | [10 empty] | -1730.23 | 1730.23 |  |  | 0
4. Allocated Total |  |  |  | 35089.12 | 86598.06 | -24137.74 | 66863.17 | 50359.74 | 30990.28 | 26118.54 | -2305.53 | -8128.77 | 10334.84 | 265.78 | -13728.79 | 258318.7
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 599609.16 | 36285.9 | [7 empty] | 635895.06
|  |  | AFUDC - Debt/Equity |  |  | 630901.7 | -630901.7 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 25819.56 | 27610.8 | 12929.21 | 27494.79 | 24584.28 | 11853.9 | 11189.6 | -1880.46 | -37.8 | 186.69 | 96.65 | -9372.01 | 130475.21
|  |  | Capitalized Overhead - Inj & Damages | 57.13 | 706.5 | -125.41 | 98.28 | 603.19 | 96.54 | 0.55 | -114.85 | 43.27 | -144.51 | 5.73 | -198.07 | 1028.35
|  |  | Capitalized Overhead - P&B/Payroll Tax | 5059.86 | 9747.73 | 12312.56 | 20126.14 | 19836.24 | 26138.77 | 3379.78 | 2395.23 | -13482.06 | 6574.4 | 527.05 | 280.09 | 92895.79
|  |  | Corporate Overheads Correction |  |  |  |  | -64313.51 | [7 empty] | -64313.51
|  | Non Budgeted Total |  | 30936.55 | 38065.03 | 656018.06 | 16426.67 | 16996.1 | 38089.21 | 14569.93 | 399.92 | -13476.59 | 6616.58 | 629.43 | -9289.99 | 795980.9
| Non Budget - Other Total |  |  | 30936.55 | 38065.03 | 656018.06 | 16426.67 | 16996.1 | 38089.21 | 14569.93 | 399.92 | -13476.59 | 6616.58 | 629.43 | -9289.99 | 795980.9
5. Corporate Overhead Total |  |  |  | 30936.55 | 38065.03 | 656018.06 | 16426.67 | 16996.1 | 38089.21 | 14569.93 | 399.92 | -13476.59 | 6616.58 | 629.43 | -9289.99 | 795980.9
Grand Total |  |  |  | 2281.24 | 1252907.84 | 771672.5 | 849138.88 | 225375.56 | 370221.65 | 333244.82 | -66081.83 | -14320.26 | 13842.27 | 201508.86 | -540316.27 | 3399475.26

## 800051827
Pin: 7014 | Project: TRTP Segment 3C
Order: 800051827 | 800051827- 9219-2303--FERC-ANTELOPE TRANSMISSION
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [10 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12
1. Project Support | Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -9160.12 | 9160.12 |  | 0
|  | Contract Total | [9 empty] | -9160.12 | 9160.12 |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -9160.12 | 9160.12 |  | 0
| HRealProp | Labor | Labor Entries <$5,000 | 22.85 | 35.94 | 55.9 | 21.5 | 224.66 | [6 empty] | 360.85
|  | Labor Total |  | 22.85 | 35.94 | 55.9 | 21.5 | 224.66 | [6 empty] | 360.85
| HRealProp Total |  |  | 22.85 | 35.94 | 55.9 | 21.5 | 224.66 | [6 empty] | 360.85
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 9469.59 | -9469.59 |  | 0
|  | IMM Correction Total | [9 empty] | 9469.59 | -9469.59 |  | 0
| IMM/Allocated - Correction Total | [10 empty] | 9469.59 | -9469.59 |  | 0
| Information System Professional Services | Contract | Contract Entries <$50,000 | 425.6 |  | -31.9 |  |  | 35.09 | [5 empty] | 428.79
|  | Contract Total |  | 425.6 |  | -31.9 |  |  | 35.09 | [5 empty] | 428.79
| Information System Professional Services Total |  |  | 425.6 |  | -31.9 |  |  | 35.09 | [5 empty] | 428.79
| Labor - Other | Labor | Labor Entries <$5,000 |  | 9.46 | -9.46 | -1.98 | 67.8 | -65.82 |  |  | -309.47 | 309.47 |  | 0
|  | Labor Total |  |  | 9.46 | -9.46 | -1.98 | 67.8 | -65.82 |  |  | -309.47 | 309.47 |  | 0
| Labor - Other Total |  |  |  | 9.46 | -9.46 | -1.98 | 67.8 | -65.82 |  |  | -309.47 | 309.47 |  | 0
| Other | Other | Other | 3593.29 | 5319.7 |  |  |  |  | 29.56 | -14500 |  | -669700 |  | -675257.45
|  | Other Total |  | 3593.29 | 5319.7 |  |  |  |  | 29.56 | -14500 |  | -669700 |  | -675257.45
| Other Total |  |  | 3593.29 | 5319.7 |  |  |  |  | 29.56 | -14500 |  | -669700 |  | -675257.45
1. Project Support Total |  |  |  | 4041.74 | 5365.1 | 14.54 | 19.52 | 292.46 | -30.73 | 29.56 | -14500 | -6.8212e-13 | -669700 |  | -674467.81
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 755.93 | 5035.21 | 1523.99 | 1587.39 | 642.5 | 0.23 | 0.2 |  | -60.46 | 60.46 |  | 9545.45
|  | Chargeback Total |  | 755.93 | 5035.21 | 1523.99 | 1587.39 | 642.5 | 0.23 | 0.2 |  | -60.46 | 60.46 |  | 9545.45
| Chargebacks Total |  |  | 755.93 | 5035.21 | 1523.99 | 1587.39 | 642.5 | 0.23 | 0.2 |  | -60.46 | 60.46 |  | 9545.45
| Labor - Other | Labor | Labor Entries <$5,000 | 150.42 | 127.16 | 9.65 | 4.35 | 65.21 | -13.91 | 0.65 |  | -208.33 | 473.48 |  | 608.68
|  | Labor Total |  | 150.42 | 127.16 | 9.65 | 4.35 | 65.21 | -13.91 | 0.65 |  | -208.33 | 473.48 |  | 608.68
| Labor - Other Total |  |  | 150.42 | 127.16 | 9.65 | 4.35 | 65.21 | -13.91 | 0.65 |  | -208.33 | 473.48 |  | 608.68
| Overhead Correction | Overhead | Overhead Correction | [10 empty] | -266.59 | -266.59
|  | Overhead Total | [11 empty] | -266.59 | -266.59
| Overhead Correction Total | [12 empty] | -266.59 | -266.59
4. Allocated Total |  |  |  | 906.35 | 5162.37 | 1533.64 | 1591.74 | 707.71 | -13.68 | 0.85 |  | -268.79 | 533.94 | -266.59 | 9887.54
Grand Total |  |  |  | 4948.09 | 10527.47 | 1548.18 | 1611.26 | 1000.17 | -44.41 | 30.41 | -14500 | -268.79 | -669166.06 | -266.59 | -664580.27

## TRTP Seg 4
WO | SumOfYTD2012 | Order | Project
900271208- Midway-Vincent No.3 Ground Clearance Upg | 672.23 | 900271208 | TRTP Segment 4
900269206- Antelope-Windhuub 500kV Cross-Over Elimi | 659.63 | 900269206 | TRTP Segment 4
800217211- I: TRTP 4-3: PATH 26 LOOP: CONSTRUCT APP | 1390698.34 | 800217211 | TRTP Segment 4
800217203- I: DRYCREEKWIND-WHIRLWIND 230KV T/L: CON | -291795.11 | 800217203 | TRTP Segment 4
800217116- I: TRTP: ANTELOPE-WHIRLWIND 500KV T/L: C | 12562831.62 | 800217116 | TRTP Segment 4
800051900- 9219-2366 - TRTP Segment 4 | 1831144.96 | 800051900 | TRTP Segment 4

## 900271208
Pin: 6435 | Project: TRTP Segment 4
Order: 900271208 | 900271208- Midway-Vincent No.3 Ground Clearance Upg
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [5 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 5 | 8 | 9 | 10
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  | 71.51 | 166.98 |  | 238.49
|  | Labor Total |  |  |  |  | 71.51 | 166.98 |  | 238.49
| BP&FM Total | [5 empty] | 71.51 | 166.98 |  | 238.49
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 44.89 | [5 empty] | 44.89
|  | Labor Total |  | 44.89 | [5 empty] | 44.89
| ENG ADVANCEMENT Total |  |  | 44.89 | [5 empty] | 44.89
| Labor - Other | Labor | Labor Entries <$5,000 | 4.71 | -4.71 |  |  | -4.38 | 4.38 | 0
|  | Labor Total |  | 4.71 | -4.71 |  |  | -4.38 | 4.38 | 0
| Labor - Other Total |  |  | 4.71 | -4.71 |  |  | -4.38 | 4.38 | 0
1. Project Support Total |  |  |  | 49.6 | -4.71 |  | 71.51 | 162.6 | 4.38 | 283.38
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 16.4 | -1.14 | 38.58 | 3.15 | 10.15 | 0.24 | 67.38
|  | Chargeback Total |  | 16.4 | -1.14 | 38.58 | 3.15 | 10.15 | 0.24 | 67.38
| Chargebacks Total |  |  | 16.4 | -1.14 | 38.58 | 3.15 | 10.15 | 0.24 | 67.38
| Labor - Other | Labor | Labor Entries <$5,000 | 14.88 | -1.63 |  | 19.35 | 41.47 | 1.27 | 75.34
|  | Labor Total |  | 14.88 | -1.63 |  | 19.35 | 41.47 | 1.27 | 75.34
| Labor - Other Total |  |  | 14.88 | -1.63 |  | 19.35 | 41.47 | 1.27 | 75.34
4. Allocated Total |  |  |  | 31.28 | -2.77 | 38.58 | 22.5 | 51.62 | 1.51 | 142.72
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G | 4.51 | -0.22 | 3.21 | 2.66 | 9.6 | 0.15 | 19.91
|  |  | Capitalized Overhead - Inj & Damages | 0.08 | -0.01 | 0.34 | 0.12 | 0.19 | 0.02 | 0.74
|  |  | Capitalized Overhead - P&B/Payroll Tax | 33.83 | -5.45 |  | 58.13 | 232.97 | 2.14 | 321.62
|  |  | Corporate Overheads Correction |  |  | -96.14 |  |  |  | -96.14
|  | Non Budgeted Total |  | 38.42 | -5.68 | -92.59 | 60.91 | 242.76 | 2.31 | 246.13
| Non Budget - Other Total |  |  | 38.42 | -5.68 | -92.59 | 60.91 | 242.76 | 2.31 | 246.13
5. Corporate Overhead Total |  |  |  | 38.42 | -5.68 | -92.59 | 60.91 | 242.76 | 2.31 | 246.13
Grand Total |  |  |  | 119.3 | -13.16 | -54.01 | 154.92 | 456.98 | 8.2 | 672.23

## 900269206
Pin: 6435 | Project: TRTP Segment 4
Order: 900269206 | 900269206- Antelope-Windhuub 500kV Cross-Over Elimi
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 |  |  |  | 2012 Total
SubCategory | Prime | Group | Details | 5 | 6 | 7 | 11
1. Project Support | ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  |  |  | 261.73 | 261.73
|  | Labor Total |  |  |  |  | 261.73 | 261.73
| ENG ADVANCEMENT Total | [5 empty] | 261.73 | 261.73
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  | -1.05 |  | -1.05
|  | IMM Correction Total |  |  |  | -1.05 |  | -1.05
| IMM/Allocated - Correction Total |  |  |  |  | -1.05 |  | -1.05
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  | 159.72 |  |  | 159.72
|  | Contract Total |  |  | 159.72 |  |  | 159.72
| Temporary/Supplementary - Trade/Labor Total |  |  |  | 159.72 |  |  | 159.72
1. Project Support Total |  |  |  |  | 159.72 | -1.05 | 261.73 | 420.4
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 |  | 1.05 |  | 18.69 | 19.74
|  | Chargeback Total |  |  | 1.05 |  | 18.69 | 19.74
| Chargebacks Total |  |  |  | 1.05 |  | 18.69 | 19.74
| Labor - Other | Labor | Labor Entries <$5,000 |  | 7.12 |  | 57.4 | 64.52
|  | Labor Total |  |  | 7.12 |  | 57.4 | 64.52
| Labor - Other Total |  |  |  | 7.12 |  | 57.4 | 64.52
4. Allocated Total |  |  |  |  | 8.17 |  | 76.09 | 84.26
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G |  | 5.99 | -0.04 | 8.93 | 14.88
|  |  | Capitalized Overhead - Inj & Damages |  | 0.01 |  | 0.56 | 0.57
|  |  | Capitalized Overhead - P&B/Payroll Tax |  |  |  | 223.26 | 223.26
|  |  | Corporate Overheads Correction | -83.74 |  |  |  | -83.74
|  | Non Budgeted Total |  | -83.74 | 6 | -0.04 | 232.75 | 154.97
| Non Budget - Other Total |  |  | -83.74 | 6 | -0.04 | 232.75 | 154.97
5. Corporate Overhead Total |  |  |  | -83.74 | 6 | -0.04 | 232.75 | 154.97
Grand Total |  |  |  | -83.74 | 173.89 | -1.09 | 570.57 | 659.63

## 800217211
Pin: 6435 | Project: TRTP Segment 4
Order: 800217211 | 800217211- I: TRTP 4-3: PATH 26 LOOP: CONSTRUCT APP
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 90.35 |  | 119.19 |  |  |  |  | 209.54
|  | Labor Total | [6 empty] | 90.35 |  | 119.19 |  |  |  |  | 209.54
| BP&FM Total | [7 empty] | 90.35 |  | 119.19 |  |  |  |  | 209.54
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 677.41 | [11 empty] | 677.41
|  | Labor Total |  | 677.41 | [11 empty] | 677.41
| ENG ADVANCEMENT Total |  |  | 677.41 | [11 empty] | 677.41
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  |  |  | 503.73 | [7 empty] | 503.73
|  | Labor Total | [5 empty] | 503.73 | [7 empty] | 503.73
| ENGINEERING Total | [6 empty] | 503.73 | [7 empty] | 503.73
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | 305634 | 103806 | 136284 | 142878 | 160054 |  | 224529 | 62847 |  |  |  |  | 1136032
|  |  | Contract Entries <$50,000 |  | 16212.94 |  |  |  |  | 22086.9 |  | 13285.13 | 12650 | -38541 | 39972.06 | 65666.03
|  | Contract Total |  | 305634 | 120018.94 | 136284 | 142878 | 160054 |  | 246615.9 | 62847 | 13285.13 | 12650 | -38541 | 39972.06 | 1201698.03
| Engineering/Technical Professional Servi Total |  |  | 305634 | 120018.94 | 136284 | 142878 | 160054 |  | 246615.9 | 62847 | 13285.13 | 12650 | -38541 | 39972.06 | 1201698.03
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -2278.74 | -1138.43 | -1573.81 | -942.99 | -4271.41 |  | -1627.66 | -414.79 | -87.53 | -83.3 | -1368.13 | -13786.79
|  | IMM Correction Total |  |  | -2278.74 | -1138.43 | -1573.81 | -942.99 | -4271.41 |  | -1627.66 | -414.79 | -87.53 | -83.3 | -1368.13 | -13786.79
| IMM/Allocated - Correction Total |  |  |  | -2278.74 | -1138.43 | -1573.81 | -942.99 | -4271.41 |  | -1627.66 | -414.79 | -87.53 | -83.3 | -1368.13 | -13786.79
| Labor - Other | Labor | Labor Entries <$5,000 | -18.24 | 18.24 |  |  | 198.77 | -198.77 | [6 empty] | 0
|  | Labor Total |  | -18.24 | 18.24 |  |  | 198.77 | -198.77 | [6 empty] | 0
| Labor - Other Total |  |  | -18.24 | 18.24 |  |  | 198.77 | -198.77 | [6 empty] | 0
| Other | Other | Other | 185592.95 | -53724.87 | -200455.55 | 130479.99 | -353512.25 | -38817.86 | -151157.49 | -31181.83 | 6114.12 | -13683.94 | -203215 | 37224.65 | -686337.08
|  | Other Total |  | 185592.95 | -53724.87 | -200455.55 | 130479.99 | -353512.25 | -38817.86 | -151157.49 | -31181.83 | 6114.12 | -13683.94 | -203215 | 37224.65 | -686337.08
| Other Total |  |  | 185592.95 | -53724.87 | -200455.55 | 130479.99 | -353512.25 | -38817.86 | -151157.49 | -31181.83 | 6114.12 | -13683.94 | -203215 | 37224.65 | -686337.08
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  |  | 319.44 | [9 empty] | 319.44
|  | Contract Total |  |  |  | 319.44 | [9 empty] | 319.44
| Temporary/Supplementary - Trade/Labor Total |  |  |  |  | 319.44 | [9 empty] | 319.44
1. Project Support Total |  |  |  | 491886.12 | 64033.57 | -64990.54 | 271784.18 | -193698.74 | -43197.69 | 95458.41 | 30156.7 | 18984.46 | -1121.47 | -241839.3 | 75828.58 | 503284.28
2. Material | Material - Other | Material | Material - Other |  |  | 0.14 |  |  | 0.01 |  | 0.04 | -1.25 | -0.93 | 0.08 |  | -1.91
|  | Material Total |  |  |  | 0.14 |  |  | 0.01 |  | 0.04 | -1.25 | -0.93 | 0.08 |  | -1.91
| Material - Other Total |  |  |  |  | 0.14 |  |  | 0.01 |  | 0.04 | -1.25 | -0.93 | 0.08 |  | -1.91
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -23.1 | -29 |  |  | -52.1
|  | Material - Direct Purchase Total | [9 empty] | -23.1 | -29 |  |  | -52.1
| Steel / Fabricated / Structural-DP Total | [10 empty] | -23.1 | -29 |  |  | -52.1
2. Material Total | [5 empty] | 0.14 |  |  | 0.01 |  | 0.04 | -24.35 | -29.93 | 0.08 |  | -54.01
3. Construction | Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 | 10857.2 | [10 empty] | 0 | 10857.2
|  |  | HENKELS & MC COY INC |  | 52470.52 | 101852.89 |  | 487128.75 | [5 empty] | 245832.93 |  | 887285.09
|  | Contract Total |  | 10857.2 | 52470.52 | 101852.89 |  | 487128.75 | [5 empty] | 245832.93 | 0 | 898142.29
| Electrical Construction, Transmission Li Total |  |  | 10857.2 | 52470.52 | 101852.89 |  | 487128.75 | [5 empty] | 245832.93 | 0 | 898142.29
| GRID OPS | Labor | Labor Entries <$5,000 |  | 608.52 | [10 empty] | 608.52
|  | Labor Total |  |  | 608.52 | [10 empty] | 608.52
| GRID OPS Total |  |  |  | 608.52 | [10 empty] | 608.52
3. Construction Total |  |  |  | 10857.2 | 53079.04 | 101852.89 |  | 487128.75 | [5 empty] | 245832.93 | 0 | 898750.81
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 7038.44 | 8198.57 | 7631.79 | 8732.92 | 10290.31 | 7766.87 | 4049.87 | 2773.02 | 2212.31 | 2178.82 | 10232.43 | 3249.89 | 74355.24
|  | Chargeback Total |  | 7038.44 | 8198.57 | 7631.79 | 8732.92 | 10290.31 | 7766.87 | 4049.87 | 2773.02 | 2212.31 | 2178.82 | 10232.43 | 3249.89 | 74355.24
| Chargebacks Total |  |  | 7038.44 | 8198.57 | 7631.79 | 8732.92 | 10290.31 | 7766.87 | 4049.87 | 2773.02 | 2212.31 | 2178.82 | 10232.43 | 3249.89 | 74355.24
| Labor - Other | Labor | Division Overhead | 6488.07 |  |  |  | 24787.5 | [7 empty] | 31275.57
|  |  | Labor Entries <$5,000 | 12015.3 | 15138.52 | 8679.82 | 4586.39 | 3623.45 | -29.99 | 10259.22 | 2609 | 421.74 | 655.03 | 2218.03 | 535.62 | 60712.13
|  | Labor Total |  | 18503.37 | 15138.52 | 8679.82 | 4586.39 | 28410.95 | -29.99 | 10259.22 | 2609 | 421.74 | 655.03 | 2218.03 | 535.62 | 91987.7
| Labor - Other Total |  |  | 18503.37 | 15138.52 | 8679.82 | 4586.39 | 28410.95 | -29.99 | 10259.22 | 2609 | 421.74 | 655.03 | 2218.03 | 535.62 | 91987.7
4. Allocated Total |  |  |  | 25541.81 | 23337.09 | 16311.61 | 13319.31 | 38701.26 | 7736.88 | 14309.09 | 5382.02 | 2634.05 | 2833.85 | 12450.46 | 3785.51 | 166342.94
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 62673 | 3765.68 | [6 empty] | 65685.07 | 132123.75
|  |  | AFUDC - Debt/Equity |  |  | 64548.33 | -64548.33 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 19125.49 | 5688.57 | 9040.54 | 5513.96 | 57066.64 | 119.81 | 9161.83 | 1887.21 | 693.49 | 397.02 | 5804.99 | 1190.14 | 115689.69
|  |  | Capitalized Overhead - Inj & Damages | 22.77 | 32.41 | 12.38 | 7.19 | 323.28 | -1.83 | 11.66 | 3.36 | 1.08 | 5.2 | 11.28 | 0.97 | 429.75
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1962.04 | 4081.35 | 2328.38 | 4891.22 | 5503.61 | 2968.41 | 726.58 | 849.87 | 1192.43 | 399.28 | 2132.56 | 1526.85 | 28562.58
|  |  | Corporate Overheads Correction |  |  |  |  | -454431.45 | [7 empty] | -454431.45
|  | Non Budgeted Total |  | 21110.3 | 9802.33 | 75929.63 | 8537.04 | -387772.24 | 3086.39 | 9900.07 | 2740.44 | 1887 | 801.5 | 7948.83 | 68403.03 | -177625.68
| Non Budget - Other Total |  |  | 21110.3 | 9802.33 | 75929.63 | 8537.04 | -387772.24 | 3086.39 | 9900.07 | 2740.44 | 1887 | 801.5 | 7948.83 | 68403.03 | -177625.68
5. Corporate Overhead Total |  |  |  | 21110.3 | 9802.33 | 75929.63 | 8537.04 | -387772.24 | 3086.39 | 9900.07 | 2740.44 | 1887 | 801.5 | 7948.83 | 68403.03 | -177625.68
Grand Total |  |  |  | 549395.43 | 150252.03 | 129103.73 | 293640.53 | -55640.97 | -32374.41 | 119667.57 | 38279.2 | 23481.16 | 2483.95 | 24393 | 148017.12 | 1390698.34

## 800217203
Pin: 6435 | Project: TRTP Segment 4
Order: 800217203 | 800217203- I: DRYCREEKWIND-WHIRLWIND 230KV T/L: CON
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [10 empty] | -17296.46 |  | -17296.46
|  | Contract Total | [11 empty] | -17296.46 |  | -17296.46
| Consultants / Prof Services - Correction Total | [12 empty] | -17296.46 |  | -17296.46
| ENGINEERING | Labor | Labor Entries <$5,000 | 1122.73 | 1046.8 | 1301.98 | 1062.98 | [8 empty] | 4534.49
|  | Labor Total |  | 1122.73 | 1046.8 | 1301.98 | 1062.98 | [8 empty] | 4534.49
| ENGINEERING Total |  |  | 1122.73 | 1046.8 | 1301.98 | 1062.98 | [8 empty] | 4534.49
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | [10 empty] | -84207.63 |  | -84207.63
|  | Contract Total | [11 empty] | -84207.63 |  | -84207.63
| Engineering/Technical Professional Servi Total | [12 empty] | -84207.63 |  | -84207.63
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [9 empty] | -0.56 | -142.71 |  | -143.27
|  | IMM Correction Total | [10 empty] | -0.56 | -142.71 |  | -143.27
| IMM/Allocated - Correction Total | [11 empty] | -0.56 | -142.71 |  | -143.27
| Labor - Other | Labor | Labor Entries <$5,000 | 41.31 | 116.77 | -121.78 | 60.44 | -43.58 | 0.61 | 1.08 | 2.08 | 0.05 |  | -61664.02 |  | -61607.04
|  | Labor Total |  | 41.31 | 116.77 | -121.78 | 60.44 | -43.58 | 0.61 | 1.08 | 2.08 | 0.05 |  | -61664.02 |  | -61607.04
| Labor - Other Total |  |  | 41.31 | 116.77 | -121.78 | 60.44 | -43.58 | 0.61 | 1.08 | 2.08 | 0.05 |  | -61664.02 |  | -61607.04
| Other | Other | Other | [10 empty] | -1099.4 |  | -1099.4
|  | Other Total | [11 empty] | -1099.4 |  | -1099.4
| Other Total | [12 empty] | -1099.4 |  | -1099.4
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [10 empty] | -23502.65 |  | -23502.65
|  | Contract Total | [11 empty] | -23502.65 |  | -23502.65
| Temporary / Supplemental - Correction Total | [12 empty] | -23502.65 |  | -23502.65
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | [8 empty] | 85 | 683.48 | 170 |  | 938.48
|  | Contract Total | [9 empty] | 85 | 683.48 | 170 |  | 938.48
| Temporary/Supplementary - Trade/Labor Total | [10 empty] | 85 | 683.48 | 170 |  | 938.48
1. Project Support Total |  |  |  | 1164.04 | 1163.57 | 1180.2 | 1123.42 | -43.58 | 0.61 | 1.08 | 2.08 | 85.05 | 682.92 | -187742.87 |  | -182383.48
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | -271.13 |  | -271.13
|  | Material - Direct Purchase Total | [11 empty] | -271.13 |  | -271.13
| Material - Direct Purchase - Correction Total | [12 empty] | -271.13 |  | -271.13
| Material - Other | Material | Material - Other | [10 empty] | -2.77 |  | -2.77
|  | Material Total | [11 empty] | -2.77 |  | -2.77
| Material - Other Total | [12 empty] | -2.77 |  | -2.77
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | -30.01 |  | -30.01
|  | Material - Direct Purchase Total | [11 empty] | -30.01 |  | -30.01
| Transportation & Mobile Equip-DP Total | [12 empty] | -30.01 |  | -30.01
2. Material Total | [13 empty] | -303.91 |  | -303.91
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [10 empty] | -24105.12 |  | -24105.12
|  | Contract Total | [11 empty] | -24105.12 |  | -24105.12
| Construction Management Services Total | [12 empty] | -24105.12 |  | -24105.12
3. Construction Total | [13 empty] | -24105.12 |  | -24105.12
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 380.83 | 282.61 | 59.99 | 60.79 | -2.18 |  |  |  | 0.56 | 4.51 | -5160.43 |  | -4373.32
|  | Chargeback Total |  | 380.83 | 282.61 | 59.99 | 60.79 | -2.18 |  |  |  | 0.56 | 4.51 | -5160.43 |  | -4373.32
| Chargebacks Total |  |  | 380.83 | 282.61 | 59.99 | 60.79 | -2.18 |  |  |  | 0.56 | 4.51 | -5160.43 |  | -4373.32
| Labor - Other | Labor | Labor Entries <$5,000 | 345.37 | 400.73 | 306.02 | 285.66 | -13.96 |  |  | 0.01 | 2.7 | 35.48 | -14425.09 |  | -13063.08
|  | Labor Total |  | 345.37 | 400.73 | 306.02 | 285.66 | -13.96 |  |  | 0.01 | 2.7 | 35.48 | -14425.09 |  | -13063.08
| Labor - Other Total |  |  | 345.37 | 400.73 | 306.02 | 285.66 | -13.96 |  |  | 0.01 | 2.7 | 35.48 | -14425.09 |  | -13063.08
4. Allocated Total |  |  |  | 726.2 | 683.34 | 366.01 | 346.45 | -16.14 |  |  | 0.01 | 3.26 | 39.99 | -19585.52 |  | -17436.4
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 5651.08 | 332.92 | [6 empty] | 3959.06 | 9943.06
|  |  | AFUDC - Debt/Equity |  |  | 5974.04 | -5974.04 |  | 6264.04 | 6305.01 | 6346.25 | 6388.06 | 6432.56 | -31735.92 |  | 3.638e-12
|  |  | Capitalized Overhead - A&G | 105.49 | 54.11 | 55.11 | 52.42 | -4.97 | 0.02 | 0.04 | 0.06 | 3.96 | 18.68 | -6124.18 |  | -5839.26
|  |  | Capitalized Overhead - Inj & Damages | 1.77 | 3.19 | 1.63 | 1.22 | -0.53 |  |  |  |  | 0.12 | -136.16 |  | -128.76
|  |  | Capitalized Overhead - P&B/Payroll Tax | 792.47 | 1343.82 | 1207.49 | 1442.43 | -67.54 | 0.68 | 1.16 | 0.05 | 0.06 |  | -52144.66 |  | -47424.04
|  |  | Corporate Overheads Correction |  |  |  |  | -24117.2 | [7 empty] | -24117.2
|  | Non Budgeted Total |  | 899.73 | 1401.12 | 7238.27 | 1173.11 | -23857.32 | 6264.74 | 6306.21 | 6346.36 | 6392.08 | 6451.36 | -90140.92 | 3959.06 | -67566.2
| Non Budget - Other Total |  |  | 899.73 | 1401.12 | 7238.27 | 1173.11 | -23857.32 | 6264.74 | 6306.21 | 6346.36 | 6392.08 | 6451.36 | -90140.92 | 3959.06 | -67566.2
5. Corporate Overhead Total |  |  |  | 899.73 | 1401.12 | 7238.27 | 1173.11 | -23857.32 | 6264.74 | 6306.21 | 6346.36 | 6392.08 | 6451.36 | -90140.92 | 3959.06 | -67566.2
Grand Total |  |  |  | 2789.97 | 3248.03 | 8784.48 | 2642.98 | -23917.04 | 6265.35 | 6307.29 | 6348.45 | 6480.39 | 7174.27 | -321878.34 | 3959.06 | -291795.11

## 800217116
Pin: 6435 | Project: TRTP Segment 4
Order: 800217116 | 800217116- I: TRTP: ANTELOPE-WHIRLWIND 500KV T/L: C
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 90.35 | [6 empty] | 90.35
|  | Labor Total | [6 empty] | 90.35 | [6 empty] | 90.35
| BP&FM Total | [7 empty] | 90.35 | [6 empty] | 90.35
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 579479.57 |  |  | 579479.57
|  |  | Contract Entries <$50,000 | [8 empty] | -579479.57 |  |  |  | -579479.57
|  | Contract Total | [9 empty] | -579479.57 | 579479.57 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -579479.57 | 579479.57 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 604.61 | 604.61
|  | Labor Total | [12 empty] | 604.61 | 604.61
| ELEC SYS PLANNING Total | [13 empty] | 604.61 | 604.61
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 319.4 | 153.83 |  | 182.96 |  |  | 175.86 | [5 empty] | 832.05
|  | Labor Total |  | 319.4 | 153.83 |  | 182.96 |  |  | 175.86 | [5 empty] | 832.05
| ENG ADVANCEMENT Total |  |  | 319.4 | 153.83 |  | 182.96 |  |  | 175.86 | [5 empty] | 832.05
| ENGINEERING | Labor | Labor Entries <$5,000 | 6968.28 | 6886.76 | 6377.24 | 4418.48 | 2873.79 | 4076.65 | 2590.4 | 1010.86 | 1012.62 | 679.24 | 719.69 | 178.82 | 37792.83
|  | Labor Total |  | 6968.28 | 6886.76 | 6377.24 | 4418.48 | 2873.79 | 4076.65 | 2590.4 | 1010.86 | 1012.62 | 679.24 | 719.69 | 178.82 | 37792.83
| ENGINEERING Total |  |  | 6968.28 | 6886.76 | 6377.24 | 4418.48 | 2873.79 | 4076.65 | 2590.4 | 1010.86 | 1012.62 | 679.24 | 719.69 | 178.82 | 37792.83
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | 639052 | 217049 | 284958 | 298745 | 334658 |  | 467773 | 131407 | 84352.01 | 84337 | 144393 | 254575 | 2941299.01
|  |  | Contract Entries <$50,000 | 1393.8 | 37191.49 | 21646.15 | 11175.49 | 13557.69 | 9895.8 | 54109.22 | 1087.18 | 1237.04 | 609.5 | -125417.55 | 6649.59 | 33135.4
|  | Contract Total |  | 640445.8 | 254240.49 | 306604.15 | 309920.49 | 348215.69 | 9895.8 | 521882.22 | 132494.18 | 85589.05 | 84946.5 | 18975.45 | 261224.59 | 2974434.41
| Engineering/Technical Professional Servi Total |  |  | 640445.8 | 254240.49 | 306604.15 | 309920.49 | 348215.69 | 9895.8 | 521882.22 | 132494.18 | 85589.05 | 84946.5 | 18975.45 | 261224.59 | 2974434.41
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 6947.67 | 2206.43 | 1943.52 | 1684.87 | 4143.85 | 3332.1 | 3807 | 3245.48 | 2617.3 | 2038 | 45001.95 | 76968.17
|  | Contract Total |  |  | 6947.67 | 2206.43 | 1943.52 | 1684.87 | 4143.85 | 3332.1 | 3807 | 3245.48 | 2617.3 | 2038 | 45001.95 | 76968.17
| Environmental/Safety Professional Servic Total |  |  |  | 6947.67 | 2206.43 | 1943.52 | 1684.87 | 4143.85 | 3332.1 | 3807 | 3245.48 | 2617.3 | 2038 | 45001.95 | 76968.17
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 8126.32 | 631.78 | -4849.59 | 1702.21 | 5567.49 | -14042.63 | 1663.24 | 2050.35 | 2103297.44 | -2095817.23 | -4775.41 | -15754.47 | -12200.5
|  | IMM Correction Total |  | 8126.32 | 631.78 | -4849.59 | 1702.21 | 5567.49 | -14042.63 | 1663.24 | 2050.35 | 2103297.44 | -2095817.23 | -4775.41 | -15754.47 | -12200.5
| IMM/Allocated - Correction Total |  |  | 8126.32 | 631.78 | -4849.59 | 1702.21 | 5567.49 | -14042.63 | 1663.24 | 2050.35 | 2103297.44 | -2095817.23 | -4775.41 | -15754.47 | -12200.5
| Labor - Other | Labor | Labor - Other | [9 empty] | 11797.93 |  |  | 11797.93
|  |  | Labor Correction | [9 empty] | 58696.42 |  |  | 58696.42
|  |  | Labor Entries <$5,000 | 1386.47 | 1211.8 | -1284.46 | 305.87 | 120.11 | -999.87 | 101.6 | 115.83 | -185387.96 | 115015.82 | 21.81 | 806.06 | -68586.92
|  | Labor Total |  | 1386.47 | 1211.8 | -1284.46 | 305.87 | 120.11 | -999.87 | 101.6 | 115.83 | -185387.96 | 185510.17 | 21.81 | 806.06 | 1907.43
| Labor - Other Total |  |  | 1386.47 | 1211.8 | -1284.46 | 305.87 | 120.11 | -999.87 | 101.6 | 115.83 | -185387.96 | 185510.17 | 21.81 | 806.06 | 1907.43
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 1525.79 | 2469.78 | [10 empty] | 3995.57
|  | Labor Total |  | 1525.79 | 2469.78 | [10 empty] | 3995.57
| MAJOR PROJECT ORG Total |  |  | 1525.79 | 2469.78 | [10 empty] | 3995.57
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | 346.7 |  | 48.09 | [7 empty] | 143.43 | 64.2 | 602.42
|  | Labor Total |  | 346.7 |  | 48.09 | [7 empty] | 143.43 | 64.2 | 602.42
| NORTH GRIDMGMTCENTER Total |  |  | 346.7 |  | 48.09 | [7 empty] | 143.43 | 64.2 | 602.42
| Other | Other | Other | -1493066.99 | -378078.41 | -293463.47 | 944111.62 | -446265.92 | -561067.41 | -458354.15 | -7225.3 | -946417.82 | 1526197.81 | -1762730.96 | 1083398.48 | -2792962.52
|  | Other Total |  | -1493066.99 | -378078.41 | -293463.47 | 944111.62 | -446265.92 | -561067.41 | -458354.15 | -7225.3 | -946417.82 | 1526197.81 | -1762730.96 | 1083398.48 | -2792962.52
| Other Total |  |  | -1493066.99 | -378078.41 | -293463.47 | 944111.62 | -446265.92 | -561067.41 | -458354.15 | -7225.3 | -946417.82 | 1526197.81 | -1762730.96 | 1083398.48 | -2792962.52
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -51955.24 |  |  |  | -51955.24
|  |  | Temporary / Supplemental - Correction | [9 empty] | 51955.24 |  |  | 51955.24
|  | Contract Total | [9 empty] | -51955.24 | 51955.24 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -51955.24 | 51955.24 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 |  | 2482.85 | 833.7 | [9 empty] | 3316.55
|  | Contract Total |  |  | 2482.85 | 833.7 | [9 empty] | 3316.55
| Temporary/Supplementary - Technical/Prof Total |  |  |  | 2482.85 | 833.7 | [9 empty] | 3316.55
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1373.62 |  |  |  |  | 146.08 | 354.08 | 728 | 208 | 292.16 | 873.06 | 595.14 | 4570.14
|  | Contract Total |  | 1373.62 |  |  |  |  | 146.08 | 354.08 | 728 | 208 | 292.16 | 873.06 | 595.14 | 4570.14
| Temporary/Supplementary - Trade/Labor Total |  |  | 1373.62 |  |  |  |  | 146.08 | 354.08 | 728 | 208 | 292.16 | 873.06 | 595.14 | 4570.14
| TRANSMISSION | Labor | Labor Entries <$5,000 | 430.69 | 17400.59 | 10938.18 | 2041.04 | 177.12 |  |  |  |  | 238.32 | 532.54 | 4242.81 | 36001.29
|  | Labor Total |  | 430.69 | 17400.59 | 10938.18 | 2041.04 | 177.12 |  |  |  |  | 238.32 | 532.54 | 4242.81 | 36001.29
| TRANSMISSION Total |  |  | 430.69 | 17400.59 | 10938.18 | 2041.04 | 177.12 |  |  |  |  | 238.32 | 532.54 | 4242.81 | 36001.29
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 7353.67 | 4367.28 | 5416.85 | 3810.26 | 1568.07 | 1528.8 | 421.85 | 500.3 | 577.41 | 651.37 | 384.99 |  | 26580.85
|  | Labor Total |  | 7353.67 | 4367.28 | 5416.85 | 3810.26 | 1568.07 | 1528.8 | 421.85 | 500.3 | 577.41 | 651.37 | 384.99 |  | 26580.85
| TRNS CAPITAL Total |  |  | 7353.67 | 4367.28 | 5416.85 | 3810.26 | 1568.07 | 1528.8 | 421.85 | 500.3 | 577.41 | 651.37 | 384.99 |  | 26580.85
| VRZN BUS TELECONF | Labor | Labor Entries <$5,000 |  |  |  |  | 5.71 | 5.25 |  | 1.82 |  |  |  |  | 12.78
|  | Labor Total | [5 empty] | 5.71 | 5.25 |  | 1.82 |  |  |  |  | 12.78
| VRZN BUS TELECONF Total | [6 empty] | 5.71 | 5.25 |  | 1.82 |  |  |  |  | 12.78
1. Project Support Total |  |  |  | -824790.25 | -81285.58 | 32827.12 | 1268436.45 | -86053.07 | -556223.13 | 72167.2 | 133483.04 | 430689.41 | 336750.45 | -1743817.4 | 1380362.19 | 362546.43
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -143.55 | 143.55 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -143.55 | 143.55 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -143.55 | 143.55 |  |  | 0
| Material - Inventory | Material | Material - Inventory | 6250.1 | [7 empty] | -13.82 | 13.82 |  |  | 6250.1
|  | Material Total |  | 6250.1 | [7 empty] | -13.82 | 13.82 |  |  | 6250.1
| Material - Inventory Total |  |  | 6250.1 | [7 empty] | -13.82 | 13.82 |  |  | 6250.1
| Material - Other | Material | Material - Other | 1017.74 | 608.36 | 20935.88 | 357.11 | -11.44 | 0.52 | 2769.52 | -38.84 | 6.62 | 511.94 | 796.98 | 0.83 | 26955.22
|  | Material Total |  | 1017.74 | 608.36 | 20935.88 | 357.11 | -11.44 | 0.52 | 2769.52 | -38.84 | 6.62 | 511.94 | 796.98 | 0.83 | 26955.22
| Material - Other Total |  |  | 1017.74 | 608.36 | 20935.88 | 357.11 | -11.44 | 0.52 | 2769.52 | -38.84 | 6.62 | 511.94 | 796.98 | 0.83 | 26955.22
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | 171.01 | 5668.38 | [10 empty] | 5839.39
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [10 empty] | 10230 |  | 10230
|  | Material - Direct Purchase Total |  | 171.01 | 5668.38 | [8 empty] | 10230 |  | 16069.39
| Pole Line Hdwe & Connectors-DP Total |  |  | 171.01 | 5668.38 | [8 empty] | 10230 |  | 16069.39
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 4113 | 338.8 |  | 4451.8
|  | Material - Direct Purchase Total | [10 empty] | 4113 | 338.8 |  | 4451.8
| Towers/Poles, Steel & Concrete-DP Total | [11 empty] | 4113 | 338.8 |  | 4451.8
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 164 |  | -1476 |  | -1312
|  |  | SOUTHWIRE COMPANY |  |  | 186468 | [9 empty] | 186468
|  | Material - Direct Purchase Total |  |  |  | 186468 | [5 empty] | 164 |  | -1476 |  | 185156
| Wire, Cable & Bus Bar-DP Total |  |  |  |  | 186468 | [5 empty] | 164 |  | -1476 |  | 185156
2. Material Total |  |  |  | 7438.85 | 6276.74 | 207403.88 | 357.11 | -11.44 | 0.52 | 2769.52 | -38.84 | 13.25 | 4782.31 | 9889.78 | 0.83 | 238882.51
3. Construction | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [6 empty] | 3500 |  |  | 413.84 | 706.46 | 73.9 | 4694.2
|  | Contract Total | [7 empty] | 3500 |  |  | 413.84 | 706.46 | 73.9 | 4694.2
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [8 empty] | 3500 |  |  | 413.84 | 706.46 | 73.9 | 4694.2
| Construction Management Services | Contract | Contract Entries <$50,000 | 31468.74 | 60448.6 | 42944.02 | 75837.01 | 18849.09 | 34479.91 | 21197.62 | [5 empty] | 285224.99
|  | Contract Total |  | 31468.74 | 60448.6 | 42944.02 | 75837.01 | 18849.09 | 34479.91 | 21197.62 | [5 empty] | 285224.99
| Construction Management Services Total |  |  | 31468.74 | 60448.6 | 42944.02 | 75837.01 | 18849.09 | 34479.91 | 21197.62 | [5 empty] | 285224.99
| Construction Services - Other | Contract | Contract Entries <$50,000 | 1043.15 | 41.5 | 877.13 |  | 188.03 | 41.5 | [6 empty] | 2191.31
|  | Contract Total |  | 1043.15 | 41.5 | 877.13 |  | 188.03 | 41.5 | [6 empty] | 2191.31
| Construction Services - Other Total |  |  | 1043.15 | 41.5 | 877.13 |  | 188.03 | 41.5 | [6 empty] | 2191.31
| Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 | [5 empty] | -288300 |  |  |  |  | 1707.41 | 0 | -286592.59
|  |  | HENKELS & MC COY INC | 366405.95 | 1636217.23 | 433416.12 |  | 2954597.88 | 940581.73 |  |  | 882140.57 |  | 1714859.65 |  | 8928219.13
|  |  | WILSON UTILITY CONSTRUCTION | [10 empty] | 639494.88 | 996689.84 | 1636184.72
|  | Contract Total |  | 366405.95 | 1636217.23 | 433416.12 |  | 2954597.88 | 652281.73 |  |  | 882140.57 |  | 2356061.94 | 996689.84 | 10277811.26
| Electrical Construction, Transmission Li Total |  |  | 366405.95 | 1636217.23 | 433416.12 |  | 2954597.88 | 652281.73 |  |  | 882140.57 |  | 2356061.94 | 996689.84 | 10277811.26
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 129.59 | 129.59
|  | Labor Total | [12 empty] | 129.59 | 129.59
| GRID OPS Total | [13 empty] | 129.59 | 129.59
| Labor - Other | Labor | ACQ/TRTP Seg. 4-Const./Antelope-Whirlwin | [9 empty] | 7698.8 |  |  | 7698.8
|  |  | Labor Entries <$5,000 | 1042.54 | 1395.1 | 591.07 | 410.95 | 601.2 | 661.01 | 2196.62 | 1094.51 | 1974.36 | 2283.33 | 5927.97 | 649.96 | 18828.62
|  | Labor Total |  | 1042.54 | 1395.1 | 591.07 | 410.95 | 601.2 | 661.01 | 2196.62 | 1094.51 | 1974.36 | 9982.13 | 5927.97 | 649.96 | 26527.42
| Labor - Other Total |  |  | 1042.54 | 1395.1 | 591.07 | 410.95 | 601.2 | 661.01 | 2196.62 | 1094.51 | 1974.36 | 9982.13 | 5927.97 | 649.96 | 26527.42
| Material - Other | Material | Material - Other | [6 empty] | 1350.63 |  | 14.27 | 29.05 |  | 16.67 | 1410.62
|  | Material Total | [7 empty] | 1350.63 |  | 14.27 | 29.05 |  | 16.67 | 1410.62
| Material - Other Total | [8 empty] | 1350.63 |  | 14.27 | 29.05 |  | 16.67 | 1410.62
| Other | Other | Other | 320398.65 |  |  | 5475 |  |  |  | 5475 | 32.99 |  | 1220.36 | 44100 | 376702
|  | Other Total |  | 320398.65 |  |  | 5475 |  |  |  | 5475 | 32.99 |  | 1220.36 | 44100 | 376702
| Other Total |  |  | 320398.65 |  |  | 5475 |  |  |  | 5475 | 32.99 |  | 1220.36 | 44100 | 376702
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 461.17 | 461.17 | 3226.78 |  | 461.17 | -33.17 |  |  |  | -461.17 |  |  | 4115.95
|  | Contract Total |  | 461.17 | 461.17 | 3226.78 |  | 461.17 | -33.17 |  |  |  | -461.17 |  |  | 4115.95
| Short Term Equipment Rent Total |  |  | 461.17 | 461.17 | 3226.78 |  | 461.17 | -33.17 |  |  |  | -461.17 |  |  | 4115.95
| TRANSMISSION | Labor | Labor Entries <$5,000 | 558.46 | 2313.33 | 1361.56 |  |  |  |  | 483.76 | 142.93 | 243.5 | 738.01 | 4633.99 | 10475.54
|  | Labor Total |  | 558.46 | 2313.33 | 1361.56 |  |  |  |  | 483.76 | 142.93 | 243.5 | 738.01 | 4633.99 | 10475.54
| TRANSMISSION Total |  |  | 558.46 | 2313.33 | 1361.56 |  |  |  |  | 483.76 | 142.93 | 243.5 | 738.01 | 4633.99 | 10475.54
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 317.24 | [5 empty] | 66.95 | [5 empty] | 384.19
|  | Labor Total |  | 317.24 | [5 empty] | 66.95 | [5 empty] | 384.19
| TRNS CAPITAL Total |  |  | 317.24 | [5 empty] | 66.95 | [5 empty] | 384.19
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | 82 | 82 | [10 empty] | 164
|  | Labor Total |  | 82 | 82 | [10 empty] | 164
| TSD-HERC - Rental Total |  |  | 82 | 82 | [10 empty] | 164
3. Construction Total |  |  |  | 721777.9 | 1700958.93 | 482416.68 | 81722.96 | 2974697.37 | 687430.98 | 28311.82 | 7053.27 | 884305.12 | 10207.35 | 2364654.74 | 1046293.95 | 10989831.07
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -83502.21 | 8871.73 | 13917.48 | 19501.43 | -1626164.35 | -1432523.46 | 18819.97 | -80067.66 | 140292.21 | -228672.89 | -1310038.7 | 7571.33 | -4551995.12
|  |  | Law-TRTP SEG 4 - TDBU | [11 empty] | 18966.04 | 18966.04
|  |  | PROCUREMENT TDBU | 7494.54 | 12975.91 | 6424.11 |  | 21935.33 | [5 empty] | 15754.47 | 8603.18 | 73187.54
|  |  | TDBU Vehicle Cost | 5971.87 | 8344.57 | [10 empty] | 14316.44
|  |  | TRTP 4 Antelope Whirlwind 500 kV-T&D | 53139.84 | 1559224.37 | 887562.76 | 1127824.16 | 205836.81 | 116578.9 | 817451.38 | 569150.33 |  | 82051.38 | 172155.11 | 185965.63 | 5776940.67
|  |  | Work Package #1 | 12924.57 | 17452.27 | 12907.36 | 17652.02 | 9257.23 | 22319.15 | 5354.88 | 13240.82 | 5548.4 | 11436.21 | 52841.15 | 7889.21 | 188823.27
|  | Chargeback Total |  | -3971.39 | 1606868.85 | 920811.71 | 1164977.61 | -1389134.98 | -1293625.41 | 841626.23 | 502323.49 | 145840.61 | -135185.3 | -1069287.97 | 228995.39 | 1520238.84
| Chargebacks Total |  |  | -3971.39 | 1606868.85 | 920811.71 | 1164977.61 | -1389134.98 | -1293625.41 | 841626.23 | 502323.49 | 145840.61 | -135185.3 | -1069287.97 | 228995.39 | 1520238.84
| Labor - Other | Labor | Division Overhead | 54062.84 | 170107.69 | 31456.47 | 5971.13 | 144926.26 | 27480.48 | 14709.71 |  |  | 37538.2 | 20289.85 | 13817.22 | 520359.85
|  |  | Labor Entries <$5,000 | 11632.97 | 10143.62 | 8740.27 | 8810.11 | 1220.75 | 5000.2 | 8901.64 | 6082.52 | -3911.12 | 5881.88 | 5994.43 | 5483.87 | 73981.14
|  |  | Paid Absence | [9 empty] | 12049.59 |  |  | 12049.59
|  | Labor Total |  | 65695.81 | 180251.31 | 40196.74 | 14781.24 | 146147.01 | 32480.68 | 23611.35 | 6082.52 | -3911.12 | 55469.67 | 26284.28 | 19301.09 | 606390.58
| Labor - Other Total |  |  | 65695.81 | 180251.31 | 40196.74 | 14781.24 | 146147.01 | 32480.68 | 23611.35 | 6082.52 | -3911.12 | 55469.67 | 26284.28 | 19301.09 | 606390.58
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -15147.37 | 15147.37 |  |  | 0
|  | Overhead Total | [9 empty] | -15147.37 | 15147.37 |  |  | 0
| Overhead Correction Total | [10 empty] | -15147.37 | 15147.37 |  |  | 0
4. Allocated Total |  |  |  | 61724.42 | 1787120.16 | 961008.45 | 1179758.85 | -1242987.97 | -1261144.73 | 865237.58 | 508406.01 | 126782.12 | -64568.26 | -1043003.69 | 248296.48 | 2126629.42
5. Corporate Overhead | Non Budget - Other | Non Budgeted | AFUDC - Debt/Equity |  |  | 378040.92 | -378040.92 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 81749.97 | 111228.18 | 70680.76 | 56564.78 | 174564.34 | -20104.94 | 50294.98 | 18598.38 | 45400.61 | 3796.98 | 35833.48 | 44685.11 | 673292.63
|  |  | Capitalized Overhead - Inj & Damages | 347.84 | 3009.94 | 1117.31 | 862.47 | -12784.2 | -1794.31 | 796.53 | 767.98 | 603.14 | -2038.27 | -2003.63 | 197.09 | -10918.11
|  |  | Capitalized Overhead - P&B/Payroll Tax | 22729.68 | 56332.55 | 35664.99 | 37472.02 | 34053.46 | 26555.04 | 20863.34 | 15026.02 | -89105.46 | 47495.66 | 27054.49 | 47711.34 | 281853.13
|  |  | Corporate Overheads Correction |  |  |  |  | -2099285.46 | [7 empty] | -2099285.46
|  | Non Budgeted Total |  | 104827.49 | 170570.67 | 485503.98 | -283141.65 | -1903451.86 | 4655.79 | 71954.85 | 34392.38 | -43101.71 | 49254.37 | 60884.34 | 92593.54 | -1155057.81
| Non Budget - Other Total |  |  | 104827.49 | 170570.67 | 485503.98 | -283141.65 | -1903451.86 | 4655.79 | 71954.85 | 34392.38 | -43101.71 | 49254.37 | 60884.34 | 92593.54 | -1155057.81
5. Corporate Overhead Total |  |  |  | 104827.49 | 170570.67 | 485503.98 | -283141.65 | -1903451.86 | 4655.79 | 71954.85 | 34392.38 | -43101.71 | 49254.37 | 60884.34 | 92593.54 | -1155057.81
Grand Total |  |  |  | 70978.41 | 3583640.92 | 2169160.11 | 2247133.72 | -257806.97 | -1125280.57 | 1040440.97 | 683295.86 | 1398688.19 | 336426.22 | -351392.23 | 2767546.99 | 12562831.62

## 800051900
Pin: 6435 | Project: TRTP Segment 4
Order: 800051900 | 800051900- 9219-2366 - TRTP Segment 4
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 143.68 | 3.19 | -0.53 |  |  |  | 1.86 |  |  |  | 0.27 |  | 148.47
|  | Contract Total |  | 143.68 | 3.19 | -0.53 |  |  |  | 1.86 |  |  |  | 0.27 |  | 148.47
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 143.68 | 3.19 | -0.53 |  |  |  | 1.86 |  |  |  | 0.27 |  | 148.47
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 489722.94 |  |  | 489722.94
|  |  | Contract Entries <$50,000 | [8 empty] | -489722.94 |  |  |  | -489722.94
|  | Contract Total | [9 empty] | -489722.94 | 489722.94 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -489722.94 | 489722.94 |  |  | 0
| HRealProp | Labor | Labor Entries <$5,000 | 3276.46 | 1123.53 | 589.97 | 806.04 | 243.13 | 693.75 | 566.54 | 986.86 | 772.87 | 671.56 | 1453.66 | 748.09 | 11932.46
|  | Labor Total |  | 3276.46 | 1123.53 | 589.97 | 806.04 | 243.13 | 693.75 | 566.54 | 986.86 | 772.87 | 671.56 | 1453.66 | 748.09 | 11932.46
| HRealProp Total |  |  | 3276.46 | 1123.53 | 589.97 | 806.04 | 243.13 | 693.75 | 566.54 | 986.86 | 772.87 | 671.56 | 1453.66 | 748.09 | 11932.46
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -93.07 | -55.37 | -23.11 |  |  |  | -0.08 | 492090.07 | -492103.38 | -3232.89 | -13.81 | -3431.64
|  | IMM Correction Total |  |  | -93.07 | -55.37 | -23.11 |  |  |  | -0.08 | 492090.07 | -492103.38 | -3232.89 | -13.81 | -3431.64
| IMM/Allocated - Correction Total |  |  |  | -93.07 | -55.37 | -23.11 |  |  |  | -0.08 | 492090.07 | -492103.38 | -3232.89 | -13.81 | -3431.64
| Information System Professional Services | Contract | Contract Entries <$50,000 |  | 6.38 | -25.52 |  |  |  | 3.19 |  |  | 9.57 | 3.19 | 12.76 | 9.57
|  | Contract Total |  |  | 6.38 | -25.52 |  |  |  | 3.19 |  |  | 9.57 | 3.19 | 12.76 | 9.57
| Information System Professional Services Total |  |  |  | 6.38 | -25.52 |  |  |  | 3.19 |  |  | 9.57 | 3.19 | 12.76 | 9.57
| Labor - Other | Labor | Labor Entries <$5,000 | 298.78 | 575.13 | 151.87 | 206.39 | 182.65 | 91.97 | -2.49 | 50.83 | -3652.02 | 4017.38 | -22.09 | 939.08 | 2837.48
|  | Labor Total |  | 298.78 | 575.13 | 151.87 | 206.39 | 182.65 | 91.97 | -2.49 | 50.83 | -3652.02 | 4017.38 | -22.09 | 939.08 | 2837.48
| Labor - Other Total |  |  | 298.78 | 575.13 | 151.87 | 206.39 | 182.65 | 91.97 | -2.49 | 50.83 | -3652.02 | 4017.38 | -22.09 | 939.08 | 2837.48
| Other | Other | Other | 9842.59 | 7850.6 | 4123.75 | 597.85 |  | 212238.21 | 753305.3 | 2017.41 | 1390 | -1290 | 2080 |  | 992155.71
|  | Other Total |  | 9842.59 | 7850.6 | 4123.75 | 597.85 |  | 212238.21 | 753305.3 | 2017.41 | 1390 | -1290 | 2080 |  | 992155.71
| Other Total |  |  | 9842.59 | 7850.6 | 4123.75 | 597.85 |  | 212238.21 | 753305.3 | 2017.41 | 1390 | -1290 | 2080 |  | 992155.71
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 4172.72 | 531.86 | [9 empty] | 214.61 | 4919.19
|  | Contract Total |  | 4172.72 | 531.86 | [9 empty] | 214.61 | 4919.19
| Temporary/Supplementary - Trade/Labor Total |  |  | 4172.72 | 531.86 | [9 empty] | 214.61 | 4919.19
1. Project Support Total |  |  |  | 17734.23 | 9997.62 | 4784.17 | 1587.17 | 425.78 | 213023.93 | 753874.4 | 3055.02 | 877.98 | 1028.07 | 282.14 | 1900.73 | 1008571.24
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 7.64 | [5 empty] | 8.85 |  |  |  | 8.97 | 8.97 | 34.43
|  | Material - Direct Purchase Total |  | 7.64 | [5 empty] | 8.85 |  |  |  | 8.97 | 8.97 | 34.43
| Transportation & Mobile Equip-DP Total |  |  | 7.64 | [5 empty] | 8.85 |  |  |  | 8.97 | 8.97 | 34.43
2. Material Total |  |  |  | 7.64 | [5 empty] | 8.85 |  |  |  | 8.97 | 8.97 | 34.43
3. Construction | HRealProp | Labor | Labor Entries <$5,000 | [10 empty] | 95.42 |  | 95.42
|  | Labor Total | [11 empty] | 95.42 |  | 95.42
| HRealProp Total | [12 empty] | 95.42 |  | 95.42
3. Construction Total | [13 empty] | 95.42 |  | 95.42
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 1046.89 | 3058.24 | 420.33 | 405.87 | -1340.34 | -13.43 | 0.08 | 13.31 | -3232.17 | 3232.89 | 13.81 | 129.07 | 3734.55
|  |  | Law-TRTP Segment 4 - CRE | 58526.83 | 59012.6 | 68390.98 | 125351.83 | 33332.76 | 102532.88 | 30715.58 | 11859.48 |  | 21029.04 | 61637.5 | 74649.89 | 647039.37
|  | Chargeback Total |  | 59573.72 | 62070.84 | 68811.31 | 125757.7 | 31992.42 | 102519.45 | 30715.66 | 11872.79 | -3232.17 | 24261.93 | 61651.31 | 74778.96 | 650773.92
| Chargebacks Total |  |  | 59573.72 | 62070.84 | 68811.31 | 125757.7 | 31992.42 | 102519.45 | 30715.66 | 11872.79 | -3232.17 | 24261.93 | 61651.31 | 74778.96 | 650773.92
| Labor - Other | Labor | Division Overhead | [9 empty] | 24688.46 |  |  | 24688.46
|  |  | Labor Entries <$5,000 | 1041.85 | 504.52 | 176.5 | 183.71 | 55.49 | 145.68 | 120.15 | 270.83 | -11240.98 | 724.52 | 440.45 | 254.38 | -7322.9
|  | Labor Total |  | 1041.85 | 504.52 | 176.5 | 183.71 | 55.49 | 145.68 | 120.15 | 270.83 | -11240.98 | 25412.98 | 440.45 | 254.38 | 17365.56
| Labor - Other Total |  |  | 1041.85 | 504.52 | 176.5 | 183.71 | 55.49 | 145.68 | 120.15 | 270.83 | -11240.98 | 25412.98 | 440.45 | 254.38 | 17365.56
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -13997.1 | -13997.1
|  | Overhead Total | [12 empty] | -13997.1 | -13997.1
| Overhead Correction Total | [13 empty] | -13997.1 | -13997.1
4. Allocated Total |  |  |  | 60615.57 | 62575.36 | 68987.81 | 125941.41 | 32047.91 | 102665.13 | 30835.81 | 12143.62 | -14473.15 | 49674.91 | 62091.76 | 61036.24 | 654142.38
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 76583.44 | 4665.42 | [6 empty] | 87052.63 | 168301.49
|  | Non Budgeted Total |  |  |  |  | 76583.44 | 4665.42 | [6 empty] | 87052.63 | 168301.49
| Non Budget - Other Total | [5 empty] | 76583.44 | 4665.42 | [6 empty] | 87052.63 | 168301.49
5. Corporate Overhead Total | [6 empty] | 76583.44 | 4665.42 | [6 empty] | 87052.63 | 168301.49
Grand Total |  |  |  | 78357.44 | 72572.98 | 73771.98 | 204112.02 | 37139.11 | 315689.06 | 784719.06 | 15198.64 | -13595.17 | 50702.98 | 62478.29 | 149998.57 | 1831144.96

## TRTP Seg 5
WO | SumOfYTD2012 | Order | Project
800433760- TRTP 4-11: LICENSING | 3026315.74 | 800433760 | TRTP Segment 5
800217232- TRTP: ANTELOPE-VINCENT #2 500KV: CONSTRU | 51695244.75 | 800217232 | TRTP Segment 5
800217225- I: TRTP 5-2: ANTELOPE-VINCENT-WINDHUB: R | -619089.92 | 800217225 | TRTP Segment 5
800062539- TRTP 4-11 & 3C: ANTELOPE-VINCENT #2 500K | 999893.83 | 800062539 | TRTP Segment 5
800051902- 9219-2369 - TRTP Segment 5 | 103846.19 | 800051902 | TRTP Segment 5

## 800433760
Pin: 5472 | Project: TRTP Segment 5
Order: 800433760 | 800433760- TRTP 4-11: LICENSING
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 919586.04 |  |  | 919586.04
|  |  | Contract Entries <$50,000 | [8 empty] | -919586.04 |  |  |  | -919586.04
|  | Contract Total | [9 empty] | -919586.04 | 919586.04 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -919586.04 | 919586.04 |  |  | 0
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 923071.94 | -923071.94 | -6069.27 |  | -6069.27
|  | IMM Correction Total | [9 empty] | 923071.94 | -923071.94 | -6069.27 |  | -6069.27
| IMM/Allocated - Correction Total | [10 empty] | 923071.94 | -923071.94 | -6069.27 |  | -6069.27
| Other | Other | Other | 98714.56 | 147.65 | 164073.98 | 7361.9 | 104900.8 | 177318.07 |  |  | 241649.92 | 127330.95 | 91689.93 |  | 1013187.76
|  | Other Total |  | 98714.56 | 147.65 | 164073.98 | 7361.9 | 104900.8 | 177318.07 |  |  | 241649.92 | 127330.95 | 91689.93 |  | 1013187.76
| Other Total |  |  | 98714.56 | 147.65 | 164073.98 | 7361.9 | 104900.8 | 177318.07 |  |  | 241649.92 | 127330.95 | 91689.93 |  | 1013187.76
1. Project Support Total |  |  |  | 98714.56 | 147.65 | 164073.98 | 7361.9 | 104900.8 | 177318.07 |  |  | 245135.82 | 123845.05 | 85620.66 |  | 1007118.49
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 2818.11 | 4033.13 | 9975.51 | -322.04 | 18698.48 | -6019.48 | 8582.63 | 5016.26 | -1983.08 | 7628.75 | 421.6 |  | 48849.87
|  |  | Law-Antelope-Vincent #2 500KV T/L: Licen | 8288 | 134330.22 | 296246.39 | 118584.35 | 26461.71 | 249970.32 | 75209.05 | 10496 |  | 20768 | 63427.03 | 605437.39 | 1609218.46
|  |  | TRTP STRUCTURES NEAR CHINO AIRPORT |  | 17043.93 | 10172.73 | 17337.12 | 6663.19 | 16615 | [6 empty] | 67831.97
|  | Chargeback Total |  | 11106.11 | 155407.28 | 316394.63 | 135599.43 | 51823.38 | 260565.84 | 83791.68 | 15512.26 | -1983.08 | 28396.75 | 63848.63 | 605437.39 | 1725900.3
| Chargebacks Total |  |  | 11106.11 | 155407.28 | 316394.63 | 135599.43 | 51823.38 | 260565.84 | 83791.68 | 15512.26 | -1983.08 | 28396.75 | 63848.63 | 605437.39 | 1725900.3
| Labor - Other | Labor | Division Overhead | [9 empty] | 15632.96 |  |  | 15632.96
|  |  | Labor Entries <$5,000 |  | 5.45 |  | 2.76 |  |  |  |  | -29242.84 | 32093.56 |  |  | 2858.93
|  | Labor Total |  |  | 5.45 |  | 2.76 |  |  |  |  | -29242.84 | 47726.52 |  |  | 18491.89
| Labor - Other Total |  |  |  | 5.45 |  | 2.76 |  |  |  |  | -29242.84 | 47726.52 |  |  | 18491.89
4. Allocated Total |  |  |  | 11106.11 | 155412.73 | 316394.63 | 135602.19 | 51823.38 | 260565.84 | 83791.68 | 15512.26 | -31225.92 | 76123.27 | 63848.63 | 605437.39 | 1744392.19
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 46387.41 | 2882.02 | [6 empty] | 59590.4 | 108859.83
|  |  | Capitalized Overhead - A&G | 10743.89 | 4557.33 | 17126.14 | 5098.18 | 13044.07 | 15628.2 | 2942.17 | 438.77 | 9582.91 | 5166.54 | 3950.06 | 16998.49 | 105276.75
|  |  | Capitalized Overhead - Inj & Damages | 172.3 | 26.3 | 194.37 | 14.45 | 1162.61 | 221.1 | 4.14 | 3.54 | 1022.54 | -2351.69 | 141.5 | 225.18 | 836.34
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1456.48 | 12780.95 | 10430.59 | 13341.26 | 10176.59 | 5526.35 | 5854.82 | 245.33 |  | 19.77 |  |  | 59832.14
|  | Non Budgeted Total |  | 12372.67 | 17364.58 | 27751.1 | 64841.3 | 27265.29 | 21375.65 | 8801.13 | 687.64 | 10605.45 | 2834.62 | 4091.56 | 76814.07 | 274805.06
| Non Budget - Other Total |  |  | 12372.67 | 17364.58 | 27751.1 | 64841.3 | 27265.29 | 21375.65 | 8801.13 | 687.64 | 10605.45 | 2834.62 | 4091.56 | 76814.07 | 274805.06
5. Corporate Overhead Total |  |  |  | 12372.67 | 17364.58 | 27751.1 | 64841.3 | 27265.29 | 21375.65 | 8801.13 | 687.64 | 10605.45 | 2834.62 | 4091.56 | 76814.07 | 274805.06
Grand Total |  |  |  | 122193.34 | 172924.96 | 508219.71 | 207805.39 | 183989.47 | 459259.56 | 92592.81 | 16199.9 | 224515.35 | 202802.94 | 153560.85 | 682251.46 | 3026315.74

## 800217232
Pin: 5472 | Project: TRTP Segment 5
Order: 800217232 | 800217232- TRTP: ANTELOPE-VINCENT #2 500KV: CONSTRU
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 90.35 | [6 empty] | 90.35
|  | Labor Total | [6 empty] | 90.35 | [6 empty] | 90.35
| BP&FM Total | [7 empty] | 90.35 | [6 empty] | 90.35
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  | 1998 | [6 empty] | 80 |  |  |  | 2078
|  | Contract Total |  |  | 1998 | [6 empty] | 80 |  |  |  | 2078
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  | 1998 | [6 empty] | 80 |  |  |  | 2078
| Consultants - Engineering/Technical | Contract | Consultants - Engineering/Technical |  |  |  | 160459.15 | [8 empty] | 160459.15
|  |  | Contract Entries <$50,000 | [5 empty] | -160459.15 | [6 empty] | -160459.15
|  | Contract Total |  |  |  |  | 160459.15 |  | -160459.15 | [6 empty] | 0
| Consultants - Engineering/Technical Total | [5 empty] | 160459.15 |  | -160459.15 | [6 empty] | 0
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 1323570.47 |  |  | 1323570.47
|  |  | Contract Entries <$50,000 | [8 empty] | -1323570.47 |  |  |  | -1323570.47
|  | Contract Total | [9 empty] | -1323570.47 | 1323570.47 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -1323570.47 | 1323570.47 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 8065.88 | 8065.88
|  | Labor Total | [12 empty] | 8065.88 | 8065.88
| ELEC SYS PLANNING Total | [13 empty] | 8065.88 | 8065.88
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 434.63 |  |  |  |  | 351.72 |  |  |  | 348.98 |  | 1135.33
|  | Labor Total |  |  | 434.63 |  |  |  |  | 351.72 |  |  |  | 348.98 |  | 1135.33
| ENG ADVANCEMENT Total |  |  |  | 434.63 |  |  |  |  | 351.72 |  |  |  | 348.98 |  | 1135.33
| ENGINEERING | Labor | Engineer | [5 empty] | 5421.65 |  | 6021.16 |  |  |  |  | 11442.81
|  |  | Labor Entries <$5,000 | 7861.52 | 12674.06 | 14484.72 | 8226.17 | 8556.16 | 8860.47 | 10068.65 | 7172.93 | 9456.52 | 7221.87 | 6457.42 | 715.26 | 101755.75
|  | Labor Total |  | 7861.52 | 12674.06 | 14484.72 | 8226.17 | 8556.16 | 14282.12 | 10068.65 | 13194.09 | 9456.52 | 7221.87 | 6457.42 | 715.26 | 113198.56
| ENGINEERING Total |  |  | 7861.52 | 12674.06 | 14484.72 | 8226.17 | 8556.16 | 14282.12 | 10068.65 | 13194.09 | 9456.52 | 7221.87 | 6457.42 | 715.26 | 113198.56
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | 1023813 | 401654.42 | 458410 | 480589 | 538363 |  | 829523.29 | 211394 | 226672 | 227158 | 392683 | 684105.01 | 5474364.72
|  |  | Contract Entries <$50,000 | 32974.45 | 14721.17 | 50738.85 | 13506.48 | 13557.67 | -293432.25 | 12307.53 | 1087.18 | 5955.4 | 54981.5 | -200681.56 | 28390.02 | -265893.56
|  |  | Engineering/Technical Professional Servi |  |  | 98700.27 | 303328.06 | [8 empty] | 402028.33
|  | Contract Total |  | 1056787.45 | 416375.59 | 607849.12 | 797423.54 | 551920.67 | -293432.25 | 841830.82 | 212481.18 | 232627.4 | 282139.5 | 192001.44 | 712495.03 | 5610499.49
| Engineering/Technical Professional Servi Total |  |  | 1056787.45 | 416375.59 | 607849.12 | 797423.54 | 551920.67 | -293432.25 | 841830.82 | 212481.18 | 232627.4 | 282139.5 | 192001.44 | 712495.03 | 5610499.49
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 13233.28 | 6029.64 | 3892.7 | 2810.17 | 5825.5 | 2960.25 | 3963 | 5577.7 | 3377.36 | 11905.8 |  | 59575.4
|  |  | SHAW ENVIRONMENTAL INC. | [11 empty] | 100415.27 | 100415.27
|  | Contract Total |  |  | 13233.28 | 6029.64 | 3892.7 | 2810.17 | 5825.5 | 2960.25 | 3963 | 5577.7 | 3377.36 | 11905.8 | 100415.27 | 159990.67
| Environmental/Safety Professional Servic Total |  |  |  | 13233.28 | 6029.64 | 3892.7 | 2810.17 | 5825.5 | 2960.25 | 3963 | 5577.7 | 3377.36 | 11905.8 | 100415.27 | 159990.67
| FIELDCONSTNORTHCOAST | Labor | Labor Entries <$5,000 |  | 260.46 | [10 empty] | 260.46
|  | Labor Total |  |  | 260.46 | [10 empty] | 260.46
| FIELDCONSTNORTHCOAST Total |  |  |  | 260.46 | [10 empty] | 260.46
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 11376.85 | -17711.87 | -23254.29 | -8454.83 | 4576.45 | -18372.79 | 5717.44 | 2332.09 | 1340838.58 | -1375810.38 | -22037.17 | -38695.94 | -139495.86
|  | IMM Correction Total |  | 11376.85 | -17711.87 | -23254.29 | -8454.83 | 4576.45 | -18372.79 | 5717.44 | 2332.09 | 1340838.58 | -1375810.38 | -22037.17 | -38695.94 | -139495.86
| IMM/Allocated - Correction Total |  |  | 11376.85 | -17711.87 | -23254.29 | -8454.83 | 4576.45 | -18372.79 | 5717.44 | 2332.09 | 1340838.58 | -1375810.38 | -22037.17 | -38695.94 | -139495.86
| Labor - Other | Labor | Labor - Other | [9 empty] | 12483.29 |  |  | 12483.29
|  |  | Labor Correction | [9 empty] | 62106.25 |  |  | 62106.25
|  |  | Labor Entries <$5,000 | 360.45 | 3130.43 | -3192.66 | 59.25 | 1105.37 | -2149.2 | 1809.29 | 542.91 | -70819.95 | 5250.26 | -3969.73 | 3675.29 | -64198.29
|  |  | SUR-TRTP SEG 5 | [8 empty] | 9616.1 | 5016.24 |  |  | 14632.34
|  | Labor Total |  | 360.45 | 3130.43 | -3192.66 | 59.25 | 1105.37 | -2149.2 | 1809.29 | 542.91 | -61203.85 | 84856.04 | -3969.73 | 3675.29 | 25023.59
| Labor - Other Total |  |  | 360.45 | 3130.43 | -3192.66 | 59.25 | 1105.37 | -2149.2 | 1809.29 | 542.91 | -61203.85 | 84856.04 | -3969.73 | 3675.29 | 25023.59
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  | 122.17 | 731.2 | [5 empty] | 74.01 | 149.39 | 2004.65 | 725.31 | 3806.73
|  | Labor Total |  |  | 122.17 | 731.2 | [5 empty] | 74.01 | 149.39 | 2004.65 | 725.31 | 3806.73
| NORTH GRIDMGMTCENTER Total |  |  |  | 122.17 | 731.2 | [5 empty] | 74.01 | 149.39 | 2004.65 | 725.31 | 3806.73
| Other | Other | Other | -236775.32 | 1340021.34 | 1666048.25 | 3814391.25 | -2948156.23 | -4217375.13 | -361282.9 | 82673.04 | 167897.63 | 1311722.64 | -525959.78 | 2488201.95 | 2581406.74
|  | Other Total |  | -236775.32 | 1340021.34 | 1666048.25 | 3814391.25 | -2948156.23 | -4217375.13 | -361282.9 | 82673.04 | 167897.63 | 1311722.64 | -525959.78 | 2488201.95 | 2581406.74
| Other Total |  |  | -236775.32 | 1340021.34 | 1666048.25 | 3814391.25 | -2948156.23 | -4217375.13 | -361282.9 | 82673.04 | 167897.63 | 1311722.64 | -525959.78 | 2488201.95 | 2581406.74
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -51955.24 |  |  |  | -51955.24
|  |  | Temporary / Supplemental - Correction | [9 empty] | 51955.24 |  |  | 51955.24
|  | Contract Total | [9 empty] | -51955.24 | 51955.24 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -51955.24 | 51955.24 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 |  | 1761.9 | 4783.85 | 1069.63 | 2640 | 2606.21 | [6 empty] | 12861.59
|  | Contract Total |  |  | 1761.9 | 4783.85 | 1069.63 | 2640 | 2606.21 | [6 empty] | 12861.59
| Temporary/Supplementary - Technical/Prof Total |  |  |  | 1761.9 | 4783.85 | 1069.63 | 2640 | 2606.21 | [6 empty] | 12861.59
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 430.76 | 335.17 | 670.34 | 13657.75 |  | 14986.08 | 1188.37 | 2090.08 | 1356.49 | 406.08 |  | 901.45 | 36022.57
|  | Contract Total |  | 430.76 | 335.17 | 670.34 | 13657.75 |  | 14986.08 | 1188.37 | 2090.08 | 1356.49 | 406.08 |  | 901.45 | 36022.57
| Temporary/Supplementary - Trade/Labor Total |  |  | 430.76 | 335.17 | 670.34 | 13657.75 |  | 14986.08 | 1188.37 | 2090.08 | 1356.49 | 406.08 |  | 901.45 | 36022.57
| TRANSMISSION | Labor | Labor Entries <$5,000 | 253.97 | 1569.61 | 679.57 |  |  |  |  | 385.46 | 215.84 | 8859.51 | 7142.25 | 19228.35 | 38334.56
|  |  | TRANSMISSION / Lineman Rbr Trn | [9 empty] | 10112.42 | 14568.13 | 14392.64 | 39073.19
|  | Labor Total |  | 253.97 | 1569.61 | 679.57 |  |  |  |  | 385.46 | 215.84 | 18971.93 | 21710.38 | 33620.99 | 77407.75
| TRANSMISSION Total |  |  | 253.97 | 1569.61 | 679.57 |  |  |  |  | 385.46 | 215.84 | 18971.93 | 21710.38 | 33620.99 | 77407.75
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 9575.22 | -184.73 | 9464.24 | 3538.07 | 1367.22 | 3609.37 | 822.75 | 2105.81 | 1571.86 | 11852.21 | 9800.64 |  | 53522.66
|  |  | Mgr-Prj/Prod |  | 30074.64 | [8 empty] | 6273.48 |  | 36348.12
|  | Labor Total |  | 9575.22 | 29889.91 | 9464.24 | 3538.07 | 1367.22 | 3609.37 | 822.75 | 2105.81 | 1571.86 | 11852.21 | 16074.12 |  | 89870.78
| TRNS CAPITAL Total |  |  | 9575.22 | 29889.91 | 9464.24 | 3538.07 | 1367.22 | 3609.37 | 822.75 | 2105.81 | 1571.86 | 11852.21 | 16074.12 |  | 89870.78
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 |  | 3862.8 | 686 | 1065.6 | [8 empty] | 5614.4
|  | Labor Total |  |  | 3862.8 | 686 | 1065.6 | [8 empty] | 5614.4
| TSD-Aircraft - Fixed Total |  |  |  | 3862.8 | 686 | 1065.6 | [8 empty] | 5614.4
1. Project Support Total |  |  |  | 849870.9 | 1807957.48 | 2284979.98 | 4795328.28 | -2375180.19 | -4650388.89 | 503466.39 | 319767.66 | 322966.47 | 1720412.35 | -301463.89 | 3310120.49 | 8587837.03
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -120.39 | 120.39 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -120.39 | 120.39 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -120.39 | 120.39 |  |  | 0
| Material - Inventory | Material | Material - Inventory | [8 empty] | -13.82 | 13.82 |  |  | 0
|  | Material Total | [9 empty] | -13.82 | 13.82 |  |  | 0
| Material - Inventory Total | [10 empty] | -13.82 | 13.82 |  |  | 0
| Material - Other | Material | Material - Other | 6284.48 | 8887.34 | 13097.78 | 0.03 | -1011.59 | 2760.15 | 10.72 | 74.72 | 1022.39 | 1827.85 | 688.9 | -94.08 | 33548.69
|  | Material Total |  | 6284.48 | 8887.34 | 13097.78 | 0.03 | -1011.59 | 2760.15 | 10.72 | 74.72 | 1022.39 | 1827.85 | 688.9 | -94.08 | 33548.69
| Material - Other Total |  |  | 6284.48 | 8887.34 | 13097.78 | 0.03 | -1011.59 | 2760.15 | 10.72 | 74.72 | 1022.39 | 1827.85 | 688.9 | -94.08 | 33548.69
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | AGILE SOURCING PARTNERS INC |  | 77140 | 22591 | [9 empty] | 99731
|  |  | Material Entries <$5,000 | [6 empty] | 98.62 | 683.34 |  |  |  |  | 781.96
|  |  | ONE SOURCE DISTRIBUTORS INC | 55130.12 |  |  |  |  | 5000 | [6 empty] | 60130.12
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC |  |  |  |  | 19131.75 | [7 empty] | 19131.75
|  | Material - Direct Purchase Total |  | 55130.12 | 77140 | 22591 |  | 19131.75 | 5000 | 98.62 | 683.34 |  |  |  |  | 179774.83
| Pole Line Hdwe & Connectors-DP Total |  |  | 55130.12 | 77140 | 22591 |  | 19131.75 | 5000 | 98.62 | 683.34 |  |  |  |  | 179774.83
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 3072.35 | [9 empty] | 3072.35
|  |  | ON-RAMP WIRELESS, INC. |  |  | 91105 | [6 empty] | 15046.76 |  |  | 106151.76
|  | Material - Direct Purchase Total |  |  |  | 94177.35 | [6 empty] | 15046.76 |  |  | 109224.11
| Power Systems, Batteries and Light-DP Total |  |  |  |  | 94177.35 | [6 empty] | 15046.76 |  |  | 109224.11
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | [5 empty] | 20200 |  |  | 7030 |  |  |  | 27230
|  |  | Material Entries <$5,000 | [8 empty] | 600 |  | 600 |  | 1200
|  |  | Steel / Fabricated / Structural-DP | [10 empty] | 7200 |  | 7200
|  | Material - Direct Purchase Total | [6 empty] | 20200 |  |  | 7630 |  | 7800 |  | 35630
| Steel / Fabricated / Structural-DP Total | [7 empty] | 20200 |  |  | 7630 |  | 7800 |  | 35630
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | -0.92 | [8 empty] | -0.92
|  | Material - Direct Purchase Total |  |  |  |  | -0.92 | [8 empty] | -0.92
| Steel Lattice Towers (T/S)-DP Total | [5 empty] | -0.92 | [8 empty] | -0.92
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 141.91 |  | 377.82 | [7 empty] | 442.85 |  | 962.58
|  | Material - Direct Purchase Total |  | 141.91 |  | 377.82 | [7 empty] | 442.85 |  | 962.58
| Transportation & Mobile Equip-DP Total |  |  | 141.91 |  | 377.82 | [7 empty] | 442.85 |  | 962.58
2. Material Total |  |  |  | 61556.51 | 86027.34 | 130243.95 | -0.89 | 18120.16 | 27960.15 | 109.34 | 758.06 | 8518.18 | 17008.82 | 8931.75 | -94.08 | 359139.29
3. Construction | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [6 empty] | 3000 |  |  |  |  | 73.9 | 3073.9
|  | Contract Total | [7 empty] | 3000 |  |  |  |  | 73.9 | 3073.9
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [8 empty] | 3000 |  |  |  |  | 73.9 | 3073.9
| Construction Management Services | Contract | Contract Entries <$50,000 | 15693.67 | 63020.75 | 45318.33 | 53541.05 | 6234.44 | 2875.22 | 413.46 | 1015.72 | 901.6 | 2769.2 |  | 46234.56 | 238018
|  |  | UTILITY LINE MANAGEMENT SERVICES | [11 empty] | 54010.7 | 54010.7
|  | Contract Total |  | 15693.67 | 63020.75 | 45318.33 | 53541.05 | 6234.44 | 2875.22 | 413.46 | 1015.72 | 901.6 | 2769.2 |  | 100245.26 | 292028.7
| Construction Management Services Total |  |  | 15693.67 | 63020.75 | 45318.33 | 53541.05 | 6234.44 | 2875.22 | 413.46 | 1015.72 | 901.6 | 2769.2 |  | 100245.26 | 292028.7
| Construction Services - Other | Contract | Construction Services - Other | [7 empty] | 966656.61 | 1548140.34 | 1659580.64 |  |  | 4174377.59
|  |  | Contract Entries <$50,000 | 1043.14 | 41.5 | 866.28 | 320 | 44690.14 | 103.75 | 558.55 | [5 empty] | 47623.36
|  |  | RJ ALLEN INC | [11 empty] | 223236.1 | 223236.1
|  | Contract Total |  | 1043.14 | 41.5 | 866.28 | 320 | 44690.14 | 103.75 | 558.55 | 966656.61 | 1548140.34 | 1659580.64 |  | 223236.1 | 4445237.05
| Construction Services - Other Total |  |  | 1043.14 | 41.5 | 866.28 | 320 | 44690.14 | 103.75 | 558.55 | 966656.61 | 1548140.34 | 1659580.64 |  | 223236.1 | 4445237.05
| Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 | [11 empty] | 0 | 0
|  |  | HENKELS & MC COY INC | 2910872.97 | 4675233.98 | 2222136.73 |  | 3830538.24 | 830652.84 |  |  | 5945506.02 |  | 3154657.84 |  | 23569598.62
|  |  | WILSON UTILITY CONSTRUCTION | [10 empty] | 2496138.51 | 2186389.88 | 4682528.39
|  | Contract Total |  | 2910872.97 | 4675233.98 | 2222136.73 |  | 3830538.24 | 830652.84 |  |  | 5945506.02 |  | 5650796.35 | 2186389.88 | 28252127.01
| Electrical Construction, Transmission Li Total |  |  | 2910872.97 | 4675233.98 | 2222136.73 |  | 3830538.24 | 830652.84 |  |  | 5945506.02 |  | 5650796.35 | 2186389.88 | 28252127.01
| FIELDCONSTNORTHCOAST | Labor | Labor Entries <$5,000 |  | 456.67 | [10 empty] | 456.67
|  | Labor Total |  |  | 456.67 | [10 empty] | 456.67
| FIELDCONSTNORTHCOAST Total |  |  |  | 456.67 | [10 empty] | 456.67
| GRID OPS | Labor | Labor Entries <$5,000 |  | 224.19 |  |  |  |  | 292.45 | 1327.18 | 302.1 | 848.67 | 130.24 | 9005.38 | 12130.21
|  | Labor Total |  |  | 224.19 |  |  |  |  | 292.45 | 1327.18 | 302.1 | 848.67 | 130.24 | 9005.38 | 12130.21
| GRID OPS Total |  |  |  | 224.19 |  |  |  |  | 292.45 | 1327.18 | 302.1 | 848.67 | 130.24 | 9005.38 | 12130.21
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | [5 empty] | 39558.69 |  | 0 |  |  |  |  | 39558.69
|  | Contract Total | [6 empty] | 39558.69 |  | 0 |  |  |  |  | 39558.69
| Hauling / Industrial Moving Services Total | [7 empty] | 39558.69 |  | 0 |  |  |  |  | 39558.69
| Labor - Other | Labor | ACQ/TRTP Seg. 5-Const./Antelope-Vincent |  |  |  | 5236.76 | [8 empty] | 5236.76
|  |  | Labor Entries <$5,000 | 3439.88 | 4524.75 | 4498.45 | 1745.3 | 4402.46 | 4928.02 | 4850.19 | 5076.8 | -24283.34 | 34095.33 | 2320.6 | 2930.82 | 48529.26
|  | Labor Total |  | 3439.88 | 4524.75 | 4498.45 | 6982.06 | 4402.46 | 4928.02 | 4850.19 | 5076.8 | -24283.34 | 34095.33 | 2320.6 | 2930.82 | 53766.02
| Labor - Other Total |  |  | 3439.88 | 4524.75 | 4498.45 | 6982.06 | 4402.46 | 4928.02 | 4850.19 | 5076.8 | -24283.34 | 34095.33 | 2320.6 | 2930.82 | 53766.02
| Material - Other | Material | Material - Other | [7 empty] | 14.26 | 12.16 | 85.13 |  | 26.43 | 137.98
|  | Material Total | [8 empty] | 14.26 | 12.16 | 85.13 |  | 26.43 | 137.98
| Material - Other Total | [9 empty] | 14.26 | 12.16 | 85.13 |  | 26.43 | 137.98
| Other | Other | Other | [5 empty] | 15.54 | 19.84 |  |  |  | 1408 |  | 1443.38
|  | Other Total | [6 empty] | 15.54 | 19.84 |  |  |  | 1408 |  | 1443.38
| Other Total | [7 empty] | 15.54 | 19.84 |  |  |  | 1408 |  | 1443.38
| SC&M | Labor | Labor Entries <$5,000 | [11 empty] | 3278.87 | 3278.87
|  | Labor Total | [12 empty] | 3278.87 | 3278.87
| SC&M Total | [13 empty] | 3278.87 | 3278.87
| TRANSMISSION | Labor | Labor Entries <$5,000 |  | 3799.41 | 3725.55 |  |  | 667.66 |  | 1958.02 | 774.03 | 12077.63 | 9045.42 | 7763.32 | 39811.04
|  |  | TRANSMISSION / Patroman Sr | [9 empty] | 10960.8 | 17944.99 | 20660.65 | 49566.44
|  | Labor Total |  |  | 3799.41 | 3725.55 |  |  | 667.66 |  | 1958.02 | 774.03 | 23038.43 | 26990.41 | 28423.97 | 89377.48
| TRANSMISSION Total |  |  |  | 3799.41 | 3725.55 |  |  | 667.66 |  | 1958.02 | 774.03 | 23038.43 | 26990.41 | 28423.97 | 89377.48
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | [6 empty] | 1308.37 | [5 empty] | 1308.37
|  | Labor Total | [7 empty] | 1308.37 | [5 empty] | 1308.37
| TRNS CAPITAL Total | [8 empty] | 1308.37 | [5 empty] | 1308.37
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | [5 empty] | 82 | [6 empty] | 82
|  | Labor Total | [6 empty] | 82 | [6 empty] | 82
| TSD-HERC - Crane Svs Total | [7 empty] | 82 | [6 empty] | 82
3. Construction Total |  |  |  | 2931049.66 | 4747301.25 | 2276545.34 | 60843.11 | 3885865.28 | 878883.72 | 10442.86 | 976048.59 | 7471352.91 | 1720417.4 | 5681645.6 | 2553610.61 | 33194006.33
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -146876.41 | 19014.4 | 18715.22 | 11539.43 | 19330.23 | 18775.89 | 27875.29 | 10068.69 | 21880.47 | 10874.65 | 26622.22 | 129721.38 | 167541.46
|  |  | PROCUREMENT TDBU | 29088.72 | 34631.14 | 19831.68 | 6800.4 | 29422.57 |  | 5590.53 | 7833.47 | 42016.22 | 22037.17 | 38695.94 | 21936.31 | 257884.15
|  |  | TDBU Vehicle Cost | [9 empty] | 7110.56 |  | 6187.02 | 13297.58
|  |  | TRTP 5 Antelope Vincent #2 500kV constru | 105010.14 | 116287.79 | 224306.94 | 205717.08 | 456425.49 | 174459.92 | 33955.59 | 128573.35 |  | 149608.91 | 278922.13 | 171893.85 | 2045161.19
|  |  | TRTP Work Package #1 |  |  |  |  | 22500 | 28275.26 | 28932.47 |  | 84356.52 | 366429.54 | 894199.02 |  | 1424692.81
|  |  | Work Package #1 | 21149.27 | 28558.26 | 28118.32 | 34857.53 | 22973.79 | 36522.25 | 38341.13 | 36412.28 | 33310.78 | 31449.56 | 155984.43 | 50010.39 | 517687.99
|  | Chargeback Total |  | 8371.72 | 198491.59 | 290972.16 | 258914.44 | 550652.08 | 258033.32 | 134695.01 | 182887.79 | 181563.99 | 587510.39 | 1394423.74 | 379748.95 | 4426265.18
| Chargebacks Total |  |  | 8371.72 | 198491.59 | 290972.16 | 258914.44 | 550652.08 | 258033.32 | 134695.01 | 182887.79 | 181563.99 | 587510.39 | 1394423.74 | 379748.95 | 4426265.18
| Labor - Other | Labor | Division Overhead | 112323.77 | 193993.08 | 109451.51 | 31596.36 | 194418.17 | 18448.38 | 30514.28 | 48697.42 | 202445.54 | 173330.04 | 59280.42 | 40887.78 | 1215386.75
|  |  | Labor Entries <$5,000 | 3867.41 | 3735.36 | 5489.83 | 4198.77 | 2848.34 | 6964.85 | 8241.72 | 5092.85 | -12786.59 | 14227.92 | 11285.97 | 8092.12 | 61258.55
|  |  | Paid Absence |  | 6781.65 | [7 empty] | 17460.2 |  | 7391.52 | 31633.37
|  |  | TOOL EXPENSE | [11 empty] | 5079.76 | 5079.76
|  | Labor Total |  | 116191.18 | 204510.09 | 114941.34 | 35795.13 | 197266.51 | 25413.23 | 38756 | 53790.27 | 189658.95 | 205018.16 | 70566.39 | 61451.18 | 1313358.43
| Labor - Other Total |  |  | 116191.18 | 204510.09 | 114941.34 | 35795.13 | 197266.51 | 25413.23 | 38756 | 53790.27 | 189658.95 | 205018.16 | 70566.39 | 61451.18 | 1313358.43
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -31595.53 | 31595.53 |  |  | 0
|  | Overhead Total | [9 empty] | -31595.53 | 31595.53 |  |  | 0
| Overhead Correction Total | [10 empty] | -31595.53 | 31595.53 |  |  | 0
4. Allocated Total |  |  |  | 124562.9 | 403001.68 | 405913.5 | 294709.57 | 747918.59 | 283446.55 | 173451.01 | 236678.06 | 339627.41 | 824124.08 | 1464990.13 | 441200.13 | 5739623.61
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 478115.67 | 30019.13 | [6 empty] | 663607.34 | 1171742.14
|  |  | Capitalized Overhead - A&G | 234631.04 | 167409.78 | 122394.61 | 47738.35 | 434961.21 | 27123.96 | 36844.73 | 41054.2 | 363650.68 | 73159.66 | 195203.91 | 107172.1 | 1851344.23
|  |  | Capitalized Overhead - Inj & Damages | 105.06 | 720.46 | 328.32 | 77.65 | 2785.07 | 123.82 | 101.38 | 158.89 | 1499.6 | -3147.72 | 481.38 | 338.1 | 3572.01
|  |  | Capitalized Overhead - P&B/Payroll Tax | 27055.32 | 86449.81 | 48657.33 | 57045.91 | 55689.1 | 51811.62 | 46710.11 | 40794.62 | -42787.67 | 81180.5 | 100774.89 | 234598.57 | 787980.11
|  | Non Budgeted Total |  | 261791.42 | 254580.05 | 171380.26 | 582977.58 | 523454.51 | 79059.4 | 83656.22 | 82007.71 | 322362.61 | 151192.44 | 296460.18 | 1005716.11 | 3814638.49
| Non Budget - Other Total |  |  | 261791.42 | 254580.05 | 171380.26 | 582977.58 | 523454.51 | 79059.4 | 83656.22 | 82007.71 | 322362.61 | 151192.44 | 296460.18 | 1005716.11 | 3814638.49
5. Corporate Overhead Total |  |  |  | 261791.42 | 254580.05 | 171380.26 | 582977.58 | 523454.51 | 79059.4 | 83656.22 | 82007.71 | 322362.61 | 151192.44 | 296460.18 | 1005716.11 | 3814638.49
Grand Total |  |  |  | 4228831.39 | 7298867.8 | 5269063.03 | 5733857.65 | 2800178.35 | -3381039.07 | 771125.82 | 1615260.08 | 8464827.58 | 4433155.09 | 7150563.77 | 7310553.26 | 51695244.75

## 800217225
Pin: 5472 | Project: TRTP Segment 5
Order: 800217225 | 800217225- I: TRTP 5-2: ANTELOPE-VINCENT-WINDHUB: R
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 480.48 | 480.48
|  | Labor Total | [12 empty] | 480.48 | 480.48
| ELEC SYS PLANNING Total | [13 empty] | 480.48 | 480.48
| ENGINEERING | Labor | Labor Entries <$5,000 | 1888.22 | 2917.31 | 1230.74 | 1007.96 | 193.74 | 309.99 |  | 309.98 | 428.38 | 417.4 | 545.64 |  | 9249.36
|  | Labor Total |  | 1888.22 | 2917.31 | 1230.74 | 1007.96 | 193.74 | 309.99 |  | 309.98 | 428.38 | 417.4 | 545.64 |  | 9249.36
| ENGINEERING Total |  |  | 1888.22 | 2917.31 | 1230.74 | 1007.96 | 193.74 | 309.99 |  | 309.98 | 428.38 | 417.4 | 545.64 |  | 9249.36
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  | -226.93 |  |  | -2793.9 | [5 empty] | -2230.9 | -5251.73
|  | IMM Correction Total |  |  |  | -226.93 |  |  | -2793.9 | [5 empty] | -2230.9 | -5251.73
| IMM/Allocated - Correction Total |  |  |  |  | -226.93 |  |  | -2793.9 | [5 empty] | -2230.9 | -5251.73
| Labor - Other | Labor | Labor Entries <$5,000 | -17.53 | 328.12 | -216.93 | -55.65 | -38.01 |  |  | 5.02 | -5.02 | 75.1 | -103.84 | 28.74 | 6.0396e-14
|  | Labor Total |  | -17.53 | 328.12 | -216.93 | -55.65 | -38.01 |  |  | 5.02 | -5.02 | 75.1 | -103.84 | 28.74 | 6.0396e-14
| Labor - Other Total |  |  | -17.53 | 328.12 | -216.93 | -55.65 | -38.01 |  |  | 5.02 | -5.02 | 75.1 | -103.84 | 28.74 | 6.0396e-14
| Other | Other | Other | 0 | 64331.72 | 74.1 | 98796.48 | -76425.79 | -98715.94 | -0.06 | 0 | 0 | 0 | -338014.94 |  | -349954.43
|  | Other Total |  | 0 | 64331.72 | 74.1 | 98796.48 | -76425.79 | -98715.94 | -0.06 | 0 | 0 | 0 | -338014.94 |  | -349954.43
| Other Total |  |  | 0 | 64331.72 | 74.1 | 98796.48 | -76425.79 | -98715.94 | -0.06 | 0 | 0 | 0 | -338014.94 |  | -349954.43
1. Project Support Total |  |  |  | 1870.69 | 67577.15 | 860.98 | 99748.79 | -76270.06 | -101199.85 | -0.06 | 315 | 423.36 | 492.5 | -337573.14 | -1721.68 | -345476.32
2. Material | Material - Other | Material | Material - Other | [6 empty] | -11.04 | -25243.83 |  | -464.15 |  | 127.74 | -25591.28
|  | Material Total | [7 empty] | -11.04 | -25243.83 |  | -464.15 |  | 127.74 | -25591.28
| Material - Other Total | [8 empty] | -11.04 | -25243.83 |  | -464.15 |  | 127.74 | -25591.28
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 1250 | 1250
|  | Material - Direct Purchase Total | [12 empty] | 1250 | 1250
| Pole Line Hdwe & Connectors-DP Total | [13 empty] | 1250 | 1250
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | -421.56 | -906239.13 |  | -11766.58 |  |  | -918427.27
|  | Material - Direct Purchase Total | [7 empty] | -421.56 | -906239.13 |  | -11766.58 |  |  | -918427.27
| Steel Lattice Towers (T/S)-DP Total | [8 empty] | -421.56 | -906239.13 |  | -11766.58 |  |  | -918427.27
2. Material Total | [9 empty] | -432.6 | -931482.96 |  | -12230.73 |  | 1377.74 | -942768.55
3. Construction | Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 |  | 34384 | [9 empty] | 0 | 34384
|  |  | HENKELS & MC COY INC |  |  |  |  | 423317.83 | [5 empty] | 338014.94 |  | 761332.77
|  | Contract Total |  |  | 34384 |  |  | 423317.83 | [5 empty] | 338014.94 | 0 | 795716.77
| Electrical Construction, Transmission Li Total |  |  |  | 34384 |  |  | 423317.83 | [5 empty] | 338014.94 | 0 | 795716.77
| GRID OPS | Labor | Labor Entries <$5,000 | [10 empty] | 803.73 |  | 803.73
|  | Labor Total | [11 empty] | 803.73 |  | 803.73
| GRID OPS Total | [12 empty] | 803.73 |  | 803.73
3. Construction Total |  |  |  |  | 34384 |  |  | 423317.83 | [5 empty] | 338818.67 | 0 | 796520.5
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 618.64 | 1023.69 | 52.21 | 51.81 | 2800.57 | 17.89 | -2.78 | -5967.3 | 26.43 | -49.35 | 2319.84 | 45.83 | 937.48
|  | Chargeback Total |  | 618.64 | 1023.69 | 52.21 | 51.81 | 2800.57 | 17.89 | -2.78 | -5967.3 | 26.43 | -49.35 | 2319.84 | 45.83 | 937.48
| Chargebacks Total |  |  | 618.64 | 1023.69 | 52.21 | 51.81 | 2800.57 | 17.89 | -2.78 | -5967.3 | 26.43 | -49.35 | 2319.84 | 45.83 | 937.48
| Labor - Other | Labor | Labor Entries <$5,000 | 561.02 | 4103.96 | 269.02 | 245.99 | 18499.97 | 85.74 | -17.54 | -37070.54 | 84.16 | -480.08 | 3865.9 | 35.28 | -9817.12
|  | Labor Total |  | 561.02 | 4103.96 | 269.02 | 245.99 | 18499.97 | 85.74 | -17.54 | -37070.54 | 84.16 | -480.08 | 3865.9 | 35.28 | -9817.12
| Labor - Other Total |  |  | 561.02 | 4103.96 | 269.02 | 245.99 | 18499.97 | 85.74 | -17.54 | -37070.54 | 84.16 | -480.08 | 3865.9 | 35.28 | -9817.12
4. Allocated Total |  |  |  | 1179.66 | 5127.65 | 321.23 | 297.8 | 21300.54 | 103.63 | -20.32 | -43037.84 | 110.59 | -529.43 | 6185.74 | 81.11 | -8879.64
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 32687.52 | 2042.3 | [6 empty] | 28299.93 | 63029.75
|  |  | AFUDC - Debt/Equity |  |  | 34084.17 | -34084.17 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 170.24 | 1252.62 | 42.13 | 47.45 | 37019.2 | -84.95 | -15.9 | -27555.73 | 23.92 | -316.96 | 9129.19 | -7.38 | 19703.83
|  |  | Capitalized Overhead - Inj & Damages | 2.85 | 14.46 | 1.25 | 1.1 | 191.59 | -3.08 | -0.41 | -1269.62 | 0.48 | -38.76 | 12.22 | -0.3 | -1088.22
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1275.83 | 3754.86 | 1039.51 | 1223.79 | 234.94 | 414.95 |  | 256.08 | 578.19 | 235.92 | 1045.39 | 973.54 | 11033
|  |  | Corporate Overheads Correction |  |  |  |  | -211164.27 | [7 empty] | -211164.27
|  | Non Budgeted Total |  | 1448.92 | 5021.94 | 35167.06 | -124.31 | -171676.24 | 326.92 | -16.31 | -28569.27 | 602.59 | -119.8 | 10186.8 | 29265.79 | -118485.91
| Non Budget - Other Total |  |  | 1448.92 | 5021.94 | 35167.06 | -124.31 | -171676.24 | 326.92 | -16.31 | -28569.27 | 602.59 | -119.8 | 10186.8 | 29265.79 | -118485.91
5. Corporate Overhead Total |  |  |  | 1448.92 | 5021.94 | 35167.06 | -124.31 | -171676.24 | 326.92 | -16.31 | -28569.27 | 602.59 | -119.8 | 10186.8 | 29265.79 | -118485.91
Grand Total |  |  |  | 4499.27 | 112110.74 | 36349.27 | 99922.28 | 196672.07 | -100769.3 | -469.29 | -1002775.07 | 1136.54 | -12387.46 | 17618.07 | 29002.96 | -619089.92

## 800062539
Pin: 5472 | Project: TRTP Segment 5
Order: 800062539 | 800062539- TRTP 4-11 & 3C: ANTELOPE-VINCENT #2 500K
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 90.35 | [6 empty] | 90.35
|  | Labor Total | [6 empty] | 90.35 | [6 empty] | 90.35
| BP&FM Total | [7 empty] | 90.35 | [6 empty] | 90.35
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -38972.81 | 38972.81 |  |  | 0
|  | Contract Total | [9 empty] | -38972.81 | 38972.81 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -38972.81 | 38972.81 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | 3249.1 | 5364 | [10 empty] | 8613.1
|  | Contract Total |  | 3249.1 | 5364 | [10 empty] | 8613.1
| Contract Consult/Contract Ord to Ord Total |  |  | 3249.1 | 5364 | [10 empty] | 8613.1
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 39796.84 | -39796.84 | -257.22 |  | -257.22
|  | IMM Correction Total | [9 empty] | 39796.84 | -39796.84 | -257.22 |  | -257.22
| IMM/Allocated - Correction Total | [10 empty] | 39796.84 | -39796.84 | -257.22 |  | -257.22
| Labor - Other | Labor | Labor Entries <$5,000 | 4621.16 | 424.29 | 144.43 | 292.79 | 86.45 | 6.67 | 11.62 | 117.2 | 206.61 | 6.75 | 110.86 |  | 6028.83
|  | Labor Total |  | 4621.16 | 424.29 | 144.43 | 292.79 | 86.45 | 6.67 | 11.62 | 117.2 | 206.61 | 6.75 | 110.86 |  | 6028.83
| Labor - Other Total |  |  | 4621.16 | 424.29 | 144.43 | 292.79 | 86.45 | 6.67 | 11.62 | 117.2 | 206.61 | 6.75 | 110.86 |  | 6028.83
| Other | Other | Other | 50156.52 | 147669.01 | 93.24 | [5 empty] | -737.13 | 737.13 |  |  | 197918.77
|  | Other Total |  | 50156.52 | 147669.01 | 93.24 | [5 empty] | -737.13 | 737.13 |  |  | 197918.77
| Other Total |  |  | 50156.52 | 147669.01 | 93.24 | [5 empty] | -737.13 | 737.13 |  |  | 197918.77
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | [8 empty] | 180.62 | 179.74 |  |  | 360.36
|  | Labor Total | [9 empty] | 180.62 | 179.74 |  |  | 360.36
| TRNS CAPITAL Total | [10 empty] | 180.62 | 179.74 |  |  | 360.36
1. Project Support Total |  |  |  | 58026.78 | 153457.3 | 237.67 | 292.79 | 86.45 | 97.02 | 11.62 | 117.2 | 474.13 | 99.59 | -146.36 |  | 212754.19
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 |  | 2237.62 | 3052.36 | 2436.45 |  | 4336.01 |  |  | 561.11 | 240.5 | 1410.35 | 3656.57 | 17930.97
|  |  | TD-TRTP Segments 4, 5 & 10 |  |  |  |  | 5815.8 |  | 9180 | 12784.5 |  |  |  | 8981.34 | 36761.64
|  | Chargeback Total |  |  | 2237.62 | 3052.36 | 2436.45 | 5815.8 | 4336.01 | 9180 | 12784.5 | 561.11 | 240.5 | 1410.35 | 12637.91 | 54692.61
| Chargebacks Total |  |  |  | 2237.62 | 3052.36 | 2436.45 | 5815.8 | 4336.01 | 9180 | 12784.5 | 561.11 | 240.5 | 1410.35 | 12637.91 | 54692.61
| Labor - Other | Labor | Labor Entries <$5,000 | 203.55 | 158.68 | -0.44 | 4.18 | 0.15 | 24.98 |  | 1.82 | -1189.62 | 2074.87 | 4.62 |  | 1282.79
|  | Labor Total |  | 203.55 | 158.68 | -0.44 | 4.18 | 0.15 | 24.98 |  | 1.82 | -1189.62 | 2074.87 | 4.62 |  | 1282.79
| Labor - Other Total |  |  | 203.55 | 158.68 | -0.44 | 4.18 | 0.15 | 24.98 |  | 1.82 | -1189.62 | 2074.87 | 4.62 |  | 1282.79
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -86.9 | 86.9 |  |  | 0
|  | Overhead Total | [9 empty] | -86.9 | 86.9 |  |  | 0
| Overhead Correction Total | [10 empty] | -86.9 | 86.9 |  |  | 0
4. Allocated Total |  |  |  | 203.55 | 2396.3 | 3051.92 | 2440.63 | 5815.95 | 4360.99 | 9180 | 12786.32 | -715.41 | 2402.27 | 1414.97 | 12637.91 | 55975.4
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 272219.17 | 16531.02 | [6 empty] | 281912.62 | 570662.81
|  |  | Capitalized Overhead - A&G | 3249.81 | 4565.92 | 117.26 | 97.48 | 491.25 | 159.11 | 322.74 | 364.98 | -10.81 | 64.64 | 33.53 | 354.83 | 9810.74
|  |  | Capitalized Overhead - Inj & Damages | 51.42 | 256.09 | 0.67 | 0.58 | 0.77 | 0.16 | 0.01 | 0.13 | 35.08 | -115.23 | -0.09 | 0.64 | 230.23
|  |  | Capitalized Overhead - P&B/Payroll Tax | 2624.21 | 408.73 | 123.31 | 313.29 | 108.6 | 128.37 | 12.53 | 64.47 | 505.26 | 338.62 | 187.62 | 967.86 | 5782.87
|  |  | Corporate Overheads Correction |  |  |  |  | -41900.16 | [7 empty] | -41900.16
|  |  | Non-Budgeted WO Pstngs- WO/WBS Pstg - Co |  | 186577.75 | [10 empty] | 186577.75
|  | Non Budgeted Total |  | 5925.44 | 191808.49 | 241.24 | 272630.52 | -24768.52 | 287.64 | 335.28 | 429.58 | 529.53 | 288.03 | 221.06 | 283235.95 | 731164.24
| Non Budget - Other Total |  |  | 5925.44 | 191808.49 | 241.24 | 272630.52 | -24768.52 | 287.64 | 335.28 | 429.58 | 529.53 | 288.03 | 221.06 | 283235.95 | 731164.24
5. Corporate Overhead Total |  |  |  | 5925.44 | 191808.49 | 241.24 | 272630.52 | -24768.52 | 287.64 | 335.28 | 429.58 | 529.53 | 288.03 | 221.06 | 283235.95 | 731164.24
Grand Total |  |  |  | 64155.77 | 347662.09 | 3530.83 | 275363.94 | -18866.12 | 4745.65 | 9526.9 | 13333.1 | 288.25 | 2789.89 | 1489.67 | 295873.86 | 999893.83

## 800051902
Pin: 5472 | Project: TRTP Segment 5
Order: 800051902 | 800051902- 9219-2369 - TRTP Segment 5
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -25323.78 | 25323.78 |  |  | 0
|  | Contract Total | [9 empty] | -25323.78 | 25323.78 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -25323.78 | 25323.78 |  |  | 0
| HRealProp | Labor | Labor Entries <$5,000 | 3105.05 | 565.53 | 145.87 | 206.13 | 242.55 | 281.24 | 134.05 |  |  | 87.95 |  |  | 4768.37
|  | Labor Total |  | 3105.05 | 565.53 | 145.87 | 206.13 | 242.55 | 281.24 | 134.05 |  |  | 87.95 |  |  | 4768.37
| HRealProp Total |  |  | 3105.05 | 565.53 | 145.87 | 206.13 | 242.55 | 281.24 | 134.05 |  |  | 87.95 |  |  | 4768.37
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -112.76 | -22.07 |  | -11.22 | -8.79 |  |  | 24413.78 | -24413.78 | -167.14 |  | -321.98
|  | IMM Correction Total |  |  | -112.76 | -22.07 |  | -11.22 | -8.79 |  |  | 24413.78 | -24413.78 | -167.14 |  | -321.98
| IMM/Allocated - Correction Total |  |  |  | -112.76 | -22.07 |  | -11.22 | -8.79 |  |  | 24413.78 | -24413.78 | -167.14 |  | -321.98
| Information System Professional Services | Contract | Contract Entries <$50,000 |  | 31.9 | [10 empty] | 31.9
|  | Contract Total |  |  | 31.9 | [10 empty] | 31.9
| Information System Professional Services Total |  |  |  | 31.9 | [10 empty] | 31.9
| Labor - Other | Labor | Labor Entries <$5,000 | 119.81 | 159.42 | 162.61 | 66.78 | 76.09 | 4.72 | 11.01 | 25.43 | 0.62 | 17.11 | -17.11 |  | 626.49
|  | Labor Total |  | 119.81 | 159.42 | 162.61 | 66.78 | 76.09 | 4.72 | 11.01 | 25.43 | 0.62 | 17.11 | -17.11 |  | 626.49
| Labor - Other Total |  |  | 119.81 | 159.42 | 162.61 | 66.78 | 76.09 | 4.72 | 11.01 | 25.43 | 0.62 | 17.11 | -17.11 |  | 626.49
| Other | Other | Other | 15152.74 | 3312.5 |  | 1700 | 1331.25 |  |  |  | 910 | -910 |  |  | 21496.49
|  | Other Total |  | 15152.74 | 3312.5 |  | 1700 | 1331.25 |  |  |  | 910 | -910 |  |  | 21496.49
| Other Total |  |  | 15152.74 | 3312.5 |  | 1700 | 1331.25 |  |  |  | 910 | -910 |  |  | 21496.49
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 508.2 | [11 empty] | 508.2
|  | Contract Total |  | 508.2 | [11 empty] | 508.2
| Temporary/Supplementary - Trade/Labor Total |  |  | 508.2 | [11 empty] | 508.2
1. Project Support Total |  |  |  | 18885.8 | 3956.59 | 286.41 | 1972.91 | 1638.67 | 277.17 | 145.06 | 25.43 | 0.62 | 105.06 | -184.25 |  | 27109.47
2. Material | Material - Other | Material | Material - Other | 346.57 | [11 empty] | 346.57
|  | Material Total |  | 346.57 | [11 empty] | 346.57
| Material - Other Total |  |  | 346.57 | [11 empty] | 346.57
2. Material Total |  |  |  | 346.57 | [11 empty] | 346.57
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 112.76 | 22.07 |  | 3875.22 | -901.21 |  | 3270.47 | 572 | -167.14 | 167.14 |  |  | 6951.31
|  |  | Law-TRTP Segment 5 - CRE |  |  |  |  | 6129.31 | 11488 |  |  |  |  | 6710 | 6381.01 | 30708.32
|  | Chargeback Total |  | 112.76 | 22.07 |  | 3875.22 | 5228.1 | 11488 | 3270.47 | 572 | -167.14 | 167.14 | 6710 | 6381.01 | 37659.63
| Chargebacks Total |  |  | 112.76 | 22.07 |  | 3875.22 | 5228.1 | 11488 | 3270.47 | 572 | -167.14 | 167.14 | 6710 | 6381.01 | 37659.63
| Labor - Other | Labor | Labor Entries <$5,000 | 1106.88 | 204.84 | 31.18 | 83.87 | 82.92 | 62.28 | 29.76 | 0.71 | -557.12 | 1292.56 | -4.3 |  | 2333.58
|  | Labor Total |  | 1106.88 | 204.84 | 31.18 | 83.87 | 82.92 | 62.28 | 29.76 | 0.71 | -557.12 | 1292.56 | -4.3 |  | 2333.58
| Labor - Other Total |  |  | 1106.88 | 204.84 | 31.18 | 83.87 | 82.92 | 62.28 | 29.76 | 0.71 | -557.12 | 1292.56 | -4.3 |  | 2333.58
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -715.39 | -715.39
|  | Overhead Total | [12 empty] | -715.39 | -715.39
| Overhead Correction Total | [13 empty] | -715.39 | -715.39
4. Allocated Total |  |  |  | 1219.64 | 226.91 | 31.18 | 3959.09 | 5311.02 | 11550.28 | 3300.23 | 572.71 | -724.26 | 1459.7 | 6705.7 | 5665.62 | 39277.82
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 17602.6 | 1072.16 | [6 empty] | 18437.57 | 37112.33
|  | Non Budgeted Total |  |  |  |  | 17602.6 | 1072.16 | [6 empty] | 18437.57 | 37112.33
| Non Budget - Other Total | [5 empty] | 17602.6 | 1072.16 | [6 empty] | 18437.57 | 37112.33
5. Corporate Overhead Total | [6 empty] | 17602.6 | 1072.16 | [6 empty] | 18437.57 | 37112.33
Grand Total |  |  |  | 20452.01 | 4183.5 | 317.59 | 23534.6 | 8021.85 | 11827.45 | 3445.29 | 598.14 | -723.64 | 1564.76 | 6521.45 | 24103.19 | 103846.19

## TRTP Seg 6
WO | SumOfYTD2012 | Order | Project
800217330- I: TRTP 6-4: NEW VINCENT-ANF 500KV: CONS | 8356783.19 | 800217330 | TRTP Segment 6
800217316- I: TRTP 6-2: NEW VINCENT-DUARTE 500KV: C | 45666501.43 | 800217316 | TRTP Segment 6
800051930- 9219-5080 - TRTP Segment 6 | 52919.65 | 800051930 | TRTP Segment 6

## 800217330
Pin: 5243 | Project: TRTP Segment 6
Order: 800217330 | 800217330- I: TRTP 6-4: NEW VINCENT-ANF 500KV: CONS
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 90.35 | 139.98 | [5 empty] | 230.33
|  | Labor Total | [6 empty] | 90.35 | 139.98 | [5 empty] | 230.33
| BP&FM Total | [7 empty] | 90.35 | 139.98 | [5 empty] | 230.33
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 1438 | 1438
|  | Labor Total | [12 empty] | 1438 | 1438
| ELEC SYS PLANNING Total | [13 empty] | 1438 | 1438
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 475.61 | 307.65 |  | 114.35 | [8 empty] | 897.61
|  | Labor Total |  | 475.61 | 307.65 |  | 114.35 | [8 empty] | 897.61
| ENG ADVANCEMENT Total |  |  | 475.61 | 307.65 |  | 114.35 | [8 empty] | 897.61
| ENGINEERING | Labor | Labor Entries <$5,000 | 1216.92 | 1450.17 | 2008.59 | 2308.26 | 2190.26 | 2415.25 | 1996.34 | 2682.7 | 2045.18 | 1840.82 | 1831.44 |  | 21985.93
|  | Labor Total |  | 1216.92 | 1450.17 | 2008.59 | 2308.26 | 2190.26 | 2415.25 | 1996.34 | 2682.7 | 2045.18 | 1840.82 | 1831.44 |  | 21985.93
| ENGINEERING Total |  |  | 1216.92 | 1450.17 | 2008.59 | 2308.26 | 2190.26 | 2415.25 | 1996.34 | 2682.7 | 2045.18 | 1840.82 | 1831.44 |  | 21985.93
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | 101464 |  | 53286 | 55864 | 62579 |  | 55597 | 78700 |  |  | 61531 | 178839.94 | 647860.94
|  |  | Contract Entries <$50,000 |  | 48776.55 | 2974.19 |  |  |  | 69450.22 |  | 59096.22 | 48990 | 37985 | 6353.64 | 273625.82
|  |  | PAR ELECTRICAL CONTRACTORS INC |  | 185544.53 | 589838.83 | 241509.53 | 167871.28 |  | 779548.81 | [5 empty] | 1964312.98
|  | Contract Total |  | 101464 | 234321.08 | 646099.02 | 297373.53 | 230450.28 |  | 904596.03 | 78700 | 59096.22 | 48990 | 99516 | 185193.58 | 2885799.74
| Engineering/Technical Professional Servi Total |  |  | 101464 | 234321.08 | 646099.02 | 297373.53 | 230450.28 |  | 904596.03 | 78700 | 59096.22 | 48990 | 99516 | 185193.58 | 2885799.74
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -742.24 | -1665.83 | -4273.89 | -1965.22 | -1520.97 |  | -8913.78 | -771.46 | -5430.89 | -368.87 | -747.89 | -26401.04
|  | IMM Correction Total |  |  | -742.24 | -1665.83 | -4273.89 | -1965.22 | -1520.97 |  | -8913.78 | -771.46 | -5430.89 | -368.87 | -747.89 | -26401.04
| IMM/Allocated - Correction Total |  |  |  | -742.24 | -1665.83 | -4273.89 | -1965.22 | -1520.97 |  | -8913.78 | -771.46 | -5430.89 | -368.87 | -747.89 | -26401.04
| Labor - Other | Labor | Labor Entries <$5,000 | -5.28 | 198.92 | -177.35 | 12.52 | 369.17 | -490.85 | 11.25 | 35.92 | -4.48 | 201.5 | -224.69 | 216.58 | 143.21
|  | Labor Total |  | -5.28 | 198.92 | -177.35 | 12.52 | 369.17 | -490.85 | 11.25 | 35.92 | -4.48 | 201.5 | -224.69 | 216.58 | 143.21
| Labor - Other Total |  |  | -5.28 | 198.92 | -177.35 | 12.52 | 369.17 | -490.85 | 11.25 | 35.92 | -4.48 | 201.5 | -224.69 | 216.58 | 143.21
| Other | Other | Other | -5438.03 | 401652.9 | -273644.72 | -52159.74 | 118339.02 | 536155.71 | -142431.88 | 53935.22 | 1065427.82 | -497113.09 | -335576.12 | 2910034.04 | 3779181.13
|  | Other Total |  | -5438.03 | 401652.9 | -273644.72 | -52159.74 | 118339.02 | 536155.71 | -142431.88 | 53935.22 | 1065427.82 | -497113.09 | -335576.12 | 2910034.04 | 3779181.13
| Other Total |  |  | -5438.03 | 401652.9 | -273644.72 | -52159.74 | 118339.02 | 536155.71 | -142431.88 | 53935.22 | 1065427.82 | -497113.09 | -335576.12 | 2910034.04 | 3779181.13
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  | 139.76 | 319.44 | 79.86 | [8 empty] | 539.06
|  | Contract Total |  |  | 139.76 | 319.44 | 79.86 | [8 empty] | 539.06
| Temporary/Supplementary - Trade/Labor Total |  |  |  | 139.76 | 319.44 | 79.86 | [8 empty] | 539.06
1. Project Support Total |  |  |  | 97713.22 | 637328.24 | 372939.15 | 243454.89 | 349383.51 | 536649.49 | 764311.72 | 126440.06 | 1125793.28 | -451511.66 | -234822.24 | 3096134.31 | 6663813.97
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  | 63.96 | [10 empty] | 63.96
|  | Material - Direct Purchase Total |  |  | 63.96 | [10 empty] | 63.96
| Building, Shop & Industrial Products/Eqp Total |  |  |  | 63.96 | [10 empty] | 63.96
| Material - Other | Material | Material - Other | 201.94 | 1642.22 | 54.3 |  | -0.12 | 1.45 | -3.24 | 0.26 | 0.94 | 0.69 |  |  | 1898.44
|  | Material Total |  | 201.94 | 1642.22 | 54.3 |  | -0.12 | 1.45 | -3.24 | 0.26 | 0.94 | 0.69 |  |  | 1898.44
| Material - Other Total |  |  | 201.94 | 1642.22 | 54.3 |  | -0.12 | 1.45 | -3.24 | 0.26 | 0.94 | 0.69 |  |  | 1898.44
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | -125.04 | [5 empty] | -125.04
|  | Material - Direct Purchase Total | [7 empty] | -125.04 | [5 empty] | -125.04
| Pole Line Hdwe & Connectors-DP Total | [8 empty] | -125.04 | [5 empty] | -125.04
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | ON-RAMP WIRELESS, INC. |  | 13015 | [10 empty] | 13015
|  | Material - Direct Purchase Total |  |  | 13015 | [10 empty] | 13015
| Power Systems, Batteries and Light-DP Total |  |  |  | 13015 | [10 empty] | 13015
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 5.9 | [9 empty] | 5.9
|  | Material - Direct Purchase Total |  |  |  | 5.9 | [9 empty] | 5.9
| Transportation & Mobile Equip-DP Total |  |  |  |  | 5.9 | [9 empty] | 5.9
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | 1625.52 | [11 empty] | 1625.52
|  | Material - Direct Purchase Total |  | 1625.52 | [11 empty] | 1625.52
| Wire, Cable & Bus Bar-DP Total |  |  | 1625.52 | [11 empty] | 1625.52
2. Material Total |  |  |  | 1827.46 | 14721.18 | 60.2 |  | -0.12 | 1.45 | -128.28 | 0.26 | 0.94 | 0.69 |  |  | 16483.78
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  | 2548.8 | [10 empty] | 2548.8
|  | Contract Total |  |  | 2548.8 | [10 empty] | 2548.8
| Construction Management Services Total |  |  |  | 2548.8 | [10 empty] | 2548.8
| Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 | [7 empty] | 38187.5 |  | 6900 | 13800 | 17250 | 76137.5
|  |  | PAR ELECTRICAL CONTRACTORS INC | [6 empty] | 438643.79 |  | 751234.36 |  |  |  | 1189878.15
|  | Contract Total | [7 empty] | 438643.79 | 38187.5 | 751234.36 | 6900 | 13800 | 17250 | 1266015.65
| Electrical Construction, Transmission Li Total | [8 empty] | 438643.79 | 38187.5 | 751234.36 | 6900 | 13800 | 17250 | 1266015.65
| GRID OPS | Labor | Labor Entries <$5,000 | [7 empty] | 544.49 |  |  |  |  | 544.49
|  | Labor Total | [8 empty] | 544.49 |  |  |  |  | 544.49
| GRID OPS Total | [9 empty] | 544.49 |  |  |  |  | 544.49
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  | 2310.37 | 1134.91 | 307.8 |  |  | 7458.47 |  | 10370.97 |  |  |  | 21582.52
|  | Contract Total |  |  | 2310.37 | 1134.91 | 307.8 |  |  | 7458.47 |  | 10370.97 |  |  |  | 21582.52
| Major Construction, Turnkey, Trans/Subs Total |  |  |  | 2310.37 | 1134.91 | 307.8 |  |  | 7458.47 |  | 10370.97 |  |  |  | 21582.52
| Security / Protection Services | Contract | Contract Entries <$50,000 | [8 empty] | 2160 |  |  | 61124 | 63284
|  | Contract Total | [9 empty] | 2160 |  |  | 61124 | 63284
| Security / Protection Services Total | [10 empty] | 2160 |  |  | 61124 | 63284
3. Construction Total |  |  |  |  | 4859.17 | 1134.91 | 307.8 |  |  | 446102.26 | 38731.99 | 763765.33 | 6900 | 13800 | 78374 | 1353975.46
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 7022.8 | 10517.82 | 13829.35 | 15671.85 | 14237.29 | 8702.06 | 8438.43 | 9530.7 | 10496.74 | 12454.41 | 18963.96 | 10091.25 | 139956.66
|  |  | PROCUREMENT TDBU | [6 empty] | 8913.78 |  | 5430.89 |  |  |  | 14344.67
|  |  | Work Package # 2 |  | 5605.96 | 10179.79 | 5396.12 |  | 7160.95 | 6859.49 | 5169.43 | 6682.39 |  |  | 15203.79 | 62257.92
|  | Chargeback Total |  | 7022.8 | 16123.78 | 24009.14 | 21067.97 | 14237.29 | 15863.01 | 24211.7 | 14700.13 | 22610.02 | 12454.41 | 18963.96 | 25295.04 | 216559.25
| Chargebacks Total |  |  | 7022.8 | 16123.78 | 24009.14 | 21067.97 | 14237.29 | 15863.01 | 24211.7 | 14700.13 | 22610.02 | 12454.41 | 18963.96 | 25295.04 | 216559.25
| Labor - Other | Labor | Division Overhead |  | 12519.92 | 16188.98 |  |  |  | 56183.85 |  | 23122.41 |  |  |  | 108015.16
|  |  | Labor Entries <$5,000 | 6421.72 | 9995.34 | 7863.25 | 10180.55 | 10752 | 558.21 | 583.71 | 5675.71 | 3564.97 | 3491.13 | 1564.86 | 3966.61 | 64618.06
|  | Labor Total |  | 6421.72 | 22515.26 | 24052.23 | 10180.55 | 10752 | 558.21 | 56767.56 | 5675.71 | 26687.38 | 3491.13 | 1564.86 | 3966.61 | 172633.22
| Labor - Other Total |  |  | 6421.72 | 22515.26 | 24052.23 | 10180.55 | 10752 | 558.21 | 56767.56 | 5675.71 | 26687.38 | 3491.13 | 1564.86 | 3966.61 | 172633.22
4. Allocated Total |  |  |  | 13444.52 | 38639.04 | 48061.37 | 31248.52 | 24989.29 | 16421.22 | 80979.26 | 20375.84 | 49297.4 | 15945.54 | 20528.82 | 29261.65 | 389192.47
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 74285.72 | 4447.04 | [6 empty] | 115425.13 | 194157.89
|  |  | AFUDC - Debt/Equity |  |  | 75689.01 | -75689.01 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 6609.15 | 8610.54 | 24802.99 | 11667.11 | 21309.55 | 604.51 | 50341.26 | 3722.71 | 39128.6 | 1768.47 | 3569.86 | 8247.04 | 180381.79
|  |  | Capitalized Overhead - Inj & Damages | 12.85 | 78.79 | 35.57 | 15.71 | 145.35 | 7.98 | 66.42 | 9.03 | 35.72 | 12.72 | 21.82 | 14.28 | 456.24
|  |  | Capitalized Overhead - P&B/Payroll Tax | 3626.11 | 6421.11 | 4790.56 | 10063.81 | 9803.02 | 7447.07 | 6822.24 | 6855.07 | 8616.9 | 2447.14 | 4224.98 | 11173 | 82291.01
|  |  | Corporate Overheads Correction |  |  |  |  | -523969.42 | [7 empty] | -523969.42
|  | Non Budgeted Total |  | 10248.11 | 15110.44 | 105318.13 | 20343.34 | -488264.46 | 8059.56 | 57229.92 | 10586.81 | 47781.22 | 4228.33 | 7816.66 | 134859.45 | -66682.49
| Non Budget - Other Total |  |  | 10248.11 | 15110.44 | 105318.13 | 20343.34 | -488264.46 | 8059.56 | 57229.92 | 10586.81 | 47781.22 | 4228.33 | 7816.66 | 134859.45 | -66682.49
5. Corporate Overhead Total |  |  |  | 10248.11 | 15110.44 | 105318.13 | 20343.34 | -488264.46 | 8059.56 | 57229.92 | 10586.81 | 47781.22 | 4228.33 | 7816.66 | 134859.45 | -66682.49
Grand Total |  |  |  | 123233.31 | 710658.07 | 527513.76 | 295354.55 | -113891.78 | 561131.72 | 1348494.88 | 196134.96 | 1986638.17 | -424437.1 | -192676.76 | 3338629.41 | 8356783.19

## 800217316
Pin: 5243 | Project: TRTP Segment 6
Order: 800217316 | 800217316- I: TRTP 6-2: NEW VINCENT-DUARTE 500KV: C
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 870.73 | [6 empty] | 870.73
|  | Labor Total | [6 empty] | 870.73 | [6 empty] | 870.73
| BP&FM Total | [7 empty] | 870.73 | [6 empty] | 870.73
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 4349558.7 |  |  | 4349558.7
|  |  | Contract Entries <$50,000 | [8 empty] | -4349558.7 |  |  |  | -4349558.7
|  | Contract Total | [9 empty] | -4349558.7 | 4349558.7 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -4349558.7 | 4349558.7 |  |  | 0
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 | [7 empty] | 69.65 | 210.79 | 14.24 |  |  | 294.68
|  | Labor Total | [8 empty] | 69.65 | 210.79 | 14.24 |  |  | 294.68
| EAST GRID MGMTCENTER Total | [9 empty] | 69.65 | 210.79 | 14.24 |  |  | 294.68
| ELEC SYS PLANNING | Labor | ELEC SYS PLANNING / Engineer | [11 empty] | 7231.12 | 7231.12
|  |  | Labor Entries <$5,000 | [11 empty] | 7585.82 | 7585.82
|  | Labor Total | [12 empty] | 14816.94 | 14816.94
| ELEC SYS PLANNING Total | [13 empty] | 14816.94 | 14816.94
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 506.71 | 461.48 | [10 empty] | 968.19
|  | Labor Total |  | 506.71 | 461.48 | [10 empty] | 968.19
| ENG ADVANCEMENT Total |  |  | 506.71 | 461.48 | [10 empty] | 968.19
| ENGINEERING | Labor | Engineer |  |  | 5216 | 5838.56 |  | 7506.72 |  | 6672.64 |  |  | 5213 |  | 30446.92
|  |  | Labor Entries <$5,000 | 16770.33 | 11641.92 | 16567.81 | 10993.43 | 16375.05 | 12967.17 | 14687.03 | 12490.07 | 16711.96 | 18789.53 | 15863.86 |  | 163858.16
|  | Labor Total |  | 16770.33 | 11641.92 | 21783.81 | 16831.99 | 16375.05 | 20473.89 | 14687.03 | 19162.71 | 16711.96 | 18789.53 | 21076.86 |  | 194305.08
| ENGINEERING Total |  |  | 16770.33 | 11641.92 | 21783.81 | 16831.99 | 16375.05 | 20473.89 | 14687.03 | 19162.71 | 16711.96 | 18789.53 | 21076.86 |  | 194305.08
| Engineering/Technical Professional Servi | Contract | BUREAU VERITAS NORTH AMERICA INC | [6 empty] | 80678.24 |  |  | 116492.63 | 60055.5 | 115192.5 | 372418.87
|  |  | BURNS & MC DONNELL INC | 348864 | 129080 | 156731 | 164314 | 184067 |  | 386701.9 | 286110 | 287019 | 329998 | 418165 | 1143938.59 | 3834988.49
|  |  | Contract Entries <$50,000 |  | 57516.14 | 17036.74 | 113880.63 | 64913.34 | 80463.36 | 118274.51 | 67902.32 | 43362.02 | 79188.6 | 118817.82 | 85652.24 | 847007.72
|  |  | Engineering/Technical Professional Servi | [10 empty] | 354603.5 |  | 354603.5
|  |  | MONTANA GEOTECHNICAL I | [7 empty] | 108534.75 |  |  |  |  | 108534.75
|  |  | PAR ELECTRICAL CONTRACTORS INC |  | 185544.53 | 589838.83 | 241509.53 | 241871.28 |  | 779548.82 | [5 empty] | 2038312.99
|  | Contract Total |  | 348864 | 372140.67 | 763606.57 | 519704.16 | 490851.62 | 80463.36 | 1365203.47 | 462547.07 | 330381.02 | 525679.23 | 951641.82 | 1344783.33 | 7555866.32
| Engineering/Technical Professional Servi Total |  |  | 348864 | 372140.67 | 763606.57 | 519704.16 | 490851.62 | 80463.36 | 1365203.47 | 462547.07 | 330381.02 | 525679.23 | 951641.82 | 1344783.33 | 7555866.32
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 8558.57 | 25984.96 | 28013.85 | 44241.92 | 38688.16 | 31378.54 | 129124.46 | 66534.32 | 67955.65 | 53522.67 | 37888.71 | 531891.81
|  |  | SHAW ENVIRONMENTAL INC. | [11 empty] | 59444.97 | 59444.97
|  | Contract Total |  |  | 8558.57 | 25984.96 | 28013.85 | 44241.92 | 38688.16 | 31378.54 | 129124.46 | 66534.32 | 67955.65 | 53522.67 | 97333.68 | 591336.78
| Environmental/Safety Professional Servic Total |  |  |  | 8558.57 | 25984.96 | 28013.85 | 44241.92 | 38688.16 | 31378.54 | 129124.46 | 66534.32 | 67955.65 | 53522.67 | 97333.68 | 591336.78
| HRealProp | Labor | Labor Entries <$5,000 |  | -162.54 | [10 empty] | -162.54
|  | Labor Total |  |  | -162.54 | [10 empty] | -162.54
| HRealProp Total |  |  |  | -162.54 | [10 empty] | -162.54
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 45507.4 | 39660.28 | 40118.55 | 37499.88 | 35921.86 | 39741.5 | 31978.86 | 17166.64 | 4564872.78 | -4519465.21 | -52378.48 | -43208.46 | 237415.6
|  | IMM Correction Total |  | 45507.4 | 39660.28 | 40118.55 | 37499.88 | 35921.86 | 39741.5 | 31978.86 | 17166.64 | 4564872.78 | -4519465.21 | -52378.48 | -43208.46 | 237415.6
| IMM/Allocated - Correction Total |  |  | 45507.4 | 39660.28 | 40118.55 | 37499.88 | 35921.86 | 39741.5 | 31978.86 | 17166.64 | 4564872.78 | -4519465.21 | -52378.48 | -43208.46 | 237415.6
| Labor - Other | Labor | Labor - Other | [9 empty] | 25383.76 |  |  | 25383.76
|  |  | Labor Accrual - SCE | [11 empty] | 6505.74 | 6505.74
|  |  | Labor Correction | [9 empty] | 126287.78 |  |  | 126287.78
|  |  | Labor Entries <$5,000 | 2870.36 | 5188.79 | -2369.6 | 3730.3 | 7140.87 | -5156.68 | 704.71 | 4991.54 | 67824.71 | -211177.4 | -4450.9 | 1745.58 | -128957.72
|  | Labor Total |  | 2870.36 | 5188.79 | -2369.6 | 3730.3 | 7140.87 | -5156.68 | 704.71 | 4991.54 | 67824.71 | -59505.86 | -4450.9 | 8251.32 | 29219.56
| Labor - Other Total |  |  | 2870.36 | 5188.79 | -2369.6 | 3730.3 | 7140.87 | -5156.68 | 704.71 | 4991.54 | 67824.71 | -59505.86 | -4450.9 | 8251.32 | 29219.56
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | [8 empty] | 657.77 |  |  |  | 657.77
|  | Labor Total | [9 empty] | 657.77 |  |  |  | 657.77
| MAJOR PROJECT ORG Total | [10 empty] | 657.77 |  |  |  | 657.77
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [7 empty] | 95.03 | 143.17 |  |  |  | 238.2
|  | Labor Total | [8 empty] | 95.03 | 143.17 |  |  |  | 238.2
| NORTH GRIDMGMTCENTER Total | [9 empty] | 95.03 | 143.17 |  |  |  | 238.2
| Other | Other | Other | -115683.47 | 422046.35 | 570499 | -12120.62 | -379408.3 | 752189.52 | -200765.92 | 261830.98 | 3659573.18 | -2750676.16 | 1285569.19 | 1431742.08 | 4924795.83
|  | Other Total |  | -115683.47 | 422046.35 | 570499 | -12120.62 | -379408.3 | 752189.52 | -200765.92 | 261830.98 | 3659573.18 | -2750676.16 | 1285569.19 | 1431742.08 | 4924795.83
| Other Total |  |  | -115683.47 | 422046.35 | 570499 | -12120.62 | -379408.3 | 752189.52 | -200765.92 | 261830.98 | 3659573.18 | -2750676.16 | 1285569.19 | 1431742.08 | 4924795.83
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -60868.2 |  |  |  | -60868.2
|  |  | Temporary / Supplemental - Correction | [9 empty] | 60868.2 |  |  | 60868.2
|  | Contract Total | [9 empty] | -60868.2 | 60868.2 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -60868.2 | 60868.2 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 80575.69 | 9579.24 | 9504 | 15688.32 | 5656.32 | 12169.07 | 22353.03 | 3843.84 | 14292.63 | 9647.88 | 8448 | 12936 | 204694.02
|  | Contract Total |  | 80575.69 | 9579.24 | 9504 | 15688.32 | 5656.32 | 12169.07 | 22353.03 | 3843.84 | 14292.63 | 9647.88 | 8448 | 12936 | 204694.02
| Temporary/Supplementary - Technical/Prof Total |  |  | 80575.69 | 9579.24 | 9504 | 15688.32 | 5656.32 | 12169.07 | 22353.03 | 3843.84 | 14292.63 | 9647.88 | 8448 | 12936 | 204694.02
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 3643.84 | 1146.81 | 295.24 | 239.58 | 774.4 | 958.32 | 7646.6 | 2779.27 | 3953.07 | 3707.96 | 14920.32 | 36991.42 | 77056.83
|  | Contract Total |  | 3643.84 | 1146.81 | 295.24 | 239.58 | 774.4 | 958.32 | 7646.6 | 2779.27 | 3953.07 | 3707.96 | 14920.32 | 36991.42 | 77056.83
| Temporary/Supplementary - Trade/Labor Total |  |  | 3643.84 | 1146.81 | 295.24 | 239.58 | 774.4 | 958.32 | 7646.6 | 2779.27 | 3953.07 | 3707.96 | 14920.32 | 36991.42 | 77056.83
| TRANSMISSION | Labor | Labor Entries <$5,000 | 253.97 | 9102.59 | 1975.62 | 262.34 | 118.06 | 1346.64 | 5426.43 | 10741.66 | 10437.99 | 9299.88 | 11205.58 | 6399.52 | 66570.28
|  |  | TRANSMISSION / Lineman Rbr Trn | [7 empty] | 5056.21 |  |  |  | 5068.22 | 10124.43
|  |  | TRANSMISSION / Mgr-Prj/Prod | [11 empty] | 10633.79 | 10633.79
|  | Labor Total |  | 253.97 | 9102.59 | 1975.62 | 262.34 | 118.06 | 1346.64 | 5426.43 | 15797.87 | 10437.99 | 9299.88 | 11205.58 | 22101.53 | 87328.5
| TRANSMISSION Total |  |  | 253.97 | 9102.59 | 1975.62 | 262.34 | 118.06 | 1346.64 | 5426.43 | 15797.87 | 10437.99 | 9299.88 | 11205.58 | 22101.53 | 87328.5
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 2454.79 | 6055.16 | 6085.47 | 3684.12 | 3946.98 | 2925.66 | 5038.05 | 334.95 | 4912.19 | 5944.74 | 5716.83 | 303.76 | 47402.7
|  |  | Mgr-Prj/Prod | 7515.44 |  |  | 6195.6 | 8054.28 | 5369.52 | 6608.64 | 14921.53 | 7434.72 |  | 6195.6 |  | 62295.33
|  | Labor Total |  | 9970.23 | 6055.16 | 6085.47 | 9879.72 | 12001.26 | 8295.18 | 11646.69 | 15256.48 | 12346.91 | 5944.74 | 11912.43 | 303.76 | 109698.03
| TRNS CAPITAL Total |  |  | 9970.23 | 6055.16 | 6085.47 | 9879.72 | 12001.26 | 8295.18 | 11646.69 | 15256.48 | 12346.91 | 5944.74 | 11912.43 | 303.76 | 109698.03
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 |  |  | 1392 |  |  | 1065.6 | 399.6 | 932.4 | 2147.6 | 2064.6 | 532.8 | 2725 | 11259.6
|  |  | TSD-Aircraft - Fixed / AIRCFT OPS-VRBL DISC | [11 empty] | 14119.2 | 14119.2
|  | Labor Total |  |  |  | 1392 |  |  | 1065.6 | 399.6 | 932.4 | 2147.6 | 2064.6 | 532.8 | 16844.2 | 25378.8
| TSD-Aircraft - Fixed Total |  |  |  |  | 1392 |  |  | 1065.6 | 399.6 | 932.4 | 2147.6 | 2064.6 | 532.8 | 16844.2 | 25378.8
1. Project Support Total |  |  |  | 393279.06 | 885419.32 | 1438875.62 | 619729.52 | 233673.06 | 951105.29 | 1290659.04 | 933597.94 | 4339661 | -2276116.62 | 2302000.29 | 2942895.8 | 14054779.32
2. Material | Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 | -321.12 | [11 empty] | -321.12
|  | Material - Direct Purchase Total |  | -321.12 | [11 empty] | -321.12
| Fuels, Chemicals & Petrochem-DP Total |  |  | -321.12 | [11 empty] | -321.12
| Insulators & Bushings-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | -9031.75 | [8 empty] | -9031.75
|  |  | ONE SOURCE DISTRIBUTORS INC | 8235.09 | [11 empty] | 8235.09
|  | Material - Direct Purchase Total |  | 8235.09 |  |  | -9031.75 | [8 empty] | -796.66
| Insulators & Bushings-DP Total |  |  | 8235.09 |  |  | -9031.75 | [8 empty] | -796.66
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -430.89 | 430.89 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -430.89 | 430.89 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -430.89 | 430.89 |  |  | 0
| Material - Inventory | Material | Material - Inventory | 1620 |  |  | 223 |  |  |  |  | -17.13 | 17.13 |  |  | 1843
|  | Material Total |  | 1620 |  |  | 223 |  |  |  |  | -17.13 | 17.13 |  |  | 1843
| Material - Inventory Total |  |  | 1620 |  |  | 223 |  |  |  |  | -17.13 | 17.13 |  |  | 1843
| Material - Other | Material | Material - Other | 43380.07 | 47166.31 | 46008.65 | 100288.86 | -7616.3 | 39174.8 | 12983 | 155944.36 | 118138.05 | 299506.84 | 302042.02 | -4041.28 | 1152975.38
|  | Material Total |  | 43380.07 | 47166.31 | 46008.65 | 100288.86 | -7616.3 | 39174.8 | 12983 | 155944.36 | 118138.05 | 299506.84 | 302042.02 | -4041.28 | 1152975.38
| Material - Other Total |  |  | 43380.07 | 47166.31 | 46008.65 | 100288.86 | -7616.3 | 39174.8 | 12983 | 155944.36 | 118138.05 | 299506.84 | 302042.02 | -4041.28 | 1152975.38
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 8.25 | [5 empty] | 20.08 |  | 28.33
|  |  | ONE SOURCE DISTRIBUTORS INC |  | 12100 | [10 empty] | 12100
|  | Material - Direct Purchase Total |  |  | 12100 |  |  | 8.25 | [5 empty] | 20.08 |  | 12128.33
| Office & Office Support Products-DP Total |  |  |  | 12100 |  |  | 8.25 | [5 empty] | 20.08 |  | 12128.33
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | AGILE SOURCING PARTNERS INC |  |  | 54549 | 154280 | 77140 | 78242 | 15979 | [5 empty] | 380190
|  |  | Material Entries <$5,000 |  |  | 180 | 1525.66 |  | 562.2 |  |  |  | -2993.01 | 50 |  | -675.15
|  |  | ONE SOURCE DISTRIBUTORS INC | 20488.86 |  |  | 339139.11 |  |  | 5508.24 | 8214.7 |  |  |  |  | 373350.91
|  | Material - Direct Purchase Total |  | 20488.86 |  | 54729 | 494944.77 | 77140 | 78804.2 | 21487.24 | 8214.7 |  | -2993.01 | 50 |  | 752865.76
| Pole Line Hdwe & Connectors-DP Total |  |  | 20488.86 |  | 54729 | 494944.77 | 77140 | 78804.2 | 21487.24 | 8214.7 |  | -2993.01 | 50 |  | 752865.76
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | ON-RAMP WIRELESS, INC. |  | 13015 | [10 empty] | 13015
|  | Material - Direct Purchase Total |  |  | 13015 | [10 empty] | 13015
| Power Systems, Batteries and Light-DP Total |  |  |  | 13015 | [10 empty] | 13015
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | 6264 | [11 empty] | 6264
|  |  | Material Entries <$5,000 | [9 empty] | 3967.04 |  |  | 3967.04
|  | Material - Direct Purchase Total |  | 6264 | [8 empty] | 3967.04 |  |  | 10231.04
| Steel / Fabricated / Structural-DP Total |  |  | 6264 | [8 empty] | 3967.04 |  |  | 10231.04
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | COMEMSA | 44321.34 |  |  | 13595.26 | 12540.86 |  |  |  |  | 42200.42 |  |  | 112657.88
|  |  | Material Entries <$5,000 |  |  | -145.6 |  |  |  |  | -0.01 |  |  |  | -458478.48 | -458624.09
|  |  | SAE TOWERS | 298402.71 | 382303.4 | 349710.39 | 385777.75 | 34771.77 | 278916.11 | 101215.78 | 1442294.23 | 869415.79 | 2450228.69 | 3456242.98 | 18017.8 | 10067297.4
|  | Material - Direct Purchase Total |  | 342724.05 | 382303.4 | 349564.79 | 399373.01 | 47312.63 | 278916.11 | 101215.78 | 1442294.22 | 869415.79 | 2492429.11 | 3456242.98 | -440460.68 | 9721331.19
| Steel Lattice Towers (T/S)-DP Total |  |  | 342724.05 | 382303.4 | 349564.79 | 399373.01 | 47312.63 | 278916.11 | 101215.78 | 1442294.22 | 869415.79 | 2492429.11 | 3456242.98 | -440460.68 | 9721331.19
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 1521.62 | 855.67 | 938.03 | 492.1 | 371.7 | 624.36 | 189.54 | 389.38 | 2451.15 | 157.07 | 7990.62
|  |  | Transportation & Mobile Equip-DP |  |  |  |  | 8170.76 | [7 empty] | 8170.76
|  | Material - Direct Purchase Total |  |  |  | 1521.62 | 855.67 | 9108.79 | 492.1 | 371.7 | 624.36 | 189.54 | 389.38 | 2451.15 | 157.07 | 16161.38
| Transportation & Mobile Equip-DP Total |  |  |  |  | 1521.62 | 855.67 | 9108.79 | 492.1 | 371.7 | 624.36 | 189.54 | 389.38 | 2451.15 | 157.07 | 16161.38
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | 1625.52 | [11 empty] | 1625.52
|  |  | Wire, Cable & Bus Bar-DP | [11 empty] | 45184.1 | 45184.1
|  | Material - Direct Purchase Total |  | 1625.52 | [10 empty] | 45184.1 | 46809.62
| Wire, Cable & Bus Bar-DP Total |  |  | 1625.52 | [10 empty] | 45184.1 | 46809.62
2. Material Total |  |  |  | 424016.47 | 454584.71 | 451824.06 | 986653.56 | 125953.37 | 397387.21 | 136057.72 | 1607077.64 | 987295.36 | 2793747.38 | 3760806.23 | -399160.79 | 11726242.92
3. Construction | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  | 544.66 | 17.97 | [5 empty] | 7000 | 503.19 |  | 1000 | 9065.82
|  | Contract Total |  |  | 544.66 | 17.97 | [5 empty] | 7000 | 503.19 |  | 1000 | 9065.82
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  | 544.66 | 17.97 | [5 empty] | 7000 | 503.19 |  | 1000 | 9065.82
| Construction Management Services | Contract | Contract Entries <$50,000 |  | 1227.2 | [9 empty] | 257.6 | 1484.8
|  | Contract Total |  |  | 1227.2 | [9 empty] | 257.6 | 1484.8
| Construction Management Services Total |  |  |  | 1227.2 | [9 empty] | 257.6 | 1484.8
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [11 empty] | 13752.26 | 13752.26
|  | Contract Total | [12 empty] | 13752.26 | 13752.26
| Construction, Civil/Structural Total | [13 empty] | 13752.26 | 13752.26
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 | [7 empty] | 47074.48 |  |  |  |  | 47074.48
|  | Contract Total | [8 empty] | 47074.48 |  |  |  |  | 47074.48
| Decontamination & Waste Disposal Service Total | [9 empty] | 47074.48 |  |  |  |  | 47074.48
| Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 | [7 empty] | 38187.5 |  | 27600 | 13800 | 17250 | 96837.5
|  |  | HENKELS & MC COY INC | [6 empty] | 172500 | [5 empty] | 172500
|  |  | PAR ELECTRICAL CONTRACTORS INC | [6 empty] | 438643.8 |  | 826234.38 | 336572 | 2045638.82 | 1202863.42 | 4849952.42
|  | Contract Total | [7 empty] | 611143.8 | 38187.5 | 826234.38 | 364172 | 2059438.82 | 1220113.42 | 5119289.92
| Electrical Construction, Transmission Li Total | [8 empty] | 611143.8 | 38187.5 | 826234.38 | 364172 | 2059438.82 | 1220113.42 | 5119289.92
| ENGINEERING | Labor | Labor Entries <$5,000 | [10 empty] | 162.87 |  | 162.87
|  | Labor Total | [11 empty] | 162.87 |  | 162.87
| ENGINEERING Total | [12 empty] | 162.87 |  | 162.87
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 215.98 | 215.98
|  | Labor Total | [12 empty] | 215.98 | 215.98
| GRID OPS Total | [13 empty] | 215.98 | 215.98
| Labor - Other | Labor | ACQ/TRTP Seg. 6-Const/New Vincent-Duarte |  |  |  |  | 6902.2 | [6 empty] | 7093.69 | 13995.89
|  |  | Labor Entries <$5,000 | 5064.01 | 6718.73 | 419.13 | 3150.42 | 532.38 | 4154.97 | 1693.69 | 4297.42 | 3077.74 | 3779.68 | 2142.26 |  | 35030.43
|  | Labor Total |  | 5064.01 | 6718.73 | 419.13 | 3150.42 | 7434.58 | 4154.97 | 1693.69 | 4297.42 | 3077.74 | 3779.68 | 2142.26 | 7093.69 | 49026.32
| Labor - Other Total |  |  | 5064.01 | 6718.73 | 419.13 | 3150.42 | 7434.58 | 4154.97 | 1693.69 | 4297.42 | 3077.74 | 3779.68 | 2142.26 | 7093.69 | 49026.32
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  | 15402.45 | 7566.05 | 2052 |  |  | 7458.48 |  | 10370.97 |  |  |  | 42849.95
|  | Contract Total |  |  | 15402.45 | 7566.05 | 2052 |  |  | 7458.48 |  | 10370.97 |  |  |  | 42849.95
| Major Construction, Turnkey, Trans/Subs Total |  |  |  | 15402.45 | 7566.05 | 2052 |  |  | 7458.48 |  | 10370.97 |  |  |  | 42849.95
| Material - Other | Material | Material - Other |  |  |  | 43.17 | [8 empty] | 43.17
|  | Material Total |  |  |  |  | 43.17 | [8 empty] | 43.17
| Material - Other Total | [5 empty] | 43.17 | [8 empty] | 43.17
| Mechanical Services | Contract | Contract Entries <$50,000 | [5 empty] | 630 | 32323.8 | [5 empty] | 32953.8
|  | Contract Total | [6 empty] | 630 | 32323.8 | [5 empty] | 32953.8
| Mechanical Services Total | [7 empty] | 630 | 32323.8 | [5 empty] | 32953.8
| Other | Other | Other |  |  |  | 37500 |  |  | 10000 | 36500 | 9.99 |  | 36500 |  | 120509.99
|  | Other Total |  |  |  |  | 37500 |  |  | 10000 | 36500 | 9.99 |  | 36500 |  | 120509.99
| Other Total | [5 empty] | 37500 |  |  | 10000 | 36500 | 9.99 |  | 36500 |  | 120509.99
| Security / Protection Services | Contract | CAPSTONE FIRE MANAGEMENT, INC. | [9 empty] | 58680 |  |  | 58680
|  |  | Contract Entries <$50,000 | [7 empty] | 2281 | 7701.06 | 1252.8 |  | 61125.25 | 72360.11
|  | Contract Total | [8 empty] | 2281 | 7701.06 | 59932.8 |  | 61125.25 | 131040.11
| Security / Protection Services Total | [9 empty] | 2281 | 7701.06 | 59932.8 |  | 61125.25 | 131040.11
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 |  | 1417.53 | 1313.16 |  | 3759.86 |  |  | 925 | 925 | 925 | 2775 | 925 | 12965.55
|  | Contract Total |  |  | 1417.53 | 1313.16 |  | 3759.86 |  |  | 925 | 925 | 925 | 2775 | 925 | 12965.55
| Short Term Equipment Rent Total |  |  |  | 1417.53 | 1313.16 |  | 3759.86 |  |  | 925 | 925 | 925 | 2775 | 925 | 12965.55
| TRANSMISSION | Labor | Labor Entries <$5,000 |  | 6906.83 | 4701.91 | 288.68 | 590.33 | 3341.08 | 4184.89 | 6743.17 | 5903.02 | 5711.28 | 3907.89 | 12234.42 | 54513.5
|  |  | TRANSMISSION / Patroman Sr |  | 5781.7 |  |  |  |  | 6627.47 | 7564.23 |  |  | 5792.64 |  | 25766.04
|  | Labor Total |  |  | 12688.53 | 4701.91 | 288.68 | 590.33 | 3341.08 | 10812.36 | 14307.4 | 5903.02 | 5711.28 | 9700.53 | 12234.42 | 80279.54
| TRANSMISSION Total |  |  |  | 12688.53 | 4701.91 | 288.68 | 590.33 | 3341.08 | 10812.36 | 14307.4 | 5903.02 | 5711.28 | 9700.53 | 12234.42 | 80279.54
| TRNS CAPITAL | Labor | Cnst/Mtrl Cndtr |  |  |  | 5020.56 |  | 5846.31 |  | 6606 |  |  | 5813.28 |  | 23286.15
|  |  | Labor Entries <$5,000 | 5375.3 | 5109.39 | 5129.97 | 786.38 | 5429.81 | 665.89 | 5049.07 | 762.72 | 5161.27 | 5125.66 | 663.59 |  | 39259.05
|  | Labor Total |  | 5375.3 | 5109.39 | 5129.97 | 5806.94 | 5429.81 | 6512.2 | 5049.07 | 7368.72 | 5161.27 | 5125.66 | 6476.87 |  | 62545.2
| TRNS CAPITAL Total |  |  | 5375.3 | 5109.39 | 5129.97 | 5806.94 | 5429.81 | 6512.2 | 5049.07 | 7368.72 | 5161.27 | 5125.66 | 6476.87 |  | 62545.2
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 |  | 41 | 41 |  | 82 |  |  |  | 41 | 41 |  | 41 | 287
|  | Labor Total |  |  | 41 | 41 |  | 82 |  |  |  | 41 | 41 |  | 41 | 287
| TSD-HERC - Rental Total |  |  |  | 41 | 41 |  | 82 |  |  |  | 41 | 41 |  | 41 | 287
3. Construction Total |  |  |  | 10439.31 | 43149.49 | 19189.19 | 48841.21 | 17296.58 | 14638.25 | 678481.2 | 150941.52 | 866424.43 | 440190.61 | 2117196.35 | 1316758.62 | 5723546.76
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -137247.09 | 29608.27 | 20779.84 | 20515.88 | 14613.88 | 26583.8 | 32602.1 | 10870.72 | 32249.27 | -28489.12 | 25082.27 | -25658.79 | 21511.03
|  |  | PGSP-TRTP Segment 6 - MPO | [5 empty] | 5322.7 |  | 7750.68 |  | 12763.37 | 9822.46 | 10642.1 | 46301.31
|  |  | PROCUREMENT TDBU | 5847.12 | 5388.85 | 8007.52 | 9585.54 |  |  | 14523.84 | 14104.01 |  | 52378.48 | 43208.46 | 15788.34 | 168832.16
|  |  | TDBU Vehicle Cost | [9 empty] | 9672.39 |  |  | 9672.39
|  |  | TRTP 6 New Vincent Duarte 500 kV | 107494.22 | 256998.71 | 423646.71 | 388762.43 | 1044469.13 | 575240.86 | 828285.68 | 1023747.07 |  | 1120967.28 | 1234831.26 | 1717969.89 | 8722413.24
|  |  | Work Package # 2 | 28989.85 | 52726.07 | 79658.48 | 73830.7 | 55590.48 | 60102.27 | 94492.55 | 98037.43 | 116526.27 | 79849.48 | 120363.94 | 161586.54 | 1021754.06
|  | Chargeback Total |  | 5084.1 | 344721.9 | 532092.55 | 492694.55 | 1114673.49 | 667249.63 | 969904.17 | 1154509.91 | 148775.54 | 1247141.88 | 1433308.39 | 1880328.08 | 9990484.19
| Chargebacks Total |  |  | 5084.1 | 344721.9 | 532092.55 | 492694.55 | 1114673.49 | 667249.63 | 969904.17 | 1154509.91 | 148775.54 | 1247141.88 | 1433308.39 | 1880328.08 | 9990484.19
| Labor - Other | Labor | Division Overhead | 17447.95 | 26776.61 | 44366.8 | 44539.43 | 26125.91 | 19366.91 | 91688.54 | 87888.08 |  | 429688.21 | 66172.63 | 25410.45 | 879471.52
|  |  | Labor Entries <$5,000 | 6852.1 | 7697.88 | 2586.48 | 4134.76 | 6634.97 | 5538.27 | 4526.76 | 6964.77 | -93002.75 | 11680.53 | 6313.98 | 10824.93 | -19247.32
|  |  | Paid Absence | 6307.54 | 6166.23 | 5791.51 | 6177.14 | 7001.75 | 5504.06 | 6475.2 | 10775.69 |  | 33176.18 | 7282.34 | 9448.39 | 104106.03
|  | Labor Total |  | 30607.59 | 40640.72 | 52744.79 | 54851.33 | 39762.63 | 30409.24 | 102690.5 | 105628.54 | -93002.75 | 474544.92 | 79768.95 | 45683.77 | 964330.23
| Labor - Other Total |  |  | 30607.59 | 40640.72 | 52744.79 | 54851.33 | 39762.63 | 30409.24 | 102690.5 | 105628.54 | -93002.75 | 474544.92 | 79768.95 | 45683.77 | 964330.23
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -99784.59 | 99784.59 |  |  | 0
|  | Overhead Total | [9 empty] | -99784.59 | 99784.59 |  |  | 0
| Overhead Correction Total | [10 empty] | -99784.59 | 99784.59 |  |  | 0
4. Allocated Total |  |  |  | 35691.69 | 385362.62 | 584837.34 | 547545.88 | 1154436.12 | 697658.87 | 1072594.67 | 1260138.45 | -44011.8 | 1821471.39 | 1513077.34 | 1926011.85 | 10954814.42
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 298281.83 | 18753.72 | [6 empty] | 527576.96 | 844612.51
|  |  | Capitalized Overhead - A&G | 56770.29 | 40574.21 | 70059.93 | 79108.21 | 162356.15 | 46808.97 | 120039.58 | 104537.68 | 118429.16 | 147237.83 | 222250.97 | 123412.81 | 1291585.79
|  |  | Capitalized Overhead - Inj & Damages | 442.96 | 1197.01 | 731.94 | 1019.83 | 3204.57 | 752.91 | 443.94 | 2574.86 | 5169.44 | -2637.94 | 6750.46 | 986.59 | 20636.57
|  |  | Capitalized Overhead - P&B/Payroll Tax | 47081.17 | 95325.72 | 64228.46 | 91924.46 | 105229.05 | 86388.55 | 108623.07 | 108881.23 | -99317.96 | 126457.95 | 84119.18 | 231342.26 | 1050283.14
|  | Non Budgeted Total |  | 104294.42 | 137096.94 | 135020.33 | 470334.33 | 289543.49 | 133950.43 | 229106.59 | 215993.77 | 24280.64 | 271057.84 | 313120.61 | 883318.62 | 3207118.01
| Non Budget - Other Total |  |  | 104294.42 | 137096.94 | 135020.33 | 470334.33 | 289543.49 | 133950.43 | 229106.59 | 215993.77 | 24280.64 | 271057.84 | 313120.61 | 883318.62 | 3207118.01
5. Corporate Overhead Total |  |  |  | 104294.42 | 137096.94 | 135020.33 | 470334.33 | 289543.49 | 133950.43 | 229106.59 | 215993.77 | 24280.64 | 271057.84 | 313120.61 | 883318.62 | 3207118.01
Grand Total |  |  |  | 967720.95 | 1905613.08 | 2629746.54 | 2673104.5 | 1820902.62 | 2194740.05 | 3406899.22 | 4167749.32 | 6173649.63 | 3050350.6 | 10006200.82 | 6669824.1 | 45666501.43

## 800051930
Pin: 5243 | Project: TRTP Segment 6
Order: 800051930 | 800051930- 9219-5080 - TRTP Segment 6
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 9.6 |  | -0.04 |  |  |  | 0.12 |  |  |  | 0.02 |  | 9.7
|  | Contract Total |  | 9.6 |  | -0.04 |  |  |  | 0.12 |  |  |  | 0.02 |  | 9.7
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 9.6 |  | -0.04 |  |  |  | 0.12 |  |  |  | 0.02 |  | 9.7
| HRealProp | Labor | Labor Entries <$5,000 | 22.85 | 307.58 |  | 145.5 |  |  |  | 267.94 |  |  |  |  | 743.87
|  | Labor Total |  | 22.85 | 307.58 |  | 145.5 |  |  |  | 267.94 |  |  |  |  | 743.87
| HRealProp Total |  |  | 22.85 | 307.58 |  | 145.5 |  |  |  | 267.94 |  |  |  |  | 743.87
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -9.47 | -7.75 | [5 empty] | -120 | 120 |  |  | -17.22
|  | IMM Correction Total |  |  | -9.47 | -7.75 | [5 empty] | -120 | 120 |  |  | -17.22
| IMM/Allocated - Correction Total |  |  |  | -9.47 | -7.75 | [5 empty] | -120 | 120 |  |  | -17.22
| Information System Professional Services | Contract | Contract Entries <$50,000 |  | 29.79 | -63.8 | [9 empty] | -34.01
|  | Contract Total |  |  | 29.79 | -63.8 | [9 empty] | -34.01
| Information System Professional Services Total |  |  |  | 29.79 | -63.8 | [9 empty] | -34.01
| Labor - Other | Labor | Labor Entries <$5,000 | 148.23 | 145.16 | 177.36 | 75.07 | 82.9 | 15.33 | 19.51 | 64.1 | 15.34 | 11.81 | 12.36 | 50.36 | 817.53
|  | Labor Total |  | 148.23 | 145.16 | 177.36 | 75.07 | 82.9 | 15.33 | 19.51 | 64.1 | 15.34 | 11.81 | 12.36 | 50.36 | 817.53
| Labor - Other Total |  |  | 148.23 | 145.16 | 177.36 | 75.07 | 82.9 | 15.33 | 19.51 | 64.1 | 15.34 | 11.81 | 12.36 | 50.36 | 817.53
| Other | Other | Other | 343.26 | 1187.53 | 3.76 | 39.95 |  | 36539.11 |  |  | 120 | -120 |  |  | 38113.61
|  | Other Total |  | 343.26 | 1187.53 | 3.76 | 39.95 |  | 36539.11 |  |  | 120 | -120 |  |  | 38113.61
| Other Total |  |  | 343.26 | 1187.53 | 3.76 | 39.95 |  | 36539.11 |  |  | 120 | -120 |  |  | 38113.61
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1045.44 | [11 empty] | 1045.44
|  | Contract Total |  | 1045.44 | [11 empty] | 1045.44
| Temporary/Supplementary - Trade/Labor Total |  |  | 1045.44 | [11 empty] | 1045.44
1. Project Support Total |  |  |  | 1569.38 | 1660.59 | 109.53 | 260.52 | 82.9 | 36554.44 | 19.63 | 332.04 | 15.34 | 11.81 | 12.38 | 50.36 | 40678.92
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  |  | 40 | [9 empty] | 40
|  | Material - Direct Purchase Total |  |  |  | 40 | [9 empty] | 40
| Building, Shop & Industrial Products/Eqp Total |  |  |  |  | 40 | [9 empty] | 40
| Material - Other | Material | Material - Other |  |  | 3.5 | [9 empty] | 3.5
|  | Material Total |  |  |  | 3.5 | [9 empty] | 3.5
| Material - Other Total |  |  |  |  | 3.5 | [9 empty] | 3.5
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 11.8 | [9 empty] | 11.8
|  | Material - Direct Purchase Total |  |  |  | 11.8 | [9 empty] | 11.8
| Transportation & Mobile Equip-DP Total |  |  |  |  | 11.8 | [9 empty] | 11.8
2. Material Total | [5 empty] | 55.3 | [9 empty] | 55.3
3. Construction | HRealProp | Labor | Labor Entries <$5,000 | 186.39 | [11 empty] | 186.39
|  | Labor Total |  | 186.39 | [11 empty] | 186.39
| HRealProp Total |  |  | 186.39 | [11 empty] | 186.39
3. Construction Total |  |  |  | 186.39 | [11 empty] | 186.39
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 9.47 | 7.75 | -0.03 |  | -120 | [7 empty] | -102.81
|  | Chargeback Total |  | 9.47 | 7.75 | -0.03 |  | -120 | [7 empty] | -102.81
| Chargebacks Total |  |  | 9.47 | 7.75 | -0.03 |  | -120 | [7 empty] | -102.81
| Labor - Other | Labor | Labor Entries <$5,000 | 81.56 | 94.45 | -0.06 | 32.96 | -0.41 | 0.06 | 0.01 | 58.77 | 1.16 | 0.08 | 0.08 | 0.33 | 268.99
|  | Labor Total |  | 81.56 | 94.45 | -0.06 | 32.96 | -0.41 | 0.06 | 0.01 | 58.77 | 1.16 | 0.08 | 0.08 | 0.33 | 268.99
| Labor - Other Total |  |  | 81.56 | 94.45 | -0.06 | 32.96 | -0.41 | 0.06 | 0.01 | 58.77 | 1.16 | 0.08 | 0.08 | 0.33 | 268.99
4. Allocated Total |  |  |  | 91.03 | 102.2 | -0.09 | 32.96 | -120.41 | 0.06 | 0.01 | 58.77 | 1.16 | 0.08 | 0.08 | 0.33 | 166.18
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 5540.49 | 336.69 | [6 empty] | 5955.68 | 11832.86
|  | Non Budgeted Total |  |  |  |  | 5540.49 | 336.69 | [6 empty] | 5955.68 | 11832.86
| Non Budget - Other Total | [5 empty] | 5540.49 | 336.69 | [6 empty] | 5955.68 | 11832.86
5. Corporate Overhead Total | [6 empty] | 5540.49 | 336.69 | [6 empty] | 5955.68 | 11832.86
Grand Total |  |  |  | 1846.8 | 1762.79 | 164.74 | 5833.97 | 299.18 | 36554.5 | 19.64 | 390.81 | 16.5 | 11.89 | 12.46 | 6006.37 | 52919.65

## TRTP Seg 7
WO | SumOfYTD2012 | Order | Project
800218138- I: TRTP 7-3: ANTELOPE-MESA 230KV T/L: CO | 41754342.63 | 800218138 | TRTP Segment 7
800218130- 03/28/20142: VINCENT-RIO HONDO #2: CONST | 4142649.19 | 800218130 | TRTP Segment 7
800051909- 9219-2378 - TRTP Segment 7 | 21536.98 | 800051909 | TRTP Segment 7

## 800218138
Pin: 6438 | Project: TRTP Segment 7
Order: 800218138 | 800218138- I: TRTP 7-3: ANTELOPE-MESA 230KV T/L: CO
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total | Grand Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [6 empty] | 292.38 | [5 empty] | 292.38 | 292.38
|  | Labor Total | [7 empty] | 292.38 | [5 empty] | 292.38 | 292.38
| BP&FM Total | [8 empty] | 292.38 | [5 empty] | 292.38 | 292.38
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 |  |  | 75 | [9 empty] | 75 | 75
|  | Contract Total |  |  |  | 75 | [9 empty] | 75 | 75
| Building/Facility Repairs & Maintenance Total |  |  |  |  | 75 | [9 empty] | 75 | 75
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 2955239.34 |  |  | 2955239.34 | 2955239.34
|  |  | Contract Entries <$50,000 | [8 empty] | -2955239.34 |  |  |  | -2955239.34 | -2955239.34
|  | Contract Total | [9 empty] | -2955239.34 | 2955239.34 |  |  | 0 | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -2955239.34 | 2955239.34 |  |  | 0 | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 4300.06 | 4300.06 | 4300.06
|  | Labor Total | [12 empty] | 4300.06 | 4300.06 | 4300.06
| ELEC SYS PLANNING Total | [13 empty] | 4300.06 | 4300.06 | 4300.06
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 349.24 | 347 |  | 182.96 | 1068.92 | [7 empty] | 1948.12 | 1948.12
|  | Labor Total |  | 349.24 | 347 |  | 182.96 | 1068.92 | [7 empty] | 1948.12 | 1948.12
| ENG ADVANCEMENT Total |  |  | 349.24 | 347 |  | 182.96 | 1068.92 | [7 empty] | 1948.12 | 1948.12
| ENGINEERING | Labor | Engineer |  |  | 5153.62 |  |  |  |  | 5160.98 |  |  |  |  | 10314.6 | 10314.6
|  |  | Labor Entries <$5,000 | 5893.7 | 5578.81 | 5164.31 | 8466.46 | 8340.93 | 8269.8 | 4889.07 | 4402.67 | 6494.75 | 6269.81 | 5794.86 |  | 69565.17 | 69565.17
|  | Labor Total |  | 5893.7 | 5578.81 | 10317.93 | 8466.46 | 8340.93 | 8269.8 | 4889.07 | 9563.65 | 6494.75 | 6269.81 | 5794.86 |  | 79879.77 | 79879.77
| ENGINEERING Total |  |  | 5893.7 | 5578.81 | 10317.93 | 8466.46 | 8340.93 | 8269.8 | 4889.07 | 9563.65 | 6494.75 | 6269.81 | 5794.86 |  | 79879.77 | 79879.77
| Engineering/Technical Professional Servi | Contract | BUREAU VERITAS NORTH AMERICA INC |  |  | 55909.63 |  | 83972.5 | [7 empty] | 139882.13 | 139882.13
|  |  | BURNS & MC DONNELL INC | 642436 | 284970 | 267251 | 280181 | 313863 |  | 522419 | 271378 | 171994 | 180827 | 222790 | 406869.86 | 3564978.86 | 3564978.86
|  |  | Contract Entries <$50,000 |  | 74943.64 | 35968.93 |  | 27516 | 792.25 | 171428.01 | 15837.88 | 19078.02 | 49081.6 | 74839.18 | 110801.63 | 580287.14 | 580287.14
|  |  | CONVERSE CONSULTANTS | [11 empty] | 60515.29 | 60515.29 | 60515.29
|  |  | ELECTRICAL CONSULTANTS INC | [8 empty] | 79895.42 |  | 52838.76 |  | 132734.18 | 132734.18
|  | Contract Total |  | 642436 | 359913.64 | 359129.56 | 280181 | 425351.5 | 792.25 | 693847.01 | 287215.88 | 270967.44 | 229908.6 | 350467.94 | 578186.78 | 4478397.6 | 4478397.6
| Engineering/Technical Professional Servi Total |  |  | 642436 | 359913.64 | 359129.56 | 280181 | 425351.5 | 792.25 | 693847.01 | 287215.88 | 270967.44 | 229908.6 | 350467.94 | 578186.78 | 4478397.6 | 4478397.6
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 12025.97 | 18729.6 | 13354.23 | 7003.85 | 18349.84 | 12945.44 | 8332.77 | 11530.97 | 9510.23 | 6994.66 | 26036.24 | 144813.8 | 144813.8
|  | Contract Total |  |  | 12025.97 | 18729.6 | 13354.23 | 7003.85 | 18349.84 | 12945.44 | 8332.77 | 11530.97 | 9510.23 | 6994.66 | 26036.24 | 144813.8 | 144813.8
| Environmental/Safety Professional Servic Total |  |  |  | 12025.97 | 18729.6 | 13354.23 | 7003.85 | 18349.84 | 12945.44 | 8332.77 | 11530.97 | 9510.23 | 6994.66 | 26036.24 | 144813.8 | 144813.8
| HRealProp | Labor | Labor Entries <$5,000 |  | -270.9 | [10 empty] | -270.9 | -270.9
|  | Labor Total |  |  | -270.9 | [10 empty] | -270.9 | -270.9
| HRealProp Total |  |  |  | -270.9 | [10 empty] | -270.9 | -270.9
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 26004.23 | 13489.04 | 20044.83 | -8169.11 | -10569.82 | 21666.54 | -11528.67 | 11407.58 | 3054836.21 | -3039855.95 | -44762.76 | -3231.84 | 29330.28 | 29330.28
|  | IMM Correction Total |  | 26004.23 | 13489.04 | 20044.83 | -8169.11 | -10569.82 | 21666.54 | -11528.67 | 11407.58 | 3054836.21 | -3039855.95 | -44762.76 | -3231.84 | 29330.28 | 29330.28
| IMM/Allocated - Correction Total |  |  | 26004.23 | 13489.04 | 20044.83 | -8169.11 | -10569.82 | 21666.54 | -11528.67 | 11407.58 | 3054836.21 | -3039855.95 | -44762.76 | -3231.84 | 29330.28 | 29330.28
| Labor - Other | Labor | Labor - Other | [9 empty] | 19045.39 |  |  | 19045.39 | 19045.39
|  |  | Labor Correction | [9 empty] | 94753.5 |  |  | 94753.5 | 94753.5
|  |  | Labor Entries <$5,000 | 739.66 | 3582.36 | 188.64 | 3246.19 | 4059.11 | -1317.66 | 2164.53 | 2127.99 | -114752.2 | 5646.22 | 1011.61 | 2162.08 | -91141.47 | -91141.47
|  | Labor Total |  | 739.66 | 3582.36 | 188.64 | 3246.19 | 4059.11 | -1317.66 | 2164.53 | 2127.99 | -114752.2 | 119445.11 | 1011.61 | 2162.08 | 22657.42 | 22657.42
| Labor - Other Total |  |  | 739.66 | 3582.36 | 188.64 | 3246.19 | 4059.11 | -1317.66 | 2164.53 | 2127.99 | -114752.2 | 119445.11 | 1011.61 | 2162.08 | 22657.42 | 22657.42
| Other | Other | Other | -229160.17 | 3614239.99 | -4063149.97 | 989384.4 | 3429455.88 | -2066028.19 | 1819216.44 | 184251.43 | -135537.38 | -2592962.99 | 1225752.93 | -639137.48 | 1536324.89 | 1536324.89
|  | Other Total |  | -229160.17 | 3614239.99 | -4063149.97 | 989384.4 | 3429455.88 | -2066028.19 | 1819216.44 | 184251.43 | -135537.38 | -2592962.99 | 1225752.93 | -639137.48 | 1536324.89 | 1536324.89
| Other Total |  |  | -229160.17 | 3614239.99 | -4063149.97 | 989384.4 | 3429455.88 | -2066028.19 | 1819216.44 | 184251.43 | -135537.38 | -2592962.99 | 1225752.93 | -639137.48 | 1536324.89 | 1536324.89
| SC&M | Labor | Labor Entries <$5,000 | [9 empty] | 177.19 | 158.31 | 226.96 | 562.46 | 562.46
|  | Labor Total | [10 empty] | 177.19 | 158.31 | 226.96 | 562.46 | 562.46
| SC&M Total | [11 empty] | 177.19 | 158.31 | 226.96 | 562.46 | 562.46
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -95246.2 |  |  |  | -95246.2 | -95246.2
|  |  | Temporary / Supplemental - Correction | [9 empty] | 95246.2 |  |  | 95246.2 | 95246.2
|  | Contract Total | [9 empty] | -95246.2 | 95246.2 |  |  | 0 | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -95246.2 | 95246.2 |  |  | 0 | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 544.81 | 1124.45 | 1906.4 | 1194.82 | 8223.61 | 466 |  | 14086.04 | 159.96 | 146.08 | 146.08 | 292.16 | 28290.41 | 28290.41
|  | Contract Total |  | 544.81 | 1124.45 | 1906.4 | 1194.82 | 8223.61 | 466 |  | 14086.04 | 159.96 | 146.08 | 146.08 | 292.16 | 28290.41 | 28290.41
| Temporary/Supplementary - Trade/Labor Total |  |  | 544.81 | 1124.45 | 1906.4 | 1194.82 | 8223.61 | 466 |  | 14086.04 | 159.96 | 146.08 | 146.08 | 292.16 | 28290.41 | 28290.41
| TRANSMISSION | Labor | Labor Entries <$5,000 | 599.29 | 448.32 | 969.68 | [8 empty] | 129.66 | 2146.95 | 2146.95
|  | Labor Total |  | 599.29 | 448.32 | 969.68 | [8 empty] | 129.66 | 2146.95 | 2146.95
| TRANSMISSION Total |  |  | 599.29 | 448.32 | 969.68 | [8 empty] | 129.66 | 2146.95 | 2146.95
| TRNS CAPITAL | Labor | Labor Entries <$5,000 |  |  | 666.45 | 522.27 | 619.57 | 774.37 | 721.49 | 411.2 | 1083.71 | 1232.51 | 1314.38 |  | 7345.95 | 7345.95
|  | Labor Total |  |  |  | 666.45 | 522.27 | 619.57 | 774.37 | 721.49 | 411.2 | 1083.71 | 1232.51 | 1314.38 |  | 7345.95 | 7345.95
| TRNS CAPITAL Total |  |  |  |  | 666.45 | 522.27 | 619.57 | 774.37 | 721.49 | 411.2 | 1083.71 | 1232.51 | 1314.38 |  | 7345.95 | 7345.95
| VRZN BUS TELECONF | Labor | Labor Entries <$5,000 |  |  |  |  | 440.2 | 175.58 |  | 142.96 |  |  |  | 69.75 | 828.49 | 828.49
|  | Labor Total | [5 empty] | 440.2 | 175.58 |  | 142.96 |  |  |  | 69.75 | 828.49 | 828.49
| VRZN BUS TELECONF Total | [6 empty] | 440.2 | 175.58 |  | 142.96 |  |  |  | 69.75 | 828.49 | 828.49
1. Project Support Total |  |  |  | 447406.76 | 4010478.68 | -3651121.88 | 1288363.22 | 3873993.75 | -2016851.47 | 2522547.69 | 517539.5 | 44297.92 | -2215643.87 | 1546878.01 | -30965.63 | 6336922.68 | 6336922.68
2. Material | Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | ONESOURCE SUPPLY SOLUTIONS, LLC |  |  |  | 10152 | [8 empty] | 10152 | 10152
|  | Material - Direct Purchase Total |  |  |  |  | 10152 | [8 empty] | 10152 | 10152
| Fuels, Chemicals & Petrochem-DP Total | [5 empty] | 10152 | [8 empty] | 10152 | 10152
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -146.46 | 146.46 |  |  | 0 | 0
|  | Material - Direct Purchase Total | [9 empty] | -146.46 | 146.46 |  |  | 0 | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -146.46 | 146.46 |  |  | 0 | 0
| Material - Inventory | Material | Material - Inventory |  | 364.5 | 16.2 | [5 empty] | -16.13 | 16.13 |  |  | 380.7 | 380.7
|  | Material Total |  |  | 364.5 | 16.2 | [5 empty] | -16.13 | 16.13 |  |  | 380.7 | 380.7
| Material - Inventory Total |  |  |  | 364.5 | 16.2 | [5 empty] | -16.13 | 16.13 |  |  | 380.7 | 380.7
| Material - Other | Material | Material - Other | 2190.64 | -115439.99 | 13155.75 | 14616.8 | -6038.87 | 28159.71 | 32611.74 | 79533.51 | -5.56 | 8197.72 | 11496.42 | 93973.85 | 162451.72 | 162451.72
|  | Material Total |  | 2190.64 | -115439.99 | 13155.75 | 14616.8 | -6038.87 | 28159.71 | 32611.74 | 79533.51 | -5.56 | 8197.72 | 11496.42 | 93973.85 | 162451.72 | 162451.72
| Material - Other Total |  |  | 2190.64 | -115439.99 | 13155.75 | 14616.8 | -6038.87 | 28159.71 | 32611.74 | 79533.51 | -5.56 | 8197.72 | 11496.42 | 93973.85 | 162451.72 | 162451.72
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | AGILE SOURCING PARTNERS INC |  | 19836 |  |  |  |  | 87058 | 168606 |  |  | 8265 | 32509 | 316274 | 316274
|  |  | Material Entries <$5,000 |  |  |  | 2688.66 |  | -265.66 |  | 2350 |  |  |  |  | 4773 | 4773
|  |  | ONE SOURCE DISTRIBUTORS INC |  |  |  | 19120.88 | 16147.69 | 257292.09 |  | 42764 |  |  |  |  | 335324.66 | 335324.66
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [9 empty] | 11019.23 | 8951.25 |  | 19970.48 | 19970.48
|  | Material - Direct Purchase Total |  |  | 19836 |  | 21809.54 | 16147.69 | 257026.43 | 87058 | 213720 |  | 11019.23 | 17216.25 | 32509 | 676342.14 | 676342.14
| Pole Line Hdwe & Connectors-DP Total |  |  |  | 19836 |  | 21809.54 | 16147.69 | 257026.43 | 87058 | 213720 |  | 11019.23 | 17216.25 | 32509 | 676342.14 | 676342.14
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | ON-RAMP WIRELESS, INC. |  |  | 117135 | 104120 | 78090 |  | 39045 | [5 empty] | 338390 | 338390
|  |  | TWR LIGHTING, INC. | 15750 | 20950 | [10 empty] | 36700 | 36700
|  | Material - Direct Purchase Total |  | 15750 | 20950 | 117135 | 104120 | 78090 |  | 39045 | [5 empty] | 375090 | 375090
| Power Systems, Batteries and Light-DP Total |  |  | 15750 | 20950 | 117135 | 104120 | 78090 |  | 39045 | [5 empty] | 375090 | 375090
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | 14450 | 62880 | [10 empty] | 77330 | 77330
|  | Material - Direct Purchase Total |  | 14450 | 62880 | [10 empty] | 77330 | 77330
| Steel / Fabricated / Structural-DP Total |  |  | 14450 | 62880 | [10 empty] | 77330 | 77330
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | Material Entries <$5,000 |  | -1108225.35 |  | -5982.96 |  |  | 134896.44 |  |  |  |  | 784305 | -195006.87 | -195006.87
|  |  | Steel Lattice Towers (T/S)-DP | [11 empty] | 458478.48 | 458478.48 | 458478.48
|  | Material - Direct Purchase Total |  |  | -1108225.35 |  | -5982.96 |  |  | 134896.44 |  |  |  |  | 1242783.48 | 263471.61 | 263471.61
| Steel Lattice Towers (T/S)-DP Total |  |  |  | -1108225.35 |  | -5982.96 |  |  | 134896.44 |  |  |  |  | 1242783.48 | 263471.61 | 263471.61
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 361.34 | 830.14 | 835.13 | 423.52 | 3288.64 | 189 | 124.6 | 130.43 | 199.39 | 67.96 | 580.13 | 131.04 | 7161.32 | 7161.32
|  |  | Transportation & Mobile Equip-DP |  |  |  |  | 5850 | [7 empty] | 5850 | 5850
|  | Material - Direct Purchase Total |  | 361.34 | 830.14 | 835.13 | 423.52 | 9138.64 | 189 | 124.6 | 130.43 | 199.39 | 67.96 | 580.13 | 131.04 | 13011.32 | 13011.32
| Transportation & Mobile Equip-DP Total |  |  | 361.34 | 830.14 | 835.13 | 423.52 | 9138.64 | 189 | 124.6 | 130.43 | 199.39 | 67.96 | 580.13 | 131.04 | 13011.32 | 13011.32
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 100.5 |  |  |  |  | 100.5 | 100.5
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [6 empty] | 47427.96 | [5 empty] | 47427.96 | 47427.96
|  |  | SOUTHWIRE COMPANY | [7 empty] | 514206 |  | 57134 | 114268 |  | 685608 | 685608
|  | Material - Direct Purchase Total | [7 empty] | 47427.96 | 514306.5 |  | 57134 | 114268 |  | 733136.46 | 733136.46
| Wire, Cable & Bus Bar-DP Total | [8 empty] | 47427.96 | 514306.5 |  | 57134 | 114268 |  | 733136.46 | 733136.46
2. Material Total |  |  |  | 32751.98 | -1118804.7 | 131142.08 | 145138.9 | 97337.46 | 285375.14 | 341163.74 | 807690.44 | 31.24 | 76581.5 | 143560.8 | 1369397.37 | 2311365.95 | 2311365.95
3. Construction | Elect Construction, Distribution | Contract | Contract Entries <$50,000 |  | 18612 | [10 empty] | 18612 | 18612
|  | Contract Total |  |  | 18612 | [10 empty] | 18612 | 18612
| Elect Construction, Distribution Total |  |  |  | 18612 | [10 empty] | 18612 | 18612
| Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 |  |  |  | 0 | [5 empty] | -1 |  |  | -1 | -1
|  |  | WILSON UTILITY CONSTRUCTION | 1064679 | 1514992 | 4679968 | 5116203 |  | 4519532.51 |  | 1844989 |  | 3423818.55 |  | 1708128 | 23872310.06 | 23872310.06
|  | Contract Total |  | 1064679 | 1514992 | 4679968 | 5116203 |  | 4519532.51 |  | 1844989 |  | 3423817.55 |  | 1708128 | 23872309.06 | 23872309.06
| Electrical Construction, Transmission Li Total |  |  | 1064679 | 1514992 | 4679968 | 5116203 |  | 4519532.51 |  | 1844989 |  | 3423817.55 |  | 1708128 | 23872309.06 | 23872309.06
| ENGINEERING | Labor | Labor Entries <$5,000 | 84.7 | [11 empty] | 84.7 | 84.7
|  | Labor Total |  | 84.7 | [11 empty] | 84.7 | 84.7
| ENGINEERING Total |  |  | 84.7 | [11 empty] | 84.7 | 84.7
| Labor - Other | Labor | ACQ/TRTP Seg. 7-Const/Antelope-Mesa | 8683.3 | 7429.86 |  |  | 5163.63 | [7 empty] | 21276.79 | 21276.79
|  |  | Labor Entries <$5,000 | 2526.17 | 3652.51 | 5596.09 | 5028.76 | 2742.6 | 5047.11 | 4276.26 | 3612.66 | 128551.6 | -122632.56 | 2121.54 | 3912.94 | 44435.68 | 44435.68
|  | Labor Total |  | 11209.47 | 11082.37 | 5596.09 | 5028.76 | 7906.23 | 5047.11 | 4276.26 | 3612.66 | 128551.6 | -122632.56 | 2121.54 | 3912.94 | 65712.47 | 65712.47
| Labor - Other Total |  |  | 11209.47 | 11082.37 | 5596.09 | 5028.76 | 7906.23 | 5047.11 | 4276.26 | 3612.66 | 128551.6 | -122632.56 | 2121.54 | 3912.94 | 65712.47 | 65712.47
| Material - Other | Material | Material - Other | [8 empty] | 8.81 |  |  |  | 8.81 | 8.81
|  | Material Total | [9 empty] | 8.81 |  |  |  | 8.81 | 8.81
| Material - Other Total | [10 empty] | 8.81 |  |  |  | 8.81 | 8.81
| Other | Other | Other | 66.59 |  | 201.26 | 103.53 | 34.99 |  |  | 18.04 |  |  |  |  | 424.41 | 424.41
|  | Other Total |  | 66.59 |  | 201.26 | 103.53 | 34.99 |  |  | 18.04 |  |  |  |  | 424.41 | 424.41
| Other Total |  |  | 66.59 |  | 201.26 | 103.53 | 34.99 |  |  | 18.04 |  |  |  |  | 424.41 | 424.41
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 863.93 | 1719.18 | 1874.7 | 1297.83 |  |  |  | 1286.78 |  |  |  |  | 7042.42 | 7042.42
|  | Labor Total |  | 863.93 | 1719.18 | 1874.7 | 1297.83 |  |  |  | 1286.78 |  |  |  |  | 7042.42 | 7042.42
| TRNS CAPITAL Total |  |  | 863.93 | 1719.18 | 1874.7 | 1297.83 |  |  |  | 1286.78 |  |  |  |  | 7042.42 | 7042.42
3. Construction Total |  |  |  | 1076903.69 | 1546405.55 | 4687640.05 | 5122633.12 | 7941.22 | 4524579.62 | 4276.26 | 1849906.48 | 128560.41 | 3301184.99 | 2121.54 | 1712040.94 | 23964193.87 | 23964193.87
4. Allocated | Chargebacks | Chargeback | Antelope-Mesa 230KV TL - Segment 7 |  |  |  |  | 5338.33 |  | 5363.34 | [5 empty] | 10701.67 | 10701.67
|  |  | Chargeback Entries <$5,000 | -187461.13 | 29452.45 | 23231.08 | 19320.84 | 24612.66 | 20423.52 | 22216.22 | 17089.84 | 12938.9 | 4087.24 | 22757.51 | -12506.52 | -3837.39 | -3837.39
|  |  | Drawing Mgmt Contingent Workers - TRTP |  | 5814.9 |  |  |  | 6046.95 | [6 empty] | 11861.85 | 11861.85
|  |  | PROCUREMENT TDBU | 12515.19 | 5959.4 | 34173.34 | 36574.05 |  | 31655.95 | 6701.27 | 19026.35 |  | 44762.76 |  | 23681.24 | 215049.55 | 215049.55
|  |  | TDBU Vehicle Cost | [9 empty] | 5781.21 |  |  | 5781.21 | 5781.21
|  |  | TRTP 7 Antelope Mesa 230 kV Construction | 123689.11 | 256461.11 | 154609.76 | 303772.47 | 968418.22 | 492568.71 | 588251.16 | 320668.34 |  | 496465.2 | 534595.98 | 357321.93 | 4596821.99 | 4596821.99
|  |  | Work Package # 3 | 12619.63 | 16183.8 | 28799.26 | 33943.87 | 28273.88 | 35035.43 | 23192.48 | 15648.77 | 21370.42 | 24248.93 | 20345.4 | 44392.65 | 304054.52 | 304054.52
|  | Chargeback Total |  | -38637.2 | 313871.66 | 240813.44 | 393611.23 | 1026643.09 | 585730.56 | 645724.47 | 372433.3 | 34309.32 | 575345.34 | 577698.89 | 412889.3 | 5140433.4 | 5140433.4
| Chargebacks Total |  |  | -38637.2 | 313871.66 | 240813.44 | 393611.23 | 1026643.09 | 585730.56 | 645724.47 | 372433.3 | 34309.32 | 575345.34 | 577698.89 | 412889.3 | 5140433.4 | 5140433.4
| Labor - Other | Labor | Division Overhead | 43819.7 | 29538.02 | 188525.41 | 177883.25 | 16212.98 | 213927 | 42238.32 | 118243.79 |  | 352002.81 |  | 44155.41 | 1226546.69 | 1226546.69
|  |  | Labor Entries <$5,000 | 6383.22 | 6187.48 | 3395.93 | 2679.7 | 11068.12 | 1923.97 | 1628.85 | 3096.91 | -110373.23 | 9353.64 | 6558.35 | 5410.25 | -52686.81 | -52686.81
|  |  | Paid Absence | [9 empty] | 20794.15 |  |  | 20794.15 | 20794.15
|  | Labor Total |  | 50202.92 | 35725.5 | 191921.34 | 180562.95 | 27281.1 | 215850.97 | 43867.17 | 121340.7 | -110373.23 | 382150.6 | 6558.35 | 49565.66 | 1194654.03 | 1194654.03
| Labor - Other Total |  |  | 50202.92 | 35725.5 | 191921.34 | 180562.95 | 27281.1 | 215850.97 | 43867.17 | 121340.7 | -110373.23 | 382150.6 | 6558.35 | 49565.66 | 1194654.03 | 1194654.03
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -68412.3 | 68412.3 |  |  | 0 | 0
|  | Overhead Total | [9 empty] | -68412.3 | 68412.3 |  |  | 0 | 0
| Overhead Correction Total | [10 empty] | -68412.3 | 68412.3 |  |  | 0 | 0
4. Allocated Total |  |  |  | 11565.72 | 349597.16 | 432734.78 | 574174.18 | 1053924.19 | 801581.53 | 689591.64 | 493774 | -144476.21 | 1025908.24 | 584257.24 | 462454.96 | 6335087.43 | 6335087.43
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 436492.21 | 28347.71 | [6 empty] | 599130.33 | 1063970.25 | 1063970.25
|  |  | Capitalized Overhead - A&G | 100370.35 | 34482.91 | 201929.87 | 218991.83 | 134103.27 | 202040.08 | 61042.62 | 98599.05 | 15266.45 | 118966.35 | 27780.15 | 116627.16 | 1330200.09 | 1330200.09
|  |  | Capitalized Overhead - Inj & Damages | -27.33 | -1703.18 | 472.1 | 346.19 | 1925.72 | 792.49 | 417.49 | 1326.04 | 2802.32 | -8176.07 | 293.95 | 1962.04 | 431.76 | 431.76
|  |  | Capitalized Overhead - P&B/Payroll Tax | 28767.2 | 56449.48 | 44842.6 | 59457.59 | 69319.46 | 43919.56 | 42878.51 | 33388.28 | -130180.54 | 77362.81 | 24373.28 | 61592.37 | 412170.6 | 412170.6
|  | Non Budgeted Total |  | 129110.22 | 89229.21 | 247244.57 | 715287.82 | 233696.16 | 246752.13 | 104338.62 | 133313.37 | -112111.77 | 188153.09 | 52447.38 | 779311.9 | 2806772.7 | 2806772.7
| Non Budget - Other Total |  |  | 129110.22 | 89229.21 | 247244.57 | 715287.82 | 233696.16 | 246752.13 | 104338.62 | 133313.37 | -112111.77 | 188153.09 | 52447.38 | 779311.9 | 2806772.7 | 2806772.7
5. Corporate Overhead Total |  |  |  | 129110.22 | 89229.21 | 247244.57 | 715287.82 | 233696.16 | 246752.13 | 104338.62 | 133313.37 | -112111.77 | 188153.09 | 52447.38 | 779311.9 | 2806772.7 | 2806772.7
Grand Total |  |  |  | 1697738.37 | 4876905.9 | 1847639.6 | 7845597.24 | 5266892.78 | 3841436.95 | 3661917.95 | 3802223.79 | -83698.41 | 2376183.95 | 2329264.97 | 4292239.54 | 41754342.63 | 41754342.63

## 800218130
Pin: 6438 | Project: TRTP Segment 7
Order: 800218130 | 800218130- 03/28/20142: VINCENT-RIO HONDO #2: CONST
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [6 empty] | 204.52 | [5 empty] | 204.52
|  | Labor Total | [7 empty] | 204.52 | [5 empty] | 204.52
| BP&FM Total | [8 empty] | 204.52 | [5 empty] | 204.52
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 5750.8 | 5750.8
|  | Labor Total | [12 empty] | 5750.8 | 5750.8
| ELEC SYS PLANNING Total | [13 empty] | 5750.8 | 5750.8
| ENGINEERING | Labor | Engineer Sr |  |  |  |  | 5205.36 | 5491.02 |  | 6506.7 |  |  | 5998.86 |  | 23201.94
|  |  | Labor Entries <$5,000 | 1041.54 | 1106.32 | 2475.97 | 284.37 | 2193.71 | 2596.97 | 6834.31 | 2905.38 | 7282.2 | 7372.79 | 2756.49 |  | 36850.05
|  | Labor Total |  | 1041.54 | 1106.32 | 2475.97 | 284.37 | 7399.07 | 8087.99 | 6834.31 | 9412.08 | 7282.2 | 7372.79 | 8755.35 |  | 60051.99
| ENGINEERING Total |  |  | 1041.54 | 1106.32 | 2475.97 | 284.37 | 7399.07 | 8087.99 | 6834.31 | 9412.08 | 7282.2 | 7372.79 | 8755.35 |  | 60051.99
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | [11 empty] | 58205 | 58205
|  |  | Contract Entries <$50,000 |  | 1338.72 |  | 3686 | 13404 |  | 8901 | 11537 | 36114.72 | 45469.74 | 38754.16 | 9964.4 | 169169.74
|  | Contract Total |  |  | 1338.72 |  | 3686 | 13404 |  | 8901 | 11537 | 36114.72 | 45469.74 | 38754.16 | 68169.4 | 227374.74
| Engineering/Technical Professional Servi Total |  |  |  | 1338.72 |  | 3686 | 13404 |  | 8901 | 11537 | 36114.72 | 45469.74 | 38754.16 | 68169.4 | 227374.74
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -6585.55 | -3612.11 | -3749.55 | -1621.22 | -94.51 | -869.59 | -65.27 | -1462.84 | -246.94 | -4107.86 | -267.48 | -22682.92
|  | IMM Correction Total |  |  | -6585.55 | -3612.11 | -3749.55 | -1621.22 | -94.51 | -869.59 | -65.27 | -1462.84 | -246.94 | -4107.86 | -267.48 | -22682.92
| IMM/Allocated - Correction Total |  |  |  | -6585.55 | -3612.11 | -3749.55 | -1621.22 | -94.51 | -869.59 | -65.27 | -1462.84 | -246.94 | -4107.86 | -267.48 | -22682.92
| Labor - Other | Labor | Labor Entries <$5,000 | -137.49 | 500.59 | -357.31 | -153.6 | 1400.18 | -1474.67 | -245.2 | 300.06 | 61.71 | 748.13 | -1039.04 | 930.67 | 534.03
|  | Labor Total |  | -137.49 | 500.59 | -357.31 | -153.6 | 1400.18 | -1474.67 | -245.2 | 300.06 | 61.71 | 748.13 | -1039.04 | 930.67 | 534.03
| Labor - Other Total |  |  | -137.49 | 500.59 | -357.31 | -153.6 | 1400.18 | -1474.67 | -245.2 | 300.06 | 61.71 | 748.13 | -1039.04 | 930.67 | 534.03
| Other | Other | Other | -1013401 | 122285.32 | 3551558.81 | -4076423.27 | 12644.3 | 142403 | 93358 | -41785 | -104827.11 | 287607.11 | 1122769 | -1374574 | -1278384.84
|  | Other Total |  | -1013401 | 122285.32 | 3551558.81 | -4076423.27 | 12644.3 | 142403 | 93358 | -41785 | -104827.11 | 287607.11 | 1122769 | -1374574 | -1278384.84
| Other Total |  |  | -1013401 | 122285.32 | 3551558.81 | -4076423.27 | 12644.3 | 142403 | 93358 | -41785 | -104827.11 | 287607.11 | 1122769 | -1374574 | -1278384.84
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  | 260 | 624 | 468 | 915.52 | 1157.3 | 988 | 2486.08 | 1300 | 1186.08 | 1773 | 6406.24 | 17564.22
|  | Contract Total |  |  | 260 | 624 | 468 | 915.52 | 1157.3 | 988 | 2486.08 | 1300 | 1186.08 | 1773 | 6406.24 | 17564.22
| Temporary/Supplementary - Trade/Labor Total |  |  |  | 260 | 624 | 468 | 915.52 | 1157.3 | 988 | 2486.08 | 1300 | 1186.08 | 1773 | 6406.24 | 17564.22
1. Project Support Total |  |  |  | -1012496.95 | 118905.4 | 3550689.36 | -4075888.05 | 34141.85 | 150079.11 | 109171.04 | -18115.05 | -61531.32 | 342136.91 | 1166904.61 | -1293584.37 | -989587.46
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  | 49.62 | [10 empty] | 49.62
|  | Material - Direct Purchase Total |  |  | 49.62 | [10 empty] | 49.62
| Building, Shop & Industrial Products/Eqp Total |  |  |  | 49.62 | [10 empty] | 49.62
| Material - Other | Material | Material - Other |  | 6.23 | [5 empty] | 0.16 |  |  |  |  | 6.39
|  | Material Total |  |  | 6.23 | [5 empty] | 0.16 |  |  |  |  | 6.39
| Material - Other Total |  |  |  | 6.23 | [5 empty] | 0.16 |  |  |  |  | 6.39
2. Material Total |  |  |  |  | 55.85 | [5 empty] | 0.16 |  |  |  |  | 56.01
3. Construction | Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 | [5 empty] | 12163 | [6 empty] | 12163
|  |  | WILSON UTILITY CONSTRUCTION | 914660 | 545641 | 567490 | 241485 |  | 118436 |  | 207620 |  | 575747 |  | 1595037 | 4766116
|  | Contract Total |  | 914660 | 545641 | 567490 | 241485 |  | 130599 |  | 207620 |  | 575747 |  | 1595037 | 4778279
| Electrical Construction, Transmission Li Total |  |  | 914660 | 545641 | 567490 | 241485 |  | 130599 |  | 207620 |  | 575747 |  | 1595037 | 4778279
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 1295.89 | 1719.18 | 2083 | 1730.44 | [8 empty] | 6828.51
|  | Labor Total |  | 1295.89 | 1719.18 | 2083 | 1730.44 | [8 empty] | 6828.51
| TRNS CAPITAL Total |  |  | 1295.89 | 1719.18 | 2083 | 1730.44 | [8 empty] | 6828.51
3. Construction Total |  |  |  | 915955.89 | 547360.18 | 569573 | 243215.44 |  | 130599 |  | 207620 |  | 575747 |  | 1595037 | 4785107.51
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 727.52 | 4428.67 | 3965.93 | 1722.47 | 471.12 | 1251.18 | 5694.12 | 5271.24 | 5773.33 | 9525.27 | 5544.64 | 8236.68 | 52612.17
|  |  | PROCUREMENT TDBU | 6585.55 | [10 empty] | 11019.44 | 17604.99
|  | Chargeback Total |  | 7313.07 | 4428.67 | 3965.93 | 1722.47 | 471.12 | 1251.18 | 5694.12 | 5271.24 | 5773.33 | 9525.27 | 5544.64 | 19256.12 | 70217.16
| Chargebacks Total |  |  | 7313.07 | 4428.67 | 3965.93 | 1722.47 | 471.12 | 1251.18 | 5694.12 | 5271.24 | 5773.33 | 9525.27 | 5544.64 | 19256.12 | 70217.16
| Labor - Other | Labor | Division Overhead | 47196.45 | 41287.58 | 14203.11 | [6 empty] | 27385.72 |  | 17697.89 | 147770.75
|  |  | Labor Entries <$5,000 | 6513.6 | 7235.96 | 7580.39 | 8360.74 | 3066.86 | 7705.56 | 2257.89 | 11716.45 | 3062.49 | 7264.73 | 2125.84 | 6430.79 | 73321.3
|  | Labor Total |  | 53710.05 | 48523.54 | 21783.5 | 8360.74 | 3066.86 | 7705.56 | 2257.89 | 11716.45 | 3062.49 | 34650.45 | 2125.84 | 24128.68 | 221092.05
| Labor - Other Total |  |  | 53710.05 | 48523.54 | 21783.5 | 8360.74 | 3066.86 | 7705.56 | 2257.89 | 11716.45 | 3062.49 | 34650.45 | 2125.84 | 24128.68 | 221092.05
4. Allocated Total |  |  |  | 61023.12 | 52952.21 | 25749.43 | 10083.21 | 3537.98 | 8956.74 | 7952.01 | 16987.69 | 8835.82 | 44175.72 | 7670.48 | 43384.8 | 291309.21
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 60894.77 | 3562.38 | [6 empty] | 79636.17 | 144093.32
|  |  | AFUDC - Debt/Equity |  |  | 75203.76 | -75203.76 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 54575.21 | 17498.01 | 21189.45 | 9051.87 | 2123.75 | 5254.75 | 834.46 | 7022.62 | 2335.43 | 17425.69 | 1369.09 | 48274.85 | 186955.18
|  |  | Capitalized Overhead - Inj & Damages | 59.13 | 86.41 | 27.8 | 6.79 | 99.94 | 20 | 10.49 | 32.9 | 11.34 | 156.53 | 14.46 | 51.43 | 577.22
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1500.38 | 3848.18 | 4308.16 | 2391.81 | 13275.14 | 8852.46 | 11085.29 | 9323.93 | 13339.51 | 4991.43 | 7911.28 | 19164.67 | 99992.24
|  |  | Corporate Overheads Correction |  |  |  |  | -375854.04 | [7 empty] | -375854.04
|  | Non Budgeted Total |  | 56134.72 | 21432.6 | 100729.17 | -2858.52 | -356792.83 | 14127.21 | 11930.24 | 16379.45 | 15686.28 | 22573.65 | 9294.83 | 147127.12 | 55763.92
| Non Budget - Other Total |  |  | 56134.72 | 21432.6 | 100729.17 | -2858.52 | -356792.83 | 14127.21 | 11930.24 | 16379.45 | 15686.28 | 22573.65 | 9294.83 | 147127.12 | 55763.92
5. Corporate Overhead Total |  |  |  | 56134.72 | 21432.6 | 100729.17 | -2858.52 | -356792.83 | 14127.21 | 11930.24 | 16379.45 | 15686.28 | 22573.65 | 9294.83 | 147127.12 | 55763.92
Grand Total |  |  |  | 20616.78 | 740706.24 | 4246740.96 | -3825447.92 | -319113 | 303762.06 | 129053.29 | 222872.25 | -37009.22 | 984633.28 | 1183869.92 | 491964.55 | 4142649.19

## 800051909
Pin: 6438 | Project: TRTP Segment 7
Order: 800051909 | 800051909- 9219-2378 - TRTP Segment 7
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | HRealProp | Labor | Labor Entries <$5,000 |  | 24.27 | 1095.11 | 60.63 |  | 121.64 | [6 empty] | 1301.65
|  | Labor Total |  |  | 24.27 | 1095.11 | 60.63 |  | 121.64 | [6 empty] | 1301.65
| HRealProp Total |  |  |  | 24.27 | 1095.11 | 60.63 |  | 121.64 | [6 empty] | 1301.65
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -8.18 |  | -3.28 |  |  |  |  | 100.95 | -100.95 | -0.3 |  | -11.76
|  | IMM Correction Total |  |  | -8.18 |  | -3.28 |  |  |  |  | 100.95 | -100.95 | -0.3 |  | -11.76
| IMM/Allocated - Correction Total |  |  |  | -8.18 |  | -3.28 |  |  |  |  | 100.95 | -100.95 | -0.3 |  | -11.76
| Information System Professional Services | Contract | Contract Entries <$50,000 |  |  | -3.19 | [9 empty] | -3.19
|  | Contract Total |  |  |  | -3.19 | [9 empty] | -3.19
| Information System Professional Services Total |  |  |  |  | -3.19 | [9 empty] | -3.19
| Labor - Other | Labor | Labor Entries <$5,000 | 199.08 | 136.35 | 147.9 | 87.87 | 75.57 | 6.67 | 11.62 | 22.87 | -100.33 | 100.95 |  |  | 688.55
|  | Labor Total |  | 199.08 | 136.35 | 147.9 | 87.87 | 75.57 | 6.67 | 11.62 | 22.87 | -100.33 | 100.95 |  |  | 688.55
| Labor - Other Total |  |  | 199.08 | 136.35 | 147.9 | 87.87 | 75.57 | 6.67 | 11.62 | 22.87 | -100.33 | 100.95 |  |  | 688.55
| Other | Other | Other | -1541.22 |  | 500 | [9 empty] | -1041.22
|  | Other Total |  | -1541.22 |  | 500 | [9 empty] | -1041.22
| Other Total |  |  | -1541.22 |  | 500 | [9 empty] | -1041.22
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1045.44 | [8 empty] | 46.06 |  |  | 1091.5
|  | Contract Total |  | 1045.44 | [8 empty] | 46.06 |  |  | 1091.5
| Temporary/Supplementary - Trade/Labor Total |  |  | 1045.44 | [8 empty] | 46.06 |  |  | 1091.5
1. Project Support Total |  |  |  | -296.7 | 152.44 | 1739.82 | 145.22 | 75.57 | 128.31 | 11.62 | 22.87 | 0.62 | 46.06 | -0.3 |  | 2025.53
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 8.18 |  | 107.53 | -3.3 | [5 empty] | 0.3 |  |  | 112.71
|  | Chargeback Total |  | 8.18 |  | 107.53 | -3.3 | [5 empty] | 0.3 |  |  | 112.71
| Chargebacks Total |  |  | 8.18 |  | 107.53 | -3.3 | [5 empty] | 0.3 |  |  | 112.71
| Labor - Other | Labor | Labor Entries <$5,000 | 29.29 | 5.41 | 250.51 | 18.73 | -0.58 | 27.13 |  | 0.14 | -18.74 | 23.4 |  |  | 335.29
|  | Labor Total |  | 29.29 | 5.41 | 250.51 | 18.73 | -0.58 | 27.13 |  | 0.14 | -18.74 | 23.4 |  |  | 335.29
| Labor - Other Total |  |  | 29.29 | 5.41 | 250.51 | 18.73 | -0.58 | 27.13 |  | 0.14 | -18.74 | 23.4 |  |  | 335.29
4. Allocated Total |  |  |  | 37.47 | 5.41 | 358.04 | 15.43 | -0.58 | 27.13 |  | 0.14 | -18.74 | 23.7 |  |  | 448
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 9093.61 | 552.66 | [6 empty] | 9417.18 | 19063.45
|  | Non Budgeted Total |  |  |  |  | 9093.61 | 552.66 | [6 empty] | 9417.18 | 19063.45
| Non Budget - Other Total | [5 empty] | 9093.61 | 552.66 | [6 empty] | 9417.18 | 19063.45
5. Corporate Overhead Total | [6 empty] | 9093.61 | 552.66 | [6 empty] | 9417.18 | 19063.45
Grand Total |  |  |  | -259.23 | 157.85 | 2097.86 | 9254.26 | 627.65 | 155.44 | 11.62 | 23.01 | -18.12 | 69.76 | -0.3 | 9417.18 | 21536.98

## TRTP Seg 8
WO | SumOfYTD2012 | Order | Project
900610533- TRTP 8: New Vincent-Mira Loma 500kV T/L | 3568814.67 | 900610533 | TRTP Segment 8
800375079- Survey & engineering design of approxima | 1061.03 | 800375079 | TRTP Segment 8
800218645- I: TRTP 8-8: MIRA LOMA-VINCENT: CONSTRUC | 54975178.42 | 800218645 | TRTP Segment 8
800218618- I: TRTP 8-7: CHINO-MIRA LOMA #1 & #2: CO | 2629646.5 | 800218618 | TRTP Segment 8
800218551- I: TRTP 8-4: CONSTRUCT 0.44 MILES 220KV | 875462.64 | 800218551 | TRTP Segment 8
800218522- I: TRTP 8-2: CONSTRUCT 1.33 MILES DOUBLE | 4175891.76 | 800218522 | TRTP Segment 8
800051911- 9219-2380 - TRTP Segment 8 | 1996202.71 | 800051911 | TRTP Segment 8

## 900610533
Pin: 6439 | Project: TRTP Segment 8
Order: 900610533 | 900610533- TRTP 8: New Vincent-Mira Loma 500kV T/L
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 1309.58 | 787.35 |  |  | 483.97 | 1601.41 |  |  | 400.47 |  | 430.77 | 506.49 | 5520.04
|  | Labor Total |  | 1309.58 | 787.35 |  |  | 483.97 | 1601.41 |  |  | 400.47 |  | 430.77 | 506.49 | 5520.04
| BP&FM Total |  |  | 1309.58 | 787.35 |  |  | 483.97 | 1601.41 |  |  | 400.47 |  | 430.77 | 506.49 | 5520.04
| BR&CA-HCC | Labor | Labor Entries <$5,000 | 535.48 | [11 empty] | 535.48
|  | Labor Total |  | 535.48 | [11 empty] | 535.48
| BR&CA-HCC Total |  |  | 535.48 | [11 empty] | 535.48
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [7 empty] | 527.43 | 1466.85 |  | 3597.75 |  | 5592.03
|  | Contract Total | [8 empty] | 527.43 | 1466.85 |  | 3597.75 |  | 5592.03
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [9 empty] | 527.43 | 1466.85 |  | 3597.75 |  | 5592.03
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 183536.02 |  |  | 183536.02
|  |  | Contract Entries <$50,000 | [8 empty] | -183536.02 |  |  |  | -183536.02
|  | Contract Total | [9 empty] | -183536.02 | 183536.02 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -183536.02 | 183536.02 |  |  | 0
| CORP COMM SVP | Labor | Labor Entries <$5,000 |  |  |  | 46.69 | [8 empty] | 46.69
|  | Labor Total |  |  |  |  | 46.69 | [8 empty] | 46.69
| CORP COMM SVP Total | [5 empty] | 46.69 | [8 empty] | 46.69
| ELEC SYS PLANNING | Labor | ELEC SYS PLANNING / Engineer | [11 empty] | 5104.44 | 5104.44
|  |  | ELEC SYS PLANNING / Engineer Sr | [11 empty] | 10756.8 | 10756.8
|  |  | ELEC SYS PLANNING / Manager | [11 empty] | 6705.88 | 6705.88
|  |  | Labor Entries <$5,000 | [6 empty] | 111.77 | 255.64 |  |  |  | 6053.31 | 6420.72
|  | Labor Total | [7 empty] | 111.77 | 255.64 |  |  |  | 28620.43 | 28987.84
| ELEC SYS PLANNING Total | [8 empty] | 111.77 | 255.64 |  |  |  | 28620.43 | 28987.84
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 1546.68 | 298.52 | 117.1 | 663.23 | 2856.64 | -36.79 | 1428.85 | 531.26 | 296.34 | 428.02 | 2988.12 | 4150.34 | 15268.31
|  |  | Techn Spl/Scientist | [5 empty] | 5373.06 | [6 empty] | 5373.06
|  | Labor Total |  | 1546.68 | 298.52 | 117.1 | 663.23 | 2856.64 | 5336.27 | 1428.85 | 531.26 | 296.34 | 428.02 | 2988.12 | 4150.34 | 20641.37
| ENG ADVANCEMENT Total |  |  | 1546.68 | 298.52 | 117.1 | 663.23 | 2856.64 | 5336.27 | 1428.85 | 531.26 | 296.34 | 428.02 | 2988.12 | 4150.34 | 20641.37
| ENGINEERING | Labor | Engineer Sr | [7 empty] | 14822.58 | 9648.96 | 14759.1 | 15996.96 |  | 55227.6
|  |  | Labor Entries <$5,000 | 3229.64 |  |  | 1263.88 | 1511.22 |  | 9047.69 | 14920.42 | 27090.24 | 22408.63 | 15697.34 |  | 95169.06
|  |  | Manager | [7 empty] | 5087.52 |  |  | 6218.08 |  | 11305.6
|  | Labor Total |  | 3229.64 |  |  | 1263.88 | 1511.22 |  | 9047.69 | 34830.52 | 36739.2 | 37167.73 | 37912.38 |  | 161702.26
| ENGINEERING Total |  |  | 3229.64 |  |  | 1263.88 | 1511.22 |  | 9047.69 | 34830.52 | 36739.2 | 37167.73 | 37912.38 |  | 161702.26
| Engineering/Technical Professional Servi | Contract | BLACK & VEATCH CORPORATION | [6 empty] | 147639.7 | 50379.53 |  | 86351.05 | 160619.18 | 919051.95 | 1364041.41
|  |  | Contract Entries <$50,000 | 42234.25 | 20443.86 |  | 1627.5 |  | 41916.91 | 9884.72 | 9962.38 |  | 5634.66 | 147069.07 | 183492.06 | 462265.41
|  |  | KLEINFELDER WEST INC | [11 empty] | 237608.5 | 237608.5
|  | Contract Total |  | 42234.25 | 20443.86 |  | 1627.5 |  | 41916.91 | 157524.42 | 60341.91 |  | 91985.71 | 307688.25 | 1340152.51 | 2063915.32
| Engineering/Technical Professional Servi Total |  |  | 42234.25 | 20443.86 |  | 1627.5 |  | 41916.91 | 157524.42 | 60341.91 |  | 91985.71 | 307688.25 | 1340152.51 | 2063915.32
| HRealProp | Labor | Labor Entries <$5,000 | 1458.39 | -1390.33 | [10 empty] | 68.06
|  | Labor Total |  | 1458.39 | -1390.33 | [10 empty] | 68.06
| HRealProp Total |  |  | 1458.39 | -1390.33 | [10 empty] | 68.06
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -321.28 | -203.06 | -60.45 | -49.17 | -5.92 | -315.61 | -1149.21 | 191328.52 | -191750.06 | -1885.2 | -2115.11 | -6526.55
|  | IMM Correction Total |  |  | -321.28 | -203.06 | -60.45 | -49.17 | -5.92 | -315.61 | -1149.21 | 191328.52 | -191750.06 | -1885.2 | -2115.11 | -6526.55
| IMM/Allocated - Correction Total |  |  |  | -321.28 | -203.06 | -60.45 | -49.17 | -5.92 | -315.61 | -1149.21 | 191328.52 | -191750.06 | -1885.2 | -2115.11 | -6526.55
| Information System Professional Services | Contract | Contract Entries <$50,000 |  |  |  |  | 3.19 |  |  | 15.95 |  |  |  |  | 19.14
|  | Contract Total | [5 empty] | 3.19 |  |  | 15.95 |  |  |  |  | 19.14
| Information System Professional Services Total | [6 empty] | 3.19 |  |  | 15.95 |  |  |  |  | 19.14
| Labor - Other | Labor | ACQ/Chino Hills Undergrounding | [7 empty] | 24131.21 | 13524.29 |  |  |  | 37655.5
|  |  | Labor Entries <$5,000 | 608.4 | 775.82 | 849.61 | 2937.44 | 653.92 | -1213.97 | 6552.79 | 4703.76 | 16802.17 | -7089.28 | -6638.48 | 8184.08 | 27126.26
|  | Labor Total |  | 608.4 | 775.82 | 849.61 | 2937.44 | 653.92 | -1213.97 | 6552.79 | 28834.97 | 30326.46 | -7089.28 | -6638.48 | 8184.08 | 64781.76
| Labor - Other Total |  |  | 608.4 | 775.82 | 849.61 | 2937.44 | 653.92 | -1213.97 | 6552.79 | 28834.97 | 30326.46 | -7089.28 | -6638.48 | 8184.08 | 64781.76
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 144.46 |  |  | 1920.99 | 621.64 |  |  | 1132.91 | 159.57 |  | 741.04 | -23.37 | 4697.24
|  |  | MAJOR PROJECT ORG / Mgr-Prj/Prod | [11 empty] | 7185.04 | 7185.04
|  | Labor Total |  | 144.46 |  |  | 1920.99 | 621.64 |  |  | 1132.91 | 159.57 |  | 741.04 | 7161.67 | 11882.28
| MAJOR PROJECT ORG Total |  |  | 144.46 |  |  | 1920.99 | 621.64 |  |  | 1132.91 | 159.57 |  | 741.04 | 7161.67 | 11882.28
| Other | Other | Other | -3524.47 | 78.81 | -275.2 |  | 3756.23 | 157573.3 | -103779.47 | -56733.41 | 108059.29 | 178920.45 | 373459.02 | -424261.4 | 233273.15
|  | Other Total |  | -3524.47 | 78.81 | -275.2 |  | 3756.23 | 157573.3 | -103779.47 | -56733.41 | 108059.29 | 178920.45 | 373459.02 | -424261.4 | 233273.15
| Other Total |  |  | -3524.47 | 78.81 | -275.2 |  | 3756.23 | 157573.3 | -103779.47 | -56733.41 | 108059.29 | 178920.45 | 373459.02 | -424261.4 | 233273.15
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 2387.6 | 2868 |  |  |  | 146.08 | 146.08 | 3511.19 | 11380.29 | 9972.02 | 7813.38 | 19209 | 57433.64
|  | Contract Total |  | 2387.6 | 2868 |  |  |  | 146.08 | 146.08 | 3511.19 | 11380.29 | 9972.02 | 7813.38 | 19209 | 57433.64
| Temporary/Supplementary - Trade/Labor Total |  |  | 2387.6 | 2868 |  |  |  | 146.08 | 146.08 | 3511.19 | 11380.29 | 9972.02 | 7813.38 | 19209 | 57433.64
1. Project Support Total |  |  |  | 49930.01 | 23540.75 | 488.45 | 8399.28 | 9837.64 | 205354.08 | 70716.52 | 72099.16 | 196620.97 | 303170.61 | 726107.03 | 981608.01 | 2647872.51
2. Material | Material - Other | Material | Material - Other |  |  |  |  | -5.04 | [7 empty] | -5.04
|  | Material Total | [5 empty] | -5.04 | [7 empty] | -5.04
| Material - Other Total | [6 empty] | -5.04 | [7 empty] | -5.04
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 41.88 | [7 empty] | 41.88
|  | Material - Direct Purchase Total | [5 empty] | 41.88 | [7 empty] | 41.88
| Transportation & Mobile Equip-DP Total | [6 empty] | 41.88 | [7 empty] | 41.88
2. Material Total | [7 empty] | 36.84 | [7 empty] | 36.84
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  | 7455 | 9159 | 5822 | 852 | 5756 | 16452 |  | 3106 | 142 | 4970 | 9798 | 63512
|  | Contract Total |  |  | 7455 | 9159 | 5822 | 852 | 5756 | 16452 |  | 3106 | 142 | 4970 | 9798 | 63512
| Construction Management Services Total |  |  |  | 7455 | 9159 | 5822 | 852 | 5756 | 16452 |  | 3106 | 142 | 4970 | 9798 | 63512
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 575.38 | 575.38
|  | Labor Total | [12 empty] | 575.38 | 575.38
| ELEC SYS PLANNING Total | [13 empty] | 575.38 | 575.38
| ENGINEERING | Labor | Labor Entries <$5,000 | [7 empty] | 333.75 |  |  | 244.3 |  | 578.05
|  | Labor Total | [8 empty] | 333.75 |  |  | 244.3 |  | 578.05
| ENGINEERING Total | [9 empty] | 333.75 |  |  | 244.3 |  | 578.05
| Labor - Other | Labor | Labor Entries <$5,000 |  | 2358.88 | -127.31 | 374.54 | -2.61 | 1133.32 | 412.95 | 918.3 | 537.24 | 991.15 | 1093.15 | 435.64 | 8125.25
|  | Labor Total |  |  | 2358.88 | -127.31 | 374.54 | -2.61 | 1133.32 | 412.95 | 918.3 | 537.24 | 991.15 | 1093.15 | 435.64 | 8125.25
| Labor - Other Total |  |  |  | 2358.88 | -127.31 | 374.54 | -2.61 | 1133.32 | 412.95 | 918.3 | 537.24 | 991.15 | 1093.15 | 435.64 | 8125.25
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | [11 empty] | 164 | 164
|  | Labor Total | [12 empty] | 164 | 164
| TSD-HERC - Rental Total | [13 empty] | 164 | 164
3. Construction Total |  |  |  |  | 9813.88 | 9031.69 | 6196.54 | 849.39 | 6889.32 | 16864.95 | 1252.05 | 3643.24 | 1133.15 | 6307.45 | 10973.02 | 72954.68
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 1640.13 | 4858.65 | 2648.54 | 4295.23 | 1030.28 | 4293.19 | 3559.85 | 5018.22 | 1853.48 | 5155.14 | 7144.82 | 5750.24 | 47247.77
|  |  | PROCUREMENT TDBU | [11 empty] | 9036.45 | 9036.45
|  |  | TRTP ACR Work - TRTP |  | 143844.3 |  |  | 17837.23 |  |  | 10966 |  | 27194.86 | 9264 | 12083 | 221189.39
|  | Chargeback Total |  | 1640.13 | 148702.95 | 2648.54 | 4295.23 | 18867.51 | 4293.19 | 3559.85 | 15984.22 | 1853.48 | 32350 | 16408.82 | 26869.69 | 277473.61
| Chargebacks Total |  |  | 1640.13 | 148702.95 | 2648.54 | 4295.23 | 18867.51 | 4293.19 | 3559.85 | 15984.22 | 1853.48 | 32350 | 16408.82 | 26869.69 | 277473.61
| Labor - Other | Labor | Division Overhead | [11 empty] | 15793.59 | 15793.59
|  |  | Labor Entries <$5,000 | 3188.36 | 1124.65 | 343.49 | 1251.42 | 1743.48 | 3718.1 | 10250.08 | 5186.41 | -3411.36 | 19121.03 | 5557.41 | 5283.89 | 53356.96
|  |  | Paid Absence | [7 empty] | 7356.49 | 6914.05 | 8858.42 | 7079.71 | 11642.92 | 41851.59
|  | Labor Total |  | 3188.36 | 1124.65 | 343.49 | 1251.42 | 1743.48 | 3718.1 | 10250.08 | 12542.9 | 3502.69 | 27979.45 | 12637.12 | 32720.4 | 111002.14
| Labor - Other Total |  |  | 3188.36 | 1124.65 | 343.49 | 1251.42 | 1743.48 | 3718.1 | 10250.08 | 12542.9 | 3502.69 | 27979.45 | 12637.12 | 32720.4 | 111002.14
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -4102.27 | 4102.27 |  |  | 0
|  | Overhead Total | [9 empty] | -4102.27 | 4102.27 |  |  | 0
| Overhead Correction Total | [10 empty] | -4102.27 | 4102.27 |  |  | 0
4. Allocated Total |  |  |  | 4828.49 | 149827.6 | 2992.03 | 5546.65 | 20610.99 | 8011.29 | 13809.93 | 28527.12 | 1253.9 | 64431.72 | 29045.94 | 59590.09 | 388475.75
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 2371.01 | 159.03 | [6 empty] | 21680.52 | 24210.56
|  |  | Capitalized Overhead - A&G | 3254.17 | 5366.54 | 455.8 | 718.29 | 2309.08 | 2238.86 | 7217.55 | 4492.64 | 4250.29 | 5079.67 | 12920.82 | 44844.57 | 93148.28
|  |  | Capitalized Overhead - Inj & Damages | 12.76 | 14.8 | 1.19 | 6.38 | 80.78 | 15.23 | 27.55 | 106.75 | 231.08 | -367.22 | 255.88 | 242.7 | 627.88
|  |  | Capitalized Overhead - P&B/Payroll Tax | 6238.87 | 2728.45 | 723.23 | 7391.33 | 9250.93 | 9387.12 | 21556.04 | 50706.45 | 58102.65 | 24476.1 | 32478.58 | 118448.42 | 341488.17
|  | Non Budgeted Total |  | 9505.8 | 8109.79 | 1180.22 | 10487.01 | 11799.82 | 11641.21 | 28801.14 | 55305.84 | 62584.02 | 29188.55 | 45655.28 | 185216.21 | 459474.89
| Non Budget - Other Total |  |  | 9505.8 | 8109.79 | 1180.22 | 10487.01 | 11799.82 | 11641.21 | 28801.14 | 55305.84 | 62584.02 | 29188.55 | 45655.28 | 185216.21 | 459474.89
5. Corporate Overhead Total |  |  |  | 9505.8 | 8109.79 | 1180.22 | 10487.01 | 11799.82 | 11641.21 | 28801.14 | 55305.84 | 62584.02 | 29188.55 | 45655.28 | 185216.21 | 459474.89
Grand Total |  |  |  | 64264.3 | 191292.02 | 13692.39 | 30629.48 | 43134.68 | 231895.9 | 130192.54 | 157184.17 | 264102.13 | 397924.03 | 807115.7 | 1237387.33 | 3568814.67

## 800375079
Pin: 6439 | Project: TRTP Segment 8
Order: 800375079 | 800375079- Survey & engineering design of approxima
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 |  |  | 2012 Total
SubCategory | Prime | Group | Details | 4 | 5 | 12
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax | 693.74 | 42.02 | 715.97 | 1451.73
|  |  | Corporate Overheads Correction |  | -390.7 |  | -390.7
|  | Non Budgeted Total |  | 693.74 | -348.68 | 715.97 | 1061.03
| Non Budget - Other Total |  |  | 693.74 | -348.68 | 715.97 | 1061.03
5. Corporate Overhead Total |  |  |  | 693.74 | -348.68 | 715.97 | 1061.03
Grand Total |  |  |  | 693.74 | -348.68 | 715.97 | 1061.03

## 800218645
Pin: 6439 | Project: TRTP Segment 8
Order: 800218645 | 800218645- I: TRTP 8-8: MIRA LOMA-VINCENT: CONSTRUC
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [6 empty] | 87.87 | [5 empty] | 87.87
|  | Labor Total | [7 empty] | 87.87 | [5 empty] | 87.87
| BP&FM Total | [8 empty] | 87.87 | [5 empty] | 87.87
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 |  |  | 100 | [9 empty] | 100
|  | Contract Total |  |  |  | 100 | [9 empty] | 100
| Building/Facility Repairs & Maintenance Total |  |  |  |  | 100 | [9 empty] | 100
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 2931368.71 |  |  | 2931368.71
|  |  | Contract Entries <$50,000 | [8 empty] | -2931368.71 |  |  |  | -2931368.71
|  | Contract Total | [9 empty] | -2931368.71 | 2931368.71 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -2931368.71 | 2931368.71 |  |  | 0
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 | 692.85 | 2223.99 | 711.74 | 657.01 | 234.49 | 1002.05 | 75.75 | 2565.86 | 4069.88 | 2941.95 | 5668.85 |  | 20844.42
|  | Labor Total |  | 692.85 | 2223.99 | 711.74 | 657.01 | 234.49 | 1002.05 | 75.75 | 2565.86 | 4069.88 | 2941.95 | 5668.85 |  | 20844.42
| EAST GRID MGMTCENTER Total |  |  | 692.85 | 2223.99 | 711.74 | 657.01 | 234.49 | 1002.05 | 75.75 | 2565.86 | 4069.88 | 2941.95 | 5668.85 |  | 20844.42
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 10908.11 | 10908.11
|  | Labor Total | [12 empty] | 10908.11 | 10908.11
| ELEC SYS PLANNING Total | [13 empty] | 10908.11 | 10908.11
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 3938.85 | 2004.19 |  |  |  |  | 98.54 | [5 empty] | 6041.58
|  | Labor Total |  | 3938.85 | 2004.19 |  |  |  |  | 98.54 | [5 empty] | 6041.58
| ENG ADVANCEMENT Total |  |  | 3938.85 | 2004.19 |  |  |  |  | 98.54 | [5 empty] | 6041.58
| ENGINEERING | Labor | Engineer |  |  | 5311.17 | [9 empty] | 5311.17
|  |  | Engineer Sr | 7289.44 | 6786.72 |  |  | 6348 | [7 empty] | 20424.16
|  |  | Labor Entries <$5,000 | 14263.96 | 12559.6 | 14418.22 | 17385.02 | 17389.35 | 19914.31 | 15564 | 20362.41 | 13744.29 | 13570.53 | 12015.12 |  | 171186.81
|  | Labor Total |  | 21553.4 | 19346.32 | 19729.39 | 17385.02 | 23737.35 | 19914.31 | 15564 | 20362.41 | 13744.29 | 13570.53 | 12015.12 |  | 196922.14
| ENGINEERING Total |  |  | 21553.4 | 19346.32 | 19729.39 | 17385.02 | 23737.35 | 19914.31 | 15564 | 20362.41 | 13744.29 | 13570.53 | 12015.12 |  | 196922.14
| Engineering/Technical Professional Servi | Contract | BUREAU VERITAS NORTH AMERICA INC |  |  | 55909.62 |  | 83972.5 | [7 empty] | 139882.12
|  |  | BURNS & MC DONNELL INC | 1217845 | 608611.99 | 508638 | 533248 | 597352 |  | 1055996.7 | 494180 | 554711.62 | 483313 | 593376 | 1127341.55 | 7774613.86
|  |  | Contract Entries <$50,000 |  | 47636.42 | 46190.77 | 41914.39 | 27516 | 58137.7 | 96171.23 | 57599.55 | 31519.3 | 84132.86 | 48195.12 | 17890.72 | 556904.06
|  |  | CONVERSE CONSULTANTS | [6 empty] | 63390.16 |  |  |  |  | 90772.95 | 154163.11
|  |  | Engineering/Technical Professional Servi | [10 empty] | 75850 |  | 75850
|  | Contract Total |  | 1217845 | 656248.41 | 610738.39 | 575162.39 | 708840.5 | 58137.7 | 1215558.09 | 551779.55 | 586230.92 | 567445.86 | 717421.12 | 1236005.22 | 8701413.15
| Engineering/Technical Professional Servi Total |  |  | 1217845 | 656248.41 | 610738.39 | 575162.39 | 708840.5 | 58137.7 | 1215558.09 | 551779.55 | 586230.92 | 567445.86 | 717421.12 | 1236005.22 | 8701413.15
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 21725.8 | 6659.75 | 13603.82 | 7642.78 | 18029.53 | 13538.69 | 9523.88 | 13564.44 | 11433.31 | 12700.53 | 25001.89 | 153424.42
|  | Contract Total |  |  | 21725.8 | 6659.75 | 13603.82 | 7642.78 | 18029.53 | 13538.69 | 9523.88 | 13564.44 | 11433.31 | 12700.53 | 25001.89 | 153424.42
| Environmental/Safety Professional Servic Total |  |  |  | 21725.8 | 6659.75 | 13603.82 | 7642.78 | 18029.53 | 13538.69 | 9523.88 | 13564.44 | 11433.31 | 12700.53 | 25001.89 | 153424.42
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 47132.66 | 29387.93 | 34147.67 | 21919.83 | 32227.97 | 37295.6 | 15814.38 | 21859.44 | 2808859.75 | -2797878.07 | -73144.24 | -8676.14 | 168946.78
|  | IMM Correction Total |  | 47132.66 | 29387.93 | 34147.67 | 21919.83 | 32227.97 | 37295.6 | 15814.38 | 21859.44 | 2808859.75 | -2797878.07 | -73144.24 | -8676.14 | 168946.78
| IMM/Allocated - Correction Total |  |  | 47132.66 | 29387.93 | 34147.67 | 21919.83 | 32227.97 | 37295.6 | 15814.38 | 21859.44 | 2808859.75 | -2797878.07 | -73144.24 | -8676.14 | 168946.78
| Labor - Other | Labor | Labor - Other | [9 empty] | 22057.47 |  |  | 22057.47
|  |  | Labor Correction | [9 empty] | 109738.98 |  |  | 109738.98
|  |  | Labor Entries <$5,000 | 2970.42 | 6048.3 | -2416.54 | 716.61 | 5089.38 | -6218.8 | 27.88 | 1278.15 | -133370.09 | 7380.51 | -20.88 | 5387.49 | -113127.57
|  | Labor Total |  | 2970.42 | 6048.3 | -2416.54 | 716.61 | 5089.38 | -6218.8 | 27.88 | 1278.15 | -133370.09 | 139176.96 | -20.88 | 5387.49 | 18668.88
| Labor - Other Total |  |  | 2970.42 | 6048.3 | -2416.54 | 716.61 | 5089.38 | -6218.8 | 27.88 | 1278.15 | -133370.09 | 139176.96 | -20.88 | 5387.49 | 18668.88
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  | 219.27 | 234.17 |  |  | 540.09 |  | 50.96 | 117.5 |  | 145.36 |  | 1307.35
|  | Labor Total |  |  | 219.27 | 234.17 |  |  | 540.09 |  | 50.96 | 117.5 |  | 145.36 |  | 1307.35
| NORTH GRIDMGMTCENTER Total |  |  |  | 219.27 | 234.17 |  |  | 540.09 |  | 50.96 | 117.5 |  | 145.36 |  | 1307.35
| Other | Other | Other | 1129491.18 | -328785.34 | -896384.07 | -235132.55 | 1569612.05 | -338023.12 | 3622065.29 | 1972833.58 | 1897183.49 | -7663956.03 | 4418061.72 | -1503112.28 | 3643853.92
|  | Other Total |  | 1129491.18 | -328785.34 | -896384.07 | -235132.55 | 1569612.05 | -338023.12 | 3622065.29 | 1972833.58 | 1897183.49 | -7663956.03 | 4418061.72 | -1503112.28 | 3643853.92
| Other Total |  |  | 1129491.18 | -328785.34 | -896384.07 | -235132.55 | 1569612.05 | -338023.12 | 3622065.29 | 1972833.58 | 1897183.49 | -7663956.03 | 4418061.72 | -1503112.28 | 3643853.92
| SC&M | Labor | Labor Entries <$5,000 | [9 empty] | 157.01 | 158.31 | 489.03 | 804.35
|  | Labor Total | [10 empty] | 157.01 | 158.31 | 489.03 | 804.35
| SC&M Total | [11 empty] | 157.01 | 158.31 | 489.03 | 804.35
| SOUTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | 145.98 | 784.04 |  |  |  |  | 100.97 | [5 empty] | 1030.99
|  | Labor Total |  | 145.98 | 784.04 |  |  |  |  | 100.97 | [5 empty] | 1030.99
| SOUTH GRIDMGMTCENTER Total |  |  | 145.98 | 784.04 |  |  |  |  | 100.97 | [5 empty] | 1030.99
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -69264.38 |  |  |  | -69264.38
|  |  | Temporary / Supplemental - Correction | [9 empty] | 69264.38 |  |  | 69264.38
|  | Contract Total | [9 empty] | -69264.38 | 69264.38 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -69264.38 | 69264.38 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | [10 empty] | 3381.07 | 2502.9 | 5883.97
|  | Contract Total | [11 empty] | 3381.07 | 2502.9 | 5883.97
| Temporary/Supplementary - Technical/Prof Total | [12 empty] | 3381.07 | 2502.9 | 5883.97
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 5708 | 4990.44 | 3433.99 | 705.43 | 7820.34 | 7093.69 | 2480.55 | 4167.65 | 3755.83 | 5960.2 | 4130.58 | 11566.36 | 61813.06
|  | Contract Total |  | 5708 | 4990.44 | 3433.99 | 705.43 | 7820.34 | 7093.69 | 2480.55 | 4167.65 | 3755.83 | 5960.2 | 4130.58 | 11566.36 | 61813.06
| Temporary/Supplementary - Trade/Labor Total |  |  | 5708 | 4990.44 | 3433.99 | 705.43 | 7820.34 | 7093.69 | 2480.55 | 4167.65 | 3755.83 | 5960.2 | 4130.58 | 11566.36 | 61813.06
| TRANSMISSION | Labor | Labor Entries <$5,000 | 9121.41 | 3663.59 | 2314.6 | 1203.27 | 1171.1 | 236.56 | 24.03 | 5191.66 | 10340.8 | 1436.25 | 3379.22 | 5158.47 | 43240.96
|  | Labor Total |  | 9121.41 | 3663.59 | 2314.6 | 1203.27 | 1171.1 | 236.56 | 24.03 | 5191.66 | 10340.8 | 1436.25 | 3379.22 | 5158.47 | 43240.96
| TRANSMISSION Total |  |  | 9121.41 | 3663.59 | 2314.6 | 1203.27 | 1171.1 | 236.56 | 24.03 | 5191.66 | 10340.8 | 1436.25 | 3379.22 | 5158.47 | 43240.96
| TRNS CAPITAL | Labor | Labor Entries <$5,000 |  |  | 1845.57 | 2402.43 | 3665.77 | 4787.55 | 2110.53 | 2518.31 | 2786.68 | 2824.51 | 2087.55 |  | 25028.9
|  | Labor Total |  |  |  | 1845.57 | 2402.43 | 3665.77 | 4787.55 | 2110.53 | 2518.31 | 2786.68 | 2824.51 | 2087.55 |  | 25028.9
| TRNS CAPITAL Total |  |  |  |  | 1845.57 | 2402.43 | 3665.77 | 4787.55 | 2110.53 | 2518.31 | 2786.68 | 2824.51 | 2087.55 |  | 25028.9
| WEST GRID MGMTCENTER | Labor | Labor Entries <$5,000 |  | 207.08 | 178.7 | 112.29 | [8 empty] | 498.07
|  | Labor Total |  |  | 207.08 | 178.7 | 112.29 | [8 empty] | 498.07
| WEST GRID MGMTCENTER Total |  |  |  | 207.08 | 178.7 | 112.29 | [8 empty] | 498.07
1. Project Support Total |  |  |  | 2438599.75 | 418064.02 | -218706.64 | 398735.55 | 2360041.73 | -197204.84 | 4887546.57 | 2592131.45 | 2206650.4 | -6716254.43 | 5105984.31 | -214768.95 | 13060818.92
2. Material | Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | ONESOURCE SUPPLY SOLUTIONS, LLC |  |  |  | 21996 | [8 empty] | 21996
|  | Material - Direct Purchase Total |  |  |  |  | 21996 | [8 empty] | 21996
| Fuels, Chemicals & Petrochem-DP Total | [5 empty] | 21996 | [8 empty] | 21996
| Insulators & Bushings-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | -5055.75 |  | -5055.75
|  | Material - Direct Purchase Total | [11 empty] | -5055.75 |  | -5055.75
| Insulators & Bushings-DP Total | [12 empty] | -5055.75 |  | -5055.75
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -179.46 | 179.46 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -179.46 | 179.46 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -179.46 | 179.46 |  |  | 0
| Material - Inventory | Material | Material - Inventory | 1239.02 | 3637.5 |  |  |  | 10277.45 |  |  | -17.28 | 17.28 |  |  | 15153.97
|  | Material Total |  | 1239.02 | 3637.5 |  |  |  | 10277.45 |  |  | -17.28 | 17.28 |  |  | 15153.97
| Material - Inventory Total |  |  | 1239.02 | 3637.5 |  |  |  | 10277.45 |  |  | -17.28 | 17.28 |  |  | 15153.97
| Material - Other | Material | Material - Other | 713.79 | 11186.64 | 26171.35 | 18382.74 | -18998.9 | 6521.57 | 42443.86 | 48357.44 | -356163.16 | 148360.35 | 50810.69 | 41538 | 19324.37
|  | Material Total |  | 713.79 | 11186.64 | 26171.35 | 18382.74 | -18998.9 | 6521.57 | 42443.86 | 48357.44 | -356163.16 | 148360.35 | 50810.69 | 41538 | 19324.37
| Material - Other Total |  |  | 713.79 | 11186.64 | 26171.35 | 18382.74 | -18998.9 | 6521.57 | 42443.86 | 48357.44 | -356163.16 | 148360.35 | 50810.69 | 41538 | 19324.37
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | AGILE SOURCING PARTNERS INC | [9 empty] | 16530 | 134995 |  | 151525
|  |  | Material Entries <$5,000 | -22.23 | 1912 | [6 empty] | -189072 |  |  | 3306 | -183876.23
|  |  | ONE SOURCE DISTRIBUTORS INC |  | 57279.02 | 56588.37 | 64344.58 | 188221.89 | 10695.1 | 5395 | 22466.02 |  |  | 15342 |  | 420331.98
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [5 empty] | 38600.77 | 24140.71 | 112566.92 | 50178 | 1113174.49 | 406841.6 | 325406.58 | 2070909.07
|  | Material - Direct Purchase Total |  | -22.23 | 59191.02 | 56588.37 | 64344.58 | 188221.89 | 49295.87 | 29535.71 | 135032.94 | -138894 | 1129704.49 | 557178.6 | 328712.58 | 2458889.82
| Pole Line Hdwe & Connectors-DP Total |  |  | -22.23 | 59191.02 | 56588.37 | 64344.58 | 188221.89 | 49295.87 | 29535.71 | 135032.94 | -138894 | 1129704.49 | 557178.6 | 328712.58 | 2458889.82
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | ON-RAMP WIRELESS, INC. | [6 empty] | 364420 | [5 empty] | 364420
|  | Material - Direct Purchase Total | [7 empty] | 364420 | [5 empty] | 364420
| Power Systems, Batteries and Light-DP Total | [8 empty] | 364420 | [5 empty] | 364420
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO |  | 26200 | [10 empty] | 26200
|  |  | Material Entries <$5,000 | 4500 | [7 empty] | -1784834 |  |  | 15.8 | -1780318.2
|  |  | PROGRESSIVE FRAME AND FABRICATION |  |  |  |  | 6316.56 |  |  |  | 40074.32 | 100024.18 | 24810.69 |  | 171225.75
|  | Material - Direct Purchase Total |  | 4500 | 26200 |  |  | 6316.56 |  |  |  | -1744759.68 | 100024.18 | 24810.69 | 15.8 | -1582892.45
| Steel / Fabricated / Structural-DP Total |  |  | 4500 | 26200 |  |  | 6316.56 |  |  |  | -1744759.68 | 100024.18 | 24810.69 | 15.8 | -1582892.45
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | COMEMSA |  |  |  |  | 242110.84 | [7 empty] | 242110.84
|  |  | Material Entries <$5,000 |  |  |  | -235714.6 |  |  |  |  | -542110.55 |  |  |  | -777825.15
|  |  | SISTTEMEX INC. |  |  | 157242.51 |  |  |  | 7500 | [5 empty] | 164742.51
|  |  | Steel Lattice Towers (T/S)-DP | [7 empty] | 906239.13 |  |  |  |  | 906239.13
|  | Material - Direct Purchase Total |  |  |  | 157242.51 | -235714.6 | 242110.84 |  | 7500 | 906239.13 | -542110.55 |  |  |  | 535267.33
| Steel Lattice Towers (T/S)-DP Total |  |  |  |  | 157242.51 | -235714.6 | 242110.84 |  | 7500 | 906239.13 | -542110.55 |  |  |  | 535267.33
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | Towers/Poles, Steel & Concrete-DP | [11 empty] | 77757 | 77757
|  | Material - Direct Purchase Total | [12 empty] | 77757 | 77757
| Towers/Poles, Steel & Concrete-DP Total | [13 empty] | 77757 | 77757
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 16.71 | 233.29 | 17.62 | 230.56 | 9.01 |  |  |  | 752.86 |  |  |  | 1260.05
|  | Material - Direct Purchase Total |  | 16.71 | 233.29 | 17.62 | 230.56 | 9.01 |  |  |  | 752.86 |  |  |  | 1260.05
| Transportation & Mobile Equip-DP Total |  |  | 16.71 | 233.29 | 17.62 | 230.56 | 9.01 |  |  |  | 752.86 |  |  |  | 1260.05
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | SOUTHWIRE COMPANY |  |  |  | 297165 | [5 empty] | 5900 |  |  | 303065
|  | Material - Direct Purchase Total |  |  |  |  | 297165 | [5 empty] | 5900 |  |  | 303065
| Wire, Cable & Bus Bar-DP Total | [5 empty] | 297165 | [5 empty] | 5900 |  |  | 303065
2. Material Total |  |  |  | 6447.29 | 100448.45 | 240019.85 | 166404.28 | 417659.4 | 66094.89 | 443899.57 | 1089629.51 | -2781371.27 | 1384185.76 | 627744.23 | 448023.38 | 2209185.34
3. Construction | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  | 29.79 |  | 6.38 | 140.41 |  |  | 6569.14 | 2686.17 |  | 3.19 | 9435.08
|  | Contract Total |  |  |  | 29.79 |  | 6.38 | 140.41 |  |  | 6569.14 | 2686.17 |  | 3.19 | 9435.08
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  |  | 29.79 |  | 6.38 | 140.41 |  |  | 6569.14 | 2686.17 |  | 3.19 | 9435.08
| Construction Management Services | Contract | Contract Entries <$50,000 | [11 empty] | 128.8 | 128.8
|  | Contract Total | [12 empty] | 128.8 | 128.8
| Construction Management Services Total | [13 empty] | 128.8 | 128.8
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 |  |  | 1938.38 | 659.06 |  |  |  |  | 77.61 |  | 189.54 |  | 2864.59
|  | Labor Total |  |  |  | 1938.38 | 659.06 |  |  |  |  | 77.61 |  | 189.54 |  | 2864.59
| EAST GRID MGMTCENTER Total |  |  |  |  | 1938.38 | 659.06 |  |  |  |  | 77.61 |  | 189.54 |  | 2864.59
| Elect Construction, Distribution | Contract | Contract Entries <$50,000 |  | 38775 |  |  |  |  | 5606.12 |  | 3436.69 |  |  |  | 47817.81
|  | Contract Total |  |  | 38775 |  |  |  |  | 5606.12 |  | 3436.69 |  |  |  | 47817.81
| Elect Construction, Distribution Total |  |  |  | 38775 |  |  |  |  | 5606.12 |  | 3436.69 |  |  |  | 47817.81
| Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 |  |  |  | 0 | -0.86 |  |  |  |  | -1.75 |  | -2 | -4.61
|  |  | Electrical Construction, Transmission Li | [11 empty] | 451798 | 451798
|  |  | HENKELS & MC COY INC |  |  |  |  | 124200 | [7 empty] | 124200
|  |  | WILSON UTILITY CONSTRUCTION | 1236498.46 | 1160058.41 | 2985344.94 | 1364167.86 |  | 2998701.62 |  | 6068302.89 |  | 6261181.75 |  | 4736761 | 26811016.93
|  | Contract Total |  | 1236498.46 | 1160058.41 | 2985344.94 | 1364167.86 | 124199.14 | 2998701.62 |  | 6068302.89 |  | 6261180 |  | 5188557 | 27387010.32
| Electrical Construction, Transmission Li Total |  |  | 1236498.46 | 1160058.41 | 2985344.94 | 1364167.86 | 124199.14 | 2998701.62 |  | 6068302.89 |  | 6261180 |  | 5188557 | 27387010.32
| GRID OPS | Labor | Labor Entries <$5,000 | [7 empty] | 238.21 | 302.1 |  |  | 528.32 | 1068.63
|  | Labor Total | [8 empty] | 238.21 | 302.1 |  |  | 528.32 | 1068.63
| GRID OPS Total | [9 empty] | 238.21 | 302.1 |  |  | 528.32 | 1068.63
| Labor - Other | Labor | ACQ/TRTP Seg. 8-Const/Mira Loma-Vincent | 7150.17 | 6062.15 | 5529.23 | 8399.66 |  |  |  | 6488.22 | 10783.77 |  |  | 12905.6 | 57318.8
|  |  | Labor Entries <$5,000 | 3904.03 | 5069.02 | 2882.23 | 3426.73 | 5123.52 | 6165.97 | 7147.13 | 1487.09 | 179417.39 | -170555.79 | 9457.46 | 3236.05 | 56760.83
|  | Labor Total |  | 11054.2 | 11131.17 | 8411.46 | 11826.39 | 5123.52 | 6165.97 | 7147.13 | 7975.31 | 190201.16 | -170555.79 | 9457.46 | 16141.65 | 114079.63
| Labor - Other Total |  |  | 11054.2 | 11131.17 | 8411.46 | 11826.39 | 5123.52 | 6165.97 | 7147.13 | 7975.31 | 190201.16 | -170555.79 | 9457.46 | 16141.65 | 114079.63
| Line Structure Services | Contract | Contract Entries <$50,000 | [6 empty] | 22314.34 | [5 empty] | 22314.34
|  | Contract Total | [7 empty] | 22314.34 | [5 empty] | 22314.34
| Line Structure Services Total | [8 empty] | 22314.34 | [5 empty] | 22314.34
| Material - Other | Material | Material - Other | [5 empty] | 12.48 | [6 empty] | 12.48
|  | Material Total | [6 empty] | 12.48 | [6 empty] | 12.48
| Material - Other Total | [7 empty] | 12.48 | [6 empty] | 12.48
| Mechanical Services | Contract | MATCO SERVICES INC. |  |  |  | 156625 | [8 empty] | 156625
|  | Contract Total |  |  |  |  | 156625 | [8 empty] | 156625
| Mechanical Services Total | [5 empty] | 156625 | [8 empty] | 156625
| Other | Other | Other | 66.63 | 54.39 | 201.21 | 225 | 2475 |  | 1500021.81 | -1271466.12 | 20253.92 | 1000 |  | 1820.41 | 254652.25
|  | Other Total |  | 66.63 | 54.39 | 201.21 | 225 | 2475 |  | 1500021.81 | -1271466.12 | 20253.92 | 1000 |  | 1820.41 | 254652.25
| Other Total |  |  | 66.63 | 54.39 | 201.21 | 225 | 2475 |  | 1500021.81 | -1271466.12 | 20253.92 | 1000 |  | 1820.41 | 254652.25
| Security / Protection Services | Contract | Contract Entries <$50,000 | [6 empty] | 83.6 | [5 empty] | 83.6
|  | Contract Total | [7 empty] | 83.6 | [5 empty] | 83.6
| Security / Protection Services Total | [8 empty] | 83.6 | [5 empty] | 83.6
| TRANSMISSION | Labor | Labor Entries <$5,000 | 13092.7 | 686.64 |  | 1354.02 | 1419.68 | 1740.44 | 25.43 | 4788.99 | 6759.73 | 239.01 | 4794.18 | 54.97 | 34955.79
|  | Labor Total |  | 13092.7 | 686.64 |  | 1354.02 | 1419.68 | 1740.44 | 25.43 | 4788.99 | 6759.73 | 239.01 | 4794.18 | 54.97 | 34955.79
| TRANSMISSION Total |  |  | 13092.7 | 686.64 |  | 1354.02 | 1419.68 | 1740.44 | 25.43 | 4788.99 | 6759.73 | 239.01 | 4794.18 | 54.97 | 34955.79
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 1295.89 | 1719.18 | 2083 | 1297.83 |  |  |  | 1799.21 | 958.96 | 654.18 |  |  | 9808.25
|  | Labor Total |  | 1295.89 | 1719.18 | 2083 | 1297.83 |  |  |  | 1799.21 | 958.96 | 654.18 |  |  | 9808.25
| TRNS CAPITAL Total |  |  | 1295.89 | 1719.18 | 2083 | 1297.83 |  |  |  | 1799.21 | 958.96 | 654.18 |  |  | 9808.25
3. Construction Total |  |  |  | 1262007.88 | 1212424.79 | 2998008.78 | 1536155.16 | 133223.72 | 3006760.92 | 1535198.43 | 4811638.49 | 228559.31 | 6095203.57 | 14441.18 | 5207234.34 | 28040856.57
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -375175.04 | 25053.96 | 26081.68 | 10720.05 | 22732.31 | 21976.55 | 18027.57 | 845.02 | 1757.26 | -12675.22 | 24374.31 | -587527.98 | -823809.53
|  |  | Mira Loma Vincent - Segment 8 |  |  |  |  | 5338.33 |  | 9518.33 |  |  | 7403 |  | 7519.5 | 29779.16
|  |  | PROCUREMENT TDBU | 17744.73 | 12984.99 | 25212.83 | 14904.69 | 8482.06 | 20666.31 | 10962.84 | 50655.3 |  | 73144.24 | 8676.14 | 45343.63 | 288777.76
|  |  | TDBU Vehicle Cost | [9 empty] | 7401.07 |  |  | 7401.07
|  |  | TRTP 8 Mira Loma Vincent Construction | 133847.84 | 358538.78 | 194020.21 | 336241.9 | 448291.02 | 433131.97 | 772129.9 | 528359.06 |  | 742053.27 | 735969.56 | 496733.17 | 5179316.68
|  |  | TRTP SEGMENT 8 CHINO HILLS SECURITY | 25761.63 | 42700.55 | [5 empty] | 6803.86 |  | 7854.53 |  |  | 83120.57
|  |  | Work Package # 3 | 30139.15 | 61266.01 | 62938.04 | 80572.43 | 67848.52 | 78118.81 | 83304.68 | 58923.14 | 82175.69 | 82804.01 | 72680.43 | 130198.61 | 890969.52
|  | Chargeback Total |  | -167681.69 | 500544.29 | 308252.76 | 442439.07 | 552692.24 | 553893.64 | 893943.32 | 645586.38 | 83932.95 | 907984.9 | 841700.44 | 92266.93 | 5655555.23
| Chargebacks Total |  |  | -167681.69 | 500544.29 | 308252.76 | 442439.07 | 552692.24 | 553893.64 | 893943.32 | 645586.38 | 83932.95 | 907984.9 | 841700.44 | 92266.93 | 5655555.23
| Labor - Other | Labor | Division Overhead | 68563.82 | 72782.63 | 139069.02 | 69108.46 | 56538.66 | 140060.03 | 69102.56 | 314691.81 |  | 575213.62 | 8033.32 | 92076.12 | 1605240.05
|  |  | Labor Entries <$5,000 | 4319.26 | 2542.93 | 7115.91 | 9584.4 | 3095.92 | 5722.71 | 4868.24 | 3364.85 | -173012.5 | 12334.23 | 10445.67 | 5339.38 | -104279
|  |  | Paid Absence | 7814.58 | 6509.99 |  |  | 6566.25 |  |  | 6056.93 |  | 26076.26 |  |  | 53024.01
|  | Labor Total |  | 80697.66 | 81835.55 | 146184.93 | 78692.86 | 66200.83 | 145782.74 | 73970.8 | 324113.59 | -173012.5 | 613624.11 | 18478.99 | 97415.5 | 1553985.06
| Labor - Other Total |  |  | 80697.66 | 81835.55 | 146184.93 | 78692.86 | 66200.83 | 145782.74 | 73970.8 | 324113.59 | -173012.5 | 613624.11 | 18478.99 | 97415.5 | 1553985.06
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -68404.08 | 68404.08 |  |  | 0
|  | Overhead Total | [9 empty] | -68404.08 | 68404.08 |  |  | 0
| Overhead Correction Total | [10 empty] | -68404.08 | 68404.08 |  |  | 0
4. Allocated Total |  |  |  | -86984.03 | 582379.84 | 454437.69 | 521131.93 | 618893.07 | 699676.38 | 967914.12 | 969699.97 | -157483.63 | 1590013.09 | 860179.43 | 189682.43 | 7209540.29
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 806825.19 | 50359.86 | [6 empty] | 1073295.32 | 1930480.37
|  |  | Capitalized Overhead - A&G | 139028.24 | 77443.62 | 155788.43 | 101907.97 | 164112.14 | 139641.47 | 147915.77 | 211874.89 | -90910.48 | 249237.04 | 57945.9 | 200307.79 | 1554292.78
|  |  | Capitalized Overhead - Inj & Damages | -110.36 | 622.53 | 576.58 | 321.14 | 5800.74 | 468.09 | 1985.88 | 428.58 | 282.79 | -2991.36 | 1189.4 | 1249.8 | 9823.81
|  |  | Capitalized Overhead - P&B/Payroll Tax | 70470.95 | 108080.57 | 72341.13 | 105137.29 | 118528.12 | 82812.38 | 85864.27 | 73517.02 | -77541.34 | 107293.43 | 63996.21 | 149680.31 | 960180.34
|  | Non Budgeted Total |  | 209388.83 | 186146.72 | 228706.14 | 1014191.59 | 338800.86 | 222921.94 | 235765.92 | 285820.49 | -168169.03 | 353539.11 | 123131.51 | 1424533.22 | 4454777.3
| Non Budget - Other Total |  |  | 209388.83 | 186146.72 | 228706.14 | 1014191.59 | 338800.86 | 222921.94 | 235765.92 | 285820.49 | -168169.03 | 353539.11 | 123131.51 | 1424533.22 | 4454777.3
5. Corporate Overhead Total |  |  |  | 209388.83 | 186146.72 | 228706.14 | 1014191.59 | 338800.86 | 222921.94 | 235765.92 | 285820.49 | -168169.03 | 353539.11 | 123131.51 | 1424533.22 | 4454777.3
Grand Total |  |  |  | 3829459.72 | 2499463.82 | 3702465.82 | 3636618.51 | 3868618.78 | 3798249.29 | 8070324.61 | 9748919.91 | -671814.22 | 2706687.1 | 6731480.66 | 7054704.42 | 54975178.42

## 800218618
Pin: 6439 | Project: TRTP Segment 8
Order: 800218618 | 800218618- I: TRTP 8-7: CHINO-MIRA LOMA #1 & #2: CO
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [6 empty] | 87.87 | [5 empty] | 87.87
|  | Labor Total | [7 empty] | 87.87 | [5 empty] | 87.87
| BP&FM Total | [8 empty] | 87.87 | [5 empty] | 87.87
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 |  |  | 550 | [9 empty] | 550
|  | Contract Total |  |  |  | 550 | [9 empty] | 550
| Building/Facility Repairs & Maintenance Total |  |  |  |  | 550 | [9 empty] | 550
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 870.48 | 870.48
|  | Labor Total | [12 empty] | 870.48 | 870.48
| ELEC SYS PLANNING Total | [13 empty] | 870.48 | 870.48
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 353.28 | 97.94 |  |  |  |  | 351.72 | [5 empty] | 802.94
|  | Labor Total |  | 353.28 | 97.94 |  |  |  |  | 351.72 | [5 empty] | 802.94
| ENG ADVANCEMENT Total |  |  | 353.28 | 97.94 |  |  |  |  | 351.72 | [5 empty] | 802.94
| ENGINEERING | Labor | Labor Entries <$5,000 | 3267.62 | 2984.39 | 1861.27 | 1179.28 |  |  | 426.23 | 1307.51 | 1668.32 | 2836.25 | 2442.14 |  | 17973.01
|  | Labor Total |  | 3267.62 | 2984.39 | 1861.27 | 1179.28 |  |  | 426.23 | 1307.51 | 1668.32 | 2836.25 | 2442.14 |  | 17973.01
| ENGINEERING Total |  |  | 3267.62 | 2984.39 | 1861.27 | 1179.28 |  |  | 426.23 | 1307.51 | 1668.32 | 2836.25 | 2442.14 |  | 17973.01
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | 145067 | 64348 | 60347 | 63267 | 70872 |  | 117966 | 61279 |  |  |  |  | 583146
|  |  | Contract Entries <$50,000 |  | 10832.17 |  | 2154.25 |  | 5690.35 | 10499.85 | 3413.35 | 2277.05 | 472.86 | 9134.8 | 16645.82 | 61120.5
|  | Contract Total |  | 145067 | 75180.17 | 60347 | 65421.25 | 70872 | 5690.35 | 128465.85 | 64692.35 | 2277.05 | 472.86 | 9134.8 | 16645.82 | 644266.5
| Engineering/Technical Professional Servi Total |  |  | 145067 | 75180.17 | 60347 | 65421.25 | 70872 | 5690.35 | 128465.85 | 64692.35 | 2277.05 | 472.86 | 9134.8 | 16645.82 | 644266.5
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -1311.67 | -572.91 | -2961.07 | -511.12 | -476.34 | -4240.21 | -847.87 | -1256.52 | -15.03 | -15383.37 |  | -27576.11
|  | IMM Correction Total |  |  | -1311.67 | -572.91 | -2961.07 | -511.12 | -476.34 | -4240.21 | -847.87 | -1256.52 | -15.03 | -15383.37 |  | -27576.11
| IMM/Allocated - Correction Total |  |  |  | -1311.67 | -572.91 | -2961.07 | -511.12 | -476.34 | -4240.21 | -847.87 | -1256.52 | -15.03 | -15383.37 |  | -27576.11
| Labor - Other | Labor | Labor Entries <$5,000 | 55.59 | 264.96 | -324.44 | 185.87 | 2095.28 | -466.08 | -51.15 | 65.76 | -41.06 | 419.15 | -438.99 | 57.42 | 1822.31
|  | Labor Total |  | 55.59 | 264.96 | -324.44 | 185.87 | 2095.28 | -466.08 | -51.15 | 65.76 | -41.06 | 419.15 | -438.99 | 57.42 | 1822.31
| Labor - Other Total |  |  | 55.59 | 264.96 | -324.44 | 185.87 | 2095.28 | -466.08 | -51.15 | 65.76 | -41.06 | 419.15 | -438.99 | 57.42 | 1822.31
| Other | Other | Other | -304226.54 | -17490.59 | 63616.05 | 39182.08 | 238553.37 | 503195.98 | -696994.56 | -140365.55 | -703.08 | -37226.93 | 26104.3 | 167400.66 | -158954.81
|  | Other Total |  | -304226.54 | -17490.59 | 63616.05 | 39182.08 | 238553.37 | 503195.98 | -696994.56 | -140365.55 | -703.08 | -37226.93 | 26104.3 | 167400.66 | -158954.81
| Other Total |  |  | -304226.54 | -17490.59 | 63616.05 | 39182.08 | 238553.37 | 503195.98 | -696994.56 | -140365.55 | -703.08 | -37226.93 | 26104.3 | 167400.66 | -158954.81
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 2629.72 | 2860 | 1612 | 1924 | 1300 | 2028 |  | 3180 |  | 127.5 |  |  | 15661.22
|  | Contract Total |  | 2629.72 | 2860 | 1612 | 1924 | 1300 | 2028 |  | 3180 |  | 127.5 |  |  | 15661.22
| Temporary/Supplementary - Trade/Labor Total |  |  | 2629.72 | 2860 | 1612 | 1924 | 1300 | 2028 |  | 3180 |  | 127.5 |  |  | 15661.22
| TRNS CAPITAL | Labor | Labor Entries <$5,000 |  |  | 512.66 | 1044.53 |  |  |  | 770.99 |  |  |  |  | 2328.18
|  | Labor Total |  |  |  | 512.66 | 1044.53 |  |  |  | 770.99 |  |  |  |  | 2328.18
| TRNS CAPITAL Total |  |  |  |  | 512.66 | 1044.53 |  |  |  | 770.99 |  |  |  |  | 2328.18
1. Project Support Total |  |  |  | -152853.33 | 62585.2 | 127601.63 | 105975.94 | 312309.53 | 509971.91 | -571954.25 | -71196.81 | 1944.71 | -33386.2 | 21858.88 | 184974.38 | 497831.59
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  | 74.43 | [10 empty] | 74.43
|  | Material - Direct Purchase Total |  |  | 74.43 | [10 empty] | 74.43
| Building, Shop & Industrial Products/Eqp Total |  |  |  | 74.43 | [10 empty] | 74.43
| Material - Inventory | Material | Material - Inventory | [5 empty] | -10351.9 | [6 empty] | -10351.9
|  | Material Total | [6 empty] | -10351.9 | [6 empty] | -10351.9
| Material - Inventory Total | [7 empty] | -10351.9 | [6 empty] | -10351.9
| Material - Other | Material | Material - Other | 3131.93 | 66.11 | 13719.27 | 169.67 |  | 40753.48 |  | -1.08 |  |  | -37547.63 |  | 20291.75
|  | Material Total |  | 3131.93 | 66.11 | 13719.27 | 169.67 |  | 40753.48 |  | -1.08 |  |  | -37547.63 |  | 20291.75
| Material - Other Total |  |  | 3131.93 | 66.11 | 13719.27 | 169.67 |  | 40753.48 |  | -1.08 |  |  | -37547.63 |  | 20291.75
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 142.5 |  | 928.83 | [8 empty] | 1071.33
|  |  | ONE SOURCE DISTRIBUTORS INC | [5 empty] | 10037.86 | [6 empty] | 10037.86
|  | Material - Direct Purchase Total |  |  | 142.5 |  | 928.83 |  | 10037.86 | [6 empty] | 11109.19
| Pole Line Hdwe & Connectors-DP Total |  |  |  | 142.5 |  | 928.83 |  | 10037.86 | [6 empty] | 11109.19
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | -12 | [8 empty] | -12
|  |  | ON-RAMP WIRELESS, INC. |  |  | 53895 | [9 empty] | 53895
|  | Material - Direct Purchase Total |  |  |  | 53895 | -12 | [8 empty] | 53883
| Power Systems, Batteries and Light-DP Total |  |  |  |  | 53895 | -12 | [8 empty] | 53883
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | 24100.14 | [11 empty] | 24100.14
|  |  | Material Entries <$5,000 | 425 |  |  |  |  | 50 | [6 empty] | 475
|  | Material - Direct Purchase Total |  | 24525.14 |  |  |  |  | 50 | [6 empty] | 24575.14
| Steel / Fabricated / Structural-DP Total |  |  | 24525.14 |  |  |  |  | 50 | [6 empty] | 24575.14
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | -385208 |  | -385208
|  |  | VALMONT INDUSTRIES INC |  |  | 57532 |  |  | 339328 | [6 empty] | 396860
|  | Material - Direct Purchase Total |  |  |  | 57532 |  |  | 339328 |  |  |  |  | -385208 |  | 11652
| Towers/Poles, Steel & Concrete-DP Total |  |  |  |  | 57532 |  |  | 339328 |  |  |  |  | -385208 |  | 11652
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 2517.07 | 1111.03 | 2576.34 | 1743.25 |  | 610.49 | [6 empty] | 8558.18
|  | Material - Direct Purchase Total |  | 2517.07 | 1111.03 | 2576.34 | 1743.25 |  | 610.49 | [6 empty] | 8558.18
| Transportation & Mobile Equip-DP Total |  |  | 2517.07 | 1111.03 | 2576.34 | 1743.25 |  | 610.49 | [6 empty] | 8558.18
2. Material Total |  |  |  | 30174.14 | 1394.07 | 127722.61 | 2829.75 |  | 380427.93 |  | -1.08 |  |  | -422755.63 |  | 119791.79
3. Construction | Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 | 7437 | 7437 |  | 7437 |  | -59263 |  |  |  | -0.13 |  |  | -36952.13
|  |  | WILSON UTILITY CONSTRUCTION |  |  | 272135 |  |  | 343975 |  | 122509 |  | 2330214.13 |  |  | 3068833.13
|  | Contract Total |  | 7437 | 7437 | 272135 | 7437 |  | 284712 |  | 122509 |  | 2330214 |  |  | 3031881
| Electrical Construction, Transmission Li Total |  |  | 7437 | 7437 | 272135 | 7437 |  | 284712 |  | 122509 |  | 2330214 |  |  | 3031881
3. Construction Total |  |  |  | 7437 | 7437 | 272135 | 7437 |  | 284712 |  | 122509 |  | 2330214 |  |  | 3031881
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 6425.63 | 9513.2 | 11555.03 | 11223.22 | 9284.23 | 7406.06 | 909.21 | 1351.09 | 116.57 | 187.2 | -2339.07 | 178.34 | 55810.71
|  |  | PROCUREMENT TDBU | [9 empty] | 15383.37 |  |  | 15383.37
|  |  | Work Package # 3 | [5 empty] | 5429.87 | [6 empty] | 5429.87
|  | Chargeback Total |  | 6425.63 | 9513.2 | 11555.03 | 11223.22 | 9284.23 | 12835.93 | 909.21 | 1351.09 | 116.57 | 15570.57 | -2339.07 | 178.34 | 76623.95
| Chargebacks Total |  |  | 6425.63 | 9513.2 | 11555.03 | 11223.22 | 9284.23 | 12835.93 | 909.21 | 1351.09 | 116.57 | 15570.57 | -2339.07 | 178.34 | 76623.95
| Labor - Other | Labor | Division Overhead |  |  | 6595.27 |  |  | 24779.34 |  |  |  | 120969.26 |  |  | 152343.87
|  |  | Labor Entries <$5,000 | 11668.79 | 8673.83 | 10274.28 | 3101.81 | 3096.61 | 3415.1 | 5565.61 | 8386.1 | 464.11 | 811.65 | -3680.71 | 438.07 | 52215.25
|  | Labor Total |  | 11668.79 | 8673.83 | 16869.55 | 3101.81 | 3096.61 | 28194.44 | 5565.61 | 8386.1 | 464.11 | 121780.91 | -3680.71 | 438.07 | 204559.12
| Labor - Other Total |  |  | 11668.79 | 8673.83 | 16869.55 | 3101.81 | 3096.61 | 28194.44 | 5565.61 | 8386.1 | 464.11 | 121780.91 | -3680.71 | 438.07 | 204559.12
4. Allocated Total |  |  |  | 18094.42 | 18187.03 | 28424.58 | 14325.03 | 12380.84 | 41030.37 | 6474.82 | 9737.19 | 580.68 | 137351.48 | -6019.78 | 616.41 | 281183.07
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G | 11556.97 | 3137.44 | 17547.09 | 3258.87 | 7169.14 | 25446.01 | 4617.88 | 5697.06 | 145.4 | 63853.23 | -11443.55 | 510.71 | 131496.25
|  |  | Capitalized Overhead - Inj & Damages | 47.98 | 33.53 | 160.54 | 9.8 | 86.29 | 534.59 | 2.79 | 14.38 | 0.88 | 444.21 | -727.16 | 1.74 | 609.57
|  |  | Capitalized Overhead - P&B/Payroll Tax | 4635.91 | 8770.07 | 4961.22 | 8713.23 | 7815.38 | 3166.44 | 1055 | 1743.14 | 2303.1 | 1538.37 | 1640.5 | 2115.95 | 48458.31
|  |  | Corporate Overheads Correction |  |  |  |  | -1481605.08 | [7 empty] | -1481605.08
|  | Non Budgeted Total |  | 16240.86 | 11941.04 | 22668.85 | 11981.9 | -1466534.27 | 29147.04 | 5675.67 | 7454.58 | 2449.38 | 65835.81 | -10530.21 | 2628.4 | -1301040.95
| Non Budget - Other Total |  |  | 16240.86 | 11941.04 | 22668.85 | 11981.9 | -1466534.27 | 29147.04 | 5675.67 | 7454.58 | 2449.38 | 65835.81 | -10530.21 | 2628.4 | -1301040.95
5. Corporate Overhead Total |  |  |  | 16240.86 | 11941.04 | 22668.85 | 11981.9 | -1466534.27 | 29147.04 | 5675.67 | 7454.58 | 2449.38 | 65835.81 | -10530.21 | 2628.4 | -1301040.95
Grand Total |  |  |  | -80906.91 | 101544.34 | 578552.67 | 142549.62 | -1141843.9 | 1245289.25 | -559803.76 | 68502.88 | 4974.77 | 2500015.09 | -417446.74 | 188219.19 | 2629646.5

## 800218551
Pin: 6439 | Project: TRTP Segment 8
Order: 800218551 | 800218551- I: TRTP 8-4: CONSTRUCT 0.44 MILES 220KV
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 126.36 | 67.01 |  |  |  |  | 49.27 | [5 empty] | 242.64
|  | Labor Total |  | 126.36 | 67.01 |  |  |  |  | 49.27 | [5 empty] | 242.64
| ENG ADVANCEMENT Total |  |  | 126.36 | 67.01 |  |  |  |  | 49.27 | [5 empty] | 242.64
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 20724 | 12396.2 | 8621 | 10545.98 | 10125 | 3983.24 | 18351.98 | 11143.35 | 1267.35 | 331.01 | 1380.06 | 2479.04 | 101348.21
|  | Contract Total |  | 20724 | 12396.2 | 8621 | 10545.98 | 10125 | 3983.24 | 18351.98 | 11143.35 | 1267.35 | 331.01 | 1380.06 | 2479.04 | 101348.21
| Engineering/Technical Professional Servi Total |  |  | 20724 | 12396.2 | 8621 | 10545.98 | 10125 | 3983.24 | 18351.98 | 11143.35 | 1267.35 | 331.01 | 1380.06 | 2479.04 | 101348.21
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -162.61 | -351.52 | -669.8 | -325.51 | -66.83 | -282.2 | -121.12 | -73.55 | -8.36 | -2429.7 | -9.11 | -4500.31
|  | IMM Correction Total |  |  | -162.61 | -351.52 | -669.8 | -325.51 | -66.83 | -282.2 | -121.12 | -73.55 | -8.36 | -2429.7 | -9.11 | -4500.31
| IMM/Allocated - Correction Total |  |  |  | -162.61 | -351.52 | -669.8 | -325.51 | -66.83 | -282.2 | -121.12 | -73.55 | -8.36 | -2429.7 | -9.11 | -4500.31
| Labor - Other | Labor | Labor Entries <$5,000 | 12.45 | 12.4 | 15.34 | 5.86 | 7.11 | 0.61 | 6.74 | -3.58 | 0.05 |  |  |  | 56.98
|  | Labor Total |  | 12.45 | 12.4 | 15.34 | 5.86 | 7.11 | 0.61 | 6.74 | -3.58 | 0.05 |  |  |  | 56.98
| Labor - Other Total |  |  | 12.45 | 12.4 | 15.34 | 5.86 | 7.11 | 0.61 | 6.74 | -3.58 | 0.05 |  |  |  | 56.98
| Other | Other | Other | -144542.95 | 12381.71 | -1967.54 | -34003.06 | 34616.02 | -21310.44 | -13351.61 | -6568.79 | 167.1 | -204285.57 | 3729.19 | 4418.57 | -370717.37
|  | Other Total |  | -144542.95 | 12381.71 | -1967.54 | -34003.06 | 34616.02 | -21310.44 | -13351.61 | -6568.79 | 167.1 | -204285.57 | 3729.19 | 4418.57 | -370717.37
| Other Total |  |  | -144542.95 | 12381.71 | -1967.54 | -34003.06 | 34616.02 | -21310.44 | -13351.61 | -6568.79 | 167.1 | -204285.57 | 3729.19 | 4418.57 | -370717.37
1. Project Support Total |  |  |  | -123680.14 | 24694.71 | 6317.28 | -24121.02 | 44422.62 | -17393.42 | 4774.18 | 4449.86 | 1360.95 | -203962.92 | 2679.55 | 6888.5 | -273569.85
2. Material | Material - Other | Material | Material - Other |  |  | 0.04 | [9 empty] | 0.04
|  | Material Total |  |  |  | 0.04 | [9 empty] | 0.04
| Material - Other Total |  |  |  |  | 0.04 | [9 empty] | 0.04
2. Material Total | [5 empty] | 0.04 | [9 empty] | 0.04
3. Construction | Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 | 1860.5 | 40864 | 38774 | 38774 |  | 38774 | [6 empty] | 159046.5
|  |  | Electrical Construction, Transmission Li | [11 empty] | 620625 | 620625
|  |  | WILSON UTILITY CONSTRUCTION |  |  | 54090 | [6 empty] | 367806 |  |  | 421896
|  | Contract Total |  | 1860.5 | 40864 | 92864 | 38774 |  | 38774 |  |  |  | 367806 |  | 620625 | 1201567.5
| Electrical Construction, Transmission Li Total |  |  | 1860.5 | 40864 | 92864 | 38774 |  | 38774 |  |  |  | 367806 |  | 620625 | 1201567.5
3. Construction Total |  |  |  | 1860.5 | 40864 | 92864 | 38774 |  | 38774 |  |  |  | 367806 |  | 620625 | 1201567.5
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 761.28 | 1527.74 | 1882.41 | 1837.07 | 1326.21 | 1772.83 | 125.25 | 73.3 | 8.36 | 2429.7 | 9.11 | 4112.49 | 15865.75
|  | Chargeback Total |  | 761.28 | 1527.74 | 1882.41 | 1837.07 | 1326.21 | 1772.83 | 125.25 | 73.3 | 8.36 | 2429.7 | 9.11 | 4112.49 | 15865.75
| Chargebacks Total |  |  | 761.28 | 1527.74 | 1882.41 | 1837.07 | 1326.21 | 1772.83 | 125.25 | 73.3 | 8.36 | 2429.7 | 9.11 | 4112.49 | 15865.75
| Labor - Other | Labor | Division Overhead | [9 empty] | 12111.71 |  |  | 12111.71
|  |  | Labor Entries <$5,000 | 1322.4 | 4630.34 | 3694.06 | 1583.17 | 441.44 | 1906.98 | 778.37 | 455.34 | 40.31 | 6994.6 | 14.77 | 8349.6 | 30211.38
|  | Labor Total |  | 1322.4 | 4630.34 | 3694.06 | 1583.17 | 441.44 | 1906.98 | 778.37 | 455.34 | 40.31 | 19106.31 | 14.77 | 8349.6 | 42323.09
| Labor - Other Total |  |  | 1322.4 | 4630.34 | 3694.06 | 1583.17 | 441.44 | 1906.98 | 778.37 | 455.34 | 40.31 | 19106.31 | 14.77 | 8349.6 | 42323.09
4. Allocated Total |  |  |  | 2083.68 | 6158.08 | 5576.47 | 3420.24 | 1767.65 | 3679.81 | 903.62 | 528.64 | 48.67 | 21536.01 | 23.88 | 12462.09 | 58188.84
5. Corporate Overhead | Non Budget - Other | Non Budgeted | AFUDC - Debt/Equity |  |  | 24003.83 | -24003.83 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 1384.47 | 1738.29 | 3804.19 | 1857.07 | 963.32 | 1654.99 | 668.18 | 326.62 | 55.66 | 10067.69 | -27.11 | 17844.14 | 40337.51
|  |  | Capitalized Overhead - Inj & Damages | 1.99 | 9.95 | 4.7 | 1.72 | 7.46 | 3.46 | 0.62 | 0.52 | -0.02 | 68.02 | -3.96 | 14.02 | 108.48
|  |  | Capitalized Overhead - P&B/Payroll Tax | 382.9 | 789.07 | 421.62 | 808.62 | 755.98 | 566.37 | 72.3 | -4.55 | 0.06 |  |  |  | 3792.37
|  |  | Corporate Overheads Correction |  |  |  |  | -154962.25 | [7 empty] | -154962.25
|  | Non Budgeted Total |  | 1769.36 | 2537.31 | 28234.34 | -21336.42 | -153235.49 | 2224.82 | 741.1 | 322.59 | 55.7 | 10135.71 | -31.07 | 17858.16 | -110723.89
| Non Budget - Other Total |  |  | 1769.36 | 2537.31 | 28234.34 | -21336.42 | -153235.49 | 2224.82 | 741.1 | 322.59 | 55.7 | 10135.71 | -31.07 | 17858.16 | -110723.89
5. Corporate Overhead Total |  |  |  | 1769.36 | 2537.31 | 28234.34 | -21336.42 | -153235.49 | 2224.82 | 741.1 | 322.59 | 55.7 | 10135.71 | -31.07 | 17858.16 | -110723.89
Grand Total |  |  |  | -117966.6 | 74254.1 | 132992.13 | -3263.2 | -107045.22 | 27285.21 | 6418.9 | 5301.09 | 1465.32 | 195514.8 | 2672.36 | 657833.75 | 875462.64

## 800218522
Pin: 6439 | Project: TRTP Segment 8
Order: 800218522 | 800218522- I: TRTP 8-2: CONSTRUCT 1.33 MILES DOUBLE
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 286.18 | 286.18
|  | Labor Total | [12 empty] | 286.18 | 286.18
| ELEC SYS PLANNING Total | [13 empty] | 286.18 | 286.18
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | [6 empty] | 49.27 | [5 empty] | 49.27
|  | Labor Total | [7 empty] | 49.27 | [5 empty] | 49.27
| ENG ADVANCEMENT Total | [8 empty] | 49.27 | [5 empty] | 49.27
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 1118.57 | 1150.87 | 1134.98 | 1391.81 | 1131.63 | 1142.89 | 1308.71 | 1140.18 | 760.1 |  | 10279.74
|  | Labor Total |  |  |  | 1118.57 | 1150.87 | 1134.98 | 1391.81 | 1131.63 | 1142.89 | 1308.71 | 1140.18 | 760.1 |  | 10279.74
| ENGINEERING Total |  |  |  |  | 1118.57 | 1150.87 | 1134.98 | 1391.81 | 1131.63 | 1142.89 | 1308.71 | 1140.18 | 760.1 |  | 10279.74
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 41447 | 21225.17 | 17242 | 18505.85 | 20250 | 1138.07 | 36704.95 | 18190.67 | 505.65 | 94.57 | 2598.16 | 4740.4 | 182642.49
|  | Contract Total |  | 41447 | 21225.17 | 17242 | 18505.85 | 20250 | 1138.07 | 36704.95 | 18190.67 | 505.65 | 94.57 | 2598.16 | 4740.4 | 182642.49
| Engineering/Technical Professional Servi Total |  |  | 41447 | 21225.17 | 17242 | 18505.85 | 20250 | 1138.07 | 36704.95 | 18190.67 | 505.65 | 94.57 | 2598.16 | 4740.4 | 182642.49
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -1356.27 | -1109.78 | -3662.29 | -379.51 | -133.65 | -1946.91 | -242.25 | -1350.17 | -3.34 | -1433.64 | -17.15 | -11634.96
|  | IMM Correction Total |  |  | -1356.27 | -1109.78 | -3662.29 | -379.51 | -133.65 | -1946.91 | -242.25 | -1350.17 | -3.34 | -1433.64 | -17.15 | -11634.96
| IMM/Allocated - Correction Total |  |  |  | -1356.27 | -1109.78 | -3662.29 | -379.51 | -133.65 | -1946.91 | -242.25 | -1350.17 | -3.34 | -1433.64 | -17.15 | -11634.96
| Labor - Other | Labor | Labor Entries <$5,000 | 12.45 | 12.4 | 25.84 | -27.81 | 126.58 | -145.81 | -12.53 | 46.81 | -20.45 | 139.88 | -100.38 | 43.34 | 100.32
|  | Labor Total |  | 12.45 | 12.4 | 25.84 | -27.81 | 126.58 | -145.81 | -12.53 | 46.81 | -20.45 | 139.88 | -100.38 | 43.34 | 100.32
| Labor - Other Total |  |  | 12.45 | 12.4 | 25.84 | -27.81 | 126.58 | -145.81 | -12.53 | 46.81 | -20.45 | 139.88 | -100.38 | 43.34 | 100.32
| Other | Other | Other | 142608.19 | 296878.43 | -446564.13 | -29454.42 | 311460.89 | -137040.71 | 66485.02 | -73437.84 | 25475.5 | 1686.87 | 1480025.06 | -1091875.92 | 546246.94
|  | Other Total |  | 142608.19 | 296878.43 | -446564.13 | -29454.42 | 311460.89 | -137040.71 | 66485.02 | -73437.84 | 25475.5 | 1686.87 | 1480025.06 | -1091875.92 | 546246.94
| Other Total |  |  | 142608.19 | 296878.43 | -446564.13 | -29454.42 | 311460.89 | -137040.71 | 66485.02 | -73437.84 | 25475.5 | 1686.87 | 1480025.06 | -1091875.92 | 546246.94
1. Project Support Total |  |  |  | 184067.64 | 316759.73 | -429287.5 | -13487.8 | 332592.94 | -134790.29 | 102411.43 | -54299.72 | 25919.24 | 3058.16 | 1481849.3 | -1086823.15 | 727969.98
2. Material | Material - Other | Material | Material - Other |  |  | 0.08 | [9 empty] | 0.08
|  | Material Total |  |  |  | 0.08 | [9 empty] | 0.08
| Material - Other Total |  |  |  |  | 0.08 | [9 empty] | 0.08
2. Material Total | [5 empty] | 0.08 | [9 empty] | 0.08
3. Construction | Electrical Construction, Transmission Li | Contract | Contract Entries <$50,000 |  |  |  | 38995 | [5 empty] | -1 |  |  | 38994
|  |  | WILSON UTILITY CONSTRUCTION | 146924 | 146924 | 537650 |  |  | 293848 |  | 186380 |  | 217124 |  | 1714837 | 3243687
|  | Contract Total |  | 146924 | 146924 | 537650 | 38995 |  | 293848 |  | 186380 |  | 217123 |  | 1714837 | 3282681
| Electrical Construction, Transmission Li Total |  |  | 146924 | 146924 | 537650 | 38995 |  | 293848 |  | 186380 |  | 217123 |  | 1714837 | 3282681
3. Construction Total |  |  |  | 146924 | 146924 | 537650 | 38995 |  | 293848 |  | 186380 |  | 217123 |  | 1714837 | 3282681
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 2470.04 | 3429.39 | 6145.72 | 3463.46 | 2706.11 | 4999.98 | 330.15 | 1402.55 | 83.73 | 1507.24 | 64.26 | 24.32 | 26626.95
|  |  | PROCUREMENT TDBU | [11 empty] | 11349.21 | 11349.21
|  | Chargeback Total |  | 2470.04 | 3429.39 | 6145.72 | 3463.46 | 2706.11 | 4999.98 | 330.15 | 1402.55 | 83.73 | 1507.24 | 64.26 | 11373.53 | 37976.16
| Chargebacks Total |  |  | 2470.04 | 3429.39 | 6145.72 | 3463.46 | 2706.11 | 4999.98 | 330.15 | 1402.55 | 83.73 | 1507.24 | 64.26 | 11373.53 | 37976.16
| Labor - Other | Labor | Division Overhead |  |  | 13872.3 | [8 empty] | 18227.53 | 32099.83
|  |  | Labor Entries <$5,000 | 10925.52 | 14544.91 | 6622.37 | 2131.32 | 1228.14 | 13500.86 | 1844.2 | 8708.88 | 344.58 | 11643.66 | 172.48 | 4901.42 | 76568.34
|  | Labor Total |  | 10925.52 | 14544.91 | 20494.67 | 2131.32 | 1228.14 | 13500.86 | 1844.2 | 8708.88 | 344.58 | 11643.66 | 172.48 | 23128.95 | 108668.17
| Labor - Other Total |  |  | 10925.52 | 14544.91 | 20494.67 | 2131.32 | 1228.14 | 13500.86 | 1844.2 | 8708.88 | 344.58 | 11643.66 | 172.48 | 23128.95 | 108668.17
4. Allocated Total |  |  |  | 13395.56 | 17974.3 | 26640.39 | 5594.78 | 3934.25 | 18500.84 | 2174.35 | 10111.43 | 428.31 | 13150.9 | 236.74 | 34502.48 | 146644.33
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 27012.83 | 1684.25 | [6 empty] | 45935.09 | 74632.17
|  |  | AFUDC - Debt/Equity |  |  | 27980.57 | -27980.57 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 11261.19 | 5413.34 | 20729.76 | 2159.48 | 2086.26 | 11228.14 | 1337.83 | 6099.15 | 39.07 | 5984.97 | 54.47 | 49256.99 | 115650.65
|  |  | Capitalized Overhead - Inj & Damages | 12.37 | 27.63 | 26.49 | 1.4 | 32.03 | 22.93 | 1.28 | 14.41 | 0.33 | 45.59 | -0.88 | 39.21 | 222.79
|  |  | Capitalized Overhead - P&B/Payroll Tax | 615.22 | 1411.21 | 1987.86 | 3046.73 | 3395.55 | 2799.07 | 1512.81 | 965.5 | 1845.77 | 625.63 | 562.74 | 770.73 | 19538.82
|  |  | Corporate Overheads Correction |  |  |  |  | -191448.06 | [7 empty] | -191448.06
|  | Non Budgeted Total |  | 11888.78 | 6852.18 | 50724.68 | 4239.87 | -184249.97 | 14050.14 | 2851.92 | 7079.06 | 1885.17 | 6656.19 | 616.33 | 96002.02 | 18596.37
| Non Budget - Other Total |  |  | 11888.78 | 6852.18 | 50724.68 | 4239.87 | -184249.97 | 14050.14 | 2851.92 | 7079.06 | 1885.17 | 6656.19 | 616.33 | 96002.02 | 18596.37
5. Corporate Overhead Total |  |  |  | 11888.78 | 6852.18 | 50724.68 | 4239.87 | -184249.97 | 14050.14 | 2851.92 | 7079.06 | 1885.17 | 6656.19 | 616.33 | 96002.02 | 18596.37
Grand Total |  |  |  | 356275.98 | 488510.21 | 185727.65 | 35341.85 | 152277.22 | 191608.69 | 107437.7 | 149270.77 | 28232.72 | 239988.25 | 1482702.37 | 758518.35 | 4175891.76

## 800051911
Pin: 6439 | Project: TRTP Segment 8
Order: 800051911 | 800051911- 9219-2380 - TRTP Segment 8
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 987.04 |  | -3.67 |  |  |  | 12.76 |  |  |  | 1.84 |  | 997.97
|  | Contract Total |  | 987.04 |  | -3.67 |  |  |  | 12.76 |  |  |  | 1.84 |  | 997.97
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 987.04 |  | -3.67 |  |  |  | 12.76 |  |  |  | 1.84 |  | 997.97
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -11931.68 | 11931.68 |  |  | 0
|  | Contract Total | [9 empty] | -11931.68 | 11931.68 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -11931.68 | 11931.68 |  |  | 0
| HRealProp | Labor | Labor Entries <$5,000 | 4008.51 | 3627.79 | 8491.95 | 6791.52 | 2958.48 | 5740.78 | 3775.51 | 3393.83 | 1034.46 | 1095.75 | 1084.7 | 830.1 | 42833.38
|  | Labor Total |  | 4008.51 | 3627.79 | 8491.95 | 6791.52 | 2958.48 | 5740.78 | 3775.51 | 3393.83 | 1034.46 | 1095.75 | 1084.7 | 830.1 | 42833.38
| HRealProp Total |  |  | 4008.51 | 3627.79 | 8491.95 | 6791.52 | 2958.48 | 5740.78 | 3775.51 | 3393.83 | 1034.46 | 1095.75 | 1084.7 | 830.1 | 42833.38
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -8.18 | -0.21 | -5.33 | -5.84 | -24.66 | -6.12 |  | 11152.4 | -11166.23 | -78.75 |  | -142.92
|  | IMM Correction Total |  |  | -8.18 | -0.21 | -5.33 | -5.84 | -24.66 | -6.12 |  | 11152.4 | -11166.23 | -78.75 |  | -142.92
| IMM/Allocated - Correction Total |  |  |  | -8.18 | -0.21 | -5.33 | -5.84 | -24.66 | -6.12 |  | 11152.4 | -11166.23 | -78.75 |  | -142.92
| Information System Professional Services | Contract | Contract Entries <$50,000 |  | 12.76 | -15.95 | 115.96 | 401.91 |  |  |  | 3.19 |  |  |  | 517.87
|  | Contract Total |  |  | 12.76 | -15.95 | 115.96 | 401.91 |  |  |  | 3.19 |  |  |  | 517.87
| Information System Professional Services Total |  |  |  | 12.76 | -15.95 | 115.96 | 401.91 |  |  |  | 3.19 |  |  |  | 517.87
| Labor - Other | Labor | Labor Entries <$5,000 | 1154.23 | 1522.6 | 771.99 | 1104.02 | 1465.54 | -229.45 | 148.74 | 96.64 | 246.95 | 2033.53 | 1149.02 | 34.43 | 9498.24
|  |  | TRTP 4-11 Title | [11 empty] | 5177.05 | 5177.05
|  | Labor Total |  | 1154.23 | 1522.6 | 771.99 | 1104.02 | 1465.54 | -229.45 | 148.74 | 96.64 | 246.95 | 2033.53 | 1149.02 | 5211.48 | 14675.29
| Labor - Other Total |  |  | 1154.23 | 1522.6 | 771.99 | 1104.02 | 1465.54 | -229.45 | 148.74 | 96.64 | 246.95 | 2033.53 | 1149.02 | 5211.48 | 14675.29
| Other | Other | Other | 60205.03 | 147584.99 | 4895.3 | 4607.2 | 3044.34 | 4950.05 |  | 1504490.46 | 4426 | -1345 |  |  | 1732858.37
|  | Other Total |  | 60205.03 | 147584.99 | 4895.3 | 4607.2 | 3044.34 | 4950.05 |  | 1504490.46 | 4426 | -1345 |  |  | 1732858.37
| Other Total |  |  | 60205.03 | 147584.99 | 4895.3 | 4607.2 | 3044.34 | 4950.05 |  | 1504490.46 | 4426 | -1345 |  |  | 1732858.37
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1045.44 |  |  | 268.25 | 290.4 |  |  | 80.48 |  |  |  |  | 1684.57
|  | Contract Total |  | 1045.44 |  |  | 268.25 | 290.4 |  |  | 80.48 |  |  |  |  | 1684.57
| Temporary/Supplementary - Trade/Labor Total |  |  | 1045.44 |  |  | 268.25 | 290.4 |  |  | 80.48 |  |  |  |  | 1684.57
1. Project Support Total |  |  |  | 67400.25 | 152739.96 | 14139.41 | 12881.62 | 8154.83 | 10436.72 | 3930.89 | 1508061.41 | 4931.32 | 2549.73 | 2156.81 | 6041.58 | 1793424.53
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 18.32 | 32.02 | [9 empty] | 50.34
|  | Material - Direct Purchase Total |  |  | 18.32 | 32.02 | [9 empty] | 50.34
| Transportation & Mobile Equip-DP Total |  |  |  | 18.32 | 32.02 | [9 empty] | 50.34
2. Material Total |  |  |  |  | 18.32 | 32.02 | [9 empty] | 50.34
3. Construction | HRealProp | Labor | Labor Entries <$5,000 |  | 67.79 | 48.38 | 3183.8 | 2332.63 |  |  | 199.13 |  | 455.15 |  |  | 6286.88
|  | Labor Total |  |  | 67.79 | 48.38 | 3183.8 | 2332.63 |  |  | 199.13 |  | 455.15 |  |  | 6286.88
| HRealProp Total |  |  |  | 67.79 | 48.38 | 3183.8 | 2332.63 |  |  | 199.13 |  | 455.15 |  |  | 6286.88
3. Construction Total |  |  |  |  | 67.79 | 48.38 | 3183.8 | 2332.63 |  |  | 199.13 |  | 455.15 |  |  | 6286.88
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 2283.18 | 3314.34 | 6170.41 | 81.99 | -1320.34 | 6.12 | 132.27 | 562.43 | 606.59 | 3997.39 | 4944.07 | 4039.39 | 24817.84
|  | Chargeback Total |  | 2283.18 | 3314.34 | 6170.41 | 81.99 | -1320.34 | 6.12 | 132.27 | 562.43 | 606.59 | 3997.39 | 4944.07 | 4039.39 | 24817.84
| Chargebacks Total |  |  | 2283.18 | 3314.34 | 6170.41 | 81.99 | -1320.34 | 6.12 | 132.27 | 562.43 | 606.59 | 3997.39 | 4944.07 | 4039.39 | 24817.84
| Labor - Other | Labor | Labor Entries <$5,000 | 924.11 | 934.44 | 1862.02 | 2285.66 | 1420.15 | 1055.2 | 848.27 | 851.74 | 49.23 | 1067.48 | 247.22 | 254.29 | 11799.81
|  | Labor Total |  | 924.11 | 934.44 | 1862.02 | 2285.66 | 1420.15 | 1055.2 | 848.27 | 851.74 | 49.23 | 1067.48 | 247.22 | 254.29 | 11799.81
| Labor - Other Total |  |  | 924.11 | 934.44 | 1862.02 | 2285.66 | 1420.15 | 1055.2 | 848.27 | 851.74 | 49.23 | 1067.48 | 247.22 | 254.29 | 11799.81
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -426.97 | -426.97
|  | Overhead Total | [12 empty] | -426.97 | -426.97
| Overhead Correction Total | [13 empty] | -426.97 | -426.97
4. Allocated Total |  |  |  | 3207.29 | 4248.78 | 8032.43 | 2367.65 | 99.81 | 1061.32 | 980.54 | 1414.17 | 655.82 | 5064.87 | 5191.29 | 3866.71 | 36190.68
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 72020.28 | 4380.5 | [6 empty] | 83849.5 | 160250.28
|  | Non Budgeted Total |  |  |  |  | 72020.28 | 4380.5 | [6 empty] | 83849.5 | 160250.28
| Non Budget - Other Total | [5 empty] | 72020.28 | 4380.5 | [6 empty] | 83849.5 | 160250.28
5. Corporate Overhead Total | [6 empty] | 72020.28 | 4380.5 | [6 empty] | 83849.5 | 160250.28
Grand Total |  |  |  | 70607.54 | 157074.85 | 22252.24 | 90453.35 | 14967.77 | 11498.04 | 4911.43 | 1509674.71 | 5587.14 | 8069.75 | 7348.1 | 93757.79 | 1996202.71

## TRTP Seg 9
WO | SumOfYTD2012 | Order | Project
900516432- TRTP 9 Lugo: Replace protective relays f | 272571.54 | 900516432 | TRTP Segment 9
900390201- Whirlwind Sub: Install two GE N60 relays | -1287.45 | 900390201 | TRTP Segment 9
900389798- Vincent: Replace existing F35 relays wit | 105914.3 | 900389798 | TRTP Segment 9
900280844- Chino Sub: Replace 220-kV relays, Remove | 14212.51 | 900280844 | TRTP Segment 9
800250145- I: TRTP 9: DRYCREEKWIND SUB: MINOR PROTE | -54325.48 | 800250145 | TRTP Segment 9
800219704- TRTP 9: GOULD: ADD CB'S ON TRANSFORMERS | 723605.27 | 800219704 | TRTP Segment 9
800219576- I: TRTP 9 & 3C: VINCENT: EXTEND 500KV SW | 91187.93 | 800219576 | TRTP Segment 9
800218712- I: TRTP 9: MIRA LOMA: ADD/CHANGE & EQUIP | 981190.66 | 800218712 | TRTP Segment 9
800218099- I: TRTP 9: MESA SUB: EQUIP POSITION FOR | 443272.49 | 800218099 | TRTP Segment 9
800218070- I: TRTP 9: PARDEE SUB: UPGRADE PROTECTIO | -11100.16 | 800218070 | TRTP Segment 9
800217014- I: TRTP 9: WINDHUB SUBSTATION - UPGRADE | 1925454.12 | 800217014 | TRTP Segment 9
800216929- I: TRTP 9: VINCENT: UPGRADE 500KV & 220K | 3112976.65 | 800216929 | TRTP Segment 9
800216848- I: TRTP 9: ANTELOPE: UPGRADE 500 KV POSI | 2421815.53 | 800216848 | TRTP Segment 9
800216839- I: TRTP 9: WHIRLWIND: CONSTRUCT NEW 500K | 9050801.41 | 800216839 | TRTP Segment 9
800208721- ACQ/TRTP Segment 9 | 60886.09 | 800208721 | TRTP Segment 9
800148389- Windhub: Construct 500kv breaker-and-a-h | 93692.69 | 800148389 | TRTP Segment 9
800148388- Whirlwind: Construct new 500/220kv subst | -161452.36 | 800148388 | TRTP Segment 9
800148387- Antelope: Construct new 500kV switchyard | 1924.46 | 800148387 | TRTP Segment 9

## 900516432
Pin: 6440 | Project: TRTP Segment 9
Order: 900516432 | 900516432- TRTP 9 Lugo: Replace protective relays f
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 100.84 |  |  | 251.57 | [8 empty] | 352.41
|  | Labor Total |  | 100.84 |  |  | 251.57 | [8 empty] | 352.41
| ENG ADVANCEMENT Total |  |  | 100.84 |  |  | 251.57 | [8 empty] | 352.41
| ENGINEERING | Labor | Labor Entries <$5,000 | 561.36 | 1046.8 | 855.31 | 2616.9 | 6656.34 | 2946.59 | 1425.52 | 2211.17 | 1878.45 | 730.06 | 660.14 | 257.35 | 21845.99
|  | Labor Total |  | 561.36 | 1046.8 | 855.31 | 2616.9 | 6656.34 | 2946.59 | 1425.52 | 2211.17 | 1878.45 | 730.06 | 660.14 | 257.35 | 21845.99
| ENGINEERING Total |  |  | 561.36 | 1046.8 | 855.31 | 2616.9 | 6656.34 | 2946.59 | 1425.52 | 2211.17 | 1878.45 | 730.06 | 660.14 | 257.35 | 21845.99
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  | 1295.22 | 3689.46 | 22083.54 | 6780 |  | 49938.72 | 684 |  |  |  |  | 84470.94
|  | Contract Total |  |  | 1295.22 | 3689.46 | 22083.54 | 6780 |  | 49938.72 | 684 |  |  |  |  | 84470.94
| Engineering/Technical Professional Servi Total |  |  |  | 1295.22 | 3689.46 | 22083.54 | 6780 |  | 49938.72 | 684 |  |  |  |  | 84470.94
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -3.64 | -14.2 | -24.35 | -147.61 | -47.18 | -14.89 | -339.29 | -335.48 | -0.71 | -206.96 | -37.14 | -1171.45
|  | IMM Correction Total |  |  | -3.64 | -14.2 | -24.35 | -147.61 | -47.18 | -14.89 | -339.29 | -335.48 | -0.71 | -206.96 | -37.14 | -1171.45
| IMM/Allocated - Correction Total |  |  |  | -3.64 | -14.2 | -24.35 | -147.61 | -47.18 | -14.89 | -339.29 | -335.48 | -0.71 | -206.96 | -37.14 | -1171.45
| Labor - Other | Labor | Labor Entries <$5,000 | 22.13 | 111.1 | -139.29 | 6.06 | 1581.02 | -1607.97 | 7.15 | -29.81 | 3.33 | 93.72 | -92.09 | 22.47 | -22.18
|  | Labor Total |  | 22.13 | 111.1 | -139.29 | 6.06 | 1581.02 | -1607.97 | 7.15 | -29.81 | 3.33 | 93.72 | -92.09 | 22.47 | -22.18
| Labor - Other Total |  |  | 22.13 | 111.1 | -139.29 | 6.06 | 1581.02 | -1607.97 | 7.15 | -29.81 | 3.33 | 93.72 | -92.09 | 22.47 | -22.18
| Other | Other | Other |  | 0 | -253 |  |  | 18763.07 | -18763.07 |  | 22566.19 | -22566.19 |  | 330 | 77
|  | Other Total |  |  | 0 | -253 |  |  | 18763.07 | -18763.07 |  | 22566.19 | -22566.19 |  | 330 | 77
| Other Total |  |  |  | 0 | -253 |  |  | 18763.07 | -18763.07 |  | 22566.19 | -22566.19 |  | 330 | 77
| SC&M | Labor | Labor Entries <$5,000 | [10 empty] | 255.75 |  | 255.75
|  | Labor Total | [11 empty] | 255.75 |  | 255.75
| SC&M Total | [12 empty] | 255.75 |  | 255.75
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 506 | 856.06 |  | 281.64 | 369.16 | 1926.14 | 1138.5 | 603.06 |  |  |  |  | 5680.56
|  | Contract Total |  | 506 | 856.06 |  | 281.64 | 369.16 | 1926.14 | 1138.5 | 603.06 |  |  |  |  | 5680.56
| Temporary/Supplementary - Trade/Labor Total |  |  | 506 | 856.06 |  | 281.64 | 369.16 | 1926.14 | 1138.5 | 603.06 |  |  |  |  | 5680.56
1. Project Support Total |  |  |  | 1190.33 | 3305.54 | 4138.28 | 25215.36 | 15238.91 | 21980.65 | 33731.93 | 3129.13 | 24112.49 | -21743.12 | 616.84 | 572.68 | 111489.02
2. Material | Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 142.6 |  | 142.6
|  | Material - Direct Purchase Total | [11 empty] | 142.6 |  | 142.6
| Cabinets, Panels and Switchboards-DP Total | [12 empty] | 142.6 |  | 142.6
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 2205.89 |  | 2205.89
|  |  | RFL ELECTRONICS INC | [7 empty] | 49465 |  |  |  |  | 49465
|  | Material - Direct Purchase Total | [8 empty] | 49465 |  |  | 2205.89 |  | 51670.89
| Electric Wiring and Components-DP Total | [9 empty] | 49465 |  |  | 2205.89 |  | 51670.89
| Material - Other | Material | Material - Other | [7 empty] | 3879.02 | 0.11 | 2455.84 | 1.7 |  | 6336.67
|  | Material Total | [8 empty] | 3879.02 | 0.11 | 2455.84 | 1.7 |  | 6336.67
| Material - Other Total | [9 empty] | 3879.02 | 0.11 | 2455.84 | 1.7 |  | 6336.67
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 1293.41 |  | 1293.41
|  | Material - Direct Purchase Total | [11 empty] | 1293.41 |  | 1293.41
| Metals & Fabricated Metal Products-DP Total | [12 empty] | 1293.41 |  | 1293.41
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 2.13 |  | 2.13
|  | Material - Direct Purchase Total | [11 empty] | 2.13 |  | 2.13
| Monitor Equipment, Gauges and Hoses-DP Total | [12 empty] | 2.13 |  | 2.13
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 51.22 |  | 51.22
|  | Material - Direct Purchase Total | [11 empty] | 51.22 |  | 51.22
| Pipe/Tubing, Fittings and Gaskets-DP Total | [12 empty] | 51.22 |  | 51.22
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 384.31 |  | 384.31
|  | Material - Direct Purchase Total | [11 empty] | 384.31 |  | 384.31
| Pole Line Hdwe & Connectors-DP Total | [12 empty] | 384.31 |  | 384.31
| Protection and Test-DP | Material - Direct Purchase | GE CONSUMER AND INDUSTRIAL | [9 empty] | 20737.58 |  |  | 20737.58
|  |  | Material Entries <$5,000 | [10 empty] | 603.11 |  | 603.11
|  |  | SCHWEITZER ENGINEERING LABS INC | [9 empty] | 10620 |  |  | 10620
|  | Material - Direct Purchase Total | [10 empty] | 31357.58 | 603.11 |  | 31960.69
| Protection and Test-DP Total | [11 empty] | 31357.58 | 603.11 |  | 31960.69
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 459.72 |  | 459.72
|  | Material - Direct Purchase Total | [11 empty] | 459.72 |  | 459.72
| Transformers CT/PT/INSTR-DP Total | [12 empty] | 459.72 |  | 459.72
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 77.84 | 108.22 |  |  |  | 186.06
|  | Material - Direct Purchase Total | [8 empty] | 77.84 | 108.22 |  |  |  | 186.06
| Transportation & Mobile Equip-DP Total | [9 empty] | 77.84 | 108.22 |  |  |  | 186.06
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 141.12 |  | 141.12
|  | Material - Direct Purchase Total | [11 empty] | 141.12 |  | 141.12
| Wire, Cable & Bus Bar-DP Total | [12 empty] | 141.12 |  | 141.12
2. Material Total | [10 empty] | 53421.86 | 108.33 | 33813.42 | 5285.21 |  | 92628.82
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [5 empty] | 330 | 330 |  |  |  | 344 | 944 | 1948
|  | Contract Total | [6 empty] | 330 | 330 |  |  |  | 344 | 944 | 1948
| Construction Management Services Total | [7 empty] | 330 | 330 |  |  |  | 344 | 944 | 1948
| SC&M | Labor | Labor Entries <$5,000 | [8 empty] | 137.32 | 122.04 |  | 624.1 | 883.46
|  | Labor Total | [9 empty] | 137.32 | 122.04 |  | 624.1 | 883.46
| SC&M Total | [10 empty] | 137.32 | 122.04 |  | 624.1 | 883.46
3. Construction Total | [8 empty] | 330 | 330 |  | 137.32 | 122.04 | 344 | 1568.1 | 2831.46
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 79.94 | 113.08 | 88.22 | 420.39 | 863.24 | 167.89 | 523.39 | 1208.82 | 545.57 | 325.56 | 125.5 | 88.47 | 4550.07
|  | Chargeback Total |  | 79.94 | 113.08 | 88.22 | 420.39 | 863.24 | 167.89 | 523.39 | 1208.82 | 545.57 | 325.56 | 125.5 | 88.47 | 4550.07
| Chargebacks Total |  |  | 79.94 | 113.08 | 88.22 | 420.39 | 863.24 | 167.89 | 523.39 | 1208.82 | 545.57 | 325.56 | 125.5 | 88.47 | 4550.07
| Labor - Other | Labor | Labor Entries <$5,000 | 303.88 | 607.63 | 516.76 | 2618.86 | 3115.25 | 566.9 | 4428.58 | 4479.15 | 636.19 | 2876.85 | 343.55 | 291.3 | 20784.9
|  | Labor Total |  | 303.88 | 607.63 | 516.76 | 2618.86 | 3115.25 | 566.9 | 4428.58 | 4479.15 | 636.19 | 2876.85 | 343.55 | 291.3 | 20784.9
| Labor - Other Total |  |  | 303.88 | 607.63 | 516.76 | 2618.86 | 3115.25 | 566.9 | 4428.58 | 4479.15 | 636.19 | 2876.85 | 343.55 | 291.3 | 20784.9
4. Allocated Total |  |  |  | 383.82 | 720.71 | 604.98 | 3039.25 | 3978.49 | 734.79 | 4951.97 | 5687.97 | 1181.76 | 3202.41 | 469.05 | 379.77 | 25334.97
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 402.71 | 35.88 | [6 empty] | 1524.52 | 1963.11
|  |  | Capitalized Overhead - A&G | 87.85 | 117.95 | 178.09 | 1007.58 | 1599.45 | 152.84 | 2028.72 | 1760.45 | 133.21 | 980.79 | 177.46 | 61.5 | 8285.89
|  |  | Capitalized Overhead - Inj & Damages | 1 | 3.24 | 1.38 | 4.88 | 107.71 | 2.62 | 5.83 | 79.44 | 2.7 | 119.94 | 10.48 | 1.4 | 340.62
|  |  | Capitalized Overhead - P&B/Payroll Tax | 466.72 | 1339.66 | 734.17 | 3694.01 | 12427.43 | 1791.85 | 1855.31 | 1773.29 | 2892.91 | 462.26 | 702.7 | 2085.01 | 30225.32
|  |  | Corporate Overheads Correction |  |  |  |  | -527.67 | [7 empty] | -527.67
|  | Non Budgeted Total |  | 555.57 | 1460.85 | 913.64 | 5109.18 | 13642.8 | 1947.31 | 3889.86 | 3613.18 | 3028.82 | 1562.99 | 890.64 | 3672.43 | 40287.27
| Non Budget - Other Total |  |  | 555.57 | 1460.85 | 913.64 | 5109.18 | 13642.8 | 1947.31 | 3889.86 | 3613.18 | 3028.82 | 1562.99 | 890.64 | 3672.43 | 40287.27
5. Corporate Overhead Total |  |  |  | 555.57 | 1460.85 | 913.64 | 5109.18 | 13642.8 | 1947.31 | 3889.86 | 3613.18 | 3028.82 | 1562.99 | 890.64 | 3672.43 | 40287.27
Grand Total |  |  |  | 2129.72 | 5487.1 | 5656.9 | 33363.79 | 32860.2 | 24992.75 | 42903.76 | 65852.14 | 28568.72 | 16957.74 | 7605.74 | 6192.98 | 272571.54

## 900390201
Pin: 6440 | Project: TRTP Segment 9
Order: 900390201 | 900390201- Whirlwind Sub: Install two GE N60 relays
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | 2012 Total
SubCategory | Prime | Group | Details | 5
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Corporate Overheads Correction | -1287.45 | -1287.45
|  | Non Budgeted Total |  | -1287.45 | -1287.45
| Non Budget - Other Total |  |  | -1287.45 | -1287.45
5. Corporate Overhead Total |  |  |  | -1287.45 | -1287.45
Grand Total |  |  |  | -1287.45 | -1287.45

## 900389798
Pin: 6440 | Project: TRTP Segment 9
Order: 900389798 | 900389798- Vincent: Replace existing F35 relays wit
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [10 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 10 | 11 | 12
1. Project Support | ENGINEERING | Labor | Labor Entries <$5,000 | 3752.08 | 2485.49 | 5057.73 | 548.06 | 2889.97 |  | 529.88 |  | 3162.97 | 107.05 |  | 18533.23
|  | Labor Total |  | 3752.08 | 2485.49 | 5057.73 | 548.06 | 2889.97 |  | 529.88 |  | 3162.97 | 107.05 |  | 18533.23
| ENGINEERING Total |  |  | 3752.08 | 2485.49 | 5057.73 | 548.06 | 2889.97 |  | 529.88 |  | 3162.97 | 107.05 |  | 18533.23
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  | -0.56 |  | -1.86 | -1.88 | -0.2 |  |  |  |  | -4.5
|  | IMM Correction Total |  |  |  | -0.56 |  | -1.86 | -1.88 | -0.2 |  |  |  |  | -4.5
| IMM/Allocated - Correction Total |  |  |  |  | -0.56 |  | -1.86 | -1.88 | -0.2 |  |  |  |  | -4.5
| Labor - Other | Labor | Labor Entries <$5,000 | 318.92 | 1277.94 | -1616.23 | 22.07 | 355.51 | -358.21 | -91.96 | 91.96 | 337.32 | -358.09 | 20.77 | 1.3145e-13
|  | Labor Total |  | 318.92 | 1277.94 | -1616.23 | 22.07 | 355.51 | -358.21 | -91.96 | 91.96 | 337.32 | -358.09 | 20.77 | 1.3145e-13
| Labor - Other Total |  |  | 318.92 | 1277.94 | -1616.23 | 22.07 | 355.51 | -358.21 | -91.96 | 91.96 | 337.32 | -358.09 | 20.77 | 1.3145e-13
| Other | Other | Other |  |  | 69.64 | 152.24 | -221.88 | [6 empty] | 0
|  | Other Total |  |  |  | 69.64 | 152.24 | -221.88 | [6 empty] | 0
| Other Total |  |  |  |  | 69.64 | 152.24 | -221.88 | [6 empty] | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  |  |  | 135.52 | [7 empty] | 135.52
|  | Contract Total |  |  |  |  | 135.52 | [7 empty] | 135.52
| Temporary/Supplementary - Trade/Labor Total | [5 empty] | 135.52 | [7 empty] | 135.52
1. Project Support Total |  |  |  | 4071 | 3763.43 | 3510.58 | 857.89 | 3021.74 | -360.09 | 437.72 | 91.96 | 3500.29 | -251.04 | 20.77 | 18664.25
2. Material | Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 139.68 | [7 empty] | 139.68
|  | Material - Direct Purchase Total |  |  |  |  | 139.68 | [7 empty] | 139.68
| Cabinets, Panels and Switchboards-DP Total | [5 empty] | 139.68 | [7 empty] | 139.68
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 795.44 | 795.44
|  | Material - Direct Purchase Total | [11 empty] | 795.44 | 795.44
| Electric Wiring and Components-DP Total | [12 empty] | 795.44 | 795.44
| Material - Inventory | Material | Material - Inventory |  | 1755.8 | [6 empty] | 813.98 |  | 2327.08 | 4896.86
|  | Material Total |  |  | 1755.8 | [6 empty] | 813.98 |  | 2327.08 | 4896.86
| Material - Inventory Total |  |  |  | 1755.8 | [6 empty] | 813.98 |  | 2327.08 | 4896.86
| Material - Other | Material | Material - Other |  | 381.66 |  | 12.27 | 5.65 | 2.7 |  |  | 71.89 |  | 277.36 | 751.53
|  | Material Total |  |  | 381.66 |  | 12.27 | 5.65 | 2.7 |  |  | 71.89 |  | 277.36 | 751.53
| Material - Other Total |  |  |  | 381.66 |  | 12.27 | 5.65 | 2.7 |  |  | 71.89 |  | 277.36 | 751.53
| Protection and Test-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 64 | [6 empty] | 64
|  | Material - Direct Purchase Total | [5 empty] | 64 | [6 empty] | 64
| Protection and Test-DP Total | [6 empty] | 64 | [6 empty] | 64
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 85.38 |  | 5.9 | [7 empty] | 91.28
|  | Material - Direct Purchase Total |  |  | 85.38 |  | 5.9 | [7 empty] | 91.28
| Transportation & Mobile Equip-DP Total |  |  |  | 85.38 |  | 5.9 | [7 empty] | 91.28
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [5 empty] | 30.4 | [5 empty] | 30.4
|  | Material - Direct Purchase Total | [6 empty] | 30.4 | [5 empty] | 30.4
| Wire, Cable & Bus Bar-DP Total | [7 empty] | 30.4 | [5 empty] | 30.4
2. Material Total |  |  |  |  | 2222.84 |  | 157.85 | 69.65 | 33.1 |  |  | 885.87 |  | 3399.88 | 6769.19
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  |  |  | 221.04 | [6 empty] | 221.04
|  | Contract Total | [5 empty] | 221.04 | [6 empty] | 221.04
| Construction Management Services Total | [6 empty] | 221.04 | [6 empty] | 221.04
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | 5454.65 | 8634.86 | 3303.19 | 139.18 | 2381 |  |  |  | -49.58 |  |  | 19863.3
|  | Labor Total |  | 5454.65 | 8634.86 | 3303.19 | 139.18 | 2381 |  |  |  | -49.58 |  |  | 19863.3
| N/W SUBSMTCETEST&APP Total |  |  | 5454.65 | 8634.86 | 3303.19 | 139.18 | 2381 |  |  |  | -49.58 |  |  | 19863.3
| SC&M | Labor | Labor Entries <$5,000 |  | 562.89 | 351.05 | [8 empty] | 913.94
|  | Labor Total |  |  | 562.89 | 351.05 | [8 empty] | 913.94
| SC&M Total |  |  |  | 562.89 | 351.05 | [8 empty] | 913.94
3. Construction Total |  |  |  | 5454.65 | 9197.75 | 3654.24 | 139.18 | 2602.04 |  |  |  | -49.58 |  |  | 20998.28
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 1380.85 | 1518.66 | 632.95 | 76.49 | 511.07 | -40.74 | 56.28 | 7.7 | 429 | -26.04 | 319.67 | 4865.89
|  | Chargeback Total |  | 1380.85 | 1518.66 | 632.95 | 76.49 | 511.07 | -40.74 | 56.28 | 7.7 | 429 | -26.04 | 319.67 | 4865.89
| Chargebacks Total |  |  | 1380.85 | 1518.66 | 632.95 | 76.49 | 511.07 | -40.74 | 56.28 | 7.7 | 429 | -26.04 | 319.67 | 4865.89
| Labor - Other | Labor | Labor Entries <$5,000 | 4083.3 | 4620.19 | 2322.4 | 235.15 | 2029.15 | -109.97 | 145.3 | 30.04 | 1245.38 | -61.31 | 119.59 | 14659.22
|  | Labor Total |  | 4083.3 | 4620.19 | 2322.4 | 235.15 | 2029.15 | -109.97 | 145.3 | 30.04 | 1245.38 | -61.31 | 119.59 | 14659.22
| Labor - Other Total |  |  | 4083.3 | 4620.19 | 2322.4 | 235.15 | 2029.15 | -109.97 | 145.3 | 30.04 | 1245.38 | -61.31 | 119.59 | 14659.22
4. Allocated Total |  |  |  | 5464.15 | 6138.85 | 2955.35 | 311.64 | 2540.22 | -150.71 | 201.58 | 37.74 | 1674.38 | -87.35 | 439.26 | 19525.11
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 1193.77 | 77.54 | [6 empty] | 1271.31
|  |  | Capitalized Overhead - A&G | 836.57 | 624.68 | 358.25 | 46.87 | 703.75 | -17.05 | 22.45 | 3.67 | 155.3 | -8.94 | 108.37 | 2833.92
|  |  | Capitalized Overhead - Inj & Damages | 14.02 | 36.82 | 10.6 | 0.98 | 73.49 | -0.62 | 0.58 | 0.17 | 18.99 | -0.56 | 4.35 | 158.82
|  |  | Capitalized Overhead - P&B/Payroll Tax | 6435.74 | 14265.54 | 7066.71 | 881.59 | 8470.19 | -479.49 | 567.1 | 74.75 | 1690.58 | -214.14 | 48.57 | 38807.14
|  |  | Corporate Overheads Correction |  |  |  |  | -3113.72 | [6 empty] | -3113.72
|  | Non Budgeted Total |  | 7286.33 | 14927.04 | 7435.56 | 2123.21 | 6211.25 | -497.16 | 590.13 | 78.59 | 1864.87 | -223.64 | 161.29 | 39957.47
| Non Budget - Other Total |  |  | 7286.33 | 14927.04 | 7435.56 | 2123.21 | 6211.25 | -497.16 | 590.13 | 78.59 | 1864.87 | -223.64 | 161.29 | 39957.47
5. Corporate Overhead Total |  |  |  | 7286.33 | 14927.04 | 7435.56 | 2123.21 | 6211.25 | -497.16 | 590.13 | 78.59 | 1864.87 | -223.64 | 161.29 | 39957.47
Grand Total |  |  |  | 22276.13 | 36249.91 | 17555.73 | 3589.77 | 14444.9 | -974.86 | 1229.43 | 208.29 | 7875.83 | -562.03 | 4021.2 | 105914.3

## 900280844
Pin: 6440 | Project: TRTP Segment 9
Order: 900280844 | 900280844- Chino Sub: Replace 220-kV relays, Remove
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [8 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1. Project Support | ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 520.79 | [6 empty] | 520.79
|  | Labor Total |  |  |  | 520.79 | [6 empty] | 520.79
| ENGINEERING Total |  |  |  |  | 520.79 | [6 empty] | 520.79
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  |  |  | 507 | 568 |  | 680 | 291 |  | 2046
|  | Contract Total |  |  |  |  | 507 | 568 |  | 680 | 291 |  | 2046
| Engineering/Technical Professional Servi Total | [5 empty] | 507 | 568 |  | 680 | 291 |  | 2046
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  |  |  | -5.02 | -13.67 |  | -4.49 | -1.92 | -25.1
|  | IMM Correction Total | [5 empty] | -5.02 | -13.67 |  | -4.49 | -1.92 | -25.1
| IMM/Allocated - Correction Total | [6 empty] | -5.02 | -13.67 |  | -4.49 | -1.92 | -25.1
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  |  |  | 253 | 126.5 |  |  |  |  | 379.5
|  | Contract Total |  |  |  |  | 253 | 126.5 |  |  |  |  | 379.5
| Temporary/Supplementary - Trade/Labor Total | [5 empty] | 253 | 126.5 |  |  |  |  | 379.5
1. Project Support Total | [5 empty] | 520.79 | 760 | 689.48 | -13.67 | 680 | 286.51 | -1.92 | 2921.19
3. Construction | Construction, Civil/Structural | Contract | Contract Entries <$50,000 |  |  |  |  | 1376.1 |  |  |  |  | 1376.1
|  | Contract Total | [5 empty] | 1376.1 |  |  |  |  | 1376.1
| Construction, Civil/Structural Total | [6 empty] | 1376.1 |  |  |  |  | 1376.1
3. Construction Total | [7 empty] | 1376.1 |  |  |  |  | 1376.1
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 500.73 | 594.92 | 880.05 | 792.1 | 737.5 | 918.92 | 4.49 | 1.92 |  | 4430.63
|  | Chargeback Total |  | 500.73 | 594.92 | 880.05 | 792.1 | 737.5 | 918.92 | 4.49 | 1.92 |  | 4430.63
| Chargebacks Total |  |  | 500.73 | 594.92 | 880.05 | 792.1 | 737.5 | 918.92 | 4.49 | 1.92 |  | 4430.63
| Labor - Other | Labor | Labor Entries <$5,000 |  |  | 171.91 | 56.92 | 142.87 |  | 52.29 | 21.57 |  | 445.56
|  | Labor Total |  |  |  | 171.91 | 56.92 | 142.87 |  | 52.29 | 21.57 |  | 445.56
| Labor - Other Total |  |  |  |  | 171.91 | 56.92 | 142.87 |  | 52.29 | 21.57 |  | 445.56
4. Allocated Total |  |  |  | 500.73 | 594.92 | 1051.96 | 849.02 | 880.37 | 918.92 | 56.78 | 23.49 |  | 4876.19
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 1777.16 | 109.28 |  |  |  |  | 1886.44
|  |  | Capitalized Overhead - A&G | 27.95 | 17.43 | 56.06 | 57.38 | 245.19 | 32.31 | 25.87 | 8.77 | -0.09 | 470.87
|  |  | Capitalized Overhead - Inj & Damages | 0.46 | 0.83 | 1.18 | 0.39 | 5.14 | 0.43 | 0.05 | 0.02 |  | 8.5
|  |  | Capitalized Overhead - P&B/Payroll Tax | 278.41 | 384.71 | 845.35 | 380.14 | 466.39 | 318.22 |  |  |  | 2673.22
|  | Non Budgeted Total |  | 306.82 | 402.97 | 902.59 | 2215.07 | 826 | 350.96 | 25.92 | 8.79 | -0.09 | 5039.03
| Non Budget - Other Total |  |  | 306.82 | 402.97 | 902.59 | 2215.07 | 826 | 350.96 | 25.92 | 8.79 | -0.09 | 5039.03
5. Corporate Overhead Total |  |  |  | 306.82 | 402.97 | 902.59 | 2215.07 | 826 | 350.96 | 25.92 | 8.79 | -0.09 | 5039.03
Grand Total |  |  |  | 807.55 | 997.89 | 2475.34 | 3824.09 | 3771.95 | 1256.21 | 762.7 | 318.79 | -2.01 | 14212.51

## 800250145
Pin: 6440 | Project: TRTP Segment 9
Order: 800250145 | 800250145- I: TRTP 9: DRYCREEKWIND SUB: MINOR PROTE
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | 2012 Total
SubCategory | Prime | Group | Details | 2
1. Project Support | Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | -471.68 | -471.68
|  | Contract Total |  | -471.68 | -471.68
| Consultants / Prof Services - Correction Total |  |  | -471.68 | -471.68
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | -2765.97 | -2765.97
|  | Contract Total |  | -2765.97 | -2765.97
| Engineering/Technical Professional Servi Total |  |  | -2765.97 | -2765.97
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 97.51 | 97.51
|  | IMM Correction Total |  | 97.51 | 97.51
| IMM/Allocated - Correction Total |  |  | 97.51 | 97.51
| Labor - Other | Labor | Labor Entries <$5,000 | -6920.86 | -6920.86
|  | Labor Total |  | -6920.86 | -6920.86
| Labor - Other Total |  |  | -6920.86 | -6920.86
| Other | Other | Other | -55.67 | -55.67
|  | Other Total |  | -55.67 | -55.67
| Other Total |  |  | -55.67 | -55.67
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | -52.08 | -52.08
|  | Contract Total |  | -52.08 | -52.08
| Temporary / Supplemental - Correction Total |  |  | -52.08 | -52.08
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | -3323.07 | -3323.07
|  | Contract Total |  | -3323.07 | -3323.07
| Temporary/Supplementary - Technical/Prof Total |  |  | -3323.07 | -3323.07
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | -50.42 | -50.42
|  | Contract Total |  | -50.42 | -50.42
| Temporary/Supplementary - Trade/Labor Total |  |  | -50.42 | -50.42
1. Project Support Total |  |  |  | -13542.24 | -13542.24
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | -0.01 | -0.01
|  | Material - Direct Purchase Total |  | -0.01 | -0.01
| Material - Direct Purchase - Correction Total |  |  | -0.01 | -0.01
2. Material Total |  |  |  | -0.01 | -0.01
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | -26269 | -26269
|  | Contract Total |  | -26269 | -26269
| Construction Management Services Total |  |  | -26269 | -26269
3. Construction Total |  |  |  | -26269 | -26269
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -795.41 | -795.41
|  | Chargeback Total |  | -795.41 | -795.41
| Chargebacks Total |  |  | -795.41 | -795.41
| Labor - Other | Labor | Labor Entries <$5,000 | -5392.4 | -5392.4
|  | Labor Total |  | -5392.4 | -5392.4
| Labor - Other Total |  |  | -5392.4 | -5392.4
4. Allocated Total |  |  |  | -6187.81 | -6187.81
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax | -703.27 | -703.27
|  |  | Capitalized Overhead - A&G | -1625.69 | -1625.69
|  |  | Capitalized Overhead - Inj & Damages | -55.37 | -55.37
|  |  | Capitalized Overhead - P&B/Payroll Tax | -5942.09 | -5942.09
|  | Non Budgeted Total |  | -8326.42 | -8326.42
| Non Budget - Other Total |  |  | -8326.42 | -8326.42
5. Corporate Overhead Total |  |  |  | -8326.42 | -8326.42
Grand Total |  |  |  | -54325.48 | -54325.48

## 800219704
Pin: 6440 | Project: TRTP Segment 9
Order: 800219704 | 800219704- TRTP 9: GOULD: ADD CB'S ON TRANSFORMERS
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [7 empty] | 238.37 |  |  |  | 754.28 | 992.65
|  | Labor Total | [8 empty] | 238.37 |  |  |  | 754.28 | 992.65
| BP&FM Total | [9 empty] | 238.37 |  |  |  | 754.28 | 992.65
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 8986.88 | 850 | 6157.15 |  |  | 6570 |  | 850 |  |  |  |  | 23414.03
|  | Contract Total |  | 8986.88 | 850 | 6157.15 |  |  | 6570 |  | 850 |  |  |  |  | 23414.03
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 8986.88 | 850 | 6157.15 |  |  | 6570 |  | 850 |  |  |  |  | 23414.03
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 | 872.98 |  | 2741.04 | 1347.95 | 1033.08 | 633.93 | [6 empty] | 6628.98
|  | Labor Total |  | 872.98 |  | 2741.04 | 1347.95 | 1033.08 | 633.93 | [6 empty] | 6628.98
| EAST GRID MGMTCENTER Total |  |  | 872.98 |  | 2741.04 | 1347.95 | 1033.08 | 633.93 | [6 empty] | 6628.98
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 100.84 |  |  |  |  | 739.22 | 576.85 |  |  | 85.6 |  |  | 1502.51
|  | Labor Total |  | 100.84 |  |  |  |  | 739.22 | 576.85 |  |  | 85.6 |  |  | 1502.51
| ENG ADVANCEMENT Total |  |  | 100.84 |  |  |  |  | 739.22 | 576.85 |  |  | 85.6 |  |  | 1502.51
| ENGINEERING | Labor | Labor Entries <$5,000 | 2361.9 | 3634.37 | 3234.95 | 1540.09 | 1351.22 | 2064.63 | 2842.82 | 1393.52 | 531.59 | 174.56 | 337.06 |  | 19466.71
|  | Labor Total |  | 2361.9 | 3634.37 | 3234.95 | 1540.09 | 1351.22 | 2064.63 | 2842.82 | 1393.52 | 531.59 | 174.56 | 337.06 |  | 19466.71
| ENGINEERING Total |  |  | 2361.9 | 3634.37 | 3234.95 | 1540.09 | 1351.22 | 2064.63 | 2842.82 | 1393.52 | 531.59 | 174.56 | 337.06 |  | 19466.71
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 2531 | 1132.86 | 1451 | 1014 | 1136 |  | 2006.64 | 6412 | 167.48 | 5233.2 | -1247 | 190.42 | 20027.6
|  | Contract Total |  | 2531 | 1132.86 | 1451 | 1014 | 1136 |  | 2006.64 | 6412 | 167.48 | 5233.2 | -1247 | 190.42 | 20027.6
| Engineering/Technical Professional Servi Total |  |  | 2531 | 1132.86 | 1451 | 1014 | 1136 |  | 2006.64 | 6412 | 167.48 | 5233.2 | -1247 | 190.42 | 20027.6
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -449.91 | -170.35 | -187.12 | -882.64 | -725.58 | -545.4 | -379.09 | 3343.61 | -3343.61 | -37.81 | -9.09 | -3386.99
|  | IMM Correction Total |  |  | -449.91 | -170.35 | -187.12 | -882.64 | -725.58 | -545.4 | -379.09 | 3343.61 | -3343.61 | -37.81 | -9.09 | -3386.99
| IMM/Allocated - Correction Total |  |  |  | -449.91 | -170.35 | -187.12 | -882.64 | -725.58 | -545.4 | -379.09 | 3343.61 | -3343.61 | -37.81 | -9.09 | -3386.99
| Labor - Other | Labor | Labor Entries <$5,000 | 451.76 | 1179.51 | 1270.44 | 1047.39 | 3058.61 | -1383.22 | 265.43 | 398.56 | -2422.3 | 2423.19 |  | 80.1 | 6369.47
|  | Labor Total |  | 451.76 | 1179.51 | 1270.44 | 1047.39 | 3058.61 | -1383.22 | 265.43 | 398.56 | -2422.3 | 2423.19 |  | 80.1 | 6369.47
| Labor - Other Total |  |  | 451.76 | 1179.51 | 1270.44 | 1047.39 | 3058.61 | -1383.22 | 265.43 | 398.56 | -2422.3 | 2423.19 |  | 80.1 | 6369.47
| Other | Other | Other | -529.26 | -673.25 | 4444.23 | -163.55 | -7393.18 | 935.52 | 62.73 | -527.86 | -98.58 | -101.62 | 150.61 | 228.31 | -3665.9
|  | Other Total |  | -529.26 | -673.25 | 4444.23 | -163.55 | -7393.18 | 935.52 | 62.73 | -527.86 | -98.58 | -101.62 | 150.61 | 228.31 | -3665.9
| Other Total |  |  | -529.26 | -673.25 | 4444.23 | -163.55 | -7393.18 | 935.52 | 62.73 | -527.86 | -98.58 | -101.62 | 150.61 | 228.31 | -3665.9
| SC&M | Labor | Labor Entries <$5,000 | 1879.89 | 528.76 | 1988.94 | 1660.21 | 1178.34 | 1863.16 | 562.34 |  |  | 206.29 |  |  | 9867.93
|  | Labor Total |  | 1879.89 | 528.76 | 1988.94 | 1660.21 | 1178.34 | 1863.16 | 562.34 |  |  | 206.29 |  |  | 9867.93
| SC&M Total |  |  | 1879.89 | 528.76 | 1988.94 | 1660.21 | 1178.34 | 1863.16 | 562.34 |  |  | 206.29 |  |  | 9867.93
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 |  |  |  | 880 | [8 empty] | 880
|  | Contract Total |  |  |  |  | 880 | [8 empty] | 880
| Temporary/Supplementary - Technical/Prof Total | [5 empty] | 880 | [8 empty] | 880
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 3909.31 | 6198.5 | 3103.16 | 6699.57 | 1328.25 | 1644.5 | 1897.5 | 379.5 |  |  |  |  | 25160.29
|  | Contract Total |  | 3909.31 | 6198.5 | 3103.16 | 6699.57 | 1328.25 | 1644.5 | 1897.5 | 379.5 |  |  |  |  | 25160.29
| Temporary/Supplementary - Trade/Labor Total |  |  | 3909.31 | 6198.5 | 3103.16 | 6699.57 | 1328.25 | 1644.5 | 1897.5 | 379.5 |  |  |  |  | 25160.29
1. Project Support Total |  |  |  | 20565.3 | 12400.84 | 24220.56 | 13838.54 | 809.68 | 12342.16 | 7668.91 | 8765 | 1521.8 | 4677.61 | -797.14 | 1244.02 | 107257.28
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  | 130.1 |  |  |  | 170.02 | [6 empty] | 300.12
|  | Material - Direct Purchase Total |  |  | 130.1 |  |  |  | 170.02 | [6 empty] | 300.12
| Building, Shop & Industrial Products/Eqp Total |  |  |  | 130.1 |  |  |  | 170.02 | [6 empty] | 300.12
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | -25 |  |  | 125.08 | [8 empty] | 100.08
|  | Material - Direct Purchase Total |  | -25 |  |  | 125.08 | [8 empty] | 100.08
| Electric Wiring and Components-DP Total |  |  | -25 |  |  | 125.08 | [8 empty] | 100.08
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 1356 | [7 empty] | 1356
|  | Material - Direct Purchase Total | [5 empty] | 1356 | [7 empty] | 1356
| Fuels, Chemicals & Petrochem-DP Total | [6 empty] | 1356 | [7 empty] | 1356
| Material - Inventory | Material | Material - Inventory |  |  |  | -33395.7 | -13203.71 | -311.18 | -11013.58 |  |  | -900 |  |  | -58824.17
|  | Material Total |  |  |  |  | -33395.7 | -13203.71 | -311.18 | -11013.58 |  |  | -900 |  |  | -58824.17
| Material - Inventory Total | [5 empty] | -33395.7 | -13203.71 | -311.18 | -11013.58 |  |  | -900 |  |  | -58824.17
| Material - Other | Material | Material - Other | 1.95 | 355.94 | 0.05 | -958.78 | -566.54 | 436.89 | -978.85 | -69.51 | -44.63 | -87.16 |  | 12.33 | -1898.31
|  | Material Total |  | 1.95 | 355.94 | 0.05 | -958.78 | -566.54 | 436.89 | -978.85 | -69.51 | -44.63 | -87.16 |  | 12.33 | -1898.31
| Material - Other Total |  |  | 1.95 | 355.94 | 0.05 | -958.78 | -566.54 | 436.89 | -978.85 | -69.51 | -44.63 | -87.16 |  | 12.33 | -1898.31
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 119.32 |  |  |  |  | 119.32
|  | Material - Direct Purchase Total | [8 empty] | 119.32 |  |  |  |  | 119.32
| Metals & Fabricated Metal Products-DP Total | [9 empty] | 119.32 |  |  |  |  | 119.32
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | BITRONICS, LLC |  |  |  |  | 5431.15 | [7 empty] | 5431.15
|  |  | Material Entries <$5,000 |  |  |  | 1356 | [8 empty] | 1356
|  | Material - Direct Purchase Total |  |  |  |  | 1356 | 5431.15 | [7 empty] | 6787.15
| Meters, Monitor and Warnings-DP Total | [5 empty] | 1356 | 5431.15 | [7 empty] | 6787.15
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 440.35 | [10 empty] | 440.35
|  | Material - Direct Purchase Total |  |  | 440.35 | [10 empty] | 440.35
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  |  | 440.35 | [10 empty] | 440.35
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | 1959 | 60.5 |  | 464.69 | [8 empty] | 2484.19
|  | Material - Direct Purchase Total |  | 1959 | 60.5 |  | 464.69 | [8 empty] | 2484.19
| Pole Line Hdwe & Connectors-DP Total |  |  | 1959 | 60.5 |  | 464.69 | [8 empty] | 2484.19
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | -91406.56 | -45703.28 |  |  |  | -137109.84
|  | Material - Direct Purchase Total | [8 empty] | -91406.56 | -45703.28 |  |  |  | -137109.84
| Steel / Fabricated / Structural-DP Total | [9 empty] | -91406.56 | -45703.28 |  |  |  | -137109.84
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 64.22 |  |  |  | 5.96 | [5 empty] | 70.18
|  | Material - Direct Purchase Total |  |  |  | 64.22 |  |  |  | 5.96 | [5 empty] | 70.18
| Transportation & Mobile Equip-DP Total |  |  |  |  | 64.22 |  |  |  | 5.96 | [5 empty] | 70.18
2. Material Total |  |  |  | 1935.95 | 986.89 | 64.27 | -32408.71 | -6983.1 | 295.73 | -11986.47 | -91356.75 | -45747.91 | -987.16 |  | 12.33 | -186174.93
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 7764.11 | 10864 | 19546.7 | 21953.6 | 6765 | 33817.4 | 5528 |  | 660 | 495 | 2625 | 4051.6 | 114070.41
|  | Contract Total |  | 7764.11 | 10864 | 19546.7 | 21953.6 | 6765 | 33817.4 | 5528 |  | 660 | 495 | 2625 | 4051.6 | 114070.41
| Construction Management Services Total |  |  | 7764.11 | 10864 | 19546.7 | 21953.6 | 6765 | 33817.4 | 5528 |  | 660 | 495 | 2625 | 4051.6 | 114070.41
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 | [5 empty] | 1915.23 | [6 empty] | 1915.23
|  | Contract Total | [6 empty] | 1915.23 | [6 empty] | 1915.23
| Decontamination & Waste Disposal Service Total | [7 empty] | 1915.23 | [6 empty] | 1915.23
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 | 432.94 | [11 empty] | 432.94
|  | Labor Total |  | 432.94 | [11 empty] | 432.94
| EAST GRID MGMTCENTER Total |  |  | 432.94 | [11 empty] | 432.94
| ENGINEERING | Labor | Labor Entries <$5,000 | [5 empty] | 166.69 | [6 empty] | 166.69
|  | Labor Total | [6 empty] | 166.69 | [6 empty] | 166.69
| ENGINEERING Total | [7 empty] | 166.69 | [6 empty] | 166.69
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | 471.75 |  |  |  |  | 2097.7 | [6 empty] | 2569.45
|  | Contract Total |  | 471.75 |  |  |  |  | 2097.7 | [6 empty] | 2569.45
| Hauling / Industrial Moving Services Total |  |  | 471.75 |  |  |  |  | 2097.7 | [6 empty] | 2569.45
| Major Construction, Turnkey, Trans/Subs | Contract | CONTRA COSTA ELECTRIC INC |  |  |  |  | 55756 | [7 empty] | 55756
|  |  | Contract Entries <$50,000 | 43453 |  |  | 44422 | 38160 | 42825 | 47800 |  |  |  |  | 24500 | 241160
|  |  | PROFESSIONAL ELECTRICAL CONSTRUCTIO |  |  |  | 55415 | [8 empty] | 55415
|  | Contract Total |  | 43453 |  |  | 99837 | 93916 | 42825 | 47800 |  |  |  |  | 24500 | 352331
| Major Construction, Turnkey, Trans/Subs Total |  |  | 43453 |  |  | 99837 | 93916 | 42825 | 47800 |  |  |  |  | 24500 | 352331
| Mechanical Services | Contract | Contract Entries <$50,000 | [5 empty] | 142.5 | 200 | [5 empty] | 342.5
|  | Contract Total | [6 empty] | 142.5 | 200 | [5 empty] | 342.5
| Mechanical Services Total | [7 empty] | 142.5 | 200 | [5 empty] | 342.5
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | 11958.62 | 8765.58 | 31721.53 | 9301.03 | 6443.08 | 4713.59 | 2977.72 | 86.95 |  | -173.2 |  |  | 75794.9
|  | Labor Total |  | 11958.62 | 8765.58 | 31721.53 | 9301.03 | 6443.08 | 4713.59 | 2977.72 | 86.95 |  | -173.2 |  |  | 75794.9
| S/E SUBS MTCETST&APP Total |  |  | 11958.62 | 8765.58 | 31721.53 | 9301.03 | 6443.08 | 4713.59 | 2977.72 | 86.95 |  | -173.2 |  |  | 75794.9
| SC&M | Labor | Labor Entries <$5,000 |  | 129.37 | 1009.26 |  |  | 489.3 | [6 empty] | 1627.93
|  | Labor Total |  |  | 129.37 | 1009.26 |  |  | 489.3 | [6 empty] | 1627.93
| SC&M Total |  |  |  | 129.37 | 1009.26 |  |  | 489.3 | [6 empty] | 1627.93
| Security / Protection Services | Contract | Contract Entries <$50,000 | 2423.64 | 6913.46 | 4187.13 | 1403.4 | [8 empty] | 14927.63
|  | Contract Total |  | 2423.64 | 6913.46 | 4187.13 | 1403.4 | [8 empty] | 14927.63
| Security / Protection Services Total |  |  | 2423.64 | 6913.46 | 4187.13 | 1403.4 | [8 empty] | 14927.63
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 2908.13 | 2141.94 | 3251.68 | 3136.5 | 1260.23 | 900.52 | [6 empty] | 13599
|  | Contract Total |  | 2908.13 | 2141.94 | 3251.68 | 3136.5 | 1260.23 | 900.52 | [6 empty] | 13599
| Short Term Equipment Rent Total |  |  | 2908.13 | 2141.94 | 3251.68 | 3136.5 | 1260.23 | 900.52 | [6 empty] | 13599
3. Construction Total |  |  |  | 69412.19 | 28814.35 | 59716.3 | 135631.53 | 108384.31 | 87067.93 | 56505.72 | 86.95 | 660 | 321.8 | 2625 | 28551.6 | 577777.68
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 4162.27 | 3407.18 | 6626.3 | -1636.62 | 4619.28 | 3798.17 | -756.61 | -386.37 | -441.75 | 171.59 | 61.66 | 353.56 | 19978.66
|  | Chargeback Total |  | 4162.27 | 3407.18 | 6626.3 | -1636.62 | 4619.28 | 3798.17 | -756.61 | -386.37 | -441.75 | 171.59 | 61.66 | 353.56 | 19978.66
| Chargebacks Total |  |  | 4162.27 | 3407.18 | 6626.3 | -1636.62 | 4619.28 | 3798.17 | -756.61 | -386.37 | -441.75 | 171.59 | 61.66 | 353.56 | 19978.66
| Labor - Other | Labor | Labor Entries <$5,000 | 14173.05 | 7626.6 | 9923.04 | 12433.7 | 10768.84 | 8298.16 | 6153.91 | -5572.33 | -3385.91 | 1161.72 | 117.19 | 1298.83 | 62996.8
|  |  | Paid Absence |  |  | 5053.82 | [9 empty] | 5053.82
|  | Labor Total |  | 14173.05 | 7626.6 | 14976.86 | 12433.7 | 10768.84 | 8298.16 | 6153.91 | -5572.33 | -3385.91 | 1161.72 | 117.19 | 1298.83 | 68050.62
| Labor - Other Total |  |  | 14173.05 | 7626.6 | 14976.86 | 12433.7 | 10768.84 | 8298.16 | 6153.91 | -5572.33 | -3385.91 | 1161.72 | 117.19 | 1298.83 | 68050.62
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -910.16 | 910.16 |  |  | 0
|  | Overhead Total | [9 empty] | -910.16 | 910.16 |  |  | 0
| Overhead Correction Total | [10 empty] | -910.16 | 910.16 |  |  | 0
4. Allocated Total |  |  |  | 18335.32 | 11033.78 | 21603.16 | 10797.08 | 15388.12 | 12096.33 | 5397.3 | -5958.7 | -4737.82 | 2243.47 | 178.85 | 1652.39 | 88029.28
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 41702.66 | 2528.18 | [7 empty] | 44230.84
|  |  | AFUDC - Debt/Equity |  |  | 42889.28 | -42889.28 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 6186.96 | 1603.69 | 3622.39 | 4577.11 | 10438.23 | 3970.1 | 2031.64 | -2483.89 | -2160.41 | -6885.91 | 45.92 | 8545.07 | 29490.9
|  |  | Capitalized Overhead - Inj & Damages | 38.6 | 48.91 | 69.27 | -3.92 | 189.7 | 26.19 | 0.39 | -124.4 | -44.43 | -310.71 | 0.74 | 114.45 | 4.79
|  |  | Capitalized Overhead - P&B/Payroll Tax | 12906.19 | 17114.49 | 41193.92 | 20458.08 | 22744.5 | 12494.95 | 9244.86 | 1711.32 | -2613.04 | -12462.82 | 269.2 | 65767.42 | 188829.07
|  |  | Corporate Overheads Correction |  |  |  |  | -125839.64 | [7 empty] | -125839.64
|  | Non Budgeted Total |  | 19131.75 | 18767.09 | 87774.86 | 23844.65 | -89939.03 | 16491.24 | 11276.89 | -896.97 | -4817.88 | -19659.44 | 315.86 | 74426.94 | 136715.96
| Non Budget - Other Total |  |  | 19131.75 | 18767.09 | 87774.86 | 23844.65 | -89939.03 | 16491.24 | 11276.89 | -896.97 | -4817.88 | -19659.44 | 315.86 | 74426.94 | 136715.96
5. Corporate Overhead Total |  |  |  | 19131.75 | 18767.09 | 87774.86 | 23844.65 | -89939.03 | 16491.24 | 11276.89 | -896.97 | -4817.88 | -19659.44 | 315.86 | 74426.94 | 136715.96
Grand Total |  |  |  | 129380.51 | 72002.95 | 193379.15 | 151703.09 | 27659.98 | 128293.39 | 68862.35 | -89360.47 | -53121.81 | -13403.72 | 2322.57 | 105887.28 | 723605.27

## 800219576
Pin: 6440 | Project: TRTP Segment 9
Order: 800219576 | 800219576- I: TRTP 9 & 3C: VINCENT: EXTEND 500KV SW
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  | 179.39 | [9 empty] | 179.39
|  | Contract Total |  |  |  | 179.39 | [9 empty] | 179.39
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  |  | 179.39 | [9 empty] | 179.39
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -16643.5 | 16643.5 |  |  | 0
|  | Contract Total | [9 empty] | -16643.5 | 16643.5 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -16643.5 | 16643.5 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  | -1660.95 | [8 empty] | -1660.95
|  | Contract Total |  |  |  |  | -1660.95 | [8 empty] | -1660.95
| Contract Consult/Contract Ord to Ord Total | [5 empty] | -1660.95 | [8 empty] | -1660.95
| ENGINEERING | Labor | Labor Entries <$5,000 | 1552.04 | 2943.13 | 672.26 | 2055.56 | 6694.61 | 606.77 | 84.58 | [5 empty] | 14608.95
|  | Labor Total |  | 1552.04 | 2943.13 | 672.26 | 2055.56 | 6694.61 | 606.77 | 84.58 | [5 empty] | 14608.95
| ENGINEERING Total |  |  | 1552.04 | 2943.13 | 672.26 | 2055.56 | 6694.61 | 606.77 | 84.58 | [5 empty] | 14608.95
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | [8 empty] | -140 |  |  |  | -140
|  | Contract Total | [9 empty] | -140 |  |  |  | -140
| Engineering/Technical Professional Servi Total | [10 empty] | -140 |  |  |  | -140
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 3237.2 |  | 1843.65 | 2107.53 | 4605.82 | 1316.3 | 2867.56 | 9552.42 | 1993.74 | 309.73 |  |  | 27833.95
|  | Contract Total |  | 3237.2 |  | 1843.65 | 2107.53 | 4605.82 | 1316.3 | 2867.56 | 9552.42 | 1993.74 | 309.73 |  |  | 27833.95
| Environmental/Safety Professional Servic Total |  |  | 3237.2 |  | 1843.65 | 2107.53 | 4605.82 | 1316.3 | 2867.56 | 9552.42 | 1993.74 | 309.73 |  |  | 27833.95
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -107.7 | -72.59 | -146.49 | -382.98 | -142.16 | -235.13 | -18.51 | 18069.67 | -18142.9 | -150.47 | -23.25 | -1352.51
|  | IMM Correction Total |  |  | -107.7 | -72.59 | -146.49 | -382.98 | -142.16 | -235.13 | -18.51 | 18069.67 | -18142.9 | -150.47 | -23.25 | -1352.51
| IMM/Allocated - Correction Total |  |  |  | -107.7 | -72.59 | -146.49 | -382.98 | -142.16 | -235.13 | -18.51 | 18069.67 | -18142.9 | -150.47 | -23.25 | -1352.51
| ITBI (HCC) | Labor | Labor Entries <$5,000 | [6 empty] | 190.14 | [5 empty] | 190.14
|  | Labor Total | [7 empty] | 190.14 | [5 empty] | 190.14
| ITBI (HCC) Total | [8 empty] | 190.14 | [5 empty] | 190.14
| Labor - Other | Labor | Labor Entries <$5,000 | 3970.83 | 5314.83 | 3403.86 | 1783.32 | 4135.55 | 3602.38 | 960.7 | 1148.46 | -652.1 | 6869.24 | 4518.22 | 4935.43 | 39990.72
|  | Labor Total |  | 3970.83 | 5314.83 | 3403.86 | 1783.32 | 4135.55 | 3602.38 | 960.7 | 1148.46 | -652.1 | 6869.24 | 4518.22 | 4935.43 | 39990.72
| Labor - Other Total |  |  | 3970.83 | 5314.83 | 3403.86 | 1783.32 | 4135.55 | 3602.38 | 960.7 | 1148.46 | -652.1 | 6869.24 | 4518.22 | 4935.43 | 39990.72
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  | 91.03 | 144.4 | [9 empty] | 235.43
|  | Labor Total |  |  | 91.03 | 144.4 | [9 empty] | 235.43
| NORTH GRIDMGMTCENTER Total |  |  |  | 91.03 | 144.4 | [9 empty] | 235.43
| Other | Other | Other | -74607.5 | 2181.5 | -91611.37 | -49206.86 | -2998.27 | -4828.53 | -111491.58 | -63872.8 | 50 | 300 | 559.21 | -109.21 | -395635.41
|  | Other Total |  | -74607.5 | 2181.5 | -91611.37 | -49206.86 | -2998.27 | -4828.53 | -111491.58 | -63872.8 | 50 | 300 | 559.21 | -109.21 | -395635.41
| Other Total |  |  | -74607.5 | 2181.5 | -91611.37 | -49206.86 | -2998.27 | -4828.53 | -111491.58 | -63872.8 | 50 | 300 | 559.21 | -109.21 | -395635.41
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 56.87 | [11 empty] | 56.87
|  | Contract Total |  | 56.87 | [11 empty] | 56.87
| Temporary/Supplementary - Trade/Labor Total |  |  | 56.87 | [11 empty] | 56.87
1. Project Support Total |  |  |  | -65790.56 | 10422.79 | -85440.4 | -45067.89 | 12054.73 | 554.76 | -107623.73 | -53190.43 | 2677.81 | 5979.57 | 4926.96 | 4802.97 | -315693.42
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 86.17 | 2476.38 | 2562.55
|  | Material - Direct Purchase Total | [11 empty] | 86.17 | 2476.38 | 2562.55
| Building, Shop & Industrial Products/Eqp Total | [12 empty] | 86.17 | 2476.38 | 2562.55
| Electric Wiring and Components-DP | Material - Direct Purchase | Electric Wiring and Components-DP | 6565.93 | [7 empty] | 16298.28 | 5844.96 |  | 6672.05 | 35381.22
|  |  | Material Entries <$5,000 | 1721.37 | 7743.37 | 2955.5 | 26.76 | 748.8 |  | -62.47 | -12.87 |  |  | 1151.94 |  | 14272.4
|  |  | SOUTHWIRE COMPANY |  |  |  | 49134 | 14330 | 34230.16 | [6 empty] | 97694.16
|  | Material - Direct Purchase Total |  | 8287.3 | 7743.37 | 2955.5 | 49160.76 | 15078.8 | 34230.16 | -62.47 | -12.87 | 16298.28 | 5844.96 | 1151.94 | 6672.05 | 147347.78
| Electric Wiring and Components-DP Total |  |  | 8287.3 | 7743.37 | 2955.5 | 49160.76 | 15078.8 | 34230.16 | -62.47 | -12.87 | 16298.28 | 5844.96 | 1151.94 | 6672.05 | 147347.78
| Material - Inventory | Material | Material - Inventory | 27777.29 | -10178.65 | -1516.95 |  | -2017.16 |  | -27871.95 | -22238.89 | -12.99 | -12226.76 |  |  | -48286.06
|  | Material Total |  | 27777.29 | -10178.65 | -1516.95 |  | -2017.16 |  | -27871.95 | -22238.89 | -12.99 | -12226.76 |  |  | -48286.06
| Material - Inventory Total |  |  | 27777.29 | -10178.65 | -1516.95 |  | -2017.16 |  | -27871.95 | -22238.89 | -12.99 | -12226.76 |  |  | -48286.06
| Material - Other | Material | Material - Other | 4076.45 | 352.47 | -2235.3 | 5728.14 | 1170.71 | 3033.98 | -10911.77 | -235.58 | 1446.52 | -39.38 | 101.79 | 759.74 | 3247.77
|  | Material Total |  | 4076.45 | 352.47 | -2235.3 | 5728.14 | 1170.71 | 3033.98 | -10911.77 | -235.58 | 1446.52 | -39.38 | 101.79 | 759.74 | 3247.77
| Material - Other Total |  |  | 4076.45 | 352.47 | -2235.3 | 5728.14 | 1170.71 | 3033.98 | -10911.77 | -235.58 | 1446.52 | -39.38 | 101.79 | 759.74 | 3247.77
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | 6.39 | [7 empty] | 48.1 |  | 233.62 |  | 288.11
|  | Material - Direct Purchase Total |  | 6.39 | [7 empty] | 48.1 |  | 233.62 |  | 288.11
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  | 6.39 | [7 empty] | 48.1 |  | 233.62 |  | 288.11
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | 929.11 | [9 empty] | 1511.41 |  | 2440.52
|  | Material - Direct Purchase Total |  | 929.11 | [9 empty] | 1511.41 |  | 2440.52
| Pole Line Hdwe & Connectors-DP Total |  |  | 929.11 | [9 empty] | 1511.41 |  | 2440.52
| Protection and Test-DP | Material - Direct Purchase | GE MULTILIN |  |  |  | 5688.46 | [8 empty] | 5688.46
|  |  | Material Entries <$5,000 |  |  | 1895.19 | [9 empty] | 1895.19
|  | Material - Direct Purchase Total |  |  |  | 1895.19 | 5688.46 | [8 empty] | 7583.65
| Protection and Test-DP Total |  |  |  |  | 1895.19 | 5688.46 | [8 empty] | 7583.65
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | 2203.76 | 3027.5 |  | 837 | [8 empty] | 6068.26
|  | Material - Direct Purchase Total |  | 2203.76 | 3027.5 |  | 837 | [8 empty] | 6068.26
| Steel / Fabricated / Structural-DP Total |  |  | 2203.76 | 3027.5 |  | 837 | [8 empty] | 6068.26
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 21.56 |  | 860.5 | 12.98 | [8 empty] | 895.04
|  | Material - Direct Purchase Total |  | 21.56 |  | 860.5 | 12.98 | [8 empty] | 895.04
| Transportation & Mobile Equip-DP Total |  |  | 21.56 |  | 860.5 | 12.98 | [8 empty] | 895.04
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | 216.83 | [9 empty] | 30.02 | 75.05 | 321.9
|  | Material - Direct Purchase Total |  | 216.83 | [9 empty] | 30.02 | 75.05 | 321.9
| Wire, Cable & Bus Bar-DP Total |  |  | 216.83 | [9 empty] | 30.02 | 75.05 | 321.9
2. Material Total |  |  |  | 43518.69 | 944.69 | 1958.94 | 61427.34 | 14232.35 | 37264.14 | -38846.19 | -22487.34 | 17779.91 | -6421.18 | 3114.95 | 9983.22 | 122469.52
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  | 4170 | 221.04 | 257.6 | [5 empty] | 510.2 | 5566.88 | 10725.72
|  | Contract Total |  |  |  | 4170 | 221.04 | 257.6 | [5 empty] | 510.2 | 5566.88 | 10725.72
| Construction Management Services Total |  |  |  |  | 4170 | 221.04 | 257.6 | [5 empty] | 510.2 | 5566.88 | 10725.72
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  |  | 10470 | [9 empty] | 10470
|  | Contract Total |  |  |  | 10470 | [9 empty] | 10470
| Major Construction, Turnkey, Trans/Subs Total |  |  |  |  | 10470 | [9 empty] | 10470
| Other | Other | Other |  |  |  |  | 14.43 | [7 empty] | 14.43
|  | Other Total | [5 empty] | 14.43 | [7 empty] | 14.43
| Other Total | [6 empty] | 14.43 | [7 empty] | 14.43
| SC&M | Labor | Labor Entries <$5,000 |  | 254.89 | 318.14 | 219.35 | 128.64 | [7 empty] | 921.02
|  | Labor Total |  |  | 254.89 | 318.14 | 219.35 | 128.64 | [7 empty] | 921.02
| SC&M Total |  |  |  | 254.89 | 318.14 | 219.35 | 128.64 | [7 empty] | 921.02
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 2031.64 | 5336.55 | 9330.46 | 4562.25 | 1523.3 | 689 | 4663.2 | 4074.87 | 1358.29 | 1358.29 | 1358.29 | 1358.29 | 37644.43
|  | Contract Total |  | 2031.64 | 5336.55 | 9330.46 | 4562.25 | 1523.3 | 689 | 4663.2 | 4074.87 | 1358.29 | 1358.29 | 1358.29 | 1358.29 | 37644.43
| Short Term Equipment Rent Total |  |  | 2031.64 | 5336.55 | 9330.46 | 4562.25 | 1523.3 | 689 | 4663.2 | 4074.87 | 1358.29 | 1358.29 | 1358.29 | 1358.29 | 37644.43
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | 164 | 328 | 164 | [9 empty] | 656
|  | Labor Total |  | 164 | 328 | 164 | [9 empty] | 656
| TSD-HERC - Rental Total |  |  | 164 | 328 | 164 | [9 empty] | 656
3. Construction Total |  |  |  | 2195.64 | 5919.44 | 24452.6 | 5002.64 | 1923.97 | 689 | 4663.2 | 4074.87 | 1358.29 | 1358.29 | 1868.49 | 6925.17 | 60431.6
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 11815.62 | 1179.42 | 1057.98 | 3498.43 | 3337.8 | 151.18 | -5096.89 | -1284.17 | 420.72 | -1113.96 | 4756.45 | 97.62 | 18820.2
|  |  | Vincent Sub-Segment 9 550kV Hybrid GIS P | [7 empty] | 7224.5 |  |  |  |  | 7224.5
|  | Chargeback Total |  | 11815.62 | 1179.42 | 1057.98 | 3498.43 | 3337.8 | 151.18 | -5096.89 | 5940.33 | 420.72 | -1113.96 | 4756.45 | 97.62 | 26044.7
| Chargebacks Total |  |  | 11815.62 | 1179.42 | 1057.98 | 3498.43 | 3337.8 | 151.18 | -5096.89 | 5940.33 | 420.72 | -1113.96 | 4756.45 | 97.62 | 26044.7
| Labor - Other | Labor | Labor Entries <$5,000 | 5159.62 | 1859.38 | 2573.67 | 5607.84 | 4045.31 | 2159.96 | -1472.09 | -639.08 | -154.55 | 1346.58 | 123.51 | 586.19 | 21196.34
|  | Labor Total |  | 5159.62 | 1859.38 | 2573.67 | 5607.84 | 4045.31 | 2159.96 | -1472.09 | -639.08 | -154.55 | 1346.58 | 123.51 | 586.19 | 21196.34
| Labor - Other Total |  |  | 5159.62 | 1859.38 | 2573.67 | 5607.84 | 4045.31 | 2159.96 | -1472.09 | -639.08 | -154.55 | 1346.58 | 123.51 | 586.19 | 21196.34
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -165.33 | 165.33 |  |  | 0
|  | Overhead Total | [9 empty] | -165.33 | 165.33 |  |  | 0
| Overhead Correction Total | [10 empty] | -165.33 | 165.33 |  |  | 0
4. Allocated Total |  |  |  | 16975.24 | 3038.8 | 3631.65 | 9106.27 | 7383.11 | 2311.14 | -6568.98 | 5301.25 | 100.84 | 397.95 | 4879.96 | 683.81 | 47241.04
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 4801.66 | 346.73 | [6 empty] | 5340.26 | 10488.65
|  |  | AFUDC - Debt/Equity |  |  | 5033.74 | -5033.74 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 318.29 | 583.52 | -4174.48 | 2950.67 | 3357.1 | 1639.16 | -5209.9 | -1875.36 | 981.85 | 33.97 | 380.05 | 640.26 | -374.87
|  |  | Capitalized Overhead - Inj & Damages | 2.25 | 28.83 | -141.41 | 65.67 | 285.8 | 57.54 | -138.34 | -110.16 | 33.25 | -49.51 | 22.81 | 19.41 | 76.14
|  |  | Capitalized Overhead - P&B/Payroll Tax | 3408.18 | 8902.37 | 4373.58 | 4830.45 | 16736.73 | 4526.81 | 1395.44 | 777.37 | -1042.25 | 3072.82 | 3209.02 | 9309.51 | 59500.03
|  |  | Corporate Overheads Correction |  |  |  |  | 107049.24 | [7 empty] | 107049.24
|  | Non Budgeted Total |  | 3728.72 | 9514.72 | 5091.43 | 7614.71 | 127775.6 | 6223.51 | -3952.8 | -1208.15 | -27.15 | 3057.28 | 3611.88 | 15309.44 | 176739.19
| Non Budget - Other Total |  |  | 3728.72 | 9514.72 | 5091.43 | 7614.71 | 127775.6 | 6223.51 | -3952.8 | -1208.15 | -27.15 | 3057.28 | 3611.88 | 15309.44 | 176739.19
5. Corporate Overhead Total |  |  |  | 3728.72 | 9514.72 | 5091.43 | 7614.71 | 127775.6 | 6223.51 | -3952.8 | -1208.15 | -27.15 | 3057.28 | 3611.88 | 15309.44 | 176739.19
Grand Total |  |  |  | 627.73 | 29840.44 | -50305.78 | 38083.07 | 163369.76 | 47042.55 | -152328.5 | -67509.8 | 21889.7 | 4371.91 | 18402.24 | 37704.61 | 91187.93

## 800218712
Pin: 6440 | Project: TRTP Segment 9
Order: 800218712 | 800218712- I: TRTP 9: MIRA LOMA: ADD/CHANGE & EQUIP
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  |  | 10.92 |  | 507.8 | [5 empty] | 518.72
|  | Labor Total | [5 empty] | 10.92 |  | 507.8 | [5 empty] | 518.72
| BP&FM Total | [6 empty] | 10.92 |  | 507.8 | [5 empty] | 518.72
| BSVHCC | Labor | Labor Entries <$5,000 | [8 empty] | 41.49 |  |  |  | 41.49
|  | Labor Total | [9 empty] | 41.49 |  |  |  | 41.49
| BSVHCC Total | [10 empty] | 41.49 |  |  |  | 41.49
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 | 168 | 168 | 168 | 336 |  | 168 | 336 |  | 168 | 168 | 185 | 370 | 2235
|  | Contract Total |  | 168 | 168 | 168 | 336 |  | 168 | 336 |  | 168 | 168 | 185 | 370 | 2235
| Cleaning / Janitorial Services Total |  |  | 168 | 168 | 168 | 336 |  | 168 | 336 |  | 168 | 168 | 185 | 370 | 2235
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [6 empty] | 3275 | [5 empty] | 3275
|  | Contract Total | [7 empty] | 3275 | [5 empty] | 3275
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [8 empty] | 3275 | [5 empty] | 3275
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -625.75 | 625.75 |  |  | 0
|  | Contract Total | [9 empty] | -625.75 | 625.75 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -625.75 | 625.75 |  |  | 0
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 | [8 empty] | 152.35 | 1771.35 | 1213.95 |  | 3137.65
|  | Labor Total | [9 empty] | 152.35 | 1771.35 | 1213.95 |  | 3137.65
| EAST GRID MGMTCENTER Total | [10 empty] | 152.35 | 1771.35 | 1213.95 |  | 3137.65
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 2894.38 | 2894.38
|  | Labor Total | [12 empty] | 2894.38 | 2894.38
| ELEC SYS PLANNING Total | [13 empty] | 2894.38 | 2894.38
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 226.9 |  |  |  |  | 69.4 | 49.27 |  |  | 107 |  |  | 452.57
|  | Labor Total |  | 226.9 |  |  |  |  | 69.4 | 49.27 |  |  | 107 |  |  | 452.57
| ENG ADVANCEMENT Total |  |  | 226.9 |  |  |  |  | 69.4 | 49.27 |  |  | 107 |  |  | 452.57
| ENGINEERING | Labor | Labor Entries <$5,000 | 3413.98 | 1173.94 | 3310.74 | 3097.03 | 6473.89 | 6126.11 | 4872.76 | 11180.83 | 2761.15 | 2842.35 | 2283.57 |  | 47536.35
|  | Labor Total |  | 3413.98 | 1173.94 | 3310.74 | 3097.03 | 6473.89 | 6126.11 | 4872.76 | 11180.83 | 2761.15 | 2842.35 | 2283.57 |  | 47536.35
| ENGINEERING Total |  |  | 3413.98 | 1173.94 | 3310.74 | 3097.03 | 6473.89 | 6126.11 | 4872.76 | 11180.83 | 2761.15 | 2842.35 | 2283.57 |  | 47536.35
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 2531 | 13616.85 | 967 | 1014 | 1136 |  | 1538.67 | 582 | 2525.48 | 8266 | 330 | 12430.92 | 44937.92
|  | Contract Total |  | 2531 | 13616.85 | 967 | 1014 | 1136 |  | 1538.67 | 582 | 2525.48 | 8266 | 330 | 12430.92 | 44937.92
| Engineering/Technical Professional Servi Total |  |  | 2531 | 13616.85 | 967 | 1014 | 1136 |  | 1538.67 | 582 | 2525.48 | 8266 | 330 | 12430.92 | 44937.92
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -1923.72 | -2048.25 | -446.16 | -1464.47 | -237.57 | -268.46 | -248.86 | 3725.14 | -3904.42 | -304.64 | -230.36 | -7351.77
|  | IMM Correction Total |  |  | -1923.72 | -2048.25 | -446.16 | -1464.47 | -237.57 | -268.46 | -248.86 | 3725.14 | -3904.42 | -304.64 | -230.36 | -7351.77
| IMM/Allocated - Correction Total |  |  |  | -1923.72 | -2048.25 | -446.16 | -1464.47 | -237.57 | -268.46 | -248.86 | 3725.14 | -3904.42 | -304.64 | -230.36 | -7351.77
| Labor - Other | Labor | Labor Accrual - SCE | [11 empty] | 7415.29 | 7415.29
|  |  | Labor Entries <$5,000 | 1326.46 | 725.14 | -1830.16 | 491.4 | 4965.32 | -7851.66 | 2487.04 | -12864.69 | -1759.49 | 7194.33 | 1269.76 | 2998.72 | -2847.83
|  |  | PSC Mira Loma 500kV TRTP | [11 empty] | 6599.05 | 6599.05
|  | Labor Total |  | 1326.46 | 725.14 | -1830.16 | 491.4 | 4965.32 | -7851.66 | 2487.04 | -12864.69 | -1759.49 | 7194.33 | 1269.76 | 17013.06 | 11166.51
| Labor - Other Total |  |  | 1326.46 | 725.14 | -1830.16 | 491.4 | 4965.32 | -7851.66 | 2487.04 | -12864.69 | -1759.49 | 7194.33 | 1269.76 | 17013.06 | 11166.51
| Other | Other | Other | -107163.54 | 4599.9 | 8412.1 | -9742.81 | 1249.4 | 2512.61 | 2392.72 | 5314.53 | 353.85 | 4488.26 | 4503.8 | 33158.71 | -49920.47
|  | Other Total |  | -107163.54 | 4599.9 | 8412.1 | -9742.81 | 1249.4 | 2512.61 | 2392.72 | 5314.53 | 353.85 | 4488.26 | 4503.8 | 33158.71 | -49920.47
| Other Total |  |  | -107163.54 | 4599.9 | 8412.1 | -9742.81 | 1249.4 | 2512.61 | 2392.72 | 5314.53 | 353.85 | 4488.26 | 4503.8 | 33158.71 | -49920.47
| SC&M | Labor | Labor Entries <$5,000 | 242.84 | 209.07 |  | 707.61 | 259.74 |  |  |  |  | 1330.01 | 518.93 |  | 3268.2
|  | Labor Total |  | 242.84 | 209.07 |  | 707.61 | 259.74 |  |  |  |  | 1330.01 | 518.93 |  | 3268.2
| SC&M Total |  |  | 242.84 | 209.07 |  | 707.61 | 259.74 |  |  |  |  | 1330.01 | 518.93 |  | 3268.2
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -740.62 | 740.62 |  |  | 0
|  | Contract Total | [9 empty] | -740.62 | 740.62 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -740.62 | 740.62 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1928.58 | 4711.58 | 1644.5 | 5318.6 | 3289 | 8060.57 | 8664.73 | 1927.48 | 627.2 | 265.2 | -2023.2 |  | 34414.24
|  | Contract Total |  | 1928.58 | 4711.58 | 1644.5 | 5318.6 | 3289 | 8060.57 | 8664.73 | 1927.48 | 627.2 | 265.2 | -2023.2 |  | 34414.24
| Temporary/Supplementary - Trade/Labor Total |  |  | 1928.58 | 4711.58 | 1644.5 | 5318.6 | 3289 | 8060.57 | 8664.73 | 1927.48 | 627.2 | 265.2 | -2023.2 |  | 34414.24
1. Project Support Total |  |  |  | -97325.78 | 23280.76 | 10623.93 | 775.67 | 15919.8 | 8847.46 | 23855.53 | 5891.29 | 7228.8 | 23894.45 | 7977.17 | 65636.71 | 96605.79
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 | 4418.59 | 700.61 |  |  |  | 8.55 | [6 empty] | 5127.75
|  | Material - Direct Purchase Total |  | 4418.59 | 700.61 |  |  |  | 8.55 | [6 empty] | 5127.75
| Building, Shop & Industrial Products/Eqp Total |  |  | 4418.59 | 700.61 |  |  |  | 8.55 | [6 empty] | 5127.75
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 1083.25 |  |  | 1083.25
|  | Material - Direct Purchase Total | [10 empty] | 1083.25 |  |  | 1083.25
| Cabinets, Panels and Switchboards-DP Total | [11 empty] | 1083.25 |  |  | 1083.25
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | 2725.32 |  |  | 99.6 | 61.6 |  |  |  |  | 3390.76 |  |  | 6277.28
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC |  |  |  | 7415.73 | [5 empty] | 14316 |  |  | 21731.73
|  | Material - Direct Purchase Total |  | 2725.32 |  |  | 7515.33 | 61.6 |  |  |  |  | 17706.76 |  |  | 28009.01
| Electric Wiring and Components-DP Total |  |  | 2725.32 |  |  | 7515.33 | 61.6 |  |  |  |  | 17706.76 |  |  | 28009.01
| Line Switches & Switchgear-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 547.2 | [5 empty] | 547.2
|  | Material - Direct Purchase Total | [7 empty] | 547.2 | [5 empty] | 547.2
| Line Switches & Switchgear-DP Total | [8 empty] | 547.2 | [5 empty] | 547.2
| Material - Inventory | Material | Material - Inventory |  | -2608.8 | -27710.82 | -14886.37 | -15113.87 | -17537.21 | -2778.2 | -3558.18 | -909.78 |  |  |  | -85103.23
|  | Material Total |  |  | -2608.8 | -27710.82 | -14886.37 | -15113.87 | -17537.21 | -2778.2 | -3558.18 | -909.78 |  |  |  | -85103.23
| Material - Inventory Total |  |  |  | -2608.8 | -27710.82 | -14886.37 | -15113.87 | -17537.21 | -2778.2 | -3558.18 | -909.78 |  |  |  | -85103.23
| Material - Other | Material | Material - Other | 609.84 | 712.69 | -597.29 | 8327.77 | -1178.4 | -873.78 | 267.52 | -281.01 | -71.43 | 1700.26 | 0.03 | 0.59 | 8616.79
|  | Material Total |  | 609.84 | 712.69 | -597.29 | 8327.77 | -1178.4 | -873.78 | 267.52 | -281.01 | -71.43 | 1700.26 | 0.03 | 0.59 | 8616.79
| Material - Other Total |  |  | 609.84 | 712.69 | -597.29 | 8327.77 | -1178.4 | -873.78 | 267.52 | -281.01 | -71.43 | 1700.26 | 0.03 | 0.59 | 8616.79
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | 2534.55 |  |  | 98.49 |  | 362.79 | 64.23 |  |  | 529.04 |  |  | 3589.1
|  | Material - Direct Purchase Total |  | 2534.55 |  |  | 98.49 |  | 362.79 | 64.23 |  |  | 529.04 |  |  | 3589.1
| Metals & Fabricated Metal Products-DP Total |  |  | 2534.55 |  |  | 98.49 |  | 362.79 | 64.23 |  |  | 529.04 |  |  | 3589.1
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 12.92 |  |  |  |  | 12.92
|  | Material - Direct Purchase Total | [8 empty] | 12.92 |  |  |  |  | 12.92
| Monitor Equipment, Gauges and Hoses-DP Total | [9 empty] | 12.92 |  |  |  |  | 12.92
| Other Consumables-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 67.99 | [9 empty] | 67.99
|  | Material - Direct Purchase Total |  |  |  | 67.99 | [9 empty] | 67.99
| Other Consumables-DP Total |  |  |  |  | 67.99 | [9 empty] | 67.99
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | 787.44 | 94.2 |  | 718.48 |  | 2242.02 | 810 | [5 empty] | 4652.14
|  | Material - Direct Purchase Total |  | 787.44 | 94.2 |  | 718.48 |  | 2242.02 | 810 | [5 empty] | 4652.14
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  | 787.44 | 94.2 |  | 718.48 |  | 2242.02 | 810 | [5 empty] | 4652.14
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | -681.45 | [7 empty] | 99.48 | -581.97
|  | Material - Direct Purchase Total |  |  |  |  | -681.45 | [7 empty] | 99.48 | -581.97
| Pole Line Hdwe & Connectors-DP Total | [5 empty] | -681.45 | [7 empty] | 99.48 | -581.97
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 263.96 | 923.61 |  |  |  |  | 291.53 | 24.14 |  | 70.53 | 385.5 | 1959.27
|  | Material - Direct Purchase Total |  |  | 263.96 | 923.61 |  |  |  |  | 291.53 | 24.14 |  | 70.53 | 385.5 | 1959.27
| Transportation & Mobile Equip-DP Total |  |  |  | 263.96 | 923.61 |  |  |  |  | 291.53 | 24.14 |  | 70.53 | 385.5 | 1959.27
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | 44.05 |  |  | 8.9 | [8 empty] | 52.95
|  | Material - Direct Purchase Total |  | 44.05 |  |  | 8.9 | [8 empty] | 52.95
| Wire, Cable & Bus Bar-DP Total |  |  | 44.05 |  |  | 8.9 | [8 empty] | 52.95
2. Material Total |  |  |  | 11119.79 | -837.34 | -27316.51 | 1101.15 | -16230.67 | -15797.63 | -1089.25 | -3534.74 | -957.07 | 21019.31 | 70.56 | 485.57 | -31966.83
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 42161.42 |  | 51811.94 | 30181.01 | 31024.05 | 29167.82 | 24540 |  | 17253 | 7039 | 35265 | 51909.32 | 320352.56
|  | Contract Total |  | 42161.42 |  | 51811.94 | 30181.01 | 31024.05 | 29167.82 | 24540 |  | 17253 | 7039 | 35265 | 51909.32 | 320352.56
| Construction Management Services Total |  |  | 42161.42 |  | 51811.94 | 30181.01 | 31024.05 | 29167.82 | 24540 |  | 17253 | 7039 | 35265 | 51909.32 | 320352.56
| Construction Services - Other | Contract | Contract Entries <$50,000 | [6 empty] | 408.51 | 687.18 |  |  | 1076.1 |  | 2171.79
|  | Contract Total | [7 empty] | 408.51 | 687.18 |  |  | 1076.1 |  | 2171.79
| Construction Services - Other Total | [8 empty] | 408.51 | 687.18 |  |  | 1076.1 |  | 2171.79
| Construction Services Correction | Contract | Contract Entries <$50,000 | [7 empty] | -87371.25 |  |  |  |  | -87371.25
|  | Contract Total | [8 empty] | -87371.25 |  |  |  |  | -87371.25
| Construction Services Correction Total | [9 empty] | -87371.25 |  |  |  |  | -87371.25
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [7 empty] | 262.5 |  | 9696.6 |  |  | 9959.1
|  | Contract Total | [8 empty] | 262.5 |  | 9696.6 |  |  | 9959.1
| Construction, Civil/Structural Total | [9 empty] | 262.5 |  | 9696.6 |  |  | 9959.1
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 |  | 7476.39 | 4635 | 3607.5 | [8 empty] | 15718.89
|  | Contract Total |  |  | 7476.39 | 4635 | 3607.5 | [8 empty] | 15718.89
| Decontamination & Waste Disposal Service Total |  |  |  | 7476.39 | 4635 | 3607.5 | [8 empty] | 15718.89
| GRID OPS | Labor | Labor Entries <$5,000 | [9 empty] | 271.57 |  | 167.6 | 439.17
|  | Labor Total | [10 empty] | 271.57 |  | 167.6 | 439.17
| GRID OPS Total | [11 empty] | 271.57 |  | 167.6 | 439.17
| Major Construction, Turnkey, Trans/Subs | Contract | STATION ELECTRIC | 204000 | 277186 |  | 168440 | [8 empty] | 649626
|  | Contract Total |  | 204000 | 277186 |  | 168440 | [8 empty] | 649626
| Major Construction, Turnkey, Trans/Subs Total |  |  | 204000 | 277186 |  | 168440 | [8 empty] | 649626
| Mechanical Services | Contract | Contract Entries <$50,000 | 2552.5 | [11 empty] | 2552.5
|  | Contract Total |  | 2552.5 | [11 empty] | 2552.5
| Mechanical Services Total |  |  | 2552.5 | [11 empty] | 2552.5
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | 11265.89 | 20528.62 | 3104.86 | 7440.27 | 7363.1 | 6328.32 | 33738.45 | 34027.85 | 36073.56 | 29961.89 | 21774.26 |  | 211607.07
|  |  | Techn Test |  |  | 6466.05 | [9 empty] | 6466.05
|  |  | Technician Test | [6 empty] | 5467.14 | 12346.38 | 5206.8 |  |  |  | 23020.32
|  |  | Tst Spr Tech |  |  | 7201.68 | 7201.68 |  | 12846.35 |  | 13235.52 | 17663.58 | 11775.72 | 20193.9 |  | 90118.43
|  | Labor Total |  | 11265.89 | 20528.62 | 16772.59 | 14641.95 | 7363.1 | 19174.67 | 39205.59 | 59609.75 | 58943.94 | 41737.61 | 41968.16 |  | 331211.87
| S/E SUBS MTCETST&APP Total |  |  | 11265.89 | 20528.62 | 16772.59 | 14641.95 | 7363.1 | 19174.67 | 39205.59 | 59609.75 | 58943.94 | 41737.61 | 41968.16 |  | 331211.87
| SC&M | Labor | Labor Entries <$5,000 | 1107.61 | 1684.06 | 1448.07 | 1585.32 | 6822.11 | 20703.83 | 22217.96 | 14797.45 | 14626.48 | 13685.81 | 13915.66 | 32606.99 | 145201.35
|  |  | SC&M / Electn Constrn |  |  |  |  | 5832 | 18002.25 |  | 18204.75 |  |  |  |  | 42039
|  |  | SC&M / Frm Wrk Elct Cnst |  |  |  |  | 7125.21 | 8382.6 | 6234.56 | 6444.12 | 5029.56 |  |  |  | 33216.05
|  |  | SC&M / Tst Spr Tech | [11 empty] | 5839.2 | 5839.2
|  | Labor Total |  | 1107.61 | 1684.06 | 1448.07 | 1585.32 | 19779.32 | 47088.68 | 28452.52 | 39446.32 | 19656.04 | 13685.81 | 13915.66 | 38446.19 | 226295.6
| SC&M Total |  |  | 1107.61 | 1684.06 | 1448.07 | 1585.32 | 19779.32 | 47088.68 | 28452.52 | 39446.32 | 19656.04 | 13685.81 | 13915.66 | 38446.19 | 226295.6
| Security / Protection Services | Contract | Contract Entries <$50,000 | 3064.77 | 5349.25 | 3433.8 | 2757.49 | [7 empty] | 39463.54 | 54068.85
|  | Contract Total |  | 3064.77 | 5349.25 | 3433.8 | 2757.49 | [7 empty] | 39463.54 | 54068.85
| Security / Protection Services Total |  |  | 3064.77 | 5349.25 | 3433.8 | 2757.49 | [7 empty] | 39463.54 | 54068.85
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 3916.92 | 4196.76 | 4332.04 | 5432.18 | 1820.38 | 1236.76 | 7386.62 | 8172.55 | 8188.7 | 6129.6 | 7297.92 | 6360.45 | 64470.88
|  | Contract Total |  | 3916.92 | 4196.76 | 4332.04 | 5432.18 | 1820.38 | 1236.76 | 7386.62 | 8172.55 | 8188.7 | 6129.6 | 7297.92 | 6360.45 | 64470.88
| Short Term Equipment Rent Total |  |  | 3916.92 | 4196.76 | 4332.04 | 5432.18 | 1820.38 | 1236.76 | 7386.62 | 8172.55 | 8188.7 | 6129.6 | 7297.92 | 6360.45 | 64470.88
3. Construction Total |  |  |  | 268069.11 | 316421.08 | 82433.44 | 226645.45 | 59986.85 | 96667.93 | 99993.24 | 20807.05 | 104041.68 | 78560.19 | 99522.84 | 136347.1 | 1589495.96
4. Allocated | Allocations Correction | Allocated Conversion | Allocations Correction | [7 empty] | -1809.61 |  |  |  |  | -1809.61
|  | Allocated Conversion Total | [8 empty] | -1809.61 |  |  |  |  | -1809.61
| Allocations Correction Total | [9 empty] | -1809.61 |  |  |  |  | -1809.61
| Chargebacks | Chargeback | Chargeback Entries <$5,000 | 8913.68 | 10500.93 | 4958.54 | 8052.5 | 8145.82 | 1482.46 | 7986.09 | 6404.14 | 8117.31 | 8952.31 | 9270.33 | 19463.11 | 102247.22
|  |  | TDBU Vehicle Cost | [5 empty] | 7156.15 | 9418.15 | 9089.34 | 8973.76 | 6235.47 | 5806.36 |  | 46679.23
|  |  | Work Package #4 | [5 empty] | 5300.95 | [6 empty] | 5300.95
|  | Chargeback Total |  | 8913.68 | 10500.93 | 4958.54 | 8052.5 | 8145.82 | 13939.56 | 17404.24 | 15493.48 | 17091.07 | 15187.78 | 15076.69 | 19463.11 | 154227.4
| Chargebacks Total |  |  | 8913.68 | 10500.93 | 4958.54 | 8052.5 | 8145.82 | 13939.56 | 17404.24 | 15493.48 | 17091.07 | 15187.78 | 15076.69 | 19463.11 | 154227.4
| Consultants /Prof Srvcs Correction | Contract | Contract Entries <$50,000 | [7 empty] | -52878.79 |  |  |  |  | -52878.79
|  | Contract Total | [8 empty] | -52878.79 |  |  |  |  | -52878.79
| Consultants /Prof Srvcs Correction Total | [9 empty] | -52878.79 |  |  |  |  | -52878.79
| Labor - Other | Labor | Division Overhead | 16293.14 | 15604.25 |  | 6798.73 |  |  |  | 6022.25 |  |  |  |  | 44718.37
|  |  | Labor Entries <$5,000 | 17649.49 | 21691.92 | 10521.64 | 16957.85 | 8451.96 | 13489.02 | 18817.79 | 15425.04 | 16703.98 | 18449.68 | 8140.14 | 8041.21 | 174339.72
|  |  | OH Tool Expenses | [11 empty] | 5009.5 | 5009.5
|  |  | Paid Absence |  |  |  |  | 6175.13 | 8278.31 | 10067.7 | 16179.01 | 10280.81 | 8083.35 | 8022.26 | 9447.04 | 76533.61
|  | Labor Total |  | 33942.63 | 37296.17 | 10521.64 | 23756.58 | 14627.09 | 21767.33 | 28885.49 | 37626.3 | 26984.79 | 26533.03 | 16162.4 | 22497.75 | 300601.2
| Labor - Other Total |  |  | 33942.63 | 37296.17 | 10521.64 | 23756.58 | 14627.09 | 21767.33 | 28885.49 | 37626.3 | 26984.79 | 26533.03 | 16162.4 | 22497.75 | 300601.2
| Material - Other | Material | Material - Other | [7 empty] | -3809.79 |  |  |  |  | -3809.79
|  | Material Total | [8 empty] | -3809.79 |  |  |  |  | -3809.79
| Material - Other Total | [9 empty] | -3809.79 |  |  |  |  | -3809.79
| Overhead Correction | Overhead | Overhead Correction | [7 empty] | -29003.48 | -366.46 | 366.46 |  |  | -29003.48
|  | Overhead Total | [8 empty] | -29003.48 | -366.46 | 366.46 |  |  | -29003.48
| Overhead Correction Total | [9 empty] | -29003.48 | -366.46 | 366.46 |  |  | -29003.48
| Temporary/Supplemental Correction | Contract | Contract Entries <$50,000 | [7 empty] | -2938.05 |  |  |  |  | -2938.05
|  | Contract Total | [8 empty] | -2938.05 |  |  |  |  | -2938.05
| Temporary/Supplemental Correction Total | [9 empty] | -2938.05 |  |  |  |  | -2938.05
4. Allocated Total |  |  |  | 42856.31 | 47797.1 | 15480.18 | 31809.08 | 22772.91 | 35706.89 | 46289.73 | -37319.94 | 43709.4 | 42087.27 | 31239.09 | 41960.86 | 364388.88
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 115601.42 | 6918.45 | [6 empty] | 116825.99 | 239345.86
|  |  | AFUDC - Debt/Equity |  |  | 119901.48 | -119901.48 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 18337.83 | 11095.03 | 7254.27 | 9723.72 | 6897.99 | -643727.14 | 5945.45 | -448.79 | 6933.24 | -12429.9 | 3660.7 | 5977.66 | -580779.94
|  |  | Capitalized Overhead - Inj & Damages | 69.62 | 122.88 | 40.11 | 45.4 | 392.88 | 9718.15 | 115.72 | 155.09 | 120.16 | -390.97 | 165.1 | 115.58 | 10669.72
|  |  | Capitalized Overhead - P&B/Payroll Tax | 14067.67 | 30530.09 | 31673.15 | 29813.4 | 61297.15 | -726002.18 | 96516.74 | 80549.72 | 112452.45 | -289518.91 | 52659.81 | 137988.2 | -367972.71
|  |  | Corporate Overheads Correction |  |  |  |  | -338596.07 | [7 empty] | -338596.07
|  | Non Budgeted Total |  | 32475.12 | 41748 | 158869.01 | 35282.46 | -263089.6 | -1360011.17 | 102577.91 | 80256.02 | 119505.85 | -302339.78 | 56485.61 | 260907.43 | -1037333.14
| Non Budget - Other Total |  |  | 32475.12 | 41748 | 158869.01 | 35282.46 | -263089.6 | -1360011.17 | 102577.91 | 80256.02 | 119505.85 | -302339.78 | 56485.61 | 260907.43 | -1037333.14
5. Corporate Overhead Total |  |  |  | 32475.12 | 41748 | 158869.01 | 35282.46 | -263089.6 | -1360011.17 | 102577.91 | 80256.02 | 119505.85 | -302339.78 | 56485.61 | 260907.43 | -1037333.14
Grand Total |  |  |  | 257194.55 | 428409.6 | 240090.05 | 295613.81 | -180640.71 | -1234586.52 | 271627.16 | 66099.68 | 273528.66 | -136778.56 | 195295.27 | 505337.67 | 981190.66

## 800218099
Pin: 6440 | Project: TRTP Segment 9
Order: 800218099 | 800218099- I: TRTP 9: MESA SUB: EQUIP POSITION FOR
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 1377.94 | 1377.94
|  | Labor Total | [12 empty] | 1377.94 | 1377.94
| ELEC SYS PLANNING Total | [13 empty] | 1377.94 | 1377.94
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | [6 empty] | 129.8 | [5 empty] | 129.8
|  | Labor Total | [7 empty] | 129.8 | [5 empty] | 129.8
| ENG ADVANCEMENT Total | [8 empty] | 129.8 | [5 empty] | 129.8
| ENGINEERING | Labor | Labor Entries <$5,000 | 930.25 | 747.35 | 1783.76 | 531.49 | 1059.75 | 529.88 |  | 543.67 | 426.91 | 3880.73 | 2892.07 |  | 13325.86
|  | Labor Total |  | 930.25 | 747.35 | 1783.76 | 531.49 | 1059.75 | 529.88 |  | 543.67 | 426.91 | 3880.73 | 2892.07 |  | 13325.86
| ENGINEERING Total |  |  | 930.25 | 747.35 | 1783.76 | 531.49 | 1059.75 | 529.88 |  | 543.67 | 426.91 | 3880.73 | 2892.07 |  | 13325.86
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 1265 | 811.93 | 485 | 507 | 568 |  | 769.8 | 291 | 672.74 | 424 | -230 | 874.21 | 6438.68
|  | Contract Total |  | 1265 | 811.93 | 485 | 507 | 568 |  | 769.8 | 291 | 672.74 | 424 | -230 | 874.21 | 6438.68
| Engineering/Technical Professional Servi Total |  |  | 1265 | 811.93 | 485 | 507 | 568 |  | 769.8 | 291 | 672.74 | 424 | -230 | 874.21 | 6438.68
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -21.03 | -24.43 | -6.54 | -18.04 | -8.76 | -15.79 | -28.15 | 236.4 | -267.38 | -7.25 | -81.4 | -242.37
|  | IMM Correction Total |  |  | -21.03 | -24.43 | -6.54 | -18.04 | -8.76 | -15.79 | -28.15 | 236.4 | -267.38 | -7.25 | -81.4 | -242.37
| IMM/Allocated - Correction Total |  |  |  | -21.03 | -24.43 | -6.54 | -18.04 | -8.76 | -15.79 | -28.15 | 236.4 | -267.38 | -7.25 | -81.4 | -242.37
| Labor - Other | Labor | Labor Accrual - SCE | [11 empty] | 5662.81 | 5662.81
|  |  | Labor Entries <$5,000 | 1209.39 | -218.12 | -166.84 | 48.39 | -50.69 | -13.46 | 11.63 | 1.83 | -31.73 | 609.16 | -430.29 | 1835.54 | 2804.81
|  | Labor Total |  | 1209.39 | -218.12 | -166.84 | 48.39 | -50.69 | -13.46 | 11.63 | 1.83 | -31.73 | 609.16 | -430.29 | 7498.35 | 8467.62
| Labor - Other Total |  |  | 1209.39 | -218.12 | -166.84 | 48.39 | -50.69 | -13.46 | 11.63 | 1.83 | -31.73 | 609.16 | -430.29 | 7498.35 | 8467.62
| Other | Other | Other | -216 | -588.74 | -718.09 | -181.67 | -162.85 | 349.28 | -136.84 | 265.07 | -204.58 | -90.52 | 110.3 | 6088.7 | 4514.06
|  | Other Total |  | -216 | -588.74 | -718.09 | -181.67 | -162.85 | 349.28 | -136.84 | 265.07 | -204.58 | -90.52 | 110.3 | 6088.7 | 4514.06
| Other Total |  |  | -216 | -588.74 | -718.09 | -181.67 | -162.85 | 349.28 | -136.84 | 265.07 | -204.58 | -90.52 | 110.3 | 6088.7 | 4514.06
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 |  | 208.61 | 1504.52 | [9 empty] | 1713.13
|  | Labor Total |  |  | 208.61 | 1504.52 | [9 empty] | 1713.13
| S/E SUBS MTCETST&APP Total |  |  |  | 208.61 | 1504.52 | [9 empty] | 1713.13
| SC&M | Labor | Labor Entries <$5,000 | [10 empty] | 834.1 | 403.89 | 1237.99
|  | Labor Total | [11 empty] | 834.1 | 403.89 | 1237.99
| SC&M Total | [12 empty] | 834.1 | 403.89 | 1237.99
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -180 | 180 |  |  | 0
|  | Contract Total | [9 empty] | -180 | 180 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -180 | 180 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1655.95 | 2727.4 | 506 | 2227.07 | 759 | 1897.5 | 2340.25 | 662.48 |  |  |  |  | 12775.65
|  | Contract Total |  | 1655.95 | 2727.4 | 506 | 2227.07 | 759 | 1897.5 | 2340.25 | 662.48 |  |  |  |  | 12775.65
| Temporary/Supplementary - Trade/Labor Total |  |  | 1655.95 | 2727.4 | 506 | 2227.07 | 759 | 1897.5 | 2340.25 | 662.48 |  |  |  |  | 12775.65
1. Project Support Total |  |  |  | 4844.59 | 3667.4 | 3369.92 | 3125.74 | 2155.17 | 2754.44 | 3098.85 | 1735.9 | 919.74 | 4735.99 | 3168.93 | 16161.69 | 49738.36
2. Material | Electric Wiring and Components-DP | Material - Direct Purchase | Electric Wiring and Components-DP | [10 empty] | 8009.78 |  | 8009.78
|  |  | Material Entries <$5,000 | [11 empty] | 252.71 | 252.71
|  | Material - Direct Purchase Total | [11 empty] | 8009.78 | 252.71 | 8262.49
| Electric Wiring and Components-DP Total | [12 empty] | 8009.78 | 252.71 | 8262.49
| Material - Other | Material | Material - Other | [10 empty] | 321.43 | 0.59 | 322.02
|  | Material Total | [11 empty] | 321.43 | 0.59 | 322.02
| Material - Other Total | [12 empty] | 321.43 | 0.59 | 322.02
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 234.43 | 234.43
|  | Material - Direct Purchase Total | [12 empty] | 234.43 | 234.43
| Transportation & Mobile Equip-DP Total | [13 empty] | 234.43 | 234.43
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 1658.84 |  | 1658.84
|  | Material - Direct Purchase Total | [11 empty] | 1658.84 |  | 1658.84
| Wire, Cable & Bus Bar-DP Total | [12 empty] | 1658.84 |  | 1658.84
2. Material Total | [13 empty] | 9990.05 | 487.73 | 10477.78
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [5 empty] | 495 | 1155 |  | 3248 | 495 | 2895 | 37203.29 | 45491.29
|  | Contract Total | [6 empty] | 495 | 1155 |  | 3248 | 495 | 2895 | 37203.29 | 45491.29
| Construction Management Services Total | [7 empty] | 495 | 1155 |  | 3248 | 495 | 2895 | 37203.29 | 45491.29
| ENGINEERING | Labor | Labor Entries <$5,000 | [10 empty] | 166.86 |  | 166.86
|  | Labor Total | [11 empty] | 166.86 |  | 166.86
| ENGINEERING Total | [12 empty] | 166.86 |  | 166.86
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 953.23 | 953.23
|  | Labor Total | [12 empty] | 953.23 | 953.23
| GRID OPS Total | [13 empty] | 953.23 | 953.23
| Major Construction, Turnkey, Trans/Subs | Contract | CAROB VALLEY ELECTRIC INC | [11 empty] | 96823.5 | 96823.5
|  | Contract Total | [12 empty] | 96823.5 | 96823.5
| Major Construction, Turnkey, Trans/Subs Total | [13 empty] | 96823.5 | 96823.5
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | 5461.11 | 2283.22 | 1006.17 |  | 197.65 |  |  |  | 350.38 | 342.84 | 15536.43 | 332.34 | 25510.14
|  | Labor Total |  | 5461.11 | 2283.22 | 1006.17 |  | 197.65 |  |  |  | 350.38 | 342.84 | 15536.43 | 332.34 | 25510.14
| S/E SUBS MTCETST&APP Total |  |  | 5461.11 | 2283.22 | 1006.17 |  | 197.65 |  |  |  | 350.38 | 342.84 | 15536.43 | 332.34 | 25510.14
| SC&M | Labor | Labor Entries <$5,000 | [7 empty] | 220.56 |  |  |  | 27804.78 | 28025.34
|  |  | SC&M / Tst Spr Tech | [11 empty] | 5449.92 | 5449.92
|  | Labor Total | [8 empty] | 220.56 |  |  |  | 33254.7 | 33475.26
| SC&M Total | [9 empty] | 220.56 |  |  |  | 33254.7 | 33475.26
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [5 empty] | 108.75 |  |  |  |  | 233.64 |  | 342.39
|  | Contract Total | [6 empty] | 108.75 |  |  |  |  | 233.64 |  | 342.39
| Short Term Equipment Rent Total | [7 empty] | 108.75 |  |  |  |  | 233.64 |  | 342.39
3. Construction Total |  |  |  | 5461.11 | 2283.22 | 1006.17 |  | 197.65 | 603.75 | 1155 | 220.56 | 3598.38 | 837.84 | 18831.93 | 168567.06 | 202762.67
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 2214.51 | 1691.96 | 2354.82 | 1942.43 | 1837.12 | 2257.28 | 2043.83 | 1686.91 | 2063.83 | 2561.71 | 4265.4 | 8663.86 | 33583.66
|  | Chargeback Total |  | 2214.51 | 1691.96 | 2354.82 | 1942.43 | 1837.12 | 2257.28 | 2043.83 | 1686.91 | 2063.83 | 2561.71 | 4265.4 | 8663.86 | 33583.66
| Chargebacks Total |  |  | 2214.51 | 1691.96 | 2354.82 | 1942.43 | 1837.12 | 2257.28 | 2043.83 | 1686.91 | 2063.83 | 2561.71 | 4265.4 | 8663.86 | 33583.66
| Labor - Other | Labor | Labor Entries <$5,000 | 3484.7 | 1624.46 | 1496.83 | 395.16 | 498.94 | 330.42 | 374.89 | 320.92 | 509.81 | 1677.14 | 4002.46 | 12186.43 | 26902.16
|  |  | Paid Absence | [11 empty] | 5957.32 | 5957.32
|  | Labor Total |  | 3484.7 | 1624.46 | 1496.83 | 395.16 | 498.94 | 330.42 | 374.89 | 320.92 | 509.81 | 1677.14 | 4002.46 | 18143.75 | 32859.48
| Labor - Other Total |  |  | 3484.7 | 1624.46 | 1496.83 | 395.16 | 498.94 | 330.42 | 374.89 | 320.92 | 509.81 | 1677.14 | 4002.46 | 18143.75 | 32859.48
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -30.96 | 30.96 |  |  | 0
|  | Overhead Total | [9 empty] | -30.96 | 30.96 |  |  | 0
| Overhead Correction Total | [10 empty] | -30.96 | 30.96 |  |  | 0
4. Allocated Total |  |  |  | 5699.21 | 3316.42 | 3851.65 | 2337.59 | 2336.06 | 2587.7 | 2418.72 | 2007.83 | 2542.68 | 4269.81 | 8267.86 | 26807.61 | 66443.14
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 13325.91 | 792.81 | [6 empty] | 15966.67 | 30085.39
|  |  | AFUDC - Debt/Equity |  |  | 14064.78 | -14064.78 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | -1100.74 | 293.48 | 318.87 | 201.3 | 408.24 | 202.14 | 239.1 | 104.63 | 325.48 | 256.67 | 1061.01 | 5803.21 | 8113.39
|  |  | Capitalized Overhead - Inj & Damages | -30.08 | 10.44 | 7.26 | 1.66 | 25.59 | 2.47 | 1.58 | 3.35 | 2.54 | 25.45 | 60.29 | 78.73 | 189.28
|  |  | Capitalized Overhead - P&B/Payroll Tax | -16873.52 | 4406.09 | 4866.91 | 1648.02 | 2928.22 | 1447.06 | 1225.95 | 1545.13 | 2317.73 | 2825.83 | 15759.25 | 96339.41 | 118436.08
|  |  | Corporate Overheads Correction |  |  |  |  | -42973.6 | [7 empty] | -42973.6
|  | Non Budgeted Total |  | -18004.34 | 4710.01 | 19257.82 | 1112.11 | -38818.74 | 1651.67 | 1466.63 | 1653.11 | 2645.75 | 3107.95 | 16880.55 | 118188.02 | 113850.54
| Non Budget - Other Total |  |  | -18004.34 | 4710.01 | 19257.82 | 1112.11 | -38818.74 | 1651.67 | 1466.63 | 1653.11 | 2645.75 | 3107.95 | 16880.55 | 118188.02 | 113850.54
5. Corporate Overhead Total |  |  |  | -18004.34 | 4710.01 | 19257.82 | 1112.11 | -38818.74 | 1651.67 | 1466.63 | 1653.11 | 2645.75 | 3107.95 | 16880.55 | 118188.02 | 113850.54
Grand Total |  |  |  | -1999.43 | 13977.05 | 27485.56 | 6575.44 | -34129.86 | 7597.56 | 8139.2 | 5617.4 | 9706.55 | 12951.59 | 57139.32 | 330212.11 | 443272.49

## 800218070
Pin: 6440 | Project: TRTP Segment 9
Order: 800218070 | 800218070- I: TRTP 9: PARDEE SUB: UPGRADE PROTECTIO
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 |  |  |  | 2012 Total
SubCategory | Prime | Group | Details | 3 | 5 | 8 | 11
1. Project Support | Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  |  |  | -3681.08 | -3681.08
|  | Contract Total |  |  |  |  | -3681.08 | -3681.08
| Engineering/Technical Professional Servi Total | [5 empty] | -3681.08 | -3681.08
1. Project Support Total | [6 empty] | -3681.08 | -3681.08
2. Material | Material - Inventory | Material | Material - Inventory |  | -807.17 | -2826.49 |  | -3633.66
|  | Material Total |  |  | -807.17 | -2826.49 |  | -3633.66
| Material - Inventory Total |  |  |  | -807.17 | -2826.49 |  | -3633.66
| Material - Other | Material | Material - Other |  | -71.82 | -249.67 |  | -321.49
|  | Material Total |  |  | -71.82 | -249.67 |  | -321.49
| Material - Other Total |  |  |  | -71.82 | -249.67 |  | -321.49
2. Material Total |  |  |  |  | -878.99 | -3076.16 |  | -3955.15
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 |  | -156.91 | -368.86 | -24.3 | -550.07
|  | Chargeback Total |  |  | -156.91 | -368.86 | -24.3 | -550.07
| Chargebacks Total |  |  |  | -156.91 | -368.86 | -24.3 | -550.07
| Labor - Other | Labor | Labor Entries <$5,000 |  | -55.69 | -209.45 | -93.13 | -358.27
|  | Labor Total |  |  | -55.69 | -209.45 | -93.13 | -358.27
| Labor - Other Total |  |  |  | -55.69 | -209.45 | -93.13 | -358.27
4. Allocated Total |  |  |  |  | -212.6 | -578.31 | -117.43 | -908.34
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G |  | 698.66 | -93.2 | -93.5 | 511.96
|  |  | Capitalized Overhead - Inj & Damages |  | 13.33 | -4.29 | -0.18 | 8.86
|  |  | Capitalized Overhead - P&B/Payroll Tax | -0.01 | 1909.03 |  |  | 1909.02
|  |  | Corporate Overheads Correction |  | -4985.43 |  |  | -4985.43
|  | Non Budgeted Total |  | -0.01 | -2364.41 | -97.49 | -93.68 | -2555.59
| Non Budget - Other Total |  |  | -0.01 | -2364.41 | -97.49 | -93.68 | -2555.59
5. Corporate Overhead Total |  |  |  | -0.01 | -2364.41 | -97.49 | -93.68 | -2555.59
Grand Total |  |  |  | -0.01 | -3456 | -3751.96 | -3892.19 | -11100.16

## 800217014
Pin: 6440 | Project: TRTP Segment 9
Order: 800217014 | 800217014- I: TRTP 9: WINDHUB SUBSTATION - UPGRADE
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  |  | 10.92 | [7 empty] | 10.92
|  | Labor Total | [5 empty] | 10.92 | [7 empty] | 10.92
| BP&FM Total | [6 empty] | 10.92 | [7 empty] | 10.92
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -539.09 | 539.09 |  |  | 0
|  | Contract Total | [9 empty] | -539.09 | 539.09 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -539.09 | 539.09 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | [8 empty] | 1022.31 |  |  |  | 1022.31
|  | Contract Total | [9 empty] | 1022.31 |  |  |  | 1022.31
| Contract Consult/Contract Ord to Ord Total | [10 empty] | 1022.31 |  |  |  | 1022.31
| Corporate Security | Labor | Labor Entries <$5,000 | [7 empty] | 738.96 |  |  |  |  | 738.96
|  | Labor Total | [8 empty] | 738.96 |  |  |  |  | 738.96
| Corporate Security Total | [9 empty] | 738.96 |  |  |  |  | 738.96
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 765.41 | 765.41
|  | Labor Total | [12 empty] | 765.41 | 765.41
| ELEC SYS PLANNING Total | [13 empty] | 765.41 | 765.41
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | [7 empty] | 51.54 |  |  |  |  | 51.54
|  | Labor Total | [8 empty] | 51.54 |  |  |  |  | 51.54
| ENG ADVANCEMENT Total | [9 empty] | 51.54 |  |  |  |  | 51.54
| ENGINEERING | Labor | Labor Entries <$5,000 | 2363.9 | 1994.96 | 2422.13 | 942.6 | 2085.19 | 2896.45 | 1030.99 | 1046.49 | 127.06 |  | 252.51 |  | 15162.28
|  | Labor Total |  | 2363.9 | 1994.96 | 2422.13 | 942.6 | 2085.19 | 2896.45 | 1030.99 | 1046.49 | 127.06 |  | 252.51 |  | 15162.28
| ENGINEERING Total |  |  | 2363.9 | 1994.96 | 2422.13 | 942.6 | 2085.19 | 2896.45 | 1030.99 | 1046.49 | 127.06 |  | 252.51 |  | 15162.28
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 18115.26 | 3383.03 | 967 | 7055.92 | 1650.67 | 1376.9 | 27896.03 | 582 | 167.48 |  | -1247 | 190.42 | 60137.71
|  | Contract Total |  | 18115.26 | 3383.03 | 967 | 7055.92 | 1650.67 | 1376.9 | 27896.03 | 582 | 167.48 |  | -1247 | 190.42 | 60137.71
| Engineering/Technical Professional Servi Total |  |  | 18115.26 | 3383.03 | 967 | 7055.92 | 1650.67 | 1376.9 | 27896.03 | 582 | 167.48 |  | -1247 | 190.42 | 60137.71
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 812.63 | 425.76 | -1740.05 | 748.33 | 636.55 | 729.34 | 496.46 | 352.3 | 1918.99 | -860.12 | -23.4 | -33.37 | 3463.42
|  | IMM Correction Total |  | 812.63 | 425.76 | -1740.05 | 748.33 | 636.55 | 729.34 | 496.46 | 352.3 | 1918.99 | -860.12 | -23.4 | -33.37 | 3463.42
| IMM/Allocated - Correction Total |  |  | 812.63 | 425.76 | -1740.05 | 748.33 | 636.55 | 729.34 | 496.46 | 352.3 | 1918.99 | -860.12 | -23.4 | -33.37 | 3463.42
| Labor - Other | Labor | Labor Entries <$5,000 | -23.54 | 275.49 | -259.79 | 58.53 | 363.12 | -474.43 | -31.34 | 547.82 | 210.04 | 971.84 | -134.92 | 358.77 | 1861.59
|  | Labor Total |  | -23.54 | 275.49 | -259.79 | 58.53 | 363.12 | -474.43 | -31.34 | 547.82 | 210.04 | 971.84 | -134.92 | 358.77 | 1861.59
| Labor - Other Total |  |  | -23.54 | 275.49 | -259.79 | 58.53 | 363.12 | -474.43 | -31.34 | 547.82 | 210.04 | 971.84 | -134.92 | 358.77 | 1861.59
| Other | Other | Other | -2443.11 | 153163.59 | -154844.33 | -300.39 | 16229.15 | -17285.46 | -2829.58 | -647.86 | 8439.42 | -3433.4 | 2513.11 | -7404.92 | -8843.78
|  | Other Total |  | -2443.11 | 153163.59 | -154844.33 | -300.39 | 16229.15 | -17285.46 | -2829.58 | -647.86 | 8439.42 | -3433.4 | 2513.11 | -7404.92 | -8843.78
| Other Total |  |  | -2443.11 | 153163.59 | -154844.33 | -300.39 | 16229.15 | -17285.46 | -2829.58 | -647.86 | 8439.42 | -3433.4 | 2513.11 | -7404.92 | -8843.78
| Software License Via Electronic Delivery | Contract | Contract Entries <$50,000 | [11 empty] | 7810.6 | 7810.6
|  | Contract Total | [12 empty] | 7810.6 | 7810.6
| Software License Via Electronic Delivery Total | [13 empty] | 7810.6 | 7810.6
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -203.12 | 203.12 |  |  | 0
|  | Contract Total | [9 empty] | -203.12 | 203.12 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -203.12 | 203.12 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 600.16 | 464.64 | 348.48 | [9 empty] | 1413.28
|  | Contract Total |  | 600.16 | 464.64 | 348.48 | [9 empty] | 1413.28
| Temporary/Supplementary - Trade/Labor Total |  |  | 600.16 | 464.64 | 348.48 | [9 empty] | 1413.28
| TRANSMISSION | Labor | Labor Entries <$5,000 | [11 empty] | 414.92 | 414.92
|  | Labor Total | [12 empty] | 414.92 | 414.92
| TRANSMISSION Total | [13 empty] | 414.92 | 414.92
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | [10 empty] | 926.52 |  | 926.52
|  | Labor Total | [11 empty] | 926.52 |  | 926.52
| TRNS CAPITAL Total | [12 empty] | 926.52 |  | 926.52
1. Project Support Total |  |  |  | 19425.3 | 159707.47 | -153106.56 | 8504.99 | 20975.6 | -12757.2 | 26562.56 | 2671.25 | 11143.09 | -2579.47 | 2286.82 | 2101.83 | 84935.68
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  |  | 0 | [9 empty] | 0
|  | Material - Direct Purchase Total |  |  |  | 0 | [9 empty] | 0
| Building, Shop & Industrial Products/Eqp Total |  |  |  |  | 0 | [9 empty] | 0
| Communication Systems and Equipment -DP | Material - Direct Purchase | Communication Systems and Equipment -DP | [11 empty] | 21483 | 21483
|  | Material - Direct Purchase Total | [12 empty] | 21483 | 21483
| Communication Systems and Equipment -DP Total | [13 empty] | 21483 | 21483
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -2.94 | 2.94 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -2.94 | 2.94 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -2.94 | 2.94 |  |  | 0
| Material - Inventory | Material | Material - Inventory |  |  | 114.2 | [5 empty] | -0.05 | 0.05 |  |  | 114.2
|  | Material Total |  |  |  | 114.2 | [5 empty] | -0.05 | 0.05 |  |  | 114.2
| Material - Inventory Total |  |  |  |  | 114.2 | [5 empty] | -0.05 | 0.05 |  |  | 114.2
| Material - Other | Material | Material - Other | 33.65 | 77.71 | 10003.85 | 3870.61 | 1333.94 | 729.71 | 0.16 |  | -0.27 | 0.27 |  | 26.2 | 16075.83
|  | Material Total |  | 33.65 | 77.71 | 10003.85 | 3870.61 | 1333.94 | 729.71 | 0.16 |  | -0.27 | 0.27 |  | 26.2 | 16075.83
| Material - Other Total |  |  | 33.65 | 77.71 | 10003.85 | 3870.61 | 1333.94 | 729.71 | 0.16 |  | -0.27 | 0.27 |  | 26.2 | 16075.83
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 1046 | [10 empty] | 1046
|  | Material - Direct Purchase Total |  |  | 1046 | [10 empty] | 1046
| Office & Office Support Products-DP Total |  |  |  | 1046 | [10 empty] | 1046
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | -817.74 | [8 empty] | -817.74
|  | Material - Direct Purchase Total |  |  |  |  | -817.74 | [8 empty] | -817.74
| Pole Line Hdwe & Connectors-DP Total | [5 empty] | -817.74 | [8 empty] | -817.74
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO |  |  |  | 14990 | [8 empty] | 14990
|  |  | Material Entries <$5,000 | 455 | [11 empty] | 455
|  |  | WASHINGTON ORNAMENTAL | [5 empty] | 9912 | [6 empty] | 9912
|  | Material - Direct Purchase Total |  | 455 |  |  | 14990 |  | 9912 | [6 empty] | 25357
| Steel / Fabricated / Structural-DP Total |  |  | 455 |  |  | 14990 |  | 9912 | [6 empty] | 25357
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 160.14 |  | 15.78 |  |  |  | 127.94 | [5 empty] | 303.86
|  | Material - Direct Purchase Total |  | 160.14 |  | 15.78 |  |  |  | 127.94 | [5 empty] | 303.86
| Transportation & Mobile Equip-DP Total |  |  | 160.14 |  | 15.78 |  |  |  | 127.94 | [5 empty] | 303.86
2. Material Total |  |  |  | 648.79 | 1123.71 | 10133.83 | 18042.87 | 1333.94 | 10641.71 | 128.1 |  | -3.26 | 3.26 |  | 21509.2 | 63562.15
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 34401.72 |  | 8410.5 | 5450 | 7430 | 6340 | 4340 |  |  |  |  | 1635.4 | 68007.62
|  | Contract Total |  | 34401.72 |  | 8410.5 | 5450 | 7430 | 6340 | 4340 |  |  |  |  | 1635.4 | 68007.62
| Construction Management Services Total |  |  | 34401.72 |  | 8410.5 | 5450 | 7430 | 6340 | 4340 |  |  |  |  | 1635.4 | 68007.62
| Construction, Property/Building | Contract | ELDRIDGE ELECTRIC & SONS INC. | [11 empty] | 119353.91 | 119353.91
|  | Contract Total | [12 empty] | 119353.91 | 119353.91
| Construction, Property/Building Total | [13 empty] | 119353.91 | 119353.91
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 1150.76 | 1150.76
|  | Labor Total | [12 empty] | 1150.76 | 1150.76
| ELEC SYS PLANNING Total | [13 empty] | 1150.76 | 1150.76
| Electrical Services | Contract | Contract Entries <$50,000 |  | 44124 | [10 empty] | 44124
|  | Contract Total |  |  | 44124 | [10 empty] | 44124
| Electrical Services Total |  |  |  | 44124 | [10 empty] | 44124
| ENGINEERING | Labor | Labor Entries <$5,000 |  | 67.62 |  |  |  |  | 163.9 | 897.89 | 486.03 | 485.44 | 407.17 |  | 2508.05
|  | Labor Total |  |  | 67.62 |  |  |  |  | 163.9 | 897.89 | 486.03 | 485.44 | 407.17 |  | 2508.05
| ENGINEERING Total |  |  |  | 67.62 |  |  |  |  | 163.9 | 897.89 | 486.03 | 485.44 | 407.17 |  | 2508.05
| GRID OPS | Labor | Labor Entries <$5,000 |  |  |  | 304.36 |  |  |  |  | 2618.22 |  | 970.22 |  | 3892.8
|  | Labor Total |  |  |  |  | 304.36 |  |  |  |  | 2618.22 |  | 970.22 |  | 3892.8
| GRID OPS Total | [5 empty] | 304.36 |  |  |  |  | 2618.22 |  | 970.22 |  | 3892.8
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [10 empty] | 4116 |  | 4116
|  |  | PROFESSIONAL ELECTRICAL CONSTRUCTIO |  | 337752 | [10 empty] | 337752
|  | Contract Total |  |  | 337752 | [8 empty] | 4116 |  | 341868
| Major Construction, Turnkey, Trans/Subs Total |  |  |  | 337752 | [8 empty] | 4116 |  | 341868
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 |  | 818.73 |  |  |  |  | 1019.86 | [5 empty] | 1838.59
|  | Labor Total |  |  | 818.73 |  |  |  |  | 1019.86 | [5 empty] | 1838.59
| N/W SUBSMTCETEST&APP Total |  |  |  | 818.73 |  |  |  |  | 1019.86 | [5 empty] | 1838.59
| Security / Protection Services | Contract | Contract Entries <$50,000 | [5 empty] | 2450 |  |  |  | 2800 | 2187.5 | 34600 | 42037.5
|  | Contract Total | [6 empty] | 2450 |  |  |  | 2800 | 2187.5 | 34600 | 42037.5
| Security / Protection Services Total | [7 empty] | 2450 |  |  |  | 2800 | 2187.5 | 34600 | 42037.5
3. Construction Total |  |  |  | 34401.72 | 382762.35 | 8410.5 | 5754.36 | 7430 | 8790 | 5523.76 | 897.89 | 3104.25 | 3285.44 | 7680.89 | 156740.07 | 624781.23
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 2910.94 | 5171.2 | 3679.33 | 3420.81 | 3217.75 | 4000.32 | 955.24 | 379.36 | 472.17 | 208.54 | 2141.4 | 4371.67 | 30928.73
|  |  | Windhub ûSubstation û IDS Install | [11 empty] | 990810.76 | 990810.76
|  | Chargeback Total |  | 2910.94 | 5171.2 | 3679.33 | 3420.81 | 3217.75 | 4000.32 | 955.24 | 379.36 | 472.17 | 208.54 | 2141.4 | 995182.43 | 1021739.49
| Chargebacks Total |  |  | 2910.94 | 5171.2 | 3679.33 | 3420.81 | 3217.75 | 4000.32 | 955.24 | 379.36 | 472.17 | 208.54 | 2141.4 | 995182.43 | 1021739.49
| Labor - Other | Labor | Division Overhead |  | 25217.38 | [10 empty] | 25217.38
|  |  | Labor Entries <$5,000 | 6218.61 | 11097.7 | 1462.84 | 2431.13 | 1409.35 | 2078.32 | 3294.57 | 953.15 | 830.44 | 635.32 | 570.13 | 7529.16 | 38510.72
|  | Labor Total |  | 6218.61 | 36315.08 | 1462.84 | 2431.13 | 1409.35 | 2078.32 | 3294.57 | 953.15 | 830.44 | 635.32 | 570.13 | 7529.16 | 63728.1
| Labor - Other Total |  |  | 6218.61 | 36315.08 | 1462.84 | 2431.13 | 1409.35 | 2078.32 | 3294.57 | 953.15 | 830.44 | 635.32 | 570.13 | 7529.16 | 63728.1
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -57.08 | 57.08 |  |  | 0
|  | Overhead Total | [9 empty] | -57.08 | 57.08 |  |  | 0
| Overhead Correction Total | [10 empty] | -57.08 | 57.08 |  |  | 0
4. Allocated Total |  |  |  | 9129.55 | 41486.28 | 5142.17 | 5851.94 | 4627.1 | 6078.64 | 4249.81 | 1332.51 | 1245.53 | 900.94 | 2711.53 | 1002711.59 | 1085467.59
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 45559.76 | 2735.53 | [7 empty] | 48295.29
|  |  | AFUDC - Debt/Equity |  |  | 48499.1 | -48499.1 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 3573.84 | 12653.5 | 906.24 | 1373.38 | 1410.48 | 1072.09 | 1290.01 | 156.97 | 321.15 | 128.38 | 268.66 | 33424.03 | 56578.73
|  |  | Capitalized Overhead - Inj & Damages | 9.77 | 78.96 | 14.68 | 20.34 | 59.38 | 22.83 | 3.89 | 6.44 | 6.09 | 4.35 | 8.38 | 51.94 | 287.05
|  |  | Capitalized Overhead - P&B/Payroll Tax | 2681.97 | 5102 | 3518.54 | 3256.23 | 5603.97 | 4521.21 | 2875.11 | 2656.12 | 4796.75 | 717.38 | 3262.58 | 11091.42 | 50083.28
|  |  | Corporate Overheads Correction |  |  |  |  | -88536.88 | [7 empty] | -88536.88
|  | Non Budgeted Total |  | 6265.58 | 17834.46 | 52938.56 | 1710.61 | -78727.52 | 5616.13 | 4169.01 | 2819.53 | 5123.99 | 850.11 | 3539.62 | 44567.39 | 66707.47
| Non Budget - Other Total |  |  | 6265.58 | 17834.46 | 52938.56 | 1710.61 | -78727.52 | 5616.13 | 4169.01 | 2819.53 | 5123.99 | 850.11 | 3539.62 | 44567.39 | 66707.47
5. Corporate Overhead Total |  |  |  | 6265.58 | 17834.46 | 52938.56 | 1710.61 | -78727.52 | 5616.13 | 4169.01 | 2819.53 | 5123.99 | 850.11 | 3539.62 | 44567.39 | 66707.47
Grand Total |  |  |  | 69870.94 | 602914.27 | -76481.5 | 39864.77 | -44360.88 | 18369.28 | 40633.24 | 7721.18 | 20613.6 | 2460.28 | 16218.86 | 1227630.08 | 1925454.12

## 800216929
Pin: 6440 | Project: TRTP Segment 9
Order: 800216929 | 800216929- I: TRTP 9: VINCENT: UPGRADE 500KV & 220K
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  | 2051.29 | 4629.82 |  |  | 1186.51 | 443.26 | [5 empty] | 8310.88
|  | Labor Total |  |  | 2051.29 | 4629.82 |  |  | 1186.51 | 443.26 | [5 empty] | 8310.88
| BP&FM Total |  |  |  | 2051.29 | 4629.82 |  |  | 1186.51 | 443.26 | [5 empty] | 8310.88
| BSVHCC | Labor | Labor Entries <$5,000 | [8 empty] | 124.48 |  |  |  | 124.48
|  | Labor Total | [9 empty] | 124.48 |  |  |  | 124.48
| BSVHCC Total | [10 empty] | 124.48 |  |  |  | 124.48
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  | 4414.63 | 9755.16 | 12860.52 |  |  |  | 9784.97 |  | 33038.85 | 725.21 | 286.35 | 70865.69
|  | Contract Total |  |  | 4414.63 | 9755.16 | 12860.52 |  |  |  | 9784.97 |  | 33038.85 | 725.21 | 286.35 | 70865.69
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  | 4414.63 | 9755.16 | 12860.52 |  |  |  | 9784.97 |  | 33038.85 | 725.21 | 286.35 | 70865.69
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 195491.39 |  |  | 195491.39
|  |  | Contract Entries <$50,000 | [8 empty] | -195491.39 |  |  |  | -195491.39
|  | Contract Total | [9 empty] | -195491.39 | 195491.39 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -195491.39 | 195491.39 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  | 841.5 |  |  |  | 711.23 | [6 empty] | 1552.73
|  | Contract Total |  |  | 841.5 |  |  |  | 711.23 | [6 empty] | 1552.73
| Contract Consult/Contract Ord to Ord Total |  |  |  | 841.5 |  |  |  | 711.23 | [6 empty] | 1552.73
| Corporate Security | Labor | Labor Entries <$5,000 |  | 687.17 | 1339.63 | 840.05 | [8 empty] | 2866.85
|  | Labor Total |  |  | 687.17 | 1339.63 | 840.05 | [8 empty] | 2866.85
| Corporate Security Total |  |  |  | 687.17 | 1339.63 | 840.05 | [8 empty] | 2866.85
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 6709.15 | 6709.15
|  | Labor Total | [12 empty] | 6709.15 | 6709.15
| ELEC SYS PLANNING Total | [13 empty] | 6709.15 | 6709.15
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 2369.8 | 534.04 | 9969.06 | 2812.14 | 109.87 | [7 empty] | 15794.91
|  |  | Techn Spl/Scientist |  | 5229.72 | [10 empty] | 5229.72
|  | Labor Total |  | 2369.8 | 5763.76 | 9969.06 | 2812.14 | 109.87 | [7 empty] | 21024.63
| ENG ADVANCEMENT Total |  |  | 2369.8 | 5763.76 | 9969.06 | 2812.14 | 109.87 | [7 empty] | 21024.63
| ENGINEERING | Labor | Engineer Sr |  |  | 5215.72 | [9 empty] | 5215.72
|  |  | Labor Entries <$5,000 | 8176.44 | 5701.9 | 4222.37 | 7278.14 | 3378.33 | 6084.32 | 6950.31 | 7563.32 | 3110.23 | 6294.83 | 13237.13 | 169.66 | 72166.98
|  | Labor Total |  | 8176.44 | 5701.9 | 9438.09 | 7278.14 | 3378.33 | 6084.32 | 6950.31 | 7563.32 | 3110.23 | 6294.83 | 13237.13 | 169.66 | 77382.7
| ENGINEERING Total |  |  | 8176.44 | 5701.9 | 9438.09 | 7278.14 | 3378.33 | 6084.32 | 6950.31 | 7563.32 | 3110.23 | 6294.83 | 13237.13 | 169.66 | 77382.7
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | 54415 | [11 empty] | 54415
|  |  | Contract Entries <$50,000 | 42385.08 | 39352.01 | 20798 | 70102.61 | 28346 |  | 33087.17 | 15947 | 17938.8 | 35127.77 | -3953 | 27669.1 | 326800.54
|  | Contract Total |  | 96800.08 | 39352.01 | 20798 | 70102.61 | 28346 |  | 33087.17 | 15947 | 17938.8 | 35127.77 | -3953 | 27669.1 | 381215.54
| Engineering/Technical Professional Servi Total |  |  | 96800.08 | 39352.01 | 20798 | 70102.61 | 28346 |  | 33087.17 | 15947 | 17938.8 | 35127.77 | -3953 | 27669.1 | 381215.54
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | [5 empty] | 2867.56 | -2867.56 | [5 empty] | 0
|  | Contract Total | [6 empty] | 2867.56 | -2867.56 | [5 empty] | 0
| Environmental/Safety Professional Servic Total | [7 empty] | 2867.56 | -2867.56 | [5 empty] | 0
| FIELDCONSTNDESERT | Labor | Labor Entries <$5,000 | [10 empty] | 139.19 |  | 139.19
|  | Labor Total | [11 empty] | 139.19 |  | 139.19
| FIELDCONSTNDESERT Total | [12 empty] | 139.19 |  | 139.19
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 7313.69 | 3964.5 | -6511.54 | 5828.84 | 749.02 | 6007.61 | 4733.56 | 4699.67 | 218336.08 | -209396.75 | -1660.02 | -144.03 | 33920.63
|  | IMM Correction Total |  | 7313.69 | 3964.5 | -6511.54 | 5828.84 | 749.02 | 6007.61 | 4733.56 | 4699.67 | 218336.08 | -209396.75 | -1660.02 | -144.03 | 33920.63
| IMM/Allocated - Correction Total |  |  | 7313.69 | 3964.5 | -6511.54 | 5828.84 | 749.02 | 6007.61 | 4733.56 | 4699.67 | 218336.08 | -209396.75 | -1660.02 | -144.03 | 33920.63
| Labor - Other | Labor | Labor Accrual - SCE |  | 7144.55 |  |  | 6494.75 |  |  |  |  | 6392.66 |  | 14853.55 | 34885.51
|  |  | Labor Correction | [9 empty] | 21136.16 |  |  | 21136.16
|  |  | Labor Entries <$5,000 | 5579.38 | 964 | -8451.96 | 1837.06 | 561.46 | -7718.89 | -410.44 | 2043.52 | -6597.22 | -13867.26 | -5736.21 | 50.23 | -31746.33
|  | Labor Total |  | 5579.38 | 8108.55 | -8451.96 | 1837.06 | 7056.21 | -7718.89 | -410.44 | 2043.52 | -6597.22 | 13661.56 | -5736.21 | 14903.78 | 24275.34
| Labor - Other Total |  |  | 5579.38 | 8108.55 | -8451.96 | 1837.06 | 7056.21 | -7718.89 | -410.44 | 2043.52 | -6597.22 | 13661.56 | -5736.21 | 14903.78 | 24275.34
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | 5457.65 | 5589.01 | 1982.26 | 505.12 | 2652.65 | 2078.98 | 1164.11 |  | 909.4 | 758.31 | 4631.18 |  | 25728.67
|  | Labor Total |  | 5457.65 | 5589.01 | 1982.26 | 505.12 | 2652.65 | 2078.98 | 1164.11 |  | 909.4 | 758.31 | 4631.18 |  | 25728.67
| NORTH GRIDMGMTCENTER Total |  |  | 5457.65 | 5589.01 | 1982.26 | 505.12 | 2652.65 | 2078.98 | 1164.11 |  | 909.4 | 758.31 | 4631.18 |  | 25728.67
| Other | Other | Other | 44446.37 | -18109.8 | 180061.89 | 73623.42 | -81595.89 | 105020.04 | 40062.99 | 73564.53 | 15136.78 | -9375.19 | 6103.19 | 34297.67 | 463236
|  | Other Total |  | 44446.37 | -18109.8 | 180061.89 | 73623.42 | -81595.89 | 105020.04 | 40062.99 | 73564.53 | 15136.78 | -9375.19 | 6103.19 | 34297.67 | 463236
| Other Total |  |  | 44446.37 | -18109.8 | 180061.89 | 73623.42 | -81595.89 | 105020.04 | 40062.99 | 73564.53 | 15136.78 | -9375.19 | 6103.19 | 34297.67 | 463236
| PLGHCC | Labor | Labor Entries <$5,000 | [10 empty] | 47.55 | 220.64 | 268.19
|  | Labor Total | [11 empty] | 47.55 | 220.64 | 268.19
| PLGHCC Total | [12 empty] | 47.55 | 220.64 | 268.19
| SC&M | Labor | Labor Entries <$5,000 | 6692.04 | 5370.54 | 7473.99 | 6569.4 | 5969.57 | 2986.55 | 5719.95 | 64.58 | 5302.51 | 5409.86 | 4539.22 | 4380.07 | 60478.28
|  |  | SC&M / Mgr-Prj/Prod | [5 empty] | 6055.2 |  | 6307.5 |  |  |  |  | 12362.7
|  | Labor Total |  | 6692.04 | 5370.54 | 7473.99 | 6569.4 | 5969.57 | 9041.75 | 5719.95 | 6372.08 | 5302.51 | 5409.86 | 4539.22 | 4380.07 | 72840.98
| SC&M Total |  |  | 6692.04 | 5370.54 | 7473.99 | 6569.4 | 5969.57 | 9041.75 | 5719.95 | 6372.08 | 5302.51 | 5409.86 | 4539.22 | 4380.07 | 72840.98
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -9037.3 | 9037.3 |  |  | 0
|  | Contract Total | [9 empty] | -9037.3 | 9037.3 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -9037.3 | 9037.3 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 788 | 1182 | 2630 | 5188 | 1540 | [7 empty] | 11328
|  | Contract Total |  | 788 | 1182 | 2630 | 5188 | 1540 | [7 empty] | 11328
| Temporary/Supplementary - Technical/Prof Total |  |  | 788 | 1182 | 2630 | 5188 | 1540 | [7 empty] | 11328
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 515.02 | 379.5 | 135.52 | 1278.52 | 885.5 | 6681.27 | 6467.25 | 2403.5 | 126.5 |  | -7273.92 |  | 11598.66
|  | Contract Total |  | 515.02 | 379.5 | 135.52 | 1278.52 | 885.5 | 6681.27 | 6467.25 | 2403.5 | 126.5 |  | -7273.92 |  | 11598.66
| Temporary/Supplementary - Trade/Labor Total |  |  | 515.02 | 379.5 | 135.52 | 1278.52 | 885.5 | 6681.27 | 6467.25 | 2403.5 | 126.5 |  | -7273.92 |  | 11598.66
1. Project Support Total |  |  |  | 178138.47 | 65296.56 | 233249.92 | 188723.82 | -30908.74 | 131960.38 | 95350.6 | 122378.59 | 49858.87 | 80047.93 | 10799.52 | 88492.39 | 1213388.31
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 65.28 | [5 empty] | 65.28
|  | Material - Direct Purchase Total | [7 empty] | 65.28 | [5 empty] | 65.28
| Breakers - Circuit-DP Total | [8 empty] | 65.28 | [5 empty] | 65.28
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | GENERAL ELECTRIC COMPANY | [6 empty] | 11660 | [5 empty] | 11660
|  |  | Material Entries <$5,000 | 3703.97 | 4126.46 | 573.12 | [6 empty] | 1923.77 |  | 2747.54 | 13074.86
|  | Material - Direct Purchase Total |  | 3703.97 | 4126.46 | 573.12 |  |  |  | 11660 |  |  | 1923.77 |  | 2747.54 | 24734.86
| Building, Shop & Industrial Products/Eqp Total |  |  | 3703.97 | 4126.46 | 573.12 |  |  |  | 11660 |  |  | 1923.77 |  | 2747.54 | 24734.86
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 3248.85 |  | 772.58 |  | 53.33 |  |  |  | 4074.76
|  | Material - Direct Purchase Total | [5 empty] | 3248.85 |  | 772.58 |  | 53.33 |  |  |  | 4074.76
| Cabinets, Panels and Switchboards-DP Total | [6 empty] | 3248.85 |  | 772.58 |  | 53.33 |  |  |  | 4074.76
| Communication Systems and Equipment -DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 443.79 | 443.79
|  | Material - Direct Purchase Total | [12 empty] | 443.79 | 443.79
| Communication Systems and Equipment -DP Total | [13 empty] | 443.79 | 443.79
| Electric Wiring and Components-DP | Material - Direct Purchase | CROSS BROTHERS INC |  | 10800 | [10 empty] | 10800
|  |  | Electric Wiring and Components-DP | 53331.91 | 5736.53 | 13103.44 |  | 11578.07 | 9239.2 | [5 empty] | 5359.28 | 98348.43
|  |  | Material Entries <$5,000 | 4680 |  |  | 3068 |  |  | 2271.65 |  | 74.15 | 363.63 | 2268.85 | 350.04 | 13076.32
|  |  | SOUTHWIRE COMPANY |  |  |  |  | 19328 | [7 empty] | 19328
|  | Material - Direct Purchase Total |  | 58011.91 | 16536.53 | 13103.44 | 3068 | 30906.07 | 9239.2 | 2271.65 |  | 74.15 | 363.63 | 2268.85 | 5709.32 | 141552.75
| Electric Wiring and Components-DP Total |  |  | 58011.91 | 16536.53 | 13103.44 | 3068 | 30906.07 | 9239.2 | 2271.65 |  | 74.15 | 363.63 | 2268.85 | 5709.32 | 141552.75
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 | 389.69 | 154.84 | 291.6 | [7 empty] | 79.93 |  | 916.06
|  | Material - Direct Purchase Total |  | 389.69 | 154.84 | 291.6 | [7 empty] | 79.93 |  | 916.06
| Fuels, Chemicals & Petrochem-DP Total |  |  | 389.69 | 154.84 | 291.6 | [7 empty] | 79.93 |  | 916.06
| Insulators & Bushings-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 3467.48 | [10 empty] | 3467.48
|  | Material - Direct Purchase Total |  |  | 3467.48 | [10 empty] | 3467.48
| Insulators & Bushings-DP Total |  |  |  | 3467.48 | [10 empty] | 3467.48
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -76.81 | 76.81 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -76.81 | 76.81 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -76.81 | 76.81 |  |  | 0
| Material - Inventory | Material | Material - Inventory | -955.2 | -6801.37 | -356301.85 | -126841.53 | -9458.11 | -7586.71 | -85097.57 | -14527.82 | -2.3 | 2.3 |  |  | -607570.16
|  | Material Total |  | -955.2 | -6801.37 | -356301.85 | -126841.53 | -9458.11 | -7586.71 | -85097.57 | -14527.82 | -2.3 | 2.3 |  |  | -607570.16
| Material - Inventory Total |  |  | -955.2 | -6801.37 | -356301.85 | -126841.53 | -9458.11 | -7586.71 | -85097.57 | -14527.82 | -2.3 | 2.3 |  |  | -607570.16
| Material - Other | Material | Material - Other | 5160.78 | 12509.44 | -23058.37 | 9146.24 | 6523.03 | 933.02 | 3229.5 | -1160.44 | 198.37 | 247.04 | 533.4 | 1557.17 | 15819.18
|  | Material Total |  | 5160.78 | 12509.44 | -23058.37 | 9146.24 | 6523.03 | 933.02 | 3229.5 | -1160.44 | 198.37 | 247.04 | 533.4 | 1557.17 | 15819.18
| Material - Other Total |  |  | 5160.78 | 12509.44 | -23058.37 | 9146.24 | 6523.03 | 933.02 | 3229.5 | -1160.44 | 198.37 | 247.04 | 533.4 | 1557.17 | 15819.18
| Mechanical Systems and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | 2200 | [11 empty] | 2200
|  | Material - Direct Purchase Total |  | 2200 | [11 empty] | 2200
| Mechanical Systems and Components-DP Total |  |  | 2200 | [11 empty] | 2200
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | 1254.69 | 426.11 | [7 empty] | 25 | 312.4 |  | 2018.2
|  | Material - Direct Purchase Total |  | 1254.69 | 426.11 | [7 empty] | 25 | 312.4 |  | 2018.2
| Metals & Fabricated Metal Products-DP Total |  |  | 1254.69 | 426.11 | [7 empty] | 25 | 312.4 |  | 2018.2
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 667.7 | [6 empty] | 262.86 |  |  |  | 930.56
|  | Material - Direct Purchase Total |  |  | 667.7 | [6 empty] | 262.86 |  |  |  | 930.56
| Office & Office Support Products-DP Total |  |  |  | 667.7 | [6 empty] | 262.86 |  |  |  | 930.56
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | 1131.51 | 788.71 | 24.32 | [9 empty] | 1944.54
|  | Material - Direct Purchase Total |  | 1131.51 | 788.71 | 24.32 | [9 empty] | 1944.54
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  | 1131.51 | 788.71 | 24.32 | [9 empty] | 1944.54
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 421.92 | -906.02 | 87.84 |  | 127.6 |  |  | 404.54 |  |  | 135.88
|  |  | ONE SOURCE DISTRIBUTORS INC | 17540 | [11 empty] | 17540
|  |  | Pole Line Hdwe & Connectors-DP | 5908.73 | 14667.17 | [10 empty] | 20575.9
|  | Material - Direct Purchase Total |  | 23448.73 | 14667.17 | 421.92 | -906.02 | 87.84 |  | 127.6 |  |  | 404.54 |  |  | 38251.78
| Pole Line Hdwe & Connectors-DP Total |  |  | 23448.73 | 14667.17 | 421.92 | -906.02 | 87.84 |  | 127.6 |  |  | 404.54 |  |  | 38251.78
| Protection and Test-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 1669.86 | [9 empty] | 1669.86
|  | Material - Direct Purchase Total |  |  |  | 1669.86 | [9 empty] | 1669.86
| Protection and Test-DP Total |  |  |  |  | 1669.86 | [9 empty] | 1669.86
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 1168 | [9 empty] | 1168
|  | Material - Direct Purchase Total |  |  |  | 1168 | [9 empty] | 1168
| Steel / Fabricated / Structural-DP Total |  |  |  |  | 1168 | [9 empty] | 1168
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 2967.09 |  | 237.04 |  |  |  | 3204.13
|  | Material - Direct Purchase Total | [7 empty] | 2967.09 |  | 237.04 |  |  |  | 3204.13
| Transformers CT/PT/INSTR-DP Total | [8 empty] | 2967.09 |  | 237.04 |  |  |  | 3204.13
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 79.79 | 475.28 | 2779.73 | 634.49 |  | 88.14 |  | 142.26 |  |  | 5.95 |  | 4205.64
|  | Material - Direct Purchase Total |  | 79.79 | 475.28 | 2779.73 | 634.49 |  | 88.14 |  | 142.26 |  |  | 5.95 |  | 4205.64
| Transportation & Mobile Equip-DP Total |  |  | 79.79 | 475.28 | 2779.73 | 634.49 |  | 88.14 |  | 142.26 |  |  | 5.95 |  | 4205.64
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | 315.51 | 26.95 |  |  | 2899.8 | [7 empty] | 3242.26
|  | Material - Direct Purchase Total |  | 315.51 | 26.95 |  |  | 2899.8 | [7 empty] | 3242.26
| Wire, Cable & Bus Bar-DP Total |  |  | 315.51 | 26.95 |  |  | 2899.8 | [7 empty] | 3242.26
2. Material Total |  |  |  | 94741.38 | 47045.3 | -359328.23 | -114898.82 | 34207.48 | 2673.65 | -64003.87 | -15546 | 746.64 | 3043.09 | 3200.53 | 10457.82 | -357661.03
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 89371.52 | 207.61 | 70697.54 | 57245.87 | 65325.75 | 12364.04 | 7949.64 | 2080.4 |  | 5837.8 | 18740.7 | 19564.61 | 349385.48
|  | Contract Total |  | 89371.52 | 207.61 | 70697.54 | 57245.87 | 65325.75 | 12364.04 | 7949.64 | 2080.4 |  | 5837.8 | 18740.7 | 19564.61 | 349385.48
| Construction Management Services Total |  |  | 89371.52 | 207.61 | 70697.54 | 57245.87 | 65325.75 | 12364.04 | 7949.64 | 2080.4 |  | 5837.8 | 18740.7 | 19564.61 | 349385.48
| Construction Services - Other | Contract | Contract Entries <$50,000 | 2144.04 | 2839.68 | [8 empty] | 667.08 |  | 5650.8
|  | Contract Total |  | 2144.04 | 2839.68 | [8 empty] | 667.08 |  | 5650.8
| Construction Services - Other Total |  |  | 2144.04 | 2839.68 | [8 empty] | 667.08 |  | 5650.8
| Construction, Earthwork | Contract | Contract Entries <$50,000 | [11 empty] | -131181 | -131181
|  | Contract Total | [12 empty] | -131181 | -131181
| Construction, Earthwork Total | [13 empty] | -131181 | -131181
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 |  |  | 1878 | [5 empty] | 1646.5 | 1661 |  |  | 5185.5
|  | Contract Total |  |  |  | 1878 | [5 empty] | 1646.5 | 1661 |  |  | 5185.5
| Decontamination & Waste Disposal Service Total |  |  |  |  | 1878 | [5 empty] | 1646.5 | 1661 |  |  | 5185.5
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 1150.76 | 1150.76
|  | Labor Total | [12 empty] | 1150.76 | 1150.76
| ELEC SYS PLANNING Total | [13 empty] | 1150.76 | 1150.76
| Electrical Services | Contract | Contract Entries <$50,000 | 1000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500
|  | Contract Total |  | 1000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500
| Electrical Services Total |  |  | 1000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500
| ENGINEERING | Labor | Labor Entries <$5,000 | 1228.2 | 946.65 | 1482.65 | 1243.3 | 584.92 | 1259.26 | 1475.09 | 1306.03 | 1053.05 | 849.52 | 1302.93 |  | 12731.6
|  | Labor Total |  | 1228.2 | 946.65 | 1482.65 | 1243.3 | 584.92 | 1259.26 | 1475.09 | 1306.03 | 1053.05 | 849.52 | 1302.93 |  | 12731.6
| ENGINEERING Total |  |  | 1228.2 | 946.65 | 1482.65 | 1243.3 | 584.92 | 1259.26 | 1475.09 | 1306.03 | 1053.05 | 849.52 | 1302.93 |  | 12731.6
| GRID OPS | Labor | Labor Entries <$5,000 |  | 288.25 |  | 236.72 |  |  |  |  | 537.07 |  |  | 1525.67 | 2587.71
|  | Labor Total |  |  | 288.25 |  | 236.72 |  |  |  |  | 537.07 |  |  | 1525.67 | 2587.71
| GRID OPS Total |  |  |  | 288.25 |  | 236.72 |  |  |  |  | 537.07 |  |  | 1525.67 | 2587.71
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | [5 empty] | 34.26 | [6 empty] | 34.26
|  | Contract Total | [6 empty] | 34.26 | [6 empty] | 34.26
| Hauling / Industrial Moving Services Total | [7 empty] | 34.26 | [6 empty] | 34.26
| Major Construction, Turnkey, Trans/Subs | Contract | CONTRA COSTA ELECTRIC INC |  | 627776 | [10 empty] | 627776
|  |  | Contract Entries <$50,000 | 27036 | 1735 | 25803 | 25446 | 33351 | 8294.3 | 14201.89 |  | 9716.89 |  | 10469.47 | -374683.81 | -218630.26
|  |  | KINDNESS GENERAL CONTRACTORS INC | 139555.5 | 294183.34 | 68298.15 | 72389.03 |  | 87267.2 | [6 empty] | 661693.22
|  |  | PROFESSIONAL ELECTRICAL CONSTRUCTIO |  | 1054155.14 |  | 756795.86 | [8 empty] | 1810951
|  | Contract Total |  | 166591.5 | 1977849.48 | 94101.15 | 854630.89 | 33351 | 95561.5 | 14201.89 |  | 9716.89 |  | 10469.47 | -374683.81 | 2881789.96
| Major Construction, Turnkey, Trans/Subs Total |  |  | 166591.5 | 1977849.48 | 94101.15 | 854630.89 | 33351 | 95561.5 | 14201.89 |  | 9716.89 |  | 10469.47 | -374683.81 | 2881789.96
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | 25611.25 | 50209.3 | 21113.74 | 13856.03 | 23224.37 | 30461.53 | 16928.41 | 19138.83 | 22183.93 | 23043.43 | 36082.02 |  | 281852.84
|  |  | Sub Stn Elect | 18638.84 | [11 empty] | 18638.84
|  |  | Technician Test | 11993.32 | 5351.14 | 5423.75 | [5 empty] | 6248.16 | 5488.84 |  |  | 34505.21
|  |  | Tst Spr Tech | [5 empty] | 11532.42 |  | 5547.24 | 7007.04 | 13795.11 | 8174.88 |  | 46056.69
|  | Labor Total |  | 56243.41 | 55560.44 | 26537.49 | 13856.03 | 23224.37 | 41993.95 | 16928.41 | 24686.07 | 35439.13 | 42327.38 | 44256.9 |  | 381053.58
| N/W SUBSMTCETEST&APP Total |  |  | 56243.41 | 55560.44 | 26537.49 | 13856.03 | 23224.37 | 41993.95 | 16928.41 | 24686.07 | 35439.13 | 42327.38 | 44256.9 |  | 381053.58
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [9 empty] | 513.47 | 156.91 |  | 670.38
|  | Labor Total | [10 empty] | 513.47 | 156.91 |  | 670.38
| NORTH GRIDMGMTCENTER Total | [11 empty] | 513.47 | 156.91 |  | 670.38
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [9 empty] | 148.95 | 999.79 |  | 1148.74
|  | Labor Total | [10 empty] | 148.95 | 999.79 |  | 1148.74
| S/E SUBS MTCETST&APP Total | [11 empty] | 148.95 | 999.79 |  | 1148.74
| SC&M | Labor | Labor Entries <$5,000 | 10089.14 | 23132.55 | 29762.15 | 4974.43 | 11582.99 | 11447.58 | 12122.02 | 7927.08 | 12859.76 | 21101.8 | 19308.1 | 62469.19 | 226776.79
|  |  | SC&M / Electn Constrn | 5103.76 | 5429.61 |  | 10692 | 5467.5 | 5184 |  |  | 5204.25 |  | 10398.5 | 5295.49 | 52775.11
|  |  | SC&M / Frm Wrk Elct Cnst | 5620.64 | [6 empty] | 16110.74 | 12967.13 | 15311.61 | 18939.79 | 14198.26 | 83148.17
|  |  | SC&M / Tst Spr Tech | [11 empty] | 11143.22 | 11143.22
|  | Labor Total |  | 20813.54 | 28562.16 | 29762.15 | 15666.43 | 17050.49 | 16631.58 | 12122.02 | 24037.82 | 31031.14 | 36413.41 | 48646.39 | 93106.16 | 373843.29
| SC&M Total |  |  | 20813.54 | 28562.16 | 29762.15 | 15666.43 | 17050.49 | 16631.58 | 12122.02 | 24037.82 | 31031.14 | 36413.41 | 48646.39 | 93106.16 | 373843.29
| Security / Protection Services | Contract | ASHLAND INTEGRATED INC | [7 empty] | 73562.98 |  |  |  |  | 73562.98
|  |  | Contract Entries <$50,000 | 17414.91 | 26321.11 | 13959.65 | 566.25 |  | 13125 | -17600 |  |  |  |  | 4112.5 | 57899.42
|  | Contract Total |  | 17414.91 | 26321.11 | 13959.65 | 566.25 |  | 13125 | -17600 | 73562.98 |  |  |  | 4112.5 | 131462.4
| Security / Protection Services Total |  |  | 17414.91 | 26321.11 | 13959.65 | 566.25 |  | 13125 | -17600 | 73562.98 |  |  |  | 4112.5 | 131462.4
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 20935.91 | 16379.18 | 13904.81 | 8374.43 | 25636.2 | 17127.55 | 16468.84 | 4451.1 | 20208.49 | 5349.44 | 38393.46 | 21848.54 | 209077.95
|  | Contract Total |  | 20935.91 | 16379.18 | 13904.81 | 8374.43 | 25636.2 | 17127.55 | 16468.84 | 4451.1 | 20208.49 | 5349.44 | 38393.46 | 21848.54 | 209077.95
| Short Term Equipment Rent Total |  |  | 20935.91 | 16379.18 | 13904.81 | 8374.43 | 25636.2 | 17127.55 | 16468.84 | 4451.1 | 20208.49 | 5349.44 | 38393.46 | 21848.54 | 209077.95
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 |  |  |  | 328 | 410 | 328 | 328 | 164 | 164 | 164 | 82 | 164 | 2132
|  | Labor Total |  |  |  |  | 328 | 410 | 328 | 328 | 164 | 164 | 164 | 82 | 164 | 2132
| TSD-HERC - Rental Total | [5 empty] | 328 | 410 | 328 | 328 | 164 | 164 | 164 | 82 | 164 | 2132
3. Construction Total |  |  |  | 375743.03 | 2109454.56 | 252823.44 | 952647.92 | 166082.73 | 198925.14 | 52373.89 | 130788.4 | 100296.27 | 93764.97 | 164215.63 | -363892.57 | 4233223.41
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -7529.11 | 14816.5 | -73986.05 | -13779.91 | 16525.7 | 13125.53 | 790.05 | 9933.99 | 15405.46 | 17030.82 | 12887.51 | 30351.97 | 35572.46
|  |  | PROCUREMENT TDBU |  | 13825.23 |  | 6564.67 | [8 empty] | 20389.9
|  |  | TDBU Vehicle Cost | 10962.8 | 9519.13 | 7247.13 |  | 5244.81 | 7733.07 | 5527.54 | 5356.01 | 6367.3 | 11294.37 | 11176.07 | 10733.97 | 91162.2
|  |  | TRTP 9 Vincent Extend 500 kV switchcrack | 27607.76 | 25177.81 | 36192.23 | 22951.82 | 18723.26 | 23828.07 | 18107.02 | 16354.92 |  | 35026.81 | 19498.15 | 12470.57 | 255938.42
|  |  | Work Package #4 | 13261.04 | 10797.19 | 23397.77 | 20928.69 | 35062.23 | 47703.19 | 44922.47 | 38609.35 | 43763.96 | 52402.4 | 54068.5 | 92471.83 | 477388.62
|  | Chargeback Total |  | 44302.49 | 74135.86 | -7148.92 | 36665.27 | 75556 | 92389.86 | 69347.08 | 70254.27 | 65536.72 | 115754.4 | 97630.23 | 146028.34 | 880451.6
| Chargebacks Total |  |  | 44302.49 | 74135.86 | -7148.92 | 36665.27 | 75556 | 92389.86 | 69347.08 | 70254.27 | 65536.72 | 115754.4 | 97630.23 | 146028.34 | 880451.6
| Labor - Other | Labor | Division Overhead | 52261.03 | 197981.69 |  | 61475.13 | 5414.87 |  |  |  |  | 15577.27 |  |  | 332709.99
|  |  | Labor Entries <$5,000 | 17276.68 | 18556.23 | 6695.52 | 13742.59 | 18555.91 | 22591.68 | 7584.97 | 17881.05 | 1539.11 | 29322.34 | 13540.91 | -2010.13 | 165276.86
|  |  | OH Tool Expenses | 7238.77 | [10 empty] | 9069.66 | 16308.43
|  |  | Paid Absence | 15672.33 | 15717.84 | 13070.48 | 7769.03 | 9240.42 | 9242.29 | 6035.25 | 9883.81 | 5897.85 | 17160.64 | 13551.66 | 18687.3 | 141928.9
|  | Labor Total |  | 92448.81 | 232255.76 | 19766 | 82986.75 | 33211.2 | 31833.97 | 13620.22 | 27764.86 | 7436.96 | 62060.25 | 27092.57 | 25746.83 | 656224.18
| Labor - Other Total |  |  | 92448.81 | 232255.76 | 19766 | 82986.75 | 33211.2 | 31833.97 | 13620.22 | 27764.86 | 7436.96 | 62060.25 | 27092.57 | 25746.83 | 656224.18
| Overhead Correction | Overhead | Overhead Correction |  |  |  | -199.71 |  |  |  |  | -5135.68 | 5135.68 |  |  | -199.71
|  | Overhead Total |  |  |  |  | -199.71 |  |  |  |  | -5135.68 | 5135.68 |  |  | -199.71
| Overhead Correction Total | [5 empty] | -199.71 |  |  |  |  | -5135.68 | 5135.68 |  |  | -199.71
4. Allocated Total |  |  |  | 136751.3 | 306391.62 | 12617.08 | 119452.31 | 108767.2 | 124223.83 | 82967.3 | 98019.13 | 67838 | 182950.33 | 124722.8 | 171775.17 | 1536476.07
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 404451.93 | 24206.41 | [6 empty] | 399216.17 | 827874.51
|  |  | AFUDC - Debt/Equity |  |  | 421030.67 | -421030.67 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 45901.6 | 75013.3 | 4392.31 | 38452.12 | 31018.83 | -2197205.36 | 8576.24 | 9234.72 | 10241.39 | 9256.05 | 8084.61 | -2639.95 | -1959674.14
|  |  | Capitalized Overhead - Inj & Damages | 391.67 | 812.46 | -151.99 | 29.58 | 1819.52 | 113311.55 | 147.21 | 259.3 | 346.63 | 47.17 | 399.27 | 340.14 | 117752.51
|  |  | Capitalized Overhead - P&B/Payroll Tax | 81067.68 | 145073.32 | 96477.85 | 78196.84 | 120623.46 | -2736092.12 | 86215.23 | 79190.29 | 105036.41 | 73495.25 | 115501.5 | 340252.29 | -1414962
|  |  | Corporate Overheads Correction |  |  |  |  | -1083440.99 | [7 empty] | -1083440.99
|  | Non Budgeted Total |  | 127360.95 | 220899.08 | 521748.84 | 100099.8 | -905772.77 | -4819985.93 | 94938.68 | 88684.31 | 115624.43 | 82798.47 | 123985.38 | 737168.65 | -3512450.11
| Non Budget - Other Total |  |  | 127360.95 | 220899.08 | 521748.84 | 100099.8 | -905772.77 | -4819985.93 | 94938.68 | 88684.31 | 115624.43 | 82798.47 | 123985.38 | 737168.65 | -3512450.11
5. Corporate Overhead Total |  |  |  | 127360.95 | 220899.08 | 521748.84 | 100099.8 | -905772.77 | -4819985.93 | 94938.68 | 88684.31 | 115624.43 | 82798.47 | 123985.38 | 737168.65 | -3512450.11
Grand Total |  |  |  | 912735.13 | 2749087.12 | 661111.05 | 1246025.03 | -627624.1 | -4362202.93 | 261626.6 | 424324.43 | 334364.21 | 442604.79 | 426923.86 | 644001.46 | 3112976.65

## 800216848
Pin: 6440 | Project: TRTP Segment 9
Order: 800216848 | 800216848- I: TRTP 9: ANTELOPE: UPGRADE 500 KV POSI
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  |  | 10.92 | 90.35 | [6 empty] | 101.27
|  | Labor Total | [5 empty] | 10.92 | 90.35 | [6 empty] | 101.27
| BP&FM Total | [6 empty] | 10.92 | 90.35 | [6 empty] | 101.27
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  |  | 11826 |  |  | 1468.76 |  |  |  | 432.32 | 13727.08
|  | Contract Total | [5 empty] | 11826 |  |  | 1468.76 |  |  |  | 432.32 | 13727.08
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [6 empty] | 11826 |  |  | 1468.76 |  |  |  | 432.32 | 13727.08
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -6861.02 | 6861.02 |  |  | 0
|  | Contract Total | [9 empty] | -6861.02 | 6861.02 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -6861.02 | 6861.02 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | [8 empty] | 971.81 |  |  |  | 971.81
|  | Contract Total | [9 empty] | 971.81 |  |  |  | 971.81
| Contract Consult/Contract Ord to Ord Total | [10 empty] | 971.81 |  |  |  | 971.81
| Corporate Security | Labor | Labor Entries <$5,000 | [7 empty] | 1640.39 |  |  |  |  | 1640.39
|  | Labor Total | [8 empty] | 1640.39 |  |  |  |  | 1640.39
| Corporate Security Total | [9 empty] | 1640.39 |  |  |  |  | 1640.39
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 630.58 | 630.58
|  | Labor Total | [12 empty] | 630.58 | 630.58
| ELEC SYS PLANNING Total | [13 empty] | 630.58 | 630.58
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 428.58 | [5 empty] | 322.13 | [5 empty] | 750.71
|  | Labor Total |  | 428.58 | [5 empty] | 322.13 | [5 empty] | 750.71
| ENG ADVANCEMENT Total |  |  | 428.58 | [5 empty] | 322.13 | [5 empty] | 750.71
| ENGINEERING | Labor | Labor Entries <$5,000 | 6776.68 | 5051.44 | 4970.76 | 2782.87 | 3596.41 | 2820.23 | 1532.09 | 1619.61 | 910.66 | 1741.54 | 562.69 |  | 32364.98
|  | Labor Total |  | 6776.68 | 5051.44 | 4970.76 | 2782.87 | 3596.41 | 2820.23 | 1532.09 | 1619.61 | 910.66 | 1741.54 | 562.69 |  | 32364.98
| ENGINEERING Total |  |  | 6776.68 | 5051.44 | 4970.76 | 2782.87 | 3596.41 | 2820.23 | 1532.09 | 1619.61 | 910.66 | 1741.54 | 562.69 |  | 32364.98
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 47518.04 | 14140.71 | 10157 | 35829.22 | 13359 |  | 25127.31 | 6116 | 1758.53 |  | -13098 | 1999.44 | 142907.25
|  | Contract Total |  | 47518.04 | 14140.71 | 10157 | 35829.22 | 13359 |  | 25127.31 | 6116 | 1758.53 |  | -13098 | 1999.44 | 142907.25
| Engineering/Technical Professional Servi Total |  |  | 47518.04 | 14140.71 | 10157 | 35829.22 | 13359 |  | 25127.31 | 6116 | 1758.53 |  | -13098 | 1999.44 | 142907.25
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 812.63 | 80.75 | -1674.7 | 315.39 | -605.58 | -785.29 | 27.65 | 175.07 | 14427.88 | -13417.66 | -84.44 | -555.95 | -1284.25
|  | IMM Correction Total |  | 812.63 | 80.75 | -1674.7 | 315.39 | -605.58 | -785.29 | 27.65 | 175.07 | 14427.88 | -13417.66 | -84.44 | -555.95 | -1284.25
| IMM/Allocated - Correction Total |  |  | 812.63 | 80.75 | -1674.7 | 315.39 | -605.58 | -785.29 | 27.65 | 175.07 | 14427.88 | -13417.66 | -84.44 | -555.95 | -1284.25
| Labor - Other | Labor | Labor Correction | [9 empty] | 5350.62 |  |  | 5350.62
|  |  | Labor Entries <$5,000 | -217.45 | 837.4 | -451.24 | -53.24 | 532.6 | -681.95 | -178.48 | 1150.85 | -4578.29 | 1469.1 | -414.96 | 177.12 | -2408.54
|  | Labor Total |  | -217.45 | 837.4 | -451.24 | -53.24 | 532.6 | -681.95 | -178.48 | 1150.85 | -4578.29 | 6819.72 | -414.96 | 177.12 | 2942.08
| Labor - Other Total |  |  | -217.45 | 837.4 | -451.24 | -53.24 | 532.6 | -681.95 | -178.48 | 1150.85 | -4578.29 | 6819.72 | -414.96 | 177.12 | 2942.08
| Other | Other | Other | 8369.3 | 35522.78 | -50921.48 | 13026.05 | 48483.64 | -7477.83 | -54714.46 | -4912.03 | 5311.51 | -4455.58 | 8046.24 | -2958.35 | -6680.21
|  | Other Total |  | 8369.3 | 35522.78 | -50921.48 | 13026.05 | 48483.64 | -7477.83 | -54714.46 | -4912.03 | 5311.51 | -4455.58 | 8046.24 | -2958.35 | -6680.21
| Other Total |  |  | 8369.3 | 35522.78 | -50921.48 | 13026.05 | 48483.64 | -7477.83 | -54714.46 | -4912.03 | 5311.51 | -4455.58 | 8046.24 | -2958.35 | -6680.21
| PLGHCC | Labor | Labor Entries <$5,000 | [10 empty] | 15.85 |  | 15.85
|  | Labor Total | [11 empty] | 15.85 |  | 15.85
| PLGHCC Total | [12 empty] | 15.85 |  | 15.85
| SC&M | Labor | Labor Entries <$5,000 | 342.57 |  |  | 207.65 |  | 392.78 | [5 empty] | 345.14 | 1288.14
|  | Labor Total |  | 342.57 |  |  | 207.65 |  | 392.78 | [5 empty] | 345.14 | 1288.14
| SC&M Total |  |  | 342.57 |  |  | 207.65 |  | 392.78 | [5 empty] | 345.14 | 1288.14
| Software License Via Electronic Delivery | Contract | Contract Entries <$50,000 | [11 empty] | 7810.6 | 7810.6
|  | Contract Total | [12 empty] | 7810.6 | 7810.6
| Software License Via Electronic Delivery Total | [13 empty] | 7810.6 | 7810.6
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -3115.16 | 3115.16 |  |  | 0
|  | Contract Total | [9 empty] | -3115.16 | 3115.16 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -3115.16 | 3115.16 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1911.68 | 2462.4 | 425.92 |  |  | 146.08 | [6 empty] | 4946.08
|  | Contract Total |  | 1911.68 | 2462.4 | 425.92 |  |  | 146.08 | [6 empty] | 4946.08
| Temporary/Supplementary - Trade/Labor Total |  |  | 1911.68 | 2462.4 | 425.92 |  |  | 146.08 | [6 empty] | 4946.08
1. Project Support Total |  |  |  | 65942.03 | 58095.48 | -37493.74 | 52107.94 | 77202.99 | -5495.63 | -27883.76 | 7258.65 | 8825.92 | 664.2 | -4972.62 | 7880.9 | 202132.36
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | MITSUBISHI ELECTRIC |  |  | 35656.26 | [9 empty] | 35656.26
|  | Material - Direct Purchase Total |  |  |  | 35656.26 | [9 empty] | 35656.26
| Breakers - Circuit-DP Total |  |  |  |  | 35656.26 | [9 empty] | 35656.26
| Communication Systems and Equipment -DP | Material - Direct Purchase | Communication Systems and Equipment -DP | [11 empty] | 21483 | 21483
|  | Material - Direct Purchase Total | [12 empty] | 21483 | 21483
| Communication Systems and Equipment -DP Total | [13 empty] | 21483 | 21483
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 |  |  | 25.12 | [5 empty] | -18.42 | 18.42 |  |  | 25.12
|  | Material - Direct Purchase Total |  |  |  | 25.12 | [5 empty] | -18.42 | 18.42 |  |  | 25.12
| Material - Direct Purchase - Correction Total |  |  |  |  | 25.12 | [5 empty] | -18.42 | 18.42 |  |  | 25.12
| Material - Inventory | Material | Material - Inventory | [8 empty] | -0.8 | 0.8 |  |  | 0
|  | Material Total | [9 empty] | -0.8 | 0.8 |  |  | 0
| Material - Inventory Total | [10 empty] | -0.8 | 0.8 |  |  | 0
| Material - Other | Material | Material - Other | -0.02 | 60.12 | 6299.91 |  | 0.01 | 3469.76 | -309.09 | -280.04 | -1.64 | 1.64 | 0.03 | 26.2 | 9266.88
|  | Material Total |  | -0.02 | 60.12 | 6299.91 |  | 0.01 | 3469.76 | -309.09 | -280.04 | -1.64 | 1.64 | 0.03 | 26.2 | 9266.88
| Material - Other Total |  |  | -0.02 | 60.12 | 6299.91 |  | 0.01 | 3469.76 | -309.09 | -280.04 | -1.64 | 1.64 | 0.03 | 26.2 | 9266.88
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | ABCO GATE SYSTEMS |  | 35995.81 |  |  |  | 39146.73 | [6 empty] | 75142.54
|  |  | Material Entries <$5,000 |  |  | -3197.81 |  |  |  | -3477.73 | [5 empty] | -6675.54
|  | Material - Direct Purchase Total |  |  | 35995.81 | -3197.81 |  |  | 39146.73 | -3477.73 | [5 empty] | 68467
| Metals & Fabricated Metal Products-DP Total |  |  |  | 35995.81 | -3197.81 |  |  | 39146.73 | -3477.73 | [5 empty] | 68467
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | -21.9 | [11 empty] | -21.9
|  | Material - Direct Purchase Total |  | -21.9 | [11 empty] | -21.9
| Office & Office Support Products-DP Total |  |  | -21.9 | [11 empty] | -21.9
2. Material Total |  |  |  | -21.92 | 36055.93 | 38783.48 |  | 0.01 | 42616.49 | -3786.82 | -280.04 | -20.86 | 20.86 | 0.03 | 21509.2 | 134876.36
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 16500 |  | 18110.5 | 23458 | 25425 | 15671 | 34695 | 1837.5 | 3465 |  | 91110.75 | 9377.5 | 239650.25
|  | Contract Total |  | 16500 |  | 18110.5 | 23458 | 25425 | 15671 | 34695 | 1837.5 | 3465 |  | 91110.75 | 9377.5 | 239650.25
| Construction Management Services Total |  |  | 16500 |  | 18110.5 | 23458 | 25425 | 15671 | 34695 | 1837.5 | 3465 |  | 91110.75 | 9377.5 | 239650.25
| Construction Services - Other | Contract | Contract Entries <$50,000 | 568.5 |  | 1137 | 568.5 | 1023.3 | [7 empty] | 3297.3
|  | Contract Total |  | 568.5 |  | 1137 | 568.5 | 1023.3 | [7 empty] | 3297.3
| Construction Services - Other Total |  |  | 568.5 |  | 1137 | 568.5 | 1023.3 | [7 empty] | 3297.3
| Construction, Property/Building | Contract | ELDRIDGE ELECTRIC & SONS INC. | [11 empty] | 181290.67 | 181290.67
|  | Contract Total | [12 empty] | 181290.67 | 181290.67
| Construction, Property/Building Total | [13 empty] | 181290.67 | 181290.67
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 1479.55 | 1479.55
|  | Labor Total | [12 empty] | 1479.55 | 1479.55
| ELEC SYS PLANNING Total | [13 empty] | 1479.55 | 1479.55
| Electrical Construction, Substations | Contract | Contract Entries <$50,000 |  | 17740.46 | [10 empty] | 17740.46
|  |  | Electrical Construction, Substations |  | 218366.83 | [10 empty] | 218366.83
|  |  | NRG POWER INC |  | 54202.14 | [10 empty] | 54202.14
|  | Contract Total |  |  | 290309.43 | [10 empty] | 290309.43
| Electrical Construction, Substations Total |  |  |  | 290309.43 | [10 empty] | 290309.43
| Electrical Services | Contract | Contract Entries <$50,000 |  |  | 4700 |  |  | 11000 | [5 empty] | 5653.99 | 21353.99
|  | Contract Total |  |  |  | 4700 |  |  | 11000 | [5 empty] | 5653.99 | 21353.99
| Electrical Services Total |  |  |  |  | 4700 |  |  | 11000 | [5 empty] | 5653.99 | 21353.99
| ENGINEERING | Labor | Labor Entries <$5,000 | 508.22 | 507.13 | 936.41 | 691.44 | 701.91 | 731.19 | 655.6 | 897.89 | 648.03 | 485.44 | 936.48 |  | 7699.74
|  | Labor Total |  | 508.22 | 507.13 | 936.41 | 691.44 | 701.91 | 731.19 | 655.6 | 897.89 | 648.03 | 485.44 | 936.48 |  | 7699.74
| ENGINEERING Total |  |  | 508.22 | 507.13 | 936.41 | 691.44 | 701.91 | 731.19 | 655.6 | 897.89 | 648.03 | 485.44 | 936.48 |  | 7699.74
| GRID OPS | Labor | Labor Entries <$5,000 |  | 1152.99 | 827.37 | 2468.67 |  | 298.51 |  |  |  | 543.15 |  | 1061.61 | 6352.3
|  | Labor Total |  |  | 1152.99 | 827.37 | 2468.67 |  | 298.51 |  |  |  | 543.15 |  | 1061.61 | 6352.3
| GRID OPS Total |  |  |  | 1152.99 | 827.37 | 2468.67 |  | 298.51 |  |  |  | 543.15 |  | 1061.61 | 6352.3
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | 27973.59 | 33960.19 | 8325.43 | 14526.93 |  | 22871.56 | 2871.48 |  | 1992.92 |  | 3247.02 | 4472.07 | 120241.19
|  |  | MISSION PAVING AND SEALING INC |  |  |  | 140498.38 | 198763.13 | [7 empty] | 339261.51
|  | Contract Total |  | 27973.59 | 33960.19 | 8325.43 | 155025.31 | 198763.13 | 22871.56 | 2871.48 |  | 1992.92 |  | 3247.02 | 4472.07 | 459502.7
| Major Construction, Turnkey, Trans/Subs Total |  |  | 27973.59 | 33960.19 | 8325.43 | 155025.31 | 198763.13 | 22871.56 | 2871.48 |  | 1992.92 |  | 3247.02 | 4472.07 | 459502.7
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | [5 empty] | 343.61 | 345.18 |  | 476.24 | 1484.91 |  | 187.88 | 2837.82
|  | Labor Total | [6 empty] | 343.61 | 345.18 |  | 476.24 | 1484.91 |  | 187.88 | 2837.82
| N/W SUBSMTCETEST&APP Total | [7 empty] | 343.61 | 345.18 |  | 476.24 | 1484.91 |  | 187.88 | 2837.82
| SC&M | Labor | Labor Entries <$5,000 | [5 empty] | 81.98 |  |  |  |  | 269.85 | 3209.19 | 3561.02
|  | Labor Total | [6 empty] | 81.98 |  |  |  |  | 269.85 | 3209.19 | 3561.02
| SC&M Total | [7 empty] | 81.98 |  |  |  |  | 269.85 | 3209.19 | 3561.02
| Security / Protection Services | Contract | Contract Entries <$50,000 | [5 empty] | 2275 |  |  |  | 2800 | 2975 | 43175 | 51225
|  | Contract Total | [6 empty] | 2275 |  |  |  | 2800 | 2975 | 43175 | 51225
| Security / Protection Services Total | [7 empty] | 2275 |  |  |  | 2800 | 2975 | 43175 | 51225
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 2616.78 |  | 5403.8 | 2661.78 | 1738.01 | 1738.01 |  |  |  | 0 | 1681.94 | 2513.04 | 18353.36
|  | Contract Total |  | 2616.78 |  | 5403.8 | 2661.78 | 1738.01 | 1738.01 |  |  |  | 0 | 1681.94 | 2513.04 | 18353.36
| Short Term Equipment Rent Total |  |  | 2616.78 |  | 5403.8 | 2661.78 | 1738.01 | 1738.01 |  |  |  | 0 | 1681.94 | 2513.04 | 18353.36
3. Construction Total |  |  |  | 48167.09 | 325929.74 | 39440.51 | 184873.7 | 227651.35 | 55010.86 | 38567.26 | 2735.39 | 6582.19 | 5313.5 | 100221.04 | 252420.5 | 1286913.13
4. Allocated | Chargebacks | Chargeback | Antelope Sub û IDS | [11 empty] | 809889.75 | 809889.75
|  |  | Chargeback Entries <$5,000 | 1944.2 | 13830.79 | 10446.34 | 16536.8 | 14159.39 | 8340.7 | 4140.8 | 1097.61 | 720.89 | 4578.49 | 4968.05 | 9064.65 | 89828.71
|  |  | Work Package #4 | 5763.45 |  | 5879.86 |  |  | 7779.32 | [6 empty] | 19422.63
|  | Chargeback Total |  | 7707.65 | 13830.79 | 16326.2 | 16536.8 | 14159.39 | 16120.02 | 4140.8 | 1097.61 | 720.89 | 4578.49 | 4968.05 | 818954.4 | 919141.09
| Chargebacks Total |  |  | 7707.65 | 13830.79 | 16326.2 | 16536.8 | 14159.39 | 16120.02 | 4140.8 | 1097.61 | 720.89 | 4578.49 | 4968.05 | 818954.4 | 919141.09
| Labor - Other | Labor | Division Overhead |  | 24585.25 |  | 6961.37 | 6635.21 | [6 empty] | 5083.29 | 43265.12
|  |  | Labor Entries <$5,000 | 13298.46 | 12413.69 | 8222.37 | 11334.37 | 11572.02 | 7396.48 | 5483.77 | 2035.97 | -1189.1 | 4229.1 | 2509.66 | 7111.51 | 84418.3
|  | Labor Total |  | 13298.46 | 36998.94 | 8222.37 | 18295.74 | 18207.23 | 7396.48 | 5483.77 | 2035.97 | -1189.1 | 4229.1 | 2509.66 | 12194.8 | 127683.42
| Labor - Other Total |  |  | 13298.46 | 36998.94 | 8222.37 | 18295.74 | 18207.23 | 7396.48 | 5483.77 | 2035.97 | -1189.1 | 4229.1 | 2509.66 | 12194.8 | 127683.42
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -447.61 | 447.61 |  |  | 0
|  | Overhead Total | [9 empty] | -447.61 | 447.61 |  |  | 0
| Overhead Correction Total | [10 empty] | -447.61 | 447.61 |  |  | 0
4. Allocated Total |  |  |  | 21006.11 | 50829.73 | 24548.57 | 34832.54 | 32366.62 | 23516.5 | 9624.57 | 3133.58 | -915.82 | 9255.2 | 7477.71 | 831149.2 | 1046824.51
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G | 7792.59 | 12761.24 | 4214.36 | 9228.54 | 24039.59 | 4394.4 | 2657.67 | 556.01 | 582.5 | 456.66 | 2523.56 | 31353.71 | 100560.83
|  |  | Capitalized Overhead - Inj & Damages | 34.89 | 159.69 | 70.82 | 30.95 | 290.38 | 79.68 | 10.05 | 12.35 | 13.4 | 12.6 | 17.25 | 66.86 | 798.92
|  |  | Capitalized Overhead - P&B/Payroll Tax | 10143.71 | 15187.44 | 12242.19 | 14890.83 | 15277.65 | 10581.1 | 4069.63 | 4639.41 | -3859.27 | 6613.23 | 3492.68 | 22953.4 | 116232
|  |  | Corporate Overheads Correction |  |  |  |  | -466522.58 | [7 empty] | -466522.58
|  | Non Budgeted Total |  | 17971.19 | 28108.37 | 16527.37 | 24150.32 | -426914.96 | 15055.18 | 6737.35 | 5207.77 | -3263.37 | 7082.49 | 6033.49 | 54373.97 | -248930.83
| Non Budget - Other Total |  |  | 17971.19 | 28108.37 | 16527.37 | 24150.32 | -426914.96 | 15055.18 | 6737.35 | 5207.77 | -3263.37 | 7082.49 | 6033.49 | 54373.97 | -248930.83
5. Corporate Overhead Total |  |  |  | 17971.19 | 28108.37 | 16527.37 | 24150.32 | -426914.96 | 15055.18 | 6737.35 | 5207.77 | -3263.37 | 7082.49 | 6033.49 | 54373.97 | -248930.83
Grand Total |  |  |  | 153064.5 | 499019.25 | 81806.19 | 295964.5 | -89693.99 | 130703.4 | 23258.6 | 18055.35 | 11208.06 | 22336.25 | 108759.65 | 1167333.77 | 2421815.53

## 800216839
Pin: 6440 | Project: TRTP Segment 9
Order: 800216839 | 800216839- I: TRTP 9: WHIRLWIND: CONSTRUCT NEW 500K
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  |  | 10.92 | 326.44 | [6 empty] | 337.36
|  | Labor Total | [5 empty] | 10.92 | 326.44 | [6 empty] | 337.36
| BP&FM Total | [6 empty] | 10.92 | 326.44 | [6 empty] | 337.36
| BSVHCC | Labor | Labor Entries <$5,000 | [8 empty] | 207.47 |  |  |  | 207.47
|  | Labor Total | [9 empty] | 207.47 |  |  |  | 207.47
| BSVHCC Total | [10 empty] | 207.47 |  |  |  | 207.47
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  | 1000 | 1708 | [8 empty] | 2708
|  | Contract Total |  |  |  | 1000 | 1708 | [8 empty] | 2708
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  |  | 1000 | 1708 | [8 empty] | 2708
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 176937.48 |  |  | 176937.48
|  |  | Contract Entries <$50,000 | [8 empty] | -176937.48 |  |  |  | -176937.48
|  | Contract Total | [9 empty] | -176937.48 | 176937.48 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -176937.48 | 176937.48 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  | 495 | [6 empty] | 991.23 |  |  |  | 1486.23
|  | Contract Total |  |  | 495 | [6 empty] | 991.23 |  |  |  | 1486.23
| Contract Consult/Contract Ord to Ord Total |  |  |  | 495 | [6 empty] | 991.23 |  |  |  | 1486.23
| CORP COMM SVP | Labor | Labor Entries <$5,000 | 63.37 | 90.85 | 77.21 | 124.52 | [8 empty] | 355.95
|  | Labor Total |  | 63.37 | 90.85 | 77.21 | 124.52 | [8 empty] | 355.95
| CORP COMM SVP Total |  |  | 63.37 | 90.85 | 77.21 | 124.52 | [8 empty] | 355.95
| Corporate Security | Labor | Labor Entries <$5,000 | [7 empty] | 680.39 |  |  |  |  | 680.39
|  | Labor Total | [8 empty] | 680.39 |  |  |  |  | 680.39
| Corporate Security Total | [9 empty] | 680.39 |  |  |  |  | 680.39
| Data Collection Services | Contract | Contract Entries <$50,000 | [5 empty] | -47.04 | [6 empty] | -47.04
|  | Contract Total | [6 empty] | -47.04 | [6 empty] | -47.04
| Data Collection Services Total | [7 empty] | -47.04 | [6 empty] | -47.04
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 2366.18 | 2366.18
|  | Labor Total | [12 empty] | 2366.18 | 2366.18
| ELEC SYS PLANNING Total | [13 empty] | 2366.18 | 2366.18
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 680.69 |  |  |  |  | 623.72 | 60.4 |  |  |  |  | 497.18 | 1861.99
|  | Labor Total |  | 680.69 |  |  |  |  | 623.72 | 60.4 |  |  |  |  | 497.18 | 1861.99
| ENG ADVANCEMENT Total |  |  | 680.69 |  |  |  |  | 623.72 | 60.4 |  |  |  |  | 497.18 | 1861.99
| ENGINEERING | Labor | Labor Entries <$5,000 | 10672.45 | 8824.03 | 7053.53 | 5581.71 | 6685.04 | 13188.83 | 5507.28 | 3910.49 | 4218.47 | 4397.47 | 3724.49 |  | 73763.79
|  | Labor Total |  | 10672.45 | 8824.03 | 7053.53 | 5581.71 | 6685.04 | 13188.83 | 5507.28 | 3910.49 | 4218.47 | 4397.47 | 3724.49 |  | 73763.79
| ENGINEERING Total |  |  | 10672.45 | 8824.03 | 7053.53 | 5581.71 | 6685.04 | 13188.83 | 5507.28 | 3910.49 | 4218.47 | 4397.47 | 3724.49 |  | 73763.79
| Engineering/Technical Professional Servi | Contract | BLACK & VEATCH CORPORATION | [6 empty] | 233295.74 | [5 empty] | 233295.74
|  |  | Contract Entries <$50,000 | 39537.41 | 30745.97 | 14510 | 35320.74 | 23419.64 | 1040 | 52535.4 | 34799.92 | 2344.71 | 3317.2 | -17461 | 6330.24 | 226440.23
|  | Contract Total |  | 39537.41 | 30745.97 | 14510 | 35320.74 | 23419.64 | 1040 | 285831.14 | 34799.92 | 2344.71 | 3317.2 | -17461 | 6330.24 | 459735.97
| Engineering/Technical Professional Servi Total |  |  | 39537.41 | 30745.97 | 14510 | 35320.74 | 23419.64 | 1040 | 285831.14 | 34799.92 | 2344.71 | 3317.2 | -17461 | 6330.24 | 459735.97
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 812.63 | -6967.58 | -13788.63 | -6552.49 | -5508.24 | -3187.41 | -2989.37 | -2654.95 | 223869.43 | -229604.97 | -1793.55 | -1224.42 | -49589.55
|  | IMM Correction Total |  | 812.63 | -6967.58 | -13788.63 | -6552.49 | -5508.24 | -3187.41 | -2989.37 | -2654.95 | 223869.43 | -229604.97 | -1793.55 | -1224.42 | -49589.55
| IMM/Allocated - Correction Total |  |  | 812.63 | -6967.58 | -13788.63 | -6552.49 | -5508.24 | -3187.41 | -2989.37 | -2654.95 | 223869.43 | -229604.97 | -1793.55 | -1224.42 | -49589.55
| Labor - Other | Labor | Labor - Other | [9 empty] | 5170.96 |  |  | 5170.96
|  |  | Labor Correction | [9 empty] | 25726.33 |  |  | 25726.33
|  |  | Labor Entries <$5,000 | 1948.53 | 5318.67 | -693.87 | 273.68 | 15442.37 | -5113.12 | 1708.63 | 1221.22 | -18218.22 | -4920.38 | -1345.15 | 4508.91 | 131.27
|  |  | PSC Whirlwind Substation | 5057.04 | [11 empty] | 5057.04
|  | Labor Total |  | 7005.57 | 5318.67 | -693.87 | 273.68 | 15442.37 | -5113.12 | 1708.63 | 1221.22 | -18218.22 | 25976.91 | -1345.15 | 4508.91 | 36085.6
| Labor - Other Total |  |  | 7005.57 | 5318.67 | -693.87 | 273.68 | 15442.37 | -5113.12 | 1708.63 | 1221.22 | -18218.22 | 25976.91 | -1345.15 | 4508.91 | 36085.6
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  | 492.24 | 47.99 |  |  | 529.37 | 2609.58 | 39.4 |  |  |  |  | 3718.58
|  | Labor Total |  |  | 492.24 | 47.99 |  |  | 529.37 | 2609.58 | 39.4 |  |  |  |  | 3718.58
| NORTH GRIDMGMTCENTER Total |  |  |  | 492.24 | 47.99 |  |  | 529.37 | 2609.58 | 39.4 |  |  |  |  | 3718.58
| Other | Other | Other | -609720.16 | 815073.4 | -726902.99 | 63761.76 | 2801.06 | -7495.66 | 1329.37 | 10923.9 | 9955.01 | -13156.6 | 106166.61 | -58634.36 | -405898.66
|  | Other Total |  | -609720.16 | 815073.4 | -726902.99 | 63761.76 | 2801.06 | -7495.66 | 1329.37 | 10923.9 | 9955.01 | -13156.6 | 106166.61 | -58634.36 | -405898.66
| Other Total |  |  | -609720.16 | 815073.4 | -726902.99 | 63761.76 | 2801.06 | -7495.66 | 1329.37 | 10923.9 | 9955.01 | -13156.6 | 106166.61 | -58634.36 | -405898.66
| PLGHCC | Labor | Labor Entries <$5,000 | [11 empty] | 63.04 | 63.04
|  | Labor Total | [12 empty] | 63.04 | 63.04
| PLGHCC Total | [13 empty] | 63.04 | 63.04
| SC&M | Labor | Labor Entries <$5,000 | 965.97 | 2451.11 | 1813.77 | 736.72 | 34509.07 | 682.27 | 265.18 | 1390.4 |  | 343.82 | -1.1369e-13 | 707.57 | 43865.88
|  | Labor Total |  | 965.97 | 2451.11 | 1813.77 | 736.72 | 34509.07 | 682.27 | 265.18 | 1390.4 |  | 343.82 | -1.1369e-13 | 707.57 | 43865.88
| SC&M Total |  |  | 965.97 | 2451.11 | 1813.77 | 736.72 | 34509.07 | 682.27 | 265.18 | 1390.4 |  | 343.82 | -1.1369e-13 | 707.57 | 43865.88
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  |  |  | 220.2 | [6 empty] | 132.85 | 353.05
|  | Labor Total | [5 empty] | 220.2 | [6 empty] | 132.85 | 353.05
| SCM HOME CENTER Total | [6 empty] | 220.2 | [6 empty] | 132.85 | 353.05
| Software License Via Electronic Delivery | Contract | Contract Entries <$50,000 | [11 empty] | 7810.6 | 7810.6
|  | Contract Total | [12 empty] | 7810.6 | 7810.6
| Software License Via Electronic Delivery Total | [13 empty] | 7810.6 | 7810.6
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -25966.65 | 25966.65 |  |  | 0
|  | Contract Total | [9 empty] | -25966.65 | 25966.65 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -25966.65 | 25966.65 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 6160 | 5500 |  |  | 1760 | 2640 | 5280 | 1760 | 440 | 1100 |  |  | 24640
|  | Contract Total |  | 6160 | 5500 |  |  | 1760 | 2640 | 5280 | 1760 | 440 | 1100 |  |  | 24640
| Temporary/Supplementary - Technical/Prof Total |  |  | 6160 | 5500 |  |  | 1760 | 2640 | 5280 | 1760 | 440 | 1100 |  |  | 24640
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 15244.2 | 13340.94 | 7823.46 | 9167.31 | 3236.86 | 3422.25 | 4240 | 2266.08 | 146.08 |  | -8413.75 |  | 50473.43
|  | Contract Total |  | 15244.2 | 13340.94 | 7823.46 | 9167.31 | 3236.86 | 3422.25 | 4240 | 2266.08 | 146.08 |  | -8413.75 |  | 50473.43
| Temporary/Supplementary - Trade/Labor Total |  |  | 15244.2 | 13340.94 | 7823.46 | 9167.31 | 3236.86 | 3422.25 | 4240 | 2266.08 | 146.08 |  | -8413.75 |  | 50473.43
| TRANSMISSION | Labor | Labor Entries <$5,000 |  |  |  |  | 0 | [7 empty] | 0
|  | Labor Total | [5 empty] | 0 | [7 empty] | 0
| TRANSMISSION Total | [6 empty] | 0 | [7 empty] | 0
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 |  | 999 | 1184.6 | 255 | 1398.6 |  |  |  | 1260.2 |  |  |  | 5097.4
|  | Labor Total |  |  | 999 | 1184.6 | 255 | 1398.6 |  |  |  | 1260.2 |  |  |  | 5097.4
| TSD-Aircraft - Fixed Total |  |  |  | 999 | 1184.6 | 255 | 1398.6 |  |  |  | 1260.2 |  |  |  | 5097.4
1. Project Support Total |  |  |  | -528577.87 | 876363.63 | -707874.93 | 110376.95 | 83975.52 | 6609.65 | 303842.21 | 54336.85 | 22310.25 | -4722.04 | 80877.65 | -37442.21 | 260075.66
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | COMPOSITE SUPPORT & SOLUTIONS |  | 71680 | [10 empty] | 71680
|  |  | Material Entries <$5,000 | 4681.29 | 3647 | [8 empty] | 2748.43 | 22.78 | 11099.5
|  | Material - Direct Purchase Total |  | 4681.29 | 75327 | [8 empty] | 2748.43 | 22.78 | 82779.5
| Building, Shop & Industrial Products/Eqp Total |  |  | 4681.29 | 75327 | [8 empty] | 2748.43 | 22.78 | 82779.5
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 3248.85 | [8 empty] | 3248.85
|  |  | ONE SOURCE DISTRIBUTORS INC |  |  |  | 25588 | [8 empty] | 25588
|  | Material - Direct Purchase Total |  |  |  |  | 28836.85 | [8 empty] | 28836.85
| Cabinets, Panels and Switchboards-DP Total | [5 empty] | 28836.85 | [8 empty] | 28836.85
| Capacitors and Regulators-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | -114378 | -114378
|  | Material - Direct Purchase Total | [12 empty] | -114378 | -114378
| Capacitors and Regulators-DP Total | [13 empty] | -114378 | -114378
| Communication Systems and Equipment -DP | Material - Direct Purchase | Communication Systems and Equipment -DP | [11 empty] | 21483 | 21483
|  |  | Material Entries <$5,000 |  | 111.2 | [10 empty] | 111.2
|  | Material - Direct Purchase Total |  |  | 111.2 | [9 empty] | 21483 | 21594.2
| Communication Systems and Equipment -DP Total |  |  |  | 111.2 | [9 empty] | 21483 | 21594.2
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | 3836.34 |  | 25.96 | 4512.79 |  |  | 1486.57 |  |  |  |  | 2447.79 | 12309.45
|  | Material - Direct Purchase Total |  | 3836.34 |  | 25.96 | 4512.79 |  |  | 1486.57 |  |  |  |  | 2447.79 | 12309.45
| Electric Wiring and Components-DP Total |  |  | 3836.34 |  | 25.96 | 4512.79 |  |  | 1486.57 |  |  |  |  | 2447.79 | 12309.45
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 | 26.42 | [11 empty] | 26.42
|  | Material - Direct Purchase Total |  | 26.42 | [11 empty] | 26.42
| Fuels, Chemicals & Petrochem-DP Total |  |  | 26.42 | [11 empty] | 26.42
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -89.79 | 89.79 |  | -1600 | -1600
|  | Material - Direct Purchase Total | [9 empty] | -89.79 | 89.79 |  | -1600 | -1600
| Material - Direct Purchase - Correction Total | [10 empty] | -89.79 | 89.79 |  | -1600 | -1600
| Material - Inventory | Material | Material - Inventory | -579850.47 | 174514.56 | -135224.45 | -246017.83 | -53314.5 | -103438.3 |  | -8079.27 | -6.91 | -14523.31 | 24523.68 | 6621.65 | -934795.15
|  | Material Total |  | -579850.47 | 174514.56 | -135224.45 | -246017.83 | -53314.5 | -103438.3 |  | -8079.27 | -6.91 | -14523.31 | 24523.68 | 6621.65 | -934795.15
| Material - Inventory Total |  |  | -579850.47 | 174514.56 | -135224.45 | -246017.83 | -53314.5 | -103438.3 |  | -8079.27 | -6.91 | -14523.31 | 24523.68 | 6621.65 | -934795.15
| Material - Other | Material | Material - Other | -35759.14 | 19709.16 | -9914.15 | 4380.69 | -3905.88 | -6595.6 | 268.6 | 2464.95 | 1619.01 | -1057.97 | 3510.59 | 1721.3 | -23558.44
|  | Material Total |  | -35759.14 | 19709.16 | -9914.15 | 4380.69 | -3905.88 | -6595.6 | 268.6 | 2464.95 | 1619.01 | -1057.97 | 3510.59 | 1721.3 | -23558.44
| Material - Other Total |  |  | -35759.14 | 19709.16 | -9914.15 | 4380.69 | -3905.88 | -6595.6 | 268.6 | 2464.95 | 1619.01 | -1057.97 | 3510.59 | 1721.3 | -23558.44
| Mechanical Systems and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | 1100 | [11 empty] | 1100
|  | Material - Direct Purchase Total |  | 1100 | [11 empty] | 1100
| Mechanical Systems and Components-DP Total |  |  | 1100 | [11 empty] | 1100
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | 23.81 | [9 empty] | 1058.1 | 352.63 | 1434.54
|  | Material - Direct Purchase Total |  | 23.81 | [9 empty] | 1058.1 | 352.63 | 1434.54
| Metals & Fabricated Metal Products-DP Total |  |  | 23.81 | [9 empty] | 1058.1 | 352.63 | 1434.54
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 6037.5 |  | 2750.58 |  | 8593.54 |  |  |  |  | 17381.62
|  | Material - Direct Purchase Total |  |  |  |  | 6037.5 |  | 2750.58 |  | 8593.54 |  |  |  |  | 17381.62
| Office & Office Support Products-DP Total | [5 empty] | 6037.5 |  | 2750.58 |  | 8593.54 |  |  |  |  | 17381.62
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 29.4 | [10 empty] | 29.4
|  | Material - Direct Purchase Total |  |  | 29.4 | [10 empty] | 29.4
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  |  | 29.4 | [10 empty] | 29.4
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | 456.01 |  |  | -340.72 |  | 144.83 | 2150.04 | [5 empty] | 2410.16
|  | Material - Direct Purchase Total |  | 456.01 |  |  | -340.72 |  | 144.83 | 2150.04 | [5 empty] | 2410.16
| Pole Line Hdwe & Connectors-DP Total |  |  | 456.01 |  |  | -340.72 |  | 144.83 | 2150.04 | [5 empty] | 2410.16
| Protection and Test-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | -12698.5 | -12698.5
|  | Material - Direct Purchase Total | [12 empty] | -12698.5 | -12698.5
| Protection and Test-DP Total | [13 empty] | -12698.5 | -12698.5
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO | [8 empty] | 22112.41 |  |  |  | 22112.41
|  |  | Material Entries <$5,000 | 824.9 | 1268 |  | -600.4 |  | 4959 | [5 empty] | -139892.6 | -133441.1
|  | Material - Direct Purchase Total |  | 824.9 | 1268 |  | -600.4 |  | 4959 |  |  | 22112.41 |  |  | -139892.6 | -111328.69
| Steel / Fabricated / Structural-DP Total |  |  | 824.9 | 1268 |  | -600.4 |  | 4959 |  |  | 22112.41 |  |  | -139892.6 | -111328.69
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 2803.23 | 8.68 | 1656.48 | 1158.72 | 1560 | 72.75 |  |  |  |  | 776.1 |  | 8035.96
|  | Material - Direct Purchase Total |  | 2803.23 | 8.68 | 1656.48 | 1158.72 | 1560 | 72.75 |  |  |  |  | 776.1 |  | 8035.96
| Transportation & Mobile Equip-DP Total |  |  | 2803.23 | 8.68 | 1656.48 | 1158.72 | 1560 | 72.75 |  |  |  |  | 776.1 |  | 8035.96
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | 2584.47 | [11 empty] | 2584.47
|  | Material - Direct Purchase Total |  | 2584.47 | [11 empty] | 2584.47
| Wire, Cable & Bus Bar-DP Total |  |  | 2584.47 | [11 empty] | 2584.47
2. Material Total |  |  |  | -599273.14 | 270968 | -143456.16 | -202032.4 | -55660.38 | -102106.74 | 3905.21 | 2979.22 | 23634.72 | -15491.49 | 32616.9 | -235919.95 | -1019836.21
3. Construction | Construction Management Services | Contract | CIRCLE WOOD SERVICES, INC | 92595.71 |  | 105451.36 | 89334.3 |  | 57759.5 | 55917.2 |  |  |  | 104699.04 |  | 505757.11
|  |  | Contract Entries <$50,000 | 109538.4 | 9672.95 | 63283.86 | 62800.36 | 137119.07 | 54985.58 | 45399.67 | 102711.49 |  | 16468.13 | 13677.54 | 17591.19 | 633248.24
|  |  | UTILITY LINE MANAGEMENT SERVICES |  |  | 52277.28 | 50476.86 | [8 empty] | 102754.14
|  | Contract Total |  | 202134.11 | 9672.95 | 221012.5 | 202611.52 | 137119.07 | 112745.08 | 101316.87 | 102711.49 |  | 16468.13 | 118376.58 | 17591.19 | 1241759.49
| Construction Management Services Total |  |  | 202134.11 | 9672.95 | 221012.5 | 202611.52 | 137119.07 | 112745.08 | 101316.87 | 102711.49 |  | 16468.13 | 118376.58 | 17591.19 | 1241759.49
| Construction Services - Other | Contract | Contract Entries <$50,000 | -33151.92 | [11 empty] | -33151.92
|  | Contract Total |  | -33151.92 | [11 empty] | -33151.92
| Construction Services - Other Total |  |  | -33151.92 | [11 empty] | -33151.92
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [8 empty] | 4480.77 | 1023 |  |  | 5503.77
|  | Contract Total | [9 empty] | 4480.77 | 1023 |  |  | 5503.77
| Construction, Civil/Structural Total | [10 empty] | 4480.77 | 1023 |  |  | 5503.77
| Construction, Property/Building | Contract | ELDRIDGE ELECTRIC & SONS INC. | [11 empty] | 148348.77 | 148348.77
|  | Contract Total | [12 empty] | 148348.77 | 148348.77
| Construction, Property/Building Total | [13 empty] | 148348.77 | 148348.77
| ECS HOME | Labor | Labor Entries <$5,000 |  |  |  |  | 3147.99 | [7 empty] | 3147.99
|  | Labor Total | [5 empty] | 3147.99 | [7 empty] | 3147.99
| ECS HOME Total | [6 empty] | 3147.99 | [7 empty] | 3147.99
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 986.37 | 986.37
|  | Labor Total | [12 empty] | 986.37 | 986.37
| ELEC SYS PLANNING Total | [13 empty] | 986.37 | 986.37
| Electrical Services | Contract | ABCO GATE SYSTEMS |  | 73358 | [10 empty] | 73358
|  |  | Contract Entries <$50,000 |  | 2400 |  |  |  |  | -2500 | [5 empty] | -100
|  | Contract Total |  |  | 75758 |  |  |  |  | -2500 | [5 empty] | 73258
| Electrical Services Total |  |  |  | 75758 |  |  |  |  | -2500 | [5 empty] | 73258
| ENGINEERING | Labor | Labor Entries <$5,000 | 1736.42 | 1487.59 | 2389.06 | 883.51 | 1386.6 | 1917.61 | 1147.29 | 1799.41 | 1134.06 | 1173.14 | 1302.93 |  | 16357.62
|  | Labor Total |  | 1736.42 | 1487.59 | 2389.06 | 883.51 | 1386.6 | 1917.61 | 1147.29 | 1799.41 | 1134.06 | 1173.14 | 1302.93 |  | 16357.62
| ENGINEERING Total |  |  | 1736.42 | 1487.59 | 2389.06 | 883.51 | 1386.6 | 1917.61 | 1147.29 | 1799.41 | 1134.06 | 1173.14 | 1302.93 |  | 16357.62
| GRID OPS | Labor | Labor Entries <$5,000 |  | 3074.65 | 297.85 | 304.36 | [8 empty] | 3676.86
|  | Labor Total |  |  | 3074.65 | 297.85 | 304.36 | [8 empty] | 3676.86
| GRID OPS Total |  |  |  | 3074.65 | 297.85 | 304.36 | [8 empty] | 3676.86
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | 73.69 |  | 147.38 |  |  | 6084.56 | [6 empty] | 6305.63
|  | Contract Total |  | 73.69 |  | 147.38 |  |  | 6084.56 | [6 empty] | 6305.63
| Hauling / Industrial Moving Services Total |  |  | 73.69 |  | 147.38 |  |  | 6084.56 | [6 empty] | 6305.63
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  | 7686 | 882 | 5688 | [7 empty] | -379345.71 | -365089.71
|  |  | KINDNESS GENERAL CONTRACTORS INC | 223566.18 | 177497.89 | 75931.67 | 268617.67 |  | 121940.12 | 60865.23 |  | 54131.73 |  | 60226.41 | 77084.43 | 1119861.33
|  |  | PAR ELECTRICAL CONTRACTORS INC | 546195.83 | 1734785.88 | 762094.67 | 367070.13 | 404570.88 | 261184.45 |  | 836655.18 |  |  |  |  | 4912557.02
|  | Contract Total |  | 769762.01 | 1919969.77 | 838908.34 | 641375.8 | 404570.88 | 383124.57 | 60865.23 | 836655.18 | 54131.73 |  | 60226.41 | -302261.28 | 5667328.64
| Major Construction, Turnkey, Trans/Subs Total |  |  | 769762.01 | 1919969.77 | 838908.34 | 641375.8 | 404570.88 | 383124.57 | 60865.23 | 836655.18 | 54131.73 |  | 60226.41 | -302261.28 | 5667328.64
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | 2669.86 | 15231.84 | 10790.23 | 5373.64 | 7366.51 | 9654.21 | 7789.97 | 830.02 |  |  |  |  | 59706.28
|  | Labor Total |  | 2669.86 | 15231.84 | 10790.23 | 5373.64 | 7366.51 | 9654.21 | 7789.97 | 830.02 |  |  |  |  | 59706.28
| N/W SUBSMTCETEST&APP Total |  |  | 2669.86 | 15231.84 | 10790.23 | 5373.64 | 7366.51 | 9654.21 | 7789.97 | 830.02 |  |  |  |  | 59706.28
| SC&M | Labor | Labor Entries <$5,000 | 666.71 | 730.1 |  |  | 4206.62 | 614.84 | 162.88 | 181.77 | 68.66 |  |  | 5333.55 | 11965.13
|  |  | SC&M / Technician Test | [11 empty] | 6888.65 | 6888.65
|  |  | SC&M / Tst Spr Tech | [11 empty] | 12907.21 | 12907.21
|  | Labor Total |  | 666.71 | 730.1 |  |  | 4206.62 | 614.84 | 162.88 | 181.77 | 68.66 |  |  | 25129.41 | 31760.99
| SC&M Total |  |  | 666.71 | 730.1 |  |  | 4206.62 | 614.84 | 162.88 | 181.77 | 68.66 |  |  | 25129.41 | 31760.99
| Security / Protection Services | Contract | Contract Entries <$50,000 | 56013.03 |  | 31400.42 | 29389.6 | 28852.12 | 31298.05 | 29338.05 | 43251.22 | 14238.71 | 46847.46 | 28206.98 | 78966.12 | 417801.76
|  |  | WACKENHUT CORPORATION (THE) |  | 79492.8 | [10 empty] | 79492.8
|  | Contract Total |  | 56013.03 | 79492.8 | 31400.42 | 29389.6 | 28852.12 | 31298.05 | 29338.05 | 43251.22 | 14238.71 | 46847.46 | 28206.98 | 78966.12 | 497294.56
| Security / Protection Services Total |  |  | 56013.03 | 79492.8 | 31400.42 | 29389.6 | 28852.12 | 31298.05 | 29338.05 | 43251.22 | 14238.71 | 46847.46 | 28206.98 | 78966.12 | 497294.56
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 64394.53 | 46555.54 | 73852.74 | 76386.77 | 59790.68 | 17102.28 | 108591.32 | 35061.49 | 73989.43 | 37494.76 | 46435.52 | 98392.83 | 738047.89
|  | Contract Total |  | 64394.53 | 46555.54 | 73852.74 | 76386.77 | 59790.68 | 17102.28 | 108591.32 | 35061.49 | 73989.43 | 37494.76 | 46435.52 | 98392.83 | 738047.89
| Short Term Equipment Rent Total |  |  | 64394.53 | 46555.54 | 73852.74 | 76386.77 | 59790.68 | 17102.28 | 108591.32 | 35061.49 | 73989.43 | 37494.76 | 46435.52 | 98392.83 | 738047.89
| TRANSMISSION | Labor | Labor Entries <$5,000 |  |  |  |  | 0 | [7 empty] | 0
|  | Labor Total | [5 empty] | 0 | [7 empty] | 0
| TRANSMISSION Total | [6 empty] | 0 | [7 empty] | 0
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | [5 empty] | 164 | [6 empty] | 164
|  | Labor Total | [6 empty] | 164 | [6 empty] | 164
| TSD-HERC - Crane Svs Total | [7 empty] | 164 | [6 empty] | 164
3. Construction Total |  |  |  | 1064298.44 | 2151973.24 | 1178798.52 | 956325.2 | 646440.47 | 562705.2 | 306711.61 | 1020490.58 | 148043.36 | 103006.49 | 254548.42 | 67153.41 | 8460494.94
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -227650.38 | 24940.91 | -12383.36 | -39272.81 | 8800.29 | 2218.21 | 11011.14 | 8127.91 | 6378.45 | 1547.64 | 18842.32 | 17386.42 | -180053.26
|  |  | MATERIAL MANAGEM |  | 40871.31 | [10 empty] | 40871.31
|  |  | PROCUREMENT TDBU | 7780.21 | 14601.26 | 7365.12 | 6320.87 |  |  |  | 6798.25 |  |  |  |  | 42865.71
|  |  | TDBU Vehicle Cost |  |  |  |  | 5644.38 | [7 empty] | 5644.38
|  |  | TRTP 9 Whirlwind New Substation | 19647.79 | 28626.59 | 32292.05 | 28261.76 | 26099.25 | 16346.5 | 19077.03 | 13230.46 |  | 33999.68 | 15800.8 | 20475.07 | 253856.98
|  |  | Whirlwind - Segment 9 | [9 empty] | 5176.67 |  |  | 5176.67
|  |  | Whirlwind Sub û IDS | [11 empty] | 965698.7 | 965698.7
|  |  | Work Package #4 | 23614.85 | 24560.66 | 41666.01 | 37269.17 | 17531.13 | 23851.6 | [6 empty] | 168493.42
|  | Chargeback Total |  | -176607.53 | 133600.73 | 68939.82 | 32578.99 | 58075.05 | 42416.31 | 30088.17 | 28156.62 | 6378.45 | 40723.99 | 34643.12 | 1003560.19 | 1302553.91
| Chargebacks Total |  |  | -176607.53 | 133600.73 | 68939.82 | 32578.99 | 58075.05 | 42416.31 | 30088.17 | 28156.62 | 6378.45 | 40723.99 | 34643.12 | 1003560.19 | 1302553.91
| Labor - Other | Labor | Division Overhead | 51007.52 | 221536.74 | 80146.81 | 55096.36 | 38999.69 | 19026.65 | 42537.52 | 78325.16 |  | 9755.27 |  |  | 596431.72
|  |  | Labor Entries <$5,000 | 12075.27 | 6427.51 | 6413.9 | 8187.2 | 17684.12 | 16985.01 | 8853.43 | 2987.77 | -8376.28 | 18865.36 | 7495.83 | 3302.71 | 100901.83
|  |  | Paid Absence |  | 5025.4 |  |  | 7982.84 |  |  |  |  | 6499.12 |  |  | 19507.36
|  | Labor Total |  | 63082.79 | 232989.65 | 86560.71 | 63283.56 | 64666.65 | 36011.66 | 51390.95 | 81312.93 | -8376.28 | 35119.75 | 7495.83 | 3302.71 | 716840.91
| Labor - Other Total |  |  | 63082.79 | 232989.65 | 86560.71 | 63283.56 | 64666.65 | 36011.66 | 51390.95 | 81312.93 | -8376.28 | 35119.75 | 7495.83 | 3302.71 | 716840.91
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -5073.1 | 5073.1 |  |  | 0
|  | Overhead Total | [9 empty] | -5073.1 | 5073.1 |  |  | 0
| Overhead Correction Total | [10 empty] | -5073.1 | 5073.1 |  |  | 0
4. Allocated Total |  |  |  | -113524.74 | 366590.38 | 155500.53 | 95862.55 | 122741.7 | 78427.97 | 81479.12 | 109469.55 | -7070.93 | 80916.84 | 42138.95 | 1006862.9 | 2019394.82
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G | 36114.36 | 83583.37 | 46465.41 | 31992.85 | 66911.89 | 19869.94 | 24711.46 | 33273.5 | 8371.35 | 4329.33 | 8034.29 | 24131.02 | 387788.77
|  |  | Capitalized Overhead - Inj & Damages | -412.09 | 1169.56 | 132.88 | -63.27 | 1472.65 | -27.7 | 188.07 | 180.74 | 283.41 | -429.25 | 174.67 | -84.62 | 2585.05
|  |  | Capitalized Overhead - P&B/Payroll Tax | 34436.98 | 67724.05 | 42461.03 | 43221.1 | 121984.1 | 41591.92 | 27201.08 | 10672.87 | -31931.58 | 22323.5 | 8900.9 | 85140.24 | 473726.19
|  |  | Corporate Overheads Correction |  |  |  |  | -1533427.81 | [7 empty] | -1533427.81
|  | Non Budgeted Total |  | 70139.25 | 152476.98 | 89059.32 | 75150.68 | -1343059.17 | 61434.16 | 52100.61 | 44127.11 | -23276.82 | 26223.58 | 17109.86 | 109186.64 | -669327.8
| Non Budget - Other Total |  |  | 70139.25 | 152476.98 | 89059.32 | 75150.68 | -1343059.17 | 61434.16 | 52100.61 | 44127.11 | -23276.82 | 26223.58 | 17109.86 | 109186.64 | -669327.8
5. Corporate Overhead Total |  |  |  | 70139.25 | 152476.98 | 89059.32 | 75150.68 | -1343059.17 | 61434.16 | 52100.61 | 44127.11 | -23276.82 | 26223.58 | 17109.86 | 109186.64 | -669327.8
Grand Total |  |  |  | -106938.06 | 3818372.23 | 572027.28 | 1035682.98 | -545561.86 | 607070.24 | 748038.76 | 1231403.31 | 163640.58 | 189933.38 | 427291.78 | 909840.79 | 9050801.41

## 800208721
Pin: 6440 | Project: TRTP Segment 9
Order: 800208721 | 800208721- ACQ/TRTP Segment 9
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 9.6 |  | -0.04 |  |  |  | 0.12 |  |  |  | 0.02 |  | 9.7
|  | Contract Total |  | 9.6 |  | -0.04 |  |  |  | 0.12 |  |  |  | 0.02 |  | 9.7
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 9.6 |  | -0.04 |  |  |  | 0.12 |  |  |  | 0.02 |  | 9.7
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -6151.89 | 6151.89 |  |  | 0
|  | Contract Total | [9 empty] | -6151.89 | 6151.89 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -6151.89 | 6151.89 |  |  | 0
| HRealProp | Labor | Labor Entries <$5,000 | 272 | 53.91 | 209.05 | 952.07 | 43.77 | 32.94 |  |  | 76.59 |  |  |  | 1640.33
|  | Labor Total |  | 272 | 53.91 | 209.05 | 952.07 | 43.77 | 32.94 |  |  | 76.59 |  |  |  | 1640.33
| HRealProp Total |  |  | 272 | 53.91 | 209.05 | 952.07 | 43.77 | 32.94 |  |  | 76.59 |  |  |  | 1640.33
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -14.67 |  | -0.06 | -1.88 | -0.05 | -0.18 |  | 6140.66 | -6140.66 | -40.6 |  | -57.44
|  | IMM Correction Total |  |  | -14.67 |  | -0.06 | -1.88 | -0.05 | -0.18 |  | 6140.66 | -6140.66 | -40.6 |  | -57.44
| IMM/Allocated - Correction Total |  |  |  | -14.67 |  | -0.06 | -1.88 | -0.05 | -0.18 |  | 6140.66 | -6140.66 | -40.6 |  | -57.44
| Information System Professional Services | Contract | Contract Entries <$50,000 |  |  | 9.57 | [9 empty] | 9.57
|  | Contract Total |  |  |  | 9.57 | [9 empty] | 9.57
| Information System Professional Services Total |  |  |  |  | 9.57 | [9 empty] | 9.57
| Labor - Other | Labor | Labor Entries <$5,000 | 118.78 | 188.8 | 159.56 | 90.12 | 87.87 | -1.08 | 12.64 | 22.87 | -65.24 | 84.05 | 12.36 | 50.36 | 761.09
|  | Labor Total |  | 118.78 | 188.8 | 159.56 | 90.12 | 87.87 | -1.08 | 12.64 | 22.87 | -65.24 | 84.05 | 12.36 | 50.36 | 761.09
| Labor - Other Total |  |  | 118.78 | 188.8 | 159.56 | 90.12 | 87.87 | -1.08 | 12.64 | 22.87 | -65.24 | 84.05 | 12.36 | 50.36 | 761.09
| Other | Other | Other | 1766.89 |  | 39.9 | 300.95 | 7.39 | 39.11 |  |  | 80 | -80 |  |  | 2154.24
|  | Other Total |  | 1766.89 |  | 39.9 | 300.95 | 7.39 | 39.11 |  |  | 80 | -80 |  |  | 2154.24
| Other Total |  |  | 1766.89 |  | 39.9 | 300.95 | 7.39 | 39.11 |  |  | 80 | -80 |  |  | 2154.24
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 301.29 |  |  |  |  | 26.83 | [6 empty] | 328.12
|  | Contract Total |  | 301.29 |  |  |  |  | 26.83 | [6 empty] | 328.12
| Temporary/Supplementary - Trade/Labor Total |  |  | 301.29 |  |  |  |  | 26.83 | [6 empty] | 328.12
1. Project Support Total |  |  |  | 2468.56 | 228.04 | 418.04 | 1343.08 | 137.15 | 97.75 | 12.58 | 22.87 | 80.12 | 15.28 | -28.22 | 50.36 | 4845.61
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 23.19 | [8 empty] | 23.19
|  | Material - Direct Purchase Total |  |  |  |  | 23.19 | [8 empty] | 23.19
| Transportation & Mobile Equip-DP Total | [5 empty] | 23.19 | [8 empty] | 23.19
2. Material Total | [6 empty] | 23.19 | [8 empty] | 23.19
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 14.67 | 4140.24 | 1023.66 | 1.88 | 512.3 | 464.75 |  |  | -40.6 | 40.6 |  |  | 6157.5
|  | Chargeback Total |  | 14.67 | 4140.24 | 1023.66 | 1.88 | 512.3 | 464.75 |  |  | -40.6 | 40.6 |  |  | 6157.5
| Chargebacks Total |  |  | 14.67 | 4140.24 | 1023.66 | 1.88 | 512.3 | 464.75 |  |  | -40.6 | 40.6 |  |  | 6157.5
| Labor - Other | Labor | Labor Entries <$5,000 | 107.75 | 21.78 | 42.9 | 222.43 | 10.62 | 4.33 | 0.01 | 0.14 | -120.51 | 311.99 | 0.08 | 0.33 | 601.85
|  | Labor Total |  | 107.75 | 21.78 | 42.9 | 222.43 | 10.62 | 4.33 | 0.01 | 0.14 | -120.51 | 311.99 | 0.08 | 0.33 | 601.85
| Labor - Other Total |  |  | 107.75 | 21.78 | 42.9 | 222.43 | 10.62 | 4.33 | 0.01 | 0.14 | -120.51 | 311.99 | 0.08 | 0.33 | 601.85
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -175.22 | -175.22
|  | Overhead Total | [12 empty] | -175.22 | -175.22
| Overhead Correction Total | [13 empty] | -175.22 | -175.22
4. Allocated Total |  |  |  | 122.42 | 4162.02 | 1066.56 | 224.31 | 522.92 | 469.08 | 0.01 | 0.14 | -161.11 | 352.59 | 0.08 | -174.89 | 6584.13
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 23578.81 | 1433.16 | [6 empty] | 24421.19 | 49433.16
|  | Non Budgeted Total |  |  |  |  | 23578.81 | 1433.16 | [6 empty] | 24421.19 | 49433.16
| Non Budget - Other Total | [5 empty] | 23578.81 | 1433.16 | [6 empty] | 24421.19 | 49433.16
5. Corporate Overhead Total | [6 empty] | 23578.81 | 1433.16 | [6 empty] | 24421.19 | 49433.16
Grand Total |  |  |  | 2590.98 | 4390.06 | 1484.6 | 25169.39 | 2093.23 | 566.83 | 12.59 | 23.01 | -80.99 | 367.87 | -28.14 | 24296.66 | 60886.09

## 800148389
Pin: 6440 | Project: TRTP Segment 9
Order: 800148389 | 800148389- Windhub: Construct 500kv breaker-and-a-h
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | [11 empty] | 10395 | 10395
|  | Contract Total | [12 empty] | 10395 | 10395
| Engineering/Technical Professional Servi Total | [13 empty] | 10395 | 10395
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -3.89 | -25.73 | -38.37 | [8 empty] | -67.99
|  | IMM Correction Total |  |  | -3.89 | -25.73 | -38.37 | [8 empty] | -67.99
| IMM/Allocated - Correction Total |  |  |  | -3.89 | -25.73 | -38.37 | [8 empty] | -67.99
| Labor - Other | Labor | Labor Entries <$5,000 |  |  | 3625.2 | 1496.46 | [8 empty] | 5121.66
|  | Labor Total |  |  |  | 3625.2 | 1496.46 | [8 empty] | 5121.66
| Labor - Other Total |  |  |  |  | 3625.2 | 1496.46 | [8 empty] | 5121.66
| Other | Other | Other |  |  | 5539.76 | 7676.89 | 51320.27 | -2355.77 | -25865.67 | 57671.69 |  |  |  |  | 93987.17
|  | Other Total |  |  |  | 5539.76 | 7676.89 | 51320.27 | -2355.77 | -25865.67 | 57671.69 |  |  |  |  | 93987.17
| Other Total |  |  |  |  | 5539.76 | 7676.89 | 51320.27 | -2355.77 | -25865.67 | 57671.69 |  |  |  |  | 93987.17
1. Project Support Total |  |  |  |  | -3.89 | 9139.23 | 9134.98 | 51320.27 | -2355.77 | -25865.67 | 57671.69 |  |  |  | 10395 | 109435.84
2. Material | Material - Inventory | Material | Material - Inventory |  | 7365 | -2855 | [9 empty] | 4510
|  | Material Total |  |  | 7365 | -2855 | [9 empty] | 4510
| Material - Inventory Total |  |  |  | 7365 | -2855 | [9 empty] | 4510
| Material - Other | Material | Material - Other |  | 35747.13 | -2422.86 |  | -33324.27 | [7 empty] | 0
|  | Material Total |  |  | 35747.13 | -2422.86 |  | -33324.27 | [7 empty] | 0
| Material - Other Total |  |  |  | 35747.13 | -2422.86 |  | -33324.27 | [7 empty] | 0
| Protection and Test-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 3898.84 | [10 empty] | 3898.84
|  | Material - Direct Purchase Total |  |  | 3898.84 | [10 empty] | 3898.84
| Protection and Test-DP Total |  |  |  | 3898.84 | [10 empty] | 3898.84
| Reactors and Line Traps-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 0 | 0 | [9 empty] | 0
|  | Material - Direct Purchase Total |  |  | 0 | 0 | [9 empty] | 0
| Reactors and Line Traps-DP Total |  |  |  | 0 | 0 | [9 empty] | 0
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | -63142.5 | [8 empty] | -63142.5
|  | Material - Direct Purchase Total |  |  |  |  | -63142.5 | [8 empty] | -63142.5
| Wire, Cable & Bus Bar-DP Total | [5 empty] | -63142.5 | [8 empty] | -63142.5
2. Material Total |  |  |  |  | 47010.97 | -5277.86 | -63142.5 | -33324.27 | [7 empty] | -54733.66
3. Construction | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [9 empty] | 3.19 |  |  | 3.19
|  | Contract Total | [10 empty] | 3.19 |  |  | 3.19
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [11 empty] | 3.19 |  |  | 3.19
| Construction Management Services | Contract | Contract Entries <$50,000 | 539.88 |  | 5813.36 | [9 empty] | 6353.24
|  | Contract Total |  | 539.88 |  | 5813.36 | [9 empty] | 6353.24
| Construction Management Services Total |  |  | 539.88 |  | 5813.36 | [9 empty] | 6353.24
| Labor - Other | Labor | Labor Entries <$5,000 | [8 empty] | 4546.96 | 1409.82 | 23.59 | 6.9 | 5987.27
|  | Labor Total | [9 empty] | 4546.96 | 1409.82 | 23.59 | 6.9 | 5987.27
| Labor - Other Total | [10 empty] | 4546.96 | 1409.82 | 23.59 | 6.9 | 5987.27
| Other | Other | Other |  |  |  |  | 14.43 | [5 empty] | 9.71 |  | 24.14
|  | Other Total | [5 empty] | 14.43 | [5 empty] | 9.71 |  | 24.14
| Other Total | [6 empty] | 14.43 | [5 empty] | 9.71 |  | 24.14
3. Construction Total |  |  |  | 539.88 |  | 5813.36 |  | 14.43 |  |  |  | 4546.96 | 1413.01 | 33.3 | 6.9 | 12367.84
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 3.89 | 1750.61 | -657.39 | -416.74 |  | 102.41 |  |  |  |  | 89.34 | 335.99 | 1208.11
|  | Chargeback Total |  | 3.89 | 1750.61 | -657.39 | -416.74 |  | 102.41 |  |  |  |  | 89.34 | 335.99 | 1208.11
| Chargebacks Total |  |  | 3.89 | 1750.61 | -657.39 | -416.74 |  | 102.41 |  |  |  |  | 89.34 | 335.99 | 1208.11
| Labor - Other | Labor | Labor Entries <$5,000 | 31.32 | 974.32 | 406.19 | -2026.86 | [5 empty] | 1.88 |  | 139.29 | -473.86
|  | Labor Total |  | 31.32 | 974.32 | 406.19 | -2026.86 | [5 empty] | 1.88 |  | 139.29 | -473.86
| Labor - Other Total |  |  | 31.32 | 974.32 | 406.19 | -2026.86 | [5 empty] | 1.88 |  | 139.29 | -473.86
4. Allocated Total |  |  |  | 35.21 | 2724.93 | -251.2 | -2443.6 |  | 102.41 |  |  |  | 1.88 | 89.34 | 475.28 | 734.25
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 6290.51 | 388.49 | [6 empty] | 6943.59 | 13622.59
|  |  | Capitalized Overhead - A&G | 32.1 | 1456.96 | 147.35 | -2283.28 | -295.09 | 3.66 |  | 1806.66 | 203.7 | 36.56 | 3.24 | 305.39 | 1417.25
|  |  | Capitalized Overhead - Inj & Damages | 0.03 | 85.87 | -1.77 | -53.08 | -31.64 | 0.13 |  | 83.24 | 4.12 | 3.57 | 0.2 | 0.54 | 91.21
|  |  | Capitalized Overhead - P&B/Payroll Tax |  |  | 3095 | 1601.23 |  |  |  |  | 5424.44 | 459.49 | 16.75 | 13.02 | 10609.93
|  |  | Corporate Overheads Correction |  |  |  |  | 147.44 | [7 empty] | 147.44
|  | Non Budgeted Total |  | 32.13 | 1542.83 | 3240.58 | 5555.38 | 209.2 | 3.79 |  | 1889.9 | 5632.26 | 499.62 | 20.19 | 7262.54 | 25888.42
| Non Budget - Other Total |  |  | 32.13 | 1542.83 | 3240.58 | 5555.38 | 209.2 | 3.79 |  | 1889.9 | 5632.26 | 499.62 | 20.19 | 7262.54 | 25888.42
5. Corporate Overhead Total |  |  |  | 32.13 | 1542.83 | 3240.58 | 5555.38 | 209.2 | 3.79 |  | 1889.9 | 5632.26 | 499.62 | 20.19 | 7262.54 | 25888.42
Grand Total |  |  |  | 607.22 | 51274.84 | 12664.11 | -50895.74 | 18219.63 | -2249.57 | -25865.67 | 59561.59 | 10179.22 | 1914.51 | 142.83 | 18139.72 | 93692.69

## 800148388
Pin: 6440 | Project: TRTP Segment 9
Order: 800148388 | 800148388- Whirlwind: Construct new 500/220kv subst
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 52431.5 |  |  | 52431.5
|  |  | Contract Entries <$50,000 | [8 empty] | -52431.5 |  |  |  | -52431.5
|  | Contract Total | [9 empty] | -52431.5 | 52431.5 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -52431.5 | 52431.5 |  |  | 0
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 12618.95 | 5664.28 |  | 13697.04 |  |  |  | 3125 |  |  |  |  | 35105.27
|  | Contract Total |  | 12618.95 | 5664.28 |  | 13697.04 |  |  |  | 3125 |  |  |  |  | 35105.27
| Engineering/Technical Professional Servi Total |  |  | 12618.95 | 5664.28 |  | 13697.04 |  |  |  | 3125 |  |  |  |  | 35105.27
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 7637.4 | 7392.36 | 5761 | 1399.17 | 1079.73 | 2306.59 | 2531.05 | 2563.56 | 3987.21 | 1034.12 | 3811.02 | 39503.21
|  | Contract Total |  |  | 7637.4 | 7392.36 | 5761 | 1399.17 | 1079.73 | 2306.59 | 2531.05 | 2563.56 | 3987.21 | 1034.12 | 3811.02 | 39503.21
| Environmental/Safety Professional Servic Total |  |  |  | 7637.4 | 7392.36 | 5761 | 1399.17 | 1079.73 | 2306.59 | 2531.05 | 2563.56 | 3987.21 | 1034.12 | 3811.02 | 39503.21
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -88.98 | -88.69 | -48.79 | -128.42 | -9.87 | -7.13 | -15.22 | 56590.15 | -56627.48 | -372.36 | -6.83 | -803.62
|  | IMM Correction Total |  |  | -88.98 | -88.69 | -48.79 | -128.42 | -9.87 | -7.13 | -15.22 | 56590.15 | -56627.48 | -372.36 | -6.83 | -803.62
| IMM/Allocated - Correction Total |  |  |  | -88.98 | -88.69 | -48.79 | -128.42 | -9.87 | -7.13 | -15.22 | 56590.15 | -56627.48 | -372.36 | -6.83 | -803.62
| Labor - Other | Labor | Labor Entries <$5,000 | [8 empty] | -3274.71 | 3274.71 |  |  | 0
|  | Labor Total | [9 empty] | -3274.71 | 3274.71 |  |  | 0
| Labor - Other Total | [10 empty] | -3274.71 | 3274.71 |  |  | 0
| Other | Other | Other | -203338.89 |  | -90875.43 | -2376 | -3401.91 | 264777.74 | -258860.16 | -15030.33 | -512.26 | 512.26 |  |  | -309104.98
|  | Other Total |  | -203338.89 |  | -90875.43 | -2376 | -3401.91 | 264777.74 | -258860.16 | -15030.33 | -512.26 | 512.26 |  |  | -309104.98
| Other Total |  |  | -203338.89 |  | -90875.43 | -2376 | -3401.91 | 264777.74 | -258860.16 | -15030.33 | -512.26 | 512.26 |  |  | -309104.98
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 96.8 | [11 empty] | 96.8
|  | Contract Total |  | 96.8 | [11 empty] | 96.8
| Temporary/Supplementary - Technical/Prof Total |  |  | 96.8 | [11 empty] | 96.8
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 96.8 | 135.52 |  |  | 96.8 | [7 empty] | 329.12
|  | Contract Total |  | 96.8 | 135.52 |  |  | 96.8 | [7 empty] | 329.12
| Temporary/Supplementary - Trade/Labor Total |  |  | 96.8 | 135.52 |  |  | 96.8 | [7 empty] | 329.12
1. Project Support Total |  |  |  | -190526.34 | 13348.22 | -83571.76 | 17033.25 | -2034.36 | 265847.6 | -256560.7 | -9389.5 | 2935.24 | 3578.2 | 661.76 | 3804.19 | -234874.2
2. Material | Material - Inventory | Material | Material - Inventory |  |  | -617.12 | [6 empty] | -4821.08 |  |  | -5438.2
|  | Material Total |  |  |  | -617.12 | [6 empty] | -4821.08 |  |  | -5438.2
| Material - Inventory Total |  |  |  |  | -617.12 | [6 empty] | -4821.08 |  |  | -5438.2
| Material - Other | Material | Material - Other |  |  | -44.74 |  |  |  |  | -32.9 |  | -349.53 |  |  | -427.17
|  | Material Total |  |  |  | -44.74 |  |  |  |  | -32.9 |  | -349.53 |  |  | -427.17
| Material - Other Total |  |  |  |  | -44.74 |  |  |  |  | -32.9 |  | -349.53 |  |  | -427.17
| Mechanical Systems and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | -453.75 | [11 empty] | -453.75
|  | Material - Direct Purchase Total |  | -453.75 | [11 empty] | -453.75
| Mechanical Systems and Components-DP Total |  |  | -453.75 | [11 empty] | -453.75
2. Material Total |  |  |  | -453.75 |  | -661.86 |  |  |  |  | -32.9 |  | -5170.61 |  |  | -6319.12
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [11 empty] | 15309.3 | 15309.3
|  | Contract Total | [12 empty] | 15309.3 | 15309.3
| Construction Management Services Total | [13 empty] | 15309.3 | 15309.3
| Labor - Other | Labor | Labor Entries <$5,000 |  |  |  |  | 261.15 | [7 empty] | 261.15
|  | Labor Total | [5 empty] | 261.15 | [7 empty] | 261.15
| Labor - Other Total | [6 empty] | 261.15 | [7 empty] | 261.15
| Other | Other | Other | [10 empty] | 9.71 |  | 9.71
|  | Other Total | [11 empty] | 9.71 |  | 9.71
| Other Total | [12 empty] | 9.71 |  | 9.71
3. Construction Total | [7 empty] | 261.15 | [5 empty] | 9.71 | 15309.3 | 15580.16
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 627.02 | 25745.06 | -23161.39 | 3641.17 | -748.4 | 476.86 | 222.23 | 110.78 | 510.43 | 140.32 | 511.99 | 126.19 | 8202.26
|  |  | New Whirlwind Sub 550kV/200kV-RosemondCA |  | 44921.5 | 6312.5 | [9 empty] | 51234
|  | Chargeback Total |  | 627.02 | 70666.56 | -16848.89 | 3641.17 | -748.4 | 476.86 | 222.23 | 110.78 | 510.43 | 140.32 | 511.99 | 126.19 | 59436.26
| Chargebacks Total |  |  | 627.02 | 70666.56 | -16848.89 | 3641.17 | -748.4 | 476.86 | 222.23 | 110.78 | 510.43 | 140.32 | 511.99 | 126.19 | 59436.26
| Labor - Other | Labor | Labor Entries <$5,000 | 716.81 | 1162.32 | 930.24 | 624.6 | 65.22 | 48.15 | 95.96 | 231.9 | -2281.1 | 3466.19 | 11.06 | 256.21 | 5327.56
|  | Labor Total |  | 716.81 | 1162.32 | 930.24 | 624.6 | 65.22 | 48.15 | 95.96 | 231.9 | -2281.1 | 3466.19 | 11.06 | 256.21 | 5327.56
| Labor - Other Total |  |  | 716.81 | 1162.32 | 930.24 | 624.6 | 65.22 | 48.15 | 95.96 | 231.9 | -2281.1 | 3466.19 | 11.06 | 256.21 | 5327.56
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -409.01 | 409.01 |  |  | 0
|  | Overhead Total | [9 empty] | -409.01 | 409.01 |  |  | 0
| Overhead Correction Total | [10 empty] | -409.01 | 409.01 |  |  | 0
4. Allocated Total |  |  |  | 1343.83 | 71828.88 | -15918.65 | 4265.77 | -683.18 | 525.01 | 318.19 | 342.68 | -2179.68 | 4015.52 | 523.05 | 382.4 | 64763.82
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 4470.79 | 271.03 | [6 empty] | 4754.66 | 9496.48
|  |  | Capitalized Overhead - A&G | -10583.51 | 2495.36 | -3654.58 | 844.27 | -204.44 | 56.92 | -228.06 | 168.31 | 33.85 | 62.61 | 31.57 | 547.37 | -10430.33
|  |  | Capitalized Overhead - Inj & Damages | -189.34 | 46.31 | -122.64 | 2.5 | -35.28 | 0.67 | -8.05 | 0.38 | 45.85 | -170.78 | -0.08 | 0.42 | -430.04
|  |  | Capitalized Overhead - P&B/Payroll Tax | 271.61 | 1112.9 | 329.4 | 576.42 | 784.81 | 342.9 | 48.91 |  | -4560.5 | 1854.42 |  |  | 760.87
|  | Non Budgeted Total |  | -10501.24 | 3654.57 | -3447.82 | 5893.98 | 816.12 | 400.49 | -187.2 | 168.69 | -4480.8 | 1746.25 | 31.49 | 5302.45 | -603.02
| Non Budget - Other Total |  |  | -10501.24 | 3654.57 | -3447.82 | 5893.98 | 816.12 | 400.49 | -187.2 | 168.69 | -4480.8 | 1746.25 | 31.49 | 5302.45 | -603.02
5. Corporate Overhead Total |  |  |  | -10501.24 | 3654.57 | -3447.82 | 5893.98 | 816.12 | 400.49 | -187.2 | 168.69 | -4480.8 | 1746.25 | 31.49 | 5302.45 | -603.02
Grand Total |  |  |  | -200137.5 | 88831.67 | -103600.09 | 27193 | -1640.27 | 266773.1 | -256429.71 | -8911.03 | -3725.24 | 4169.36 | 1226.01 | 24798.34 | -161452.36

## 800148387
Pin: 6440 | Project: TRTP Segment 9
Order: 800148387 | 800148387- Antelope: Construct new 500kV switchyard
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | [6 empty] | 1980 |  |  | 2385 |  |  | 4365
|  | Contract Total | [7 empty] | 1980 |  |  | 2385 |  |  | 4365
| Engineering/Technical Professional Servi Total | [8 empty] | 1980 |  |  | 2385 |  |  | 4365
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 5268.33 | 2252.12 | 2031.53 | 1136.86 | 2112.98 | 5160.76 | 1411.5 | 2710.58 |  | 1104.31 | 7358.97 | 30547.94
|  | Contract Total |  |  | 5268.33 | 2252.12 | 2031.53 | 1136.86 | 2112.98 | 5160.76 | 1411.5 | 2710.58 |  | 1104.31 | 7358.97 | 30547.94
| Environmental/Safety Professional Servic Total |  |  |  | 5268.33 | 2252.12 | 2031.53 | 1136.86 | 2112.98 | 5160.76 | 1411.5 | 2710.58 |  | 1104.31 | 7358.97 | 30547.94
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -0.79 | -34.77 | -14.14 | -13.41 | -7.5 | -13.95 | -47.13 | -9.32 | -17.89 | -15.74 | -7.29 | -181.93
|  | IMM Correction Total |  |  | -0.79 | -34.77 | -14.14 | -13.41 | -7.5 | -13.95 | -47.13 | -9.32 | -17.89 | -15.74 | -7.29 | -181.93
| IMM/Allocated - Correction Total |  |  |  | -0.79 | -34.77 | -14.14 | -13.41 | -7.5 | -13.95 | -47.13 | -9.32 | -17.89 | -15.74 | -7.29 | -181.93
| Other | Other | Other | -24362.11 |  | 4041.87 | -1628 | -11236.16 | 6166.28 | -16970.03 | -749.51 |  |  |  |  | -44737.66
|  | Other Total |  | -24362.11 |  | 4041.87 | -1628 | -11236.16 | 6166.28 | -16970.03 | -749.51 |  |  |  |  | -44737.66
| Other Total |  |  | -24362.11 |  | 4041.87 | -1628 | -11236.16 | 6166.28 | -16970.03 | -749.51 |  |  |  |  | -44737.66
1. Project Support Total |  |  |  | -24362.11 | 5267.54 | 6259.22 | 389.39 | -10112.71 | 8271.76 | -9843.22 | 614.86 | 2701.26 | 2367.11 | 1088.57 | 7351.68 | -10006.65
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 |  |  | -109.2 | [9 empty] | -109.2
|  | Material - Direct Purchase Total |  |  |  | -109.2 | [9 empty] | -109.2
| Material - Direct Purchase - Correction Total |  |  |  |  | -109.2 | [9 empty] | -109.2
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 109.2 | [11 empty] | 109.2
|  | Material - Direct Purchase Total |  | 109.2 | [11 empty] | 109.2
| Transportation & Mobile Equip-DP Total |  |  | 109.2 | [11 empty] | 109.2
2. Material Total |  |  |  | 109.2 |  | -109.2 | [9 empty] | 0
3. Construction | Other | Other | Other |  |  |  |  | 19.98 | 15.54 | 19.85 |  |  |  | 9.71 |  | 65.08
|  | Other Total | [5 empty] | 19.98 | 15.54 | 19.85 |  |  |  | 9.71 |  | 65.08
| Other Total | [6 empty] | 19.98 | 15.54 | 19.85 |  |  |  | 9.71 |  | 65.08
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 887.44 | 0.02 | -637.38 | [9 empty] | 250.08
|  | Contract Total |  | 887.44 | 0.02 | -637.38 | [9 empty] | 250.08
| Short Term Equipment Rent Total |  |  | 887.44 | 0.02 | -637.38 | [9 empty] | 250.08
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | 82 | [11 empty] | 82
|  | Labor Total |  | 82 | [11 empty] | 82
| TSD-HERC - Rental Total |  |  | 82 | [11 empty] | 82
3. Construction Total |  |  |  | 969.44 | 0.02 | -637.38 |  | 19.98 | 15.54 | 19.85 |  |  |  | 9.71 |  | 397.16
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 53.67 | 34.77 | 46.47 | 509.56 | 126.16 | 138.68 | 53 | 9.32 | 908.79 | 165.59 | 7.29 | 48.57 | 2101.87
|  | Chargeback Total |  | 53.67 | 34.77 | 46.47 | 509.56 | 126.16 | 138.68 | 53 | 9.32 | 908.79 | 165.59 | 7.29 | 48.57 | 2101.87
| Chargebacks Total |  |  | 53.67 | 34.77 | 46.47 | 509.56 | 126.16 | 138.68 | 53 | 9.32 | 908.79 | 165.59 | 7.29 | 48.57 | 2101.87
| Labor - Other | Labor | Labor Entries <$5,000 | 27.71 | 194.4 | 54.8 | 65.22 | 20.79 | 94.24 | 297.05 | 57.88 | 86.2 | 123.78 | 11.82 | 98.61 | 1132.5
|  | Labor Total |  | 27.71 | 194.4 | 54.8 | 65.22 | 20.79 | 94.24 | 297.05 | 57.88 | 86.2 | 123.78 | 11.82 | 98.61 | 1132.5
| Labor - Other Total |  |  | 27.71 | 194.4 | 54.8 | 65.22 | 20.79 | 94.24 | 297.05 | 57.88 | 86.2 | 123.78 | 11.82 | 98.61 | 1132.5
4. Allocated Total |  |  |  | 81.38 | 229.17 | 101.27 | 574.78 | 146.95 | 232.92 | 350.05 | 67.2 | 994.99 | 289.37 | 19.11 | 147.18 | 3234.37
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 4211.54 | 252.59 | [6 empty] | 4393.07 | 8857.2
|  |  | Capitalized Overhead - A&G | -1294.9 | 161.03 | -234.91 | 92.44 | 52.47 | 84.01 | -116.12 | 19.29 | 165.59 | 68.63 | 29.53 | 210.54 | -762.4
|  |  | Capitalized Overhead - Inj & Damages | -21.7 | 0.39 | -9.33 | 0.46 | -4.52 | 0.31 | -9.56 | -0.95 | 0.89 | 0.86 | 0.02 | 0.16 | -42.97
|  |  | Corporate Overheads Correction |  |  |  |  | 247.75 | [7 empty] | 247.75
|  | Non Budgeted Total |  | -1316.6 | 161.42 | -244.24 | 4304.44 | 548.29 | 84.32 | -125.68 | 18.34 | 166.48 | 69.49 | 29.55 | 4603.77 | 8299.58
| Non Budget - Other Total |  |  | -1316.6 | 161.42 | -244.24 | 4304.44 | 548.29 | 84.32 | -125.68 | 18.34 | 166.48 | 69.49 | 29.55 | 4603.77 | 8299.58
5. Corporate Overhead Total |  |  |  | -1316.6 | 161.42 | -244.24 | 4304.44 | 548.29 | 84.32 | -125.68 | 18.34 | 166.48 | 69.49 | 29.55 | 4603.77 | 8299.58
Grand Total |  |  |  | -24518.69 | 5658.15 | 5369.67 | 5268.61 | -9397.49 | 8604.54 | -9599 | 700.4 | 3862.73 | 2725.97 | 1146.94 | 12102.63 | 1924.46

## TRTP Seg 10
WO | SumOfYTD2012 | Order | Project
800217239- I: TRTP 10-1: WHIRLWIND-WINDHUB 500KV: C | 14690348.79 | 800217239 | TRTP Segment 10
800208725- ACQ-TRTP Segment 10 | 82316.24 | 800208725 | TRTP Segment 10

## 800217239
Pin: 6441 | Project: TRTP Segment 10
Order: 800217239 | 800217239- I: TRTP 10-1: WHIRLWIND-WINDHUB 500KV: C
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 90.35 | [6 empty] | 90.35
|  | Labor Total | [6 empty] | 90.35 | [6 empty] | 90.35
| BP&FM Total | [7 empty] | 90.35 | [6 empty] | 90.35
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 |  |  | 75 | [9 empty] | 75
|  | Contract Total |  |  |  | 75 | [9 empty] | 75
| Building/Facility Repairs & Maintenance Total |  |  |  |  | 75 | [9 empty] | 75
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 1414852.33 |  |  | 1414852.33
|  |  | Contract Entries <$50,000 | [8 empty] | -1414852.33 |  |  |  | -1414852.33
|  | Contract Total | [9 empty] | -1414852.33 | 1414852.33 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -1414852.33 | 1414852.33 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 923.63 | 923.63
|  | Labor Total | [12 empty] | 923.63 | 923.63
| ELEC SYS PLANNING Total | [13 empty] | 923.63 | 923.63
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 365.79 | 354.86 |  |  |  |  | 351.72 | [5 empty] | 1072.37
|  | Labor Total |  | 365.79 | 354.86 |  |  |  |  | 351.72 | [5 empty] | 1072.37
| ENG ADVANCEMENT Total |  |  | 365.79 | 354.86 |  |  |  |  | 351.72 | [5 empty] | 1072.37
| ENGINEERING | Labor | Labor Entries <$5,000 | 4579.79 | 5202.68 | 5374.69 | 6301.85 | 4958.63 | 2767.43 | 1750.98 | 2308.38 | 2259.59 | 1423.07 | 3459.4 |  | 40386.49
|  | Labor Total |  | 4579.79 | 5202.68 | 5374.69 | 6301.85 | 4958.63 | 2767.43 | 1750.98 | 2308.38 | 2259.59 | 1423.07 | 3459.4 |  | 40386.49
| ENGINEERING Total |  |  | 4579.79 | 5202.68 | 5374.69 | 6301.85 | 4958.63 | 2767.43 | 1750.98 | 2308.38 | 2259.59 | 1423.07 | 3459.4 |  | 40386.49
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | 805761 | 273671 | 359294 | 376678 | 421960 |  | 650167.09 | 165689 | 80733.45 | 80120 | 137174 | 248054.33 | 3599301.87
|  |  | Contract Entries <$50,000 | 10257.1 | 46034.92 | 17389.77 | 8600.44 | 12879.57 | 5695.9 | 6481.66 | -12675.34 |  | 609.49 | -158704 | 517.84 | -62912.65
|  | Contract Total |  | 816018.1 | 319705.92 | 376683.77 | 385278.44 | 434839.57 | 5695.9 | 656648.75 | 153013.66 | 80733.45 | 80729.49 | -21530 | 248572.17 | 3536389.22
| Engineering/Technical Professional Servi Total |  |  | 816018.1 | 319705.92 | 376683.77 | 385278.44 | 434839.57 | 5695.9 | 656648.75 | 153013.66 | 80733.45 | 80729.49 | -21530 | 248572.17 | 3536389.22
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 6526 | 1838.55 | 1534 | 681.91 | 3767.1 | 8101.1 | 3826.5 | 3197.35 | 2764.5 | 1830.5 | 20198.81 | 54266.32
|  | Contract Total |  |  | 6526 | 1838.55 | 1534 | 681.91 | 3767.1 | 8101.1 | 3826.5 | 3197.35 | 2764.5 | 1830.5 | 20198.81 | 54266.32
| Environmental/Safety Professional Servic Total |  |  |  | 6526 | 1838.55 | 1534 | 681.91 | 3767.1 | 8101.1 | 3826.5 | 3197.35 | 2764.5 | 1830.5 | 20198.81 | 54266.32
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 9751.58 | -9802.91 | -6759.61 | 2721.31 | 6923.76 | -10325.69 | 6670.69 | 2419.95 | 1384464.19 | -1374692.68 | -14435.66 | -3693.36 | -6758.43
|  | IMM Correction Total |  | 9751.58 | -9802.91 | -6759.61 | 2721.31 | 6923.76 | -10325.69 | 6670.69 | 2419.95 | 1384464.19 | -1374692.68 | -14435.66 | -3693.36 | -6758.43
| IMM/Allocated - Correction Total |  |  | 9751.58 | -9802.91 | -6759.61 | 2721.31 | 6923.76 | -10325.69 | 6670.69 | 2419.95 | 1384464.19 | -1374692.68 | -14435.66 | -3693.36 | -6758.43
| Labor - Other | Labor | Labor - Other | [9 empty] | 11854.6 |  |  | 11854.6
|  |  | Labor Correction | [9 empty] | 58978.4 |  |  | 58978.4
|  |  | Labor Entries <$5,000 | 494.1 | 687.95 | -1034.21 | 41.08 | 4156.85 | -4402.81 | 102.28 | -61.25 | -18410.17 | -52169.89 | -180.88 | 214.03 | -70562.92
|  | Labor Total |  | 494.1 | 687.95 | -1034.21 | 41.08 | 4156.85 | -4402.81 | 102.28 | -61.25 | -18410.17 | 18663.11 | -180.88 | 214.03 | 270.08
| Labor - Other Total |  |  | 494.1 | 687.95 | -1034.21 | 41.08 | 4156.85 | -4402.81 | 102.28 | -61.25 | -18410.17 | 18663.11 | -180.88 | 214.03 | 270.08
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | 231.87 | [11 empty] | 231.87
|  | Labor Total |  | 231.87 | [11 empty] | 231.87
| NORTH GRIDMGMTCENTER Total |  |  | 231.87 | [11 empty] | 231.87
| Other | Other | Other | 273488.12 | -2006183.03 | -502739.11 | 786386.2 | -690859.09 | -670668.76 | -378049.49 | -34218.53 | 206093.11 | 40413 | 110073.51 | 598524.52 | -2267739.55
|  | Other Total |  | 273488.12 | -2006183.03 | -502739.11 | 786386.2 | -690859.09 | -670668.76 | -378049.49 | -34218.53 | 206093.11 | 40413 | 110073.51 | 598524.52 | -2267739.55
| Other Total |  |  | 273488.12 | -2006183.03 | -502739.11 | 786386.2 | -690859.09 | -670668.76 | -378049.49 | -34218.53 | 206093.11 | 40413 | 110073.51 | 598524.52 | -2267739.55
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -47627.48 | 47627.48 |  |  | 0
|  | Contract Total | [9 empty] | -47627.48 | 47627.48 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -47627.48 | 47627.48 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 2312.5 | 1510.2 | 1969.08 | [9 empty] | 5791.78
|  | Contract Total |  | 2312.5 | 1510.2 | 1969.08 | [9 empty] | 5791.78
| Temporary/Supplementary - Technical/Prof Total |  |  | 2312.5 | 1510.2 | 1969.08 | [9 empty] | 5791.78
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 350.9 | 510.62 | 399.3 |  |  | 239.58 | 146.08 | 91.3 | 223.86 | 146.08 |  |  | 2107.72
|  | Contract Total |  | 350.9 | 510.62 | 399.3 |  |  | 239.58 | 146.08 | 91.3 | 223.86 | 146.08 |  |  | 2107.72
| Temporary/Supplementary - Trade/Labor Total |  |  | 350.9 | 510.62 | 399.3 |  |  | 239.58 | 146.08 | 91.3 | 223.86 | 146.08 |  |  | 2107.72
| TRANSMISSION | Labor | Labor Entries <$5,000 | 15066.25 | 4969.67 | 5213.73 | 381.59 | 2928.3 | [6 empty] | 2849.25 | 31408.79
|  | Labor Total |  | 15066.25 | 4969.67 | 5213.73 | 381.59 | 2928.3 | [6 empty] | 2849.25 | 31408.79
| TRANSMISSION Total |  |  | 15066.25 | 4969.67 | 5213.73 | 381.59 | 2928.3 | [6 empty] | 2849.25 | 31408.79
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 8782.08 | 1155.13 |  |  | 1457.02 | 1104.29 | 542.85 | [5 empty] | 13041.37
|  | Labor Total |  | 8782.08 | 1155.13 |  |  | 1457.02 | 1104.29 | 542.85 | [5 empty] | 13041.37
| TRNS CAPITAL Total |  |  | 8782.08 | 1155.13 |  |  | 1457.02 | 1104.29 | 542.85 | [5 empty] | 13041.37
1. Project Support Total |  |  |  | 1131441.08 | -1675362.91 | -118978.81 | 1182644.47 | -234913.05 | -671732.61 | 296264.96 | 127380.01 | 196081.57 | 231926.38 | 79216.87 | 867589.05 | 1411557.01
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -117.16 | 117.16 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -117.16 | 117.16 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -117.16 | 117.16 |  |  | 0
| Material - Inventory | Material | Material - Inventory |  |  |  |  | 86416 |  |  |  | -12.67 | 12.67 |  |  | 86416
|  | Material Total | [5 empty] | 86416 |  |  |  | -12.67 | 12.67 |  |  | 86416
| Material - Inventory Total | [6 empty] | 86416 |  |  |  | -12.67 | 12.67 |  |  | 86416
| Material - Other | Material | Material - Other | 68.23 |  | 1459.03 | 1910.7 | 377.16 | 0.49 | -432.15 | -3225.65 | -14.9 | 1634.83 | 2601.14 | 6810.61 | 11189.49
|  | Material Total |  | 68.23 |  | 1459.03 | 1910.7 | 377.16 | 0.49 | -432.15 | -3225.65 | -14.9 | 1634.83 | 2601.14 | 6810.61 | 11189.49
| Material - Other Total |  |  | 68.23 |  | 1459.03 | 1910.7 | 377.16 | 0.49 | -432.15 | -3225.65 | -14.9 | 1634.83 | 2601.14 | 6810.61 | 11189.49
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | ONE SOURCE DISTRIBUTORS INC |  |  |  | 17022 | [8 empty] | 17022
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [9 empty] | 13490.92 | 29686.37 | 76847.8 | 120025.09
|  | Material - Direct Purchase Total |  |  |  |  | 17022 | [5 empty] | 13490.92 | 29686.37 | 76847.8 | 137047.09
| Pole Line Hdwe & Connectors-DP Total | [5 empty] | 17022 | [5 empty] | 13490.92 | 29686.37 | 76847.8 | 137047.09
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | ON-RAMP WIRELESS, INC. |  |  | 13015 | [9 empty] | 13015
|  | Material - Direct Purchase Total |  |  |  | 13015 | [9 empty] | 13015
| Power Systems, Batteries and Light-DP Total |  |  |  |  | 13015 | [9 empty] | 13015
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | 595 | [11 empty] | 595
|  | Material - Direct Purchase Total |  | 595 | [11 empty] | 595
| Steel / Fabricated / Structural-DP Total |  |  | 595 | [11 empty] | 595
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | -16508.7 | -115811.09 |  |  |  | -46075.09 | -178394.88
|  | Material - Direct Purchase Total | [7 empty] | -16508.7 | -115811.09 |  |  |  | -46075.09 | -178394.88
| Steel Lattice Towers (T/S)-DP Total | [8 empty] | -16508.7 | -115811.09 |  |  |  | -46075.09 | -178394.88
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 517.83 | 569.72 | 1087.55
|  | Material - Direct Purchase Total | [11 empty] | 517.83 | 569.72 | 1087.55
| Transportation & Mobile Equip-DP Total | [12 empty] | 517.83 | 569.72 | 1087.55
2. Material Total |  |  |  | 663.23 |  | 14474.03 | 18932.7 | 86793.16 | 0.49 | -16940.85 | -119036.74 | -144.73 | 15255.58 | 32805.34 | 38153.04 | 70955.25
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 15516.02 | 59384.71 | 8587.48 | 23166.72 | 6881.72 | 2546.6 | [6 empty] | 116083.25
|  | Contract Total |  | 15516.02 | 59384.71 | 8587.48 | 23166.72 | 6881.72 | 2546.6 | [6 empty] | 116083.25
| Construction Management Services Total |  |  | 15516.02 | 59384.71 | 8587.48 | 23166.72 | 6881.72 | 2546.6 | [6 empty] | 116083.25
| Construction Services - Other | Contract | Construction Services - Other | [7 empty] | 392183.14 | 570558.76 | 627493.46 |  |  | 1590235.36
|  |  | Contract Entries <$50,000 | 1042.1 | 41.5 | 1299.84 | 1388.71 | 188.02 | 186.83 | 13865 | 18356.94 |  |  |  |  | 36368.94
|  | Contract Total |  | 1042.1 | 41.5 | 1299.84 | 1388.71 | 188.02 | 186.83 | 13865 | 410540.08 | 570558.76 | 627493.46 |  |  | 1626604.3
| Construction Services - Other Total |  |  | 1042.1 | 41.5 | 1299.84 | 1388.71 | 188.02 | 186.83 | 13865 | 410540.08 | 570558.76 | 627493.46 |  |  | 1626604.3
| Electrical Construction, Transmission Li | Contract | HENKELS & MC COY INC | 1880066.75 | 2114016.65 | 661324.65 |  | 2556943.35 | 120447.25 |  |  | 678220.92 |  |  |  | 8011019.57
|  |  | WILSON UTILITY CONSTRUCTION | [10 empty] | 549094.88 | 435670.14 | 984765.02
|  | Contract Total |  | 1880066.75 | 2114016.65 | 661324.65 |  | 2556943.35 | 120447.25 |  |  | 678220.92 |  | 549094.88 | 435670.14 | 8995784.59
| Electrical Construction, Transmission Li Total |  |  | 1880066.75 | 2114016.65 | 661324.65 |  | 2556943.35 | 120447.25 |  |  | 678220.92 |  | 549094.88 | 435670.14 | 8995784.59
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 1463.5 | 1463.5
|  | Labor Total | [12 empty] | 1463.5 | 1463.5
| GRID OPS Total | [13 empty] | 1463.5 | 1463.5
| Labor - Other | Labor | Labor Entries <$5,000 | 860 | 967.6 | 970.17 | 930.78 | 1182.27 | 1031.53 | 523.2 | 1102.78 | 1154.75 | 1717.78 | 1055.35 | 892.61 | 12388.82
|  | Labor Total |  | 860 | 967.6 | 970.17 | 930.78 | 1182.27 | 1031.53 | 523.2 | 1102.78 | 1154.75 | 1717.78 | 1055.35 | 892.61 | 12388.82
| Labor - Other Total |  |  | 860 | 967.6 | 970.17 | 930.78 | 1182.27 | 1031.53 | 523.2 | 1102.78 | 1154.75 | 1717.78 | 1055.35 | 892.61 | 12388.82
| Other | Other | Other | 1240.26 | [11 empty] | 1240.26
|  | Other Total |  | 1240.26 | [11 empty] | 1240.26
| Other Total |  |  | 1240.26 | [11 empty] | 1240.26
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 3915.78 |  |  | 3915.78 |  | 689 |  | 689 |  |  |  |  | 9209.56
|  | Contract Total |  | 3915.78 |  |  | 3915.78 |  | 689 |  | 689 |  |  |  |  | 9209.56
| Short Term Equipment Rent Total |  |  | 3915.78 |  |  | 3915.78 |  | 689 |  | 689 |  |  |  |  | 9209.56
| TRANSMISSION | Labor | Labor Entries <$5,000 | 3287.51 | 2762.06 | 303.18 |  | 2225.95 |  |  | 464.24 |  |  |  |  | 9042.94
|  | Labor Total |  | 3287.51 | 2762.06 | 303.18 |  | 2225.95 |  |  | 464.24 |  |  |  |  | 9042.94
| TRANSMISSION Total |  |  | 3287.51 | 2762.06 | 303.18 |  | 2225.95 |  |  | 464.24 |  |  |  |  | 9042.94
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | [8 empty] | 305.9 |  |  |  | 305.9
|  | Labor Total | [9 empty] | 305.9 |  |  |  | 305.9
| TRNS CAPITAL Total | [10 empty] | 305.9 |  |  |  | 305.9
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | [7 empty] | 164 | 164 |  |  |  | 328
|  | Labor Total | [8 empty] | 164 | 164 |  |  |  | 328
| TSD-HERC - Rental Total | [9 empty] | 164 | 164 |  |  |  | 328
3. Construction Total |  |  |  | 1905928.42 | 2177172.52 | 672485.32 | 29401.99 | 2567421.31 | 124901.21 | 14388.2 | 412960.1 | 1250404.33 | 629211.24 | 550150.23 | 438026.25 | 10772451.12
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -193907.93 | 19424.86 | 15815.45 | 13788.96 | 15829.24 | 12884.17 | 27301.96 | 8646.23 | 20026.88 | -2035.56 | 14923.56 | 14077.78 | -33224.4
|  |  | MATERIAL MANAGEM |  |  |  |  | 16799.27 | [7 empty] | 16799.27
|  |  | PROCUREMENT TDBU | 19554.49 | 16511.19 | 7030.27 |  | 19796.93 |  |  |  |  | 14435.66 |  |  | 77328.54
|  |  | TDBU Vehicle Cost | 10628.84 | [11 empty] | 10628.84
|  |  | TRTP 10 Whirlwind Windhub 500 kV | 101050.67 | 164507.45 | 201471.62 | 240124.6 | 391497.2 | 147280.77 | 139333.02 | 157509.84 |  | 185895.34 | 123640.38 | 122249.82 | 1974560.71
|  |  | Work Package #1 | 16449.4 | 22211.9 | 21869.83 | 22466.22 | 17868.5 | 28406.2 | 5087.14 | 12578.78 | 5271.01 | 10864.38 | 50199.1 | 7494.75 | 220767.21
|  | Chargeback Total |  | -46224.53 | 222655.4 | 246187.17 | 276379.78 | 461791.14 | 188571.14 | 171722.12 | 178734.85 | 25297.89 | 209159.82 | 188763.04 | 143822.35 | 2266860.17
| Chargebacks Total |  |  | -46224.53 | 222655.4 | 246187.17 | 276379.78 | 461791.14 | 188571.14 | 171722.12 | 178734.85 | 25297.89 | 209159.82 | 188763.04 | 143822.35 | 2266860.17
| Labor - Other | Labor | Division Overhead | 157755.28 | 216407.8 | 34300.56 | 6696.23 | 134621.08 |  | 23846.03 | 6605.54 |  | 113523.96 |  |  | 693756.48
|  |  | Labor Entries <$5,000 | 8711.83 | 4793.56 | 7116.21 | 9023.11 | 4392.97 | 5613.36 | 4371.14 | 12712.46 | -18585.12 | 5477.64 | 6422.25 | 10757.71 | 60807.12
|  |  | Paid Absence | [9 empty] | 12180.52 |  |  | 12180.52
|  | Labor Total |  | 166467.11 | 221201.36 | 41416.77 | 15719.34 | 139014.05 | 5613.36 | 28217.17 | 19318 | -18585.12 | 131182.12 | 6422.25 | 10757.71 | 766744.12
| Labor - Other Total |  |  | 166467.11 | 221201.36 | 41416.77 | 15719.34 | 139014.05 | 5613.36 | 28217.17 | 19318 | -18585.12 | 131182.12 | 6422.25 | 10757.71 | 766744.12
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -33432.71 | 33432.71 |  |  | 0
|  | Overhead Total | [9 empty] | -33432.71 | 33432.71 |  |  | 0
| Overhead Correction Total | [10 empty] | -33432.71 | 33432.71 |  |  | 0
4. Allocated Total |  |  |  | 120242.58 | 443856.76 | 287603.94 | 292099.12 | 600805.19 | 194184.5 | 199939.29 | 198052.85 | -26719.94 | 373774.65 | 195185.29 | 154580.06 | 3033604.29
5. Corporate Overhead | Non Budget - Other | Non Budgeted | AFUDC - Debt/Equity |  |  | 332530.86 | -332530.86 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 161004.31 | 86481.68 | 48418.48 | 26360.54 | 309002.31 | 11350.31 | 30612.79 | 18524.63 | 62827.72 | 26438.53 | 19748.66 | 25266.31 | 826036.27
|  |  | Capitalized Overhead - Inj & Damages | 63.92 | 485.71 | 103.65 | 72.41 | 2932.73 | 33.52 | 50.66 | -91.12 | 1381.57 | -4170.75 | 134.05 | 145.85 | 1142.2
|  |  | Capitalized Overhead - P&B/Payroll Tax | 32299.01 | 39513.89 | 27558.24 | 38286.56 | 55967.52 | 22634.33 | 17156.8 | 14725.03 | -88130.23 | 44079.15 | 23087.71 | 37692.92 | 264870.93
|  |  | Corporate Overheads Correction |  |  |  |  | -1690268.28 | [7 empty] | -1690268.28
|  | Non Budgeted Total |  | 193367.24 | 126481.28 | 408611.23 | -267811.35 | -1322365.72 | 34018.16 | 47820.25 | 33158.54 | -23920.94 | 66346.93 | 42970.42 | 63105.08 | -598218.88
| Non Budget - Other Total |  |  | 193367.24 | 126481.28 | 408611.23 | -267811.35 | -1322365.72 | 34018.16 | 47820.25 | 33158.54 | -23920.94 | 66346.93 | 42970.42 | 63105.08 | -598218.88
5. Corporate Overhead Total |  |  |  | 193367.24 | 126481.28 | 408611.23 | -267811.35 | -1322365.72 | 34018.16 | 47820.25 | 33158.54 | -23920.94 | 66346.93 | 42970.42 | 63105.08 | -598218.88
Grand Total |  |  |  | 3351642.55 | 1072147.65 | 1264195.71 | 1255266.93 | 1697740.89 | -318628.25 | 541471.85 | 652514.76 | 1395700.29 | 1316514.78 | 900328.15 | 1561453.48 | 14690348.79

## 800208725
Pin: 6441 | Project: TRTP Segment 10
Order: 800208725 | 800208725- ACQ-TRTP Segment 10
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 76.64 |  | -0.29 |  |  |  | 0.99 |  |  |  | 0.14 |  | 77.48
|  | Contract Total |  | 76.64 |  | -0.29 |  |  |  | 0.99 |  |  |  | 0.14 |  | 77.48
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 76.64 |  | -0.29 |  |  |  | 0.99 |  |  |  | 0.14 |  | 77.48
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -14344.1 | 14344.1 |  |  | 0
|  | Contract Total | [9 empty] | -14344.1 | 14344.1 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -14344.1 | 14344.1 |  |  | 0
| HRealProp | Labor | Labor Entries <$5,000 | 551.31 | 1002.66 | 1364.65 | 1561.97 | 349.16 | 277.72 | 380.32 | 809.7 |  |  |  |  | 6297.49
|  | Labor Total |  | 551.31 | 1002.66 | 1364.65 | 1561.97 | 349.16 | 277.72 | 380.32 | 809.7 |  |  |  |  | 6297.49
| HRealProp Total |  |  | 551.31 | 1002.66 | 1364.65 | 1561.97 | 349.16 | 277.72 | 380.32 | 809.7 |  |  |  |  | 6297.49
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -0.1 | -1.77 |  | -0.79 | -2.07 | -0.06 | -0.11 | 15694.88 | -15694.88 | -94.67 |  | -99.57
|  | IMM Correction Total |  |  | -0.1 | -1.77 |  | -0.79 | -2.07 | -0.06 | -0.11 | 15694.88 | -15694.88 | -94.67 |  | -99.57
| IMM/Allocated - Correction Total |  |  |  | -0.1 | -1.77 |  | -0.79 | -2.07 | -0.06 | -0.11 | 15694.88 | -15694.88 | -94.67 |  | -99.57
| Information System Professional Services | Contract | Contract Entries <$50,000 | 6.38 |  |  |  | 98.86 |  | 15.95 | [5 empty] | 121.19
|  | Contract Total |  | 6.38 |  |  |  | 98.86 |  | 15.95 | [5 empty] | 121.19
| Information System Professional Services Total |  |  | 6.38 |  |  |  | 98.86 |  | 15.95 | [5 empty] | 121.19
| Labor - Other | Labor | Labor Entries <$5,000 | 213.65 | 302.34 | 124.45 | 163.27 | 177.26 | 28.92 | 23.91 | 31.06 | -1177.26 | 1328.01 | 98.65 | 401.97 | 1716.23
|  | Labor Total |  | 213.65 | 302.34 | 124.45 | 163.27 | 177.26 | 28.92 | 23.91 | 31.06 | -1177.26 | 1328.01 | 98.65 | 401.97 | 1716.23
| Labor - Other Total |  |  | 213.65 | 302.34 | 124.45 | 163.27 | 177.26 | 28.92 | 23.91 | 31.06 | -1177.26 | 1328.01 | 98.65 | 401.97 | 1716.23
| Other | Other | Other | 584.8 | 170 | 179.97 | 389.9 | 80 | 312.18 |  | -131.19 | -117 | 117 |  |  | 1585.66
|  | Other Total |  | 584.8 | 170 | 179.97 | 389.9 | 80 | 312.18 |  | -131.19 | -117 | 117 |  |  | 1585.66
| Other Total |  |  | 584.8 | 170 | 179.97 | 389.9 | 80 | 312.18 |  | -131.19 | -117 | 117 |  |  | 1585.66
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  | 80.48 | 107.3 | 48.99 | 134.13 | [7 empty] | 370.9
|  | Contract Total |  |  | 80.48 | 107.3 | 48.99 | 134.13 | [7 empty] | 370.9
| Temporary/Supplementary - Trade/Labor Total |  |  |  | 80.48 | 107.3 | 48.99 | 134.13 | [7 empty] | 370.9
1. Project Support Total |  |  |  | 1432.78 | 1555.38 | 1774.31 | 2164.13 | 838.62 | 616.75 | 421.11 | 709.46 | 56.52 | 94.23 | 4.12 | 401.97 | 10069.38
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 7.64 | 17.78 |  |  |  | 9.01 | [6 empty] | 34.43
|  | Material - Direct Purchase Total |  | 7.64 | 17.78 |  |  |  | 9.01 | [6 empty] | 34.43
| Transportation & Mobile Equip-DP Total |  |  | 7.64 | 17.78 |  |  |  | 9.01 | [6 empty] | 34.43
2. Material Total |  |  |  | 7.64 | 17.78 |  |  |  | 9.01 | [6 empty] | 34.43
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 72.1 | 794.5 | 713.66 | 443.53 | 732.84 | 691.04 | 732.12 |  | -94.67 | 150.67 | 1068.46 | 868.83 | 6173.08
|  |  | Law-TRTP Segment 10 - CRE |  | 6110.45 |  | 5409.32 | [8 empty] | 11519.77
|  | Chargeback Total |  | 72.1 | 6904.95 | 713.66 | 5852.85 | 732.84 | 691.04 | 732.12 |  | -94.67 | 150.67 | 1068.46 | 868.83 | 17692.85
| Chargebacks Total |  |  | 72.1 | 6904.95 | 713.66 | 5852.85 | 732.84 | 691.04 | 732.12 |  | -94.67 | 150.67 | 1068.46 | 868.83 | 17692.85
| Labor - Other | Labor | Labor Entries <$5,000 | 123.75 | 251.02 | 278.61 | 358.22 | 95.1 | 52.13 | 86.14 | 180.23 | -500.98 | 933.58 | 0.65 | 2.65 | 1861.1
|  | Labor Total |  | 123.75 | 251.02 | 278.61 | 358.22 | 95.1 | 52.13 | 86.14 | 180.23 | -500.98 | 933.58 | 0.65 | 2.65 | 1861.1
| Labor - Other Total |  |  | 123.75 | 251.02 | 278.61 | 358.22 | 95.1 | 52.13 | 86.14 | 180.23 | -500.98 | 933.58 | 0.65 | 2.65 | 1861.1
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -433.98 | -433.98
|  | Overhead Total | [12 empty] | -433.98 | -433.98
| Overhead Correction Total | [13 empty] | -433.98 | -433.98
4. Allocated Total |  |  |  | 195.85 | 7155.97 | 992.27 | 6211.07 | 827.94 | 743.17 | 818.26 | 180.23 | -595.65 | 1084.25 | 1069.11 | 437.5 | 19119.97
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 50050.22 | 3042.24 | [7 empty] | 53092.46
|  | Non Budgeted Total |  |  |  |  | 50050.22 | 3042.24 | [7 empty] | 53092.46
| Non Budget - Other Total | [5 empty] | 50050.22 | 3042.24 | [7 empty] | 53092.46
5. Corporate Overhead Total | [6 empty] | 50050.22 | 3042.24 | [7 empty] | 53092.46
Grand Total |  |  |  | 1636.27 | 8729.13 | 2766.58 | 58425.42 | 4708.8 | 1368.93 | 1239.37 | 889.69 | -539.13 | 1178.48 | 1073.23 | 839.47 | 82316.24

## TRTP Seg 11
WO | SumOfYTD2012 | Order | Project
800217381- I: TRTP 11-4: EAGLE ROCK-PARDEE 230KV: C | 528819.65 | 800217381 | TRTP Segment 11
800217366- I: TRTP 11-2: MESA-GOULD 220KV: STRING A | 1997814.54 | 800217366 | TRTP Segment 11
800217339- I: TRTP 11-1: MESA-VINCENT #1 500KV: CON | 7534249.4 | 800217339 | TRTP Segment 11
800208616- ACQ-TRTP Segment 11 | 3092927.55 | 800208616 | TRTP Segment 11

## 800217381
Pin: 6442 | Project: TRTP Segment 11
Order: 800217381 | 800217381- I: TRTP 11-4: EAGLE ROCK-PARDEE 230KV: C
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [6 empty] | 116.65 | [5 empty] | 116.65
|  | Labor Total | [7 empty] | 116.65 | [5 empty] | 116.65
| BP&FM Total | [8 empty] | 116.65 | [5 empty] | 116.65
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 842.36 | 842.36
|  | Labor Total | [12 empty] | 842.36 | 842.36
| ELEC SYS PLANNING Total | [13 empty] | 842.36 | 842.36
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 806.74 | [11 empty] | 806.74
|  | Labor Total |  | 806.74 | [11 empty] | 806.74
| ENG ADVANCEMENT Total |  |  | 806.74 | [11 empty] | 806.74
| ENGINEERING | Labor | Labor Entries <$5,000 |  | 425.84 | 834.05 | 1644.45 | 1687.58 | 2076.75 | 1243.52 | 1253.88 | 1707.64 | 1671.01 | 1336.47 |  | 13881.19
|  | Labor Total |  |  | 425.84 | 834.05 | 1644.45 | 1687.58 | 2076.75 | 1243.52 | 1253.88 | 1707.64 | 1671.01 | 1336.47 |  | 13881.19
| ENGINEERING Total |  |  |  | 425.84 | 834.05 | 1644.45 | 1687.58 | 2076.75 | 1243.52 | 1253.88 | 1707.64 | 1671.01 | 1336.47 |  | 13881.19
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 46119 | 20320.12 | 24221 | 25393 | 28445 |  | 56839.19 | 38829.87 | 4743.91 | 39.22 | 15632 | 16197.42 | 276779.73
|  |  | PAR ELECTRICAL CONTRACTORS INC | 150202.03 | [11 empty] | 150202.03
|  | Contract Total |  | 196321.03 | 20320.12 | 24221 | 25393 | 28445 |  | 56839.19 | 38829.87 | 4743.91 | 39.22 | 15632 | 16197.42 | 426981.76
| Engineering/Technical Professional Servi Total |  |  | 196321.03 | 20320.12 | 24221 | 25393 | 28445 |  | 56839.19 | 38829.87 | 4743.91 | 39.22 | 15632 | 16197.42 | 426981.76
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -1413.51 | -144.28 | -164.85 | -168.95 | -187.74 |  | -375.14 | -256.28 | -31.31 | -0.26 | -103.17 | -2845.49
|  | IMM Correction Total |  |  | -1413.51 | -144.28 | -164.85 | -168.95 | -187.74 |  | -375.14 | -256.28 | -31.31 | -0.26 | -103.17 | -2845.49
| IMM/Allocated - Correction Total |  |  |  | -1413.51 | -144.28 | -164.85 | -168.95 | -187.74 |  | -375.14 | -256.28 | -31.31 | -0.26 | -103.17 | -2845.49
| Labor - Other | Labor | Labor Entries <$5,000 | -53.33 | 53.33 | 9.59 | 10.54 | 261.1 | -374.1 | 61.09 | 18.32 | -22.77 | 187.55 | -229.45 | 155.8 | 77.67
|  | Labor Total |  | -53.33 | 53.33 | 9.59 | 10.54 | 261.1 | -374.1 | 61.09 | 18.32 | -22.77 | 187.55 | -229.45 | 155.8 | 77.67
| Labor - Other Total |  |  | -53.33 | 53.33 | 9.59 | 10.54 | 261.1 | -374.1 | 61.09 | 18.32 | -22.77 | 187.55 | -229.45 | 155.8 | 77.67
| Other | Other | Other | -2472 | -6640.25 | 3004.2 | 9320.11 | -15377.89 | 32600.74 | -30222.72 | -25840.68 | 2360.38 | 1508.84 | 19651.33 | 35527.09 | 23419.15
|  | Other Total |  | -2472 | -6640.25 | 3004.2 | 9320.11 | -15377.89 | 32600.74 | -30222.72 | -25840.68 | 2360.38 | 1508.84 | 19651.33 | 35527.09 | 23419.15
| Other Total |  |  | -2472 | -6640.25 | 3004.2 | 9320.11 | -15377.89 | 32600.74 | -30222.72 | -25840.68 | 2360.38 | 1508.84 | 19651.33 | 35527.09 | 23419.15
1. Project Support Total |  |  |  | 194602.44 | 12745.53 | 27924.56 | 36203.25 | 14846.84 | 34115.65 | 28037.73 | 13886.25 | 8532.88 | 3375.31 | 36390.09 | 52619.5 | 463280.03
2. Material | Material - Other | Material | Material - Other |  | 0.01 | 21.64 |  | -0.05 | 0.59 | [6 empty] | 22.19
|  | Material Total |  |  | 0.01 | 21.64 |  | -0.05 | 0.59 | [6 empty] | 22.19
| Material - Other Total |  |  |  | 0.01 | 21.64 |  | -0.05 | 0.59 | [6 empty] | 22.19
2. Material Total |  |  |  |  | 0.01 | 21.64 |  | -0.05 | 0.59 | [6 empty] | 22.19
3. Construction | Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  | 1540.24 | 756.61 | 205.2 | [8 empty] | 2502.05
|  | Contract Total |  |  | 1540.24 | 756.61 | 205.2 | [8 empty] | 2502.05
| Major Construction, Turnkey, Trans/Subs Total |  |  |  | 1540.24 | 756.61 | 205.2 | [8 empty] | 2502.05
3. Construction Total |  |  |  |  | 1540.24 | 756.61 | 205.2 | [8 empty] | 2502.05
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 3951.68 | 5852.93 | 8406.95 | 7955.77 | 5313.85 | 6396.94 | 482.17 | 312.38 | 136.44 | 107.13 | 182.22 | 180.57 | 39279.03
|  | Chargeback Total |  | 3951.68 | 5852.93 | 8406.95 | 7955.77 | 5313.85 | 6396.94 | 482.17 | 312.38 | 136.44 | 107.13 | 182.22 | 180.57 | 39279.03
| Chargebacks Total |  |  | 3951.68 | 5852.93 | 8406.95 | 7955.77 | 5313.85 | 6396.94 | 482.17 | 312.38 | 136.44 | 107.13 | 182.22 | 180.57 | 39279.03
| Labor - Other | Labor | Labor Entries <$5,000 | 11612.57 | 2057.73 | 1130.81 | 1244.71 | 1776.48 | 470.95 | 2750.81 | 1936.4 | 580.5 | 539.35 | 410.04 | 479.37 | 24989.72
|  | Labor Total |  | 11612.57 | 2057.73 | 1130.81 | 1244.71 | 1776.48 | 470.95 | 2750.81 | 1936.4 | 580.5 | 539.35 | 410.04 | 479.37 | 24989.72
| Labor - Other Total |  |  | 11612.57 | 2057.73 | 1130.81 | 1244.71 | 1776.48 | 470.95 | 2750.81 | 1936.4 | 580.5 | 539.35 | 410.04 | 479.37 | 24989.72
4. Allocated Total |  |  |  | 15564.25 | 7910.66 | 9537.76 | 9200.48 | 7090.33 | 6867.89 | 3232.98 | 2248.78 | 716.94 | 646.48 | 592.26 | 659.94 | 64268.75
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 10147.62 | 597.07 | [6 empty] | 11419.19 | 22163.88
|  |  | AFUDC - Debt/Equity |  |  | 10332.12 | -10332.12 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 11867.27 | 844.8 | 1255.99 | 1294.08 | 3105.71 | 299.21 | 2159.21 | 1187.3 | 308.64 | 64.93 | 458.01 | 498.42 | 23343.57
|  |  | Capitalized Overhead - Inj & Damages | 14.06 | 5.85 | 4.67 | 5.4 | 45.97 | 5.27 | 4.26 | 4.1 | 1.94 | 7.82 | 2.79 | 1.75 | 103.88
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1518.42 | 2217.26 | 2030.17 | 4900.57 | 5316.62 | 4179.14 | 1840.52 | 1034.21 | 2414.04 | 908.37 | 944.29 | 2334.66 | 29638.27
|  |  | Corporate Overheads Correction |  |  |  |  | -76502.97 | [7 empty] | -76502.97
|  | Non Budgeted Total |  | 13399.75 | 3067.91 | 13622.95 | 6015.55 | -67437.6 | 4483.62 | 4003.99 | 2225.61 | 2724.62 | 981.12 | 1405.09 | 14254.02 | -1253.37
| Non Budget - Other Total |  |  | 13399.75 | 3067.91 | 13622.95 | 6015.55 | -67437.6 | 4483.62 | 4003.99 | 2225.61 | 2724.62 | 981.12 | 1405.09 | 14254.02 | -1253.37
5. Corporate Overhead Total |  |  |  | 13399.75 | 3067.91 | 13622.95 | 6015.55 | -67437.6 | 4483.62 | 4003.99 | 2225.61 | 2724.62 | 981.12 | 1405.09 | 14254.02 | -1253.37
Grand Total |  |  |  | 223566.44 | 25264.35 | 51863.52 | 51624.48 | -45500.48 | 45467.75 | 35274.7 | 18360.64 | 11974.44 | 5002.91 | 38387.44 | 67533.46 | 528819.65

## 800217366
Pin: 6442 | Project: TRTP Segment 11
Order: 800217366 | 800217366- I: TRTP 11-2: MESA-GOULD 220KV: STRING A
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 |  |  | 73.35 |  |  |  |  | 51.33 |  |  |  |  | 124.68
|  | Labor Total |  |  |  | 73.35 |  |  |  |  | 51.33 |  |  |  |  | 124.68
| EAST GRID MGMTCENTER Total |  |  |  |  | 73.35 |  |  |  |  | 51.33 |  |  |  |  | 124.68
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 3340.95 | 3340.95
|  | Labor Total | [12 empty] | 3340.95 | 3340.95
| ELEC SYS PLANNING Total | [13 empty] | 3340.95 | 3340.95
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 319.4 | 622.22 | [10 empty] | 941.62
|  | Labor Total |  | 319.4 | 622.22 | [10 empty] | 941.62
| ENG ADVANCEMENT Total |  |  | 319.4 | 622.22 | [10 empty] | 941.62
| ENGINEERING | Labor | Labor Entries <$5,000 | 1976.96 | 2750.17 | 3396.97 | 3263.56 | 2747.33 | 3401.46 | 2038.33 | 3286.94 | 3866.52 | 3001.85 | 3045.97 |  | 32776.06
|  | Labor Total |  | 1976.96 | 2750.17 | 3396.97 | 3263.56 | 2747.33 | 3401.46 | 2038.33 | 3286.94 | 3866.52 | 3001.85 | 3045.97 |  | 32776.06
| ENGINEERING Total |  |  | 1976.96 | 2750.17 | 3396.97 | 3263.56 | 2747.33 | 3401.46 | 2038.33 | 3286.94 | 3866.52 | 3001.85 | 3045.97 |  | 32776.06
| Engineering/Technical Professional Servi | Contract | BURNS & MC DONNELL INC | 119912 |  | 62974 | 66021 | 73958 |  | 116559 | 93009 |  |  |  | 71946.29 | 604379.29
|  |  | Contract Entries <$50,000 |  | 52832.7 |  |  |  |  | 31223.89 | 9170.63 | 24767.23 | 12364.68 | 56025 | 8734.57 | 195118.7
|  |  | PAR ELECTRICAL CONTRACTORS INC | 150202.03 |  |  |  | 96000 | [7 empty] | 246202.03
|  | Contract Total |  | 270114.03 | 52832.7 | 62974 | 66021 | 169958 |  | 147782.89 | 102179.63 | 24767.23 | 12364.68 | 56025 | 80680.86 | 1045700.02
| Engineering/Technical Professional Servi Total |  |  | 270114.03 | 52832.7 | 62974 | 66021 | 169958 |  | 147782.89 | 102179.63 | 24767.23 | 12364.68 | 56025 | 80680.86 | 1045700.02
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -2112.24 | -1190.53 | -1114.92 | -1120.2 | -1132.87 | -29.41 | -975.37 | -696.91 | -823.46 | -81.61 | -369.77 | -9647.29
|  | IMM Correction Total |  |  | -2112.24 | -1190.53 | -1114.92 | -1120.2 | -1132.87 | -29.41 | -975.37 | -696.91 | -823.46 | -81.61 | -369.77 | -9647.29
| IMM/Allocated - Correction Total |  |  |  | -2112.24 | -1190.53 | -1114.92 | -1120.2 | -1132.87 | -29.41 | -975.37 | -696.91 | -823.46 | -81.61 | -369.77 | -9647.29
| Labor - Other | Labor | Labor Entries <$5,000 | -17.01 | 1392.74 | -955.83 | 5621.34 | -2815.82 | -2869.11 | -328.81 | 423.87 | 33 | 345.75 | -264.88 | 610.4 | 1175.64
|  | Labor Total |  | -17.01 | 1392.74 | -955.83 | 5621.34 | -2815.82 | -2869.11 | -328.81 | 423.87 | 33 | 345.75 | -264.88 | 610.4 | 1175.64
| Labor - Other Total |  |  | -17.01 | 1392.74 | -955.83 | 5621.34 | -2815.82 | -2869.11 | -328.81 | 423.87 | 33 | 345.75 | -264.88 | 610.4 | 1175.64
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | [8 empty] | 1315.53 |  |  |  | 1315.53
|  | Labor Total | [9 empty] | 1315.53 |  |  |  | 1315.53
| MAJOR PROJECT ORG Total | [10 empty] | 1315.53 |  |  |  | 1315.53
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  |  | 144.27 | [9 empty] | 144.27
|  | Labor Total |  |  |  | 144.27 | [9 empty] | 144.27
| NORTH GRIDMGMTCENTER Total |  |  |  |  | 144.27 | [9 empty] | 144.27
| Other | Other | Other | -13412.89 | 20574.51 | 145070.04 | -54809.08 | 495608.36 | 84829.5 | -708419.16 | -55363.93 | 7681 | 7075.3 | 52210.45 | 84597.23 | 65641.33
|  | Other Total |  | -13412.89 | 20574.51 | 145070.04 | -54809.08 | 495608.36 | 84829.5 | -708419.16 | -55363.93 | 7681 | 7075.3 | 52210.45 | 84597.23 | 65641.33
| Other Total |  |  | -13412.89 | 20574.51 | 145070.04 | -54809.08 | 495608.36 | 84829.5 | -708419.16 | -55363.93 | 7681 | 7075.3 | 52210.45 | 84597.23 | 65641.33
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 738.71 | 479.16 |  | 239.58 | [7 empty] | 5364 | 6821.45
|  | Contract Total |  | 738.71 | 479.16 |  | 239.58 | [7 empty] | 5364 | 6821.45
| Temporary/Supplementary - Trade/Labor Total |  |  | 738.71 | 479.16 |  | 239.58 | [7 empty] | 5364 | 6821.45
| TRANSMISSION | Labor | Labor Entries <$5,000 |  |  | 826.02 | 20877.13 | 7237.79 |  | 720.89 | 2476.89 | 1546.47 |  | 530.03 | 430.59 | 34645.81
|  | Labor Total |  |  |  | 826.02 | 20877.13 | 7237.79 |  | 720.89 | 2476.89 | 1546.47 |  | 530.03 | 430.59 | 34645.81
| TRANSMISSION Total |  |  |  |  | 826.02 | 20877.13 | 7237.79 |  | 720.89 | 2476.89 | 1546.47 |  | 530.03 | 430.59 | 34645.81
| TRNS CAPITAL | Labor | Labor Entries <$5,000 |  | 3423.68 | 3454.25 | 2471.32 | 154.89 |  | 745.45 | 257 |  |  |  |  | 10506.59
|  |  | Mgr-Prj/Prod |  |  | 5890.48 | [9 empty] | 5890.48
|  | Labor Total |  |  | 3423.68 | 9344.73 | 2471.32 | 154.89 |  | 745.45 | 257 |  |  |  |  | 16397.07
| TRNS CAPITAL Total |  |  |  | 3423.68 | 9344.73 | 2471.32 | 154.89 |  | 745.45 | 257 |  |  |  |  | 16397.07
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 | [6 empty] | 973 | 4056 |  |  |  |  | 5029
|  |  | TSD-Aircraft - Fixed / AIRCFT OPS-VRBL DISC | [7 empty] | 19580.4 |  |  |  |  | 19580.4
|  | Labor Total | [7 empty] | 973 | 23636.4 |  |  |  |  | 24609.4
| TSD-Aircraft - Fixed Total | [8 empty] | 973 | 23636.4 |  |  |  |  | 24609.4
1. Project Support Total |  |  |  | 259719.2 | 79962.94 | 219683.02 | 42569.93 | 671770.35 | 84228.98 | -556516.82 | 75972.76 | 38512.84 | 21964.12 | 111464.96 | 174654.26 | 1223986.54
2. Material | Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 4500 | [10 empty] | 4500
|  | Material - Direct Purchase Total |  |  | 4500 | [10 empty] | 4500
| Fuels, Chemicals & Petrochem-DP Total |  |  |  | 4500 | [10 empty] | 4500
| Insulators & Bushings-DP | Material - Direct Purchase | ONESOURCE SUPPLY SOLUTIONS, LLC |  | 64730.56 | [10 empty] | 64730.56
|  | Material - Direct Purchase Total |  |  | 64730.56 | [10 empty] | 64730.56
| Insulators & Bushings-DP Total |  |  |  | 64730.56 | [10 empty] | 64730.56
| Material - Other | Material | Material - Other | 2846.72 | 14152.05 | 11685.13 | 11681.88 | -14.35 | 483.35 | 0.01 | -0.79 | 0.23 | 0.18 |  | -17.01 | 40817.4
|  | Material Total |  | 2846.72 | 14152.05 | 11685.13 | 11681.88 | -14.35 | 483.35 | 0.01 | -0.79 | 0.23 | 0.18 |  | -17.01 | 40817.4
| Material - Other Total |  |  | 2846.72 | 14152.05 | 11685.13 | 11681.88 | -14.35 | 483.35 | 0.01 | -0.79 | 0.23 | 0.18 |  | -17.01 | 40817.4
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | 2494.2 | 347.4 | [5 empty] | -30.77 |  |  |  |  | 2810.83
|  |  | ONE SOURCE DISTRIBUTORS INC |  |  |  | 90645 | [8 empty] | 90645
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC |  | 53258.36 | 103627.52 | 12257.7 | [8 empty] | 169143.58
|  |  | Pole Line Hdwe & Connectors-DP | 5914.82 | [11 empty] | 5914.82
|  |  | PROGRESSIVE FRAME AND FABRICATION | 13664 | [11 empty] | 13664
|  | Material - Direct Purchase Total |  | 22073.02 | 53605.76 | 103627.52 | 102902.7 |  |  |  | -30.77 |  |  |  |  | 282178.23
| Pole Line Hdwe & Connectors-DP Total |  |  | 22073.02 | 53605.76 | 103627.52 | 102902.7 |  |  |  | -30.77 |  |  |  |  | 282178.23
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | [5 empty] | 4400 | [6 empty] | 4400
|  | Material - Direct Purchase Total | [6 empty] | 4400 | [6 empty] | 4400
| Steel / Fabricated / Structural-DP Total | [7 empty] | 4400 | [6 empty] | 4400
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 440.56 |  | 244.83 |  | 117.97 | [7 empty] | 803.36
|  | Material - Direct Purchase Total |  | 440.56 |  | 244.83 |  | 117.97 | [7 empty] | 803.36
| Transportation & Mobile Equip-DP Total |  |  | 440.56 |  | 244.83 |  | 117.97 | [7 empty] | 803.36
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | -742.4 | -742.4
|  | Material - Direct Purchase Total | [12 empty] | -742.4 | -742.4
| Wire, Cable & Bus Bar-DP Total | [13 empty] | -742.4 | -742.4
2. Material Total |  |  |  | 25360.3 | 136988.37 | 115557.48 | 114584.58 | 103.62 | 4883.35 | 0.01 | -31.56 | 0.23 | 0.18 |  | -759.41 | 396687.15
3. Construction | Electrical Construction, Transmission Li | Contract | PAR ELECTRICAL CONTRACTORS INC | [8 empty] | 100000 |  |  |  | 100000
|  | Contract Total | [9 empty] | 100000 |  |  |  | 100000
| Electrical Construction, Transmission Li Total | [10 empty] | 100000 |  |  |  | 100000
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 1694.17 | 1694.17
|  | Labor Total | [12 empty] | 1694.17 | 1694.17
| GRID OPS Total | [13 empty] | 1694.17 | 1694.17
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  | 4235.67 | 2080.66 | 564.3 | [8 empty] | 6880.63
|  | Contract Total |  |  | 4235.67 | 2080.66 | 564.3 | [8 empty] | 6880.63
| Major Construction, Turnkey, Trans/Subs Total |  |  |  | 4235.67 | 2080.66 | 564.3 | [8 empty] | 6880.63
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 |  | 841.26 | 8095.68 | [9 empty] | 8936.94
|  | Labor Total |  |  | 841.26 | 8095.68 | [9 empty] | 8936.94
| S/E SUBS MTCETST&APP Total |  |  |  | 841.26 | 8095.68 | [9 empty] | 8936.94
| Security / Protection Services | Contract | Contract Entries <$50,000 | [7 empty] | 2385.42 |  |  |  |  | 2385.42
|  | Contract Total | [8 empty] | 2385.42 |  |  |  |  | 2385.42
| Security / Protection Services Total | [9 empty] | 2385.42 |  |  |  |  | 2385.42
| TRANSMISSION | Labor | Labor Entries <$5,000 |  |  | 1876.52 | 21210.92 | 7689.07 |  | 2055.71 | 3724.33 | 666.26 |  | 482.49 | 487.52 | 38192.82
|  | Labor Total |  |  |  | 1876.52 | 21210.92 | 7689.07 |  | 2055.71 | 3724.33 | 666.26 |  | 482.49 | 487.52 | 38192.82
| TRANSMISSION Total |  |  |  |  | 1876.52 | 21210.92 | 7689.07 |  | 2055.71 | 3724.33 | 666.26 |  | 482.49 | 487.52 | 38192.82
3. Construction Total |  |  |  |  | 5076.93 | 12052.86 | 21775.22 | 7689.07 |  | 2055.71 | 6109.75 | 100666.26 |  | 482.49 | 2181.69 | 158089.98
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 9733.14 | 13453.36 | 9081.19 | 20295.11 | 10981.71 | 10362.87 | 5149.51 | 4593.17 | 5946.91 | 3729.4 | 5165.75 | 6905.71 | 105397.83
|  |  | Work Package # 2 |  | 6727.15 | 17488.73 | 6475.32 | 5928.33 | 8593.14 | [6 empty] | 45212.67
|  | Chargeback Total |  | 9733.14 | 20180.51 | 26569.92 | 26770.43 | 16910.04 | 18956.01 | 5149.51 | 4593.17 | 5946.91 | 3729.4 | 5165.75 | 6905.71 | 150610.5
| Chargebacks Total |  |  | 9733.14 | 20180.51 | 26569.92 | 26770.43 | 16910.04 | 18956.01 | 5149.51 | 4593.17 | 5946.91 | 3729.4 | 5165.75 | 6905.71 | 150610.5
| Labor - Other | Labor | Division Overhead | 6014.01 | 5015.19 | [10 empty] | 11029.2
|  |  | Labor Entries <$5,000 | 11684.82 | 13478.59 | 10768.52 | 12469.99 | 12442.19 | 345.27 | 7522.62 | 7287.01 | 6032.2 | 1609.06 | 1415.54 | 2768.94 | 87824.75
|  |  | Paid Absence |  |  |  | 9054.53 | [8 empty] | 9054.53
|  | Labor Total |  | 17698.83 | 18493.78 | 10768.52 | 21524.52 | 12442.19 | 345.27 | 7522.62 | 7287.01 | 6032.2 | 1609.06 | 1415.54 | 2768.94 | 107908.48
| Labor - Other Total |  |  | 17698.83 | 18493.78 | 10768.52 | 21524.52 | 12442.19 | 345.27 | 7522.62 | 7287.01 | 6032.2 | 1609.06 | 1415.54 | 2768.94 | 107908.48
4. Allocated Total |  |  |  | 27431.97 | 38674.29 | 37338.44 | 48294.95 | 29352.23 | 19301.28 | 12672.13 | 11880.18 | 11979.11 | 5338.46 | 6581.29 | 9674.65 | 258518.98
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 49183.15 | 3082.66 | [6 empty] | 53842.67 | 106108.48
|  |  | AFUDC - Debt/Equity |  |  | 49037.86 | -49037.86 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 18189.69 | 7035.38 | 8540.6 | 10057.49 | 17896.66 | 844.11 | 5851.92 | 4254.48 | 6427.62 | 523.03 | 1752.61 | 2840.04 | 84213.63
|  |  | Capitalized Overhead - Inj & Damages | 47.89 | 296.72 | 165.71 | 168.02 | 288.65 | 13.8 | 14.89 | 55.83 | 14.43 | 18.16 | 13.43 | 12.09 | 1109.62
|  |  | Capitalized Overhead - P&B/Payroll Tax | 4568.28 | 15131.88 | 25184.49 | 75195.77 | 29383.74 | 6411.85 | 7565.7 | 9248.41 | 12032.2 | 1997.99 | 3886.21 | 16431.09 | 207037.61
|  |  | Corporate Overheads Correction |  |  |  |  | -437937.45 | [7 empty] | -437937.45
|  | Non Budgeted Total |  | 22805.86 | 22463.98 | 82928.66 | 85566.57 | -387285.74 | 7269.76 | 13432.51 | 13558.72 | 18474.25 | 2539.18 | 5652.25 | 73125.89 | -39468.11
| Non Budget - Other Total |  |  | 22805.86 | 22463.98 | 82928.66 | 85566.57 | -387285.74 | 7269.76 | 13432.51 | 13558.72 | 18474.25 | 2539.18 | 5652.25 | 73125.89 | -39468.11
5. Corporate Overhead Total |  |  |  | 22805.86 | 22463.98 | 82928.66 | 85566.57 | -387285.74 | 7269.76 | 13432.51 | 13558.72 | 18474.25 | 2539.18 | 5652.25 | 73125.89 | -39468.11
Grand Total |  |  |  | 335317.33 | 283166.51 | 467560.46 | 312791.25 | 321629.53 | 115683.37 | -528356.46 | 107489.85 | 169632.69 | 29841.94 | 124180.99 | 258877.08 | 1997814.54

## 800217339
Pin: 6442 | Project: TRTP Segment 11
Order: 800217339 | 800217339- I: TRTP 11-1: MESA-VINCENT #1 500KV: CON
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [6 empty] | 87.87 | [5 empty] | 87.87
|  | Labor Total | [7 empty] | 87.87 | [5 empty] | 87.87
| BP&FM Total | [8 empty] | 87.87 | [5 empty] | 87.87
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  | 398.24 | [9 empty] | 398.24
|  | Contract Total |  |  |  | 398.24 | [9 empty] | 398.24
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  |  | 398.24 | [9 empty] | 398.24
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 675433.21 |  |  | 675433.21
|  |  | Contract Entries <$50,000 | [8 empty] | -675433.21 |  |  |  | -675433.21
|  | Contract Total | [9 empty] | -675433.21 | 675433.21 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -675433.21 | 675433.21 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 3377.58 | 3377.58
|  | Labor Total | [12 empty] | 3377.58 | 3377.58
| ELEC SYS PLANNING Total | [13 empty] | 3377.58 | 3377.58
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 2799.31 | 552.69 |  |  |  | 184.81 | 1011.19 | [5 empty] | 4548
|  | Labor Total |  | 2799.31 | 552.69 |  |  |  | 184.81 | 1011.19 | [5 empty] | 4548
| ENG ADVANCEMENT Total |  |  | 2799.31 | 552.69 |  |  |  | 184.81 | 1011.19 | [5 empty] | 4548
| ENGINEERING | Labor | Engineer | [8 empty] | 5789.52 |  |  |  | 5789.52
|  |  | Engineer Sr |  | 5058.62 | [10 empty] | 5058.62
|  |  | Labor Entries <$5,000 | 4005.55 | 1771.17 | 4388.96 | 1821.31 | 3186.28 | 4929.18 | 3824 | 9537.89 | 2981.84 | 7773.64 | 9967.87 |  | 54187.69
|  | Labor Total |  | 4005.55 | 6829.79 | 4388.96 | 1821.31 | 3186.28 | 4929.18 | 3824 | 9537.89 | 8771.36 | 7773.64 | 9967.87 |  | 65035.83
| ENGINEERING Total |  |  | 4005.55 | 6829.79 | 4388.96 | 1821.31 | 3186.28 | 4929.18 | 3824 | 9537.89 | 8771.36 | 7773.64 | 9967.87 |  | 65035.83
| Engineering/Technical Professional Servi | Contract | BUREAU VERITAS NORTH AMERICA INC | [6 empty] | 80678.26 |  |  | 116492.62 | 60055.5 |  | 257226.38
|  |  | BURNS & MC DONNELL INC | 258271 | 101310 | 135636 | 142199 | 159293 |  | 251050 | 200328 | 93316.71 | 104103 | 130754 | 392323.94 | 1968584.65
|  |  | Contract Entries <$50,000 |  | 38824.94 |  | 13992.02 | 85576.44 | 12002.75 | 170373.5 | 84437.83 |  | 104051.76 | 74978.13 | 107083.1 | 691320.47
|  |  | ELECTRICAL CONSULTANTS INC | [8 empty] | 64878.11 |  |  |  | 64878.11
|  |  | Engineering/Technical Professional Servi | [10 empty] | 87538 |  | 87538
|  |  | PAR ELECTRICAL CONTRACTORS INC | 150202.03 | [11 empty] | 150202.03
|  | Contract Total |  | 408473.03 | 140134.94 | 135636 | 156191.02 | 244869.44 | 12002.75 | 502101.76 | 284765.83 | 158194.82 | 324647.38 | 353325.63 | 499407.04 | 3219749.64
| Engineering/Technical Professional Servi Total |  |  | 408473.03 | 140134.94 | 135636 | 156191.02 | 244869.44 | 12002.75 | 502101.76 | 284765.83 | 158194.82 | 324647.38 | 353325.63 | 499407.04 | 3219749.64
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 6258.1 | 6982.97 | 8720.39 | 11193.53 | 6614.59 | 11592.64 | 11985.72 | 14497.6 | 4096.39 | 18480.23 | 11817.68 | 112239.84
|  | Contract Total |  |  | 6258.1 | 6982.97 | 8720.39 | 11193.53 | 6614.59 | 11592.64 | 11985.72 | 14497.6 | 4096.39 | 18480.23 | 11817.68 | 112239.84
| Environmental/Safety Professional Servic Total |  |  |  | 6258.1 | 6982.97 | 8720.39 | 11193.53 | 6614.59 | 11592.64 | 11985.72 | 14497.6 | 4096.39 | 18480.23 | 11817.68 | 112239.84
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 4875.79 | 1851.58 | 3710.37 | 3836.39 | 3729.1 | 3042.71 | 1086.56 | 4.06 | 784703.61 | -780287.51 | -8988.41 | -2503.02 | 15061.23
|  | IMM Correction Total |  | 4875.79 | 1851.58 | 3710.37 | 3836.39 | 3729.1 | 3042.71 | 1086.56 | 4.06 | 784703.61 | -780287.51 | -8988.41 | -2503.02 | 15061.23
| IMM/Allocated - Correction Total |  |  | 4875.79 | 1851.58 | 3710.37 | 3836.39 | 3729.1 | 3042.71 | 1086.56 | 4.06 | 784703.61 | -780287.51 | -8988.41 | -2503.02 | 15061.23
| Labor - Other | Labor | Labor - Other | [9 empty] | 16275.51 |  |  | 16275.51
|  |  | Labor Correction | [9 empty] | 80972.67 |  |  | 80972.67
|  |  | Labor Entries <$5,000 | 319.15 | 2247.19 | -871.74 | 282.88 | 755.05 | -261.58 | 176.21 | 577.17 | -28201.87 | -65100.71 | -1820.67 | 3506.74 | -88392.18
|  | Labor Total |  | 319.15 | 2247.19 | -871.74 | 282.88 | 755.05 | -261.58 | 176.21 | 577.17 | -28201.87 | 32147.47 | -1820.67 | 3506.74 | 8856
| Labor - Other Total |  |  | 319.15 | 2247.19 | -871.74 | 282.88 | 755.05 | -261.58 | 176.21 | 577.17 | -28201.87 | 32147.47 | -1820.67 | 3506.74 | 8856
| Legal Professional Services (OC & Attys) | Contract | Contract Entries <$50,000 |  |  |  | 1510 |  |  | 3688.75 | [5 empty] | 5198.75
|  | Contract Total |  |  |  |  | 1510 |  |  | 3688.75 | [5 empty] | 5198.75
| Legal Professional Services (OC & Attys) Total | [5 empty] | 1510 |  |  | 3688.75 | [5 empty] | 5198.75
| Other | Other | Other | -19929.77 | -37146.83 | 30747.18 | 45714.49 | -85521.9 | 182664.01 | -164999.98 | -56008.62 | 101455.59 | -9854.56 | 121712.11 | 115851.63 | 224683.35
|  | Other Total |  | -19929.77 | -37146.83 | 30747.18 | 45714.49 | -85521.9 | 182664.01 | -164999.98 | -56008.62 | 101455.59 | -9854.56 | 121712.11 | 115851.63 | 224683.35
| Other Total |  |  | -19929.77 | -37146.83 | 30747.18 | 45714.49 | -85521.9 | 182664.01 | -164999.98 | -56008.62 | 101455.59 | -9854.56 | 121712.11 | 115851.63 | 224683.35
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -43277.7 | 43277.7 |  |  | 0
|  | Contract Total | [9 empty] | -43277.7 | 43277.7 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -43277.7 | 43277.7 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 11296.47 | [11 empty] | 11296.47
|  | Contract Total |  | 11296.47 | [11 empty] | 11296.47
| Temporary/Supplementary - Technical/Prof Total |  |  | 11296.47 | [11 empty] | 11296.47
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 259.55 | 405.79 |  | 4510.28 | 135.52 | 419.98 | 146.08 | 237.38 | 11660 | 5446.08 | 146.08 | 5510.08 | 28876.82
|  | Contract Total |  | 259.55 | 405.79 |  | 4510.28 | 135.52 | 419.98 | 146.08 | 237.38 | 11660 | 5446.08 | 146.08 | 5510.08 | 28876.82
| Temporary/Supplementary - Trade/Labor Total |  |  | 259.55 | 405.79 |  | 4510.28 | 135.52 | 419.98 | 146.08 | 237.38 | 11660 | 5446.08 | 146.08 | 5510.08 | 28876.82
| TRANSMISSION | Labor | Labor Entries <$5,000 |  | 99.63 | [9 empty] | 1231.56 | 1331.19
|  | Labor Total |  |  | 99.63 | [9 empty] | 1231.56 | 1331.19
| TRANSMISSION Total |  |  |  | 99.63 | [9 empty] | 1231.56 | 1331.19
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 511.08 | [8 empty] | 5881.55 | 4052.58 |  | 10445.21
|  | Labor Total |  | 511.08 | [8 empty] | 5881.55 | 4052.58 |  | 10445.21
| TRNS CAPITAL Total |  |  | 511.08 | [8 empty] | 5881.55 | 4052.58 |  | 10445.21
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 |  |  |  | 1531.8 |  |  | 399.6 |  |  | 466.2 | 1198.8 | 1314.8 | 4911.2
|  | Labor Total |  |  |  |  | 1531.8 |  |  | 399.6 |  |  | 466.2 | 1198.8 | 1314.8 | 4911.2
| TSD-Aircraft - Fixed Total | [5 empty] | 1531.8 |  |  | 399.6 |  |  | 466.2 | 1198.8 | 1314.8 | 4911.2
1. Project Support Total |  |  |  | 412610.16 | 121232.88 | 180991.98 | 224118.56 | 178347.02 | 209596.45 | 359114.68 | 251099.43 | 332370.2 | 309027.55 | 498074.22 | 639514.09 | 3716097.22
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -182.14 | 182.14 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -182.14 | 182.14 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -182.14 | 182.14 |  |  | 0
| Material - Inventory | Material | Material - Inventory | [8 empty] | -11.53 | 11.53 | 1903.43 |  | 1903.43
|  | Material Total | [9 empty] | -11.53 | 11.53 | 1903.43 |  | 1903.43
| Material - Inventory Total | [10 empty] | -11.53 | 11.53 | 1903.43 |  | 1903.43
| Material - Other | Material | Material - Other | 169.67 | 2280.33 | 1261.52 | 335.22 | -11.41 | 42486.26 | 0.06 | 0.63 | -15.56 | 37047.21 | 802.95 | 2322.29 | 86679.17
|  | Material Total |  | 169.67 | 2280.33 | 1261.52 | 335.22 | -11.41 | 42486.26 | 0.06 | 0.63 | -15.56 | 37047.21 | 802.95 | 2322.29 | 86679.17
| Material - Other Total |  |  | 169.67 | 2280.33 | 1261.52 | 335.22 | -11.41 | 42486.26 | 0.06 | 0.63 | -15.56 | 37047.21 | 802.95 | 2322.29 | 86679.17
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 30.79 |  | 30.79
|  | Material - Direct Purchase Total | [11 empty] | 30.79 |  | 30.79
| Office & Office Support Products-DP Total | [12 empty] | 30.79 |  | 30.79
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Pole Line Hdwe & Connectors-DP | [11 empty] | 22724.21 | 22724.21
|  | Material - Direct Purchase Total | [12 empty] | 22724.21 | 22724.21
| Pole Line Hdwe & Connectors-DP Total | [13 empty] | 22724.21 | 22724.21
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | Steel Lattice Towers (T/S)-DP | [10 empty] | 7262.4 |  | 7262.4
|  | Material - Direct Purchase Total | [11 empty] | 7262.4 |  | 7262.4
| Steel Lattice Towers (T/S)-DP Total | [12 empty] | 7262.4 |  | 7262.4
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 2986 | [8 empty] | 2986
|  |  | VALMONT INDUSTRIES INC |  | 19768 | 9948 |  |  | 388130 | [6 empty] | 417846
|  | Material - Direct Purchase Total |  |  | 19768 | 9948 | 2986 |  | 388130 | [6 empty] | 420832
| Towers/Poles, Steel & Concrete-DP Total |  |  |  | 19768 | 9948 | 2986 |  | 388130 | [6 empty] | 420832
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 13.68 |  |  |  | 13.68
|  | Material - Direct Purchase Total | [9 empty] | 13.68 |  |  |  | 13.68
| Transportation & Mobile Equip-DP Total | [10 empty] | 13.68 |  |  |  | 13.68
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | NATIONAL STRAND PRODUCTS INC | [9 empty] | 52125 |  |  | 52125
|  |  | SOUTHWIRE COMPANY | [9 empty] | 256440 |  |  | 256440
|  | Material - Direct Purchase Total | [10 empty] | 308565 |  |  | 308565
| Wire, Cable & Bus Bar-DP Total | [11 empty] | 308565 |  |  | 308565
2. Material Total |  |  |  | 169.67 | 22048.33 | 11209.52 | 3321.22 | -11.41 | 430616.26 | 0.06 | 0.63 | -195.55 | 345805.88 | 9999.57 | 25046.5 | 848010.68
3. Construction | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  | 4094 |  |  |  | 2500 | 500 | -4094 | 4094 |  | 110.85 | 7204.85
|  | Contract Total |  |  |  | 4094 |  |  |  | 2500 | 500 | -4094 | 4094 |  | 110.85 | 7204.85
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  |  | 4094 |  |  |  | 2500 | 500 | -4094 | 4094 |  | 110.85 | 7204.85
| ENGINEERING | Labor | Labor Entries <$5,000 | [10 empty] | 162.87 |  | 162.87
|  | Labor Total | [11 empty] | 162.87 |  | 162.87
| ENGINEERING Total | [12 empty] | 162.87 |  | 162.87
| GRID OPS | Labor | Labor Entries <$5,000 | [8 empty] | 537.07 |  |  | 300.4 | 837.47
|  | Labor Total | [9 empty] | 537.07 |  |  | 300.4 | 837.47
| GRID OPS Total | [10 empty] | 537.07 |  |  | 300.4 | 837.47
| Labor - Other | Labor | ACQ/TRTP Seg. 11-Const/Mesa-Vincent |  | 6453.9 | 5355.14 | [9 empty] | 11809.04
|  |  | Labor Entries <$5,000 | 6320.5 | 4778.98 | 2880.13 | 4593.66 | 1950.52 | 4032.58 | 3041.93 | 3507.09 | 2564.45 | 3668.45 | 1599.37 | 4466.65 | 43404.31
|  | Labor Total |  | 6320.5 | 11232.88 | 8235.27 | 4593.66 | 1950.52 | 4032.58 | 3041.93 | 3507.09 | 2564.45 | 3668.45 | 1599.37 | 4466.65 | 55213.35
| Labor - Other Total |  |  | 6320.5 | 11232.88 | 8235.27 | 4593.66 | 1950.52 | 4032.58 | 3041.93 | 3507.09 | 2564.45 | 3668.45 | 1599.37 | 4466.65 | 55213.35
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  | 10011.59 | 4917.93 | 1333.8 | [8 empty] | 16263.32
|  | Contract Total |  |  | 10011.59 | 4917.93 | 1333.8 | [8 empty] | 16263.32
| Major Construction, Turnkey, Trans/Subs Total |  |  |  | 10011.59 | 4917.93 | 1333.8 | [8 empty] | 16263.32
| Material - Other | Material | Material - Other |  |  | 20.34 | [9 empty] | 20.34
|  | Material Total |  |  |  | 20.34 | [9 empty] | 20.34
| Material - Other Total |  |  |  |  | 20.34 | [9 empty] | 20.34
| Other | Other | Other |  |  |  |  | 1677.12 |  |  | 2080.75 |  |  |  |  | 3757.87
|  | Other Total | [5 empty] | 1677.12 |  |  | 2080.75 |  |  |  |  | 3757.87
| Other Total | [6 empty] | 1677.12 |  |  | 2080.75 |  |  |  |  | 3757.87
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 |  | 1417.53 | 3915.32 |  | 1934.01 |  |  | 925 | 925 | 925 | 925 | 925 | 11891.86
|  | Contract Total |  |  | 1417.53 | 3915.32 |  | 1934.01 |  |  | 925 | 925 | 925 | 925 | 925 | 11891.86
| Short Term Equipment Rent Total |  |  |  | 1417.53 | 3915.32 |  | 1934.01 |  |  | 925 | 925 | 925 | 925 | 925 | 11891.86
| TRANSMISSION | Labor | Labor Entries <$5,000 | [9 empty] | 1296.18 |  | 7445.87 | 8742.05
|  | Labor Total | [10 empty] | 1296.18 |  | 7445.87 | 8742.05
| TRANSMISSION Total | [11 empty] | 1296.18 |  | 7445.87 | 8742.05
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 1295.89 | 429.8 | [10 empty] | 1725.69
|  | Labor Total |  | 1295.89 | 429.8 | [10 empty] | 1725.69
| TRNS CAPITAL Total |  |  | 1295.89 | 429.8 | [10 empty] | 1725.69
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 |  | 41 | 41 |  | 82 |  |  |  | 41 | 41 |  | 41 | 287
|  | Labor Total |  |  | 41 | 41 |  | 82 |  |  |  | 41 | 41 |  | 41 | 287
| TSD-HERC - Rental Total |  |  |  | 41 | 41 |  | 82 |  |  |  | 41 | 41 |  | 41 | 287
3. Construction Total |  |  |  | 7616.39 | 23132.8 | 21223.86 | 5927.46 | 5643.65 | 4032.58 | 5541.93 | 7012.84 | -26.48 | 10024.63 | 2687.24 | 13289.77 | 106106.67
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -36583.25 | 32488.72 | 21319.78 | 19421.07 | 19452.61 | 15623.66 | 26126.79 | 18556.21 | 22342.7 | -186.95 | 16451.95 | 16026.92 | 171040.21
|  |  | Mesa-Vincent#1 500KV - Segment 11 |  |  |  |  | 6512.92 |  | 5363.33 |  |  | 20898.46 |  |  | 32774.71
|  |  | PGSP-TRTP Segment 11 MPO | [5 empty] | 5322.7 | [6 empty] | 5322.7
|  |  | PROCUREMENT TDBU | [9 empty] | 8988.41 |  |  | 8988.41
|  |  | TDBU Vehicle Cost | [9 empty] | 5430.4 |  |  | 5430.4
|  |  | TRTP 11 Mesa Vincent #1 500kV | 47398.37 | 93126.65 | 100581.28 | 105795.78 | 147701.66 | 88339.05 | 99172.24 | 66400.06 |  | 165686.83 | 163580.88 | 162453.15 | 1240235.95
|  |  | Work Package # 2 | 18636.37 | 30007.11 | 47020.06 | 42803.37 | 31705.02 | 35304.74 | 26216.65 | 19944.02 | 27831.76 | 15178.55 | 31991.16 | 38864.61 | 365503.42
|  | Chargeback Total |  | 29451.49 | 155622.48 | 168921.12 | 168020.22 | 205372.21 | 144590.15 | 156879.01 | 104900.29 | 50174.46 | 215995.7 | 212023.99 | 217344.68 | 1829295.8
| Chargebacks Total |  |  | 29451.49 | 155622.48 | 168921.12 | 168020.22 | 205372.21 | 144590.15 | 156879.01 | 104900.29 | 50174.46 | 215995.7 | 212023.99 | 217344.68 | 1829295.8
| Labor - Other | Labor | Division Overhead | 6090.42 |  |  |  |  | 11607.1 | 13925.93 |  |  | 72221.14 |  |  | 103844.59
|  |  | Labor Entries <$5,000 | 7593.91 | 9015.73 | 7157.1 | 6118.2 | 12268.88 | 7808.97 | 8890.58 | 14977.66 | -30061.73 | 3636.83 | 6365 | 11121.68 | 64892.81
|  |  | Paid Absence | [9 empty] | 19159.98 |  |  | 19159.98
|  | Labor Total |  | 13684.33 | 9015.73 | 7157.1 | 6118.2 | 12268.88 | 19416.07 | 22816.51 | 14977.66 | -30061.73 | 95017.95 | 6365 | 11121.68 | 187897.38
| Labor - Other Total |  |  | 13684.33 | 9015.73 | 7157.1 | 6118.2 | 12268.88 | 19416.07 | 22816.51 | 14977.66 | -30061.73 | 95017.95 | 6365 | 11121.68 | 187897.38
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -17578.29 | 17578.29 |  |  | 0
|  | Overhead Total | [9 empty] | -17578.29 | 17578.29 |  |  | 0
| Overhead Correction Total | [10 empty] | -17578.29 | 17578.29 |  |  | 0
4. Allocated Total |  |  |  | 43135.82 | 164638.21 | 176078.22 | 174138.42 | 217641.09 | 164006.22 | 179695.52 | 119877.95 | 2534.44 | 328591.94 | 218388.99 | 228466.36 | 2017193.18
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 126160.15 | 7834.22 | [6 empty] | 162912.52 | 296906.89
|  |  | Capitalized Overhead - A&G | 26981.78 | 10788.14 | 13053.16 | 12901.69 | 40593.73 | 22330.94 | 24913.32 | 12326.98 | 12815.03 | 25336.23 | 16110.33 | 22299.85 | 240451.18
|  |  | Capitalized Overhead - Inj & Damages | 0.66 | 147.93 | 82.72 | 50.7 | 475.73 | 637.6 | 66.08 | 75.62 | 723.56 | -809.44 | 110.12 | 177.64 | 1738.92
|  |  | Capitalized Overhead - P&B/Payroll Tax | 21295.87 | 40639.36 | 27383.62 | 39080.39 | 38277.68 | 37099.65 | 32046.51 | 28477.05 | -110535.65 | 67085.98 | 22726.87 | 64167.33 | 307744.66
|  | Non Budgeted Total |  | 48278.31 | 51575.43 | 40519.5 | 178192.93 | 87181.36 | 60068.19 | 57025.91 | 40879.65 | -96997.06 | 91612.77 | 38947.32 | 249557.34 | 846841.65
| Non Budget - Other Total |  |  | 48278.31 | 51575.43 | 40519.5 | 178192.93 | 87181.36 | 60068.19 | 57025.91 | 40879.65 | -96997.06 | 91612.77 | 38947.32 | 249557.34 | 846841.65
5. Corporate Overhead Total |  |  |  | 48278.31 | 51575.43 | 40519.5 | 178192.93 | 87181.36 | 60068.19 | 57025.91 | 40879.65 | -96997.06 | 91612.77 | 38947.32 | 249557.34 | 846841.65
Grand Total |  |  |  | 511810.35 | 382627.65 | 430023.08 | 585698.59 | 488801.71 | 868319.7 | 601378.1 | 418870.5 | 237685.55 | 1085062.77 | 768097.34 | 1155874.06 | 7534249.4

## 800208616
Pin: 6442 | Project: TRTP Segment 11
Order: 800208616 | 800208616- ACQ-TRTP Segment 11
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 487.94 |  | -1.81 |  |  |  | 6.32 |  |  |  | 0.9 |  | 493.35
|  | Contract Total |  | 487.94 |  | -1.81 |  |  |  | 6.32 |  |  |  | 0.9 |  | 493.35
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 487.94 |  | -1.81 |  |  |  | 6.32 |  |  |  | 0.9 |  | 493.35
| HRealProp | Labor | Labor Entries <$5,000 | 1943.98 | 1456.52 | 630.73 | 774.84 | 1024.4 | 1016.47 | 689.96 | 1060.47 | 488.24 | 484.63 | 406.76 | 938.62 | 10915.62
|  | Labor Total |  | 1943.98 | 1456.52 | 630.73 | 774.84 | 1024.4 | 1016.47 | 689.96 | 1060.47 | 488.24 | 484.63 | 406.76 | 938.62 | 10915.62
| HRealProp Total |  |  | 1943.98 | 1456.52 | 630.73 | 774.84 | 1024.4 | 1016.47 | 689.96 | 1060.47 | 488.24 | 484.63 | 406.76 | 938.62 | 10915.62
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -14.8 | -0.08 | -2.13 |  |  |  | -0.04 | -0.24 |  |  |  | -17.29
|  | IMM Correction Total |  |  | -14.8 | -0.08 | -2.13 |  |  |  | -0.04 | -0.24 |  |  |  | -17.29
| IMM/Allocated - Correction Total |  |  |  | -14.8 | -0.08 | -2.13 |  |  |  | -0.04 | -0.24 |  |  |  | -17.29
| Information System Professional Services | Contract | Contract Entries <$50,000 |  | 3.19 | 38.28 |  |  |  | 6.38 | [5 empty] | 47.85
|  | Contract Total |  |  | 3.19 | 38.28 |  |  |  | 6.38 | [5 empty] | 47.85
| Information System Professional Services Total |  |  |  | 3.19 | 38.28 |  |  |  | 6.38 | [5 empty] | 47.85
| Labor - Other | Labor | Labor Entries <$5,000 | 647.3 | 957.9 | 325.32 | 475.37 | 558.22 | 217.32 | 61.51 | 33.28 | 371.35 | 717.47 | 542.73 | 2540.59 | 7448.36
|  | Labor Total |  | 647.3 | 957.9 | 325.32 | 475.37 | 558.22 | 217.32 | 61.51 | 33.28 | 371.35 | 717.47 | 542.73 | 2540.59 | 7448.36
| Labor - Other Total |  |  | 647.3 | 957.9 | 325.32 | 475.37 | 558.22 | 217.32 | 61.51 | 33.28 | 371.35 | 717.47 | 542.73 | 2540.59 | 7448.36
| Other | Other | Other | 54623.96 | 2959850 | 2205.04 | 2030.43 | -267.93 | 1987.65 |  | 42.7 |  |  |  |  | 3020471.85
|  | Other Total |  | 54623.96 | 2959850 | 2205.04 | 2030.43 | -267.93 | 1987.65 |  | 42.7 |  |  |  |  | 3020471.85
| Other Total |  |  | 54623.96 | 2959850 | 2205.04 | 2030.43 | -267.93 | 1987.65 |  | 42.7 |  |  |  |  | 3020471.85
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1154.34 |  | 107.3 | [9 empty] | 1261.64
|  | Contract Total |  | 1154.34 |  | 107.3 | [9 empty] | 1261.64
| Temporary/Supplementary - Trade/Labor Total |  |  | 1154.34 |  | 107.3 | [9 empty] | 1261.64
1. Project Support Total |  |  |  | 58857.52 | 2962252.81 | 3304.78 | 3278.51 | 1314.69 | 3221.44 | 764.17 | 1136.41 | 859.35 | 1202.1 | 950.39 | 3479.21 | 3040621.38
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 8.89 | [10 empty] | 8.89
|  | Material - Direct Purchase Total |  |  | 8.89 | [10 empty] | 8.89
| Transportation & Mobile Equip-DP Total |  |  |  | 8.89 | [10 empty] | 8.89
2. Material Total |  |  |  |  | 8.89 | [10 empty] | 8.89
3. Construction | HRealProp | Labor | Labor Entries <$5,000 | 53.25 | 406.73 | [10 empty] | 459.98
|  | Labor Total |  | 53.25 | 406.73 | [10 empty] | 459.98
| HRealProp Total |  |  | 53.25 | 406.73 | [10 empty] | 459.98
3. Construction Total |  |  |  | 53.25 | 406.73 | [10 empty] | 459.98
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 14.8 | 0.08 | 2.13 |  |  |  | 0.04 | 0.24 |  |  |  |  | 17.29
|  | Chargeback Total |  | 14.8 | 0.08 | 2.13 |  |  |  | 0.04 | 0.24 |  |  |  |  | 17.29
| Chargebacks Total |  |  | 14.8 | 0.08 | 2.13 |  |  |  | 0.04 | 0.24 |  |  |  |  | 17.29
| Labor - Other | Labor | Labor Entries <$5,000 | 500.6 | 500.34 | 86.4 | 170.44 | 260.67 | 178.35 | 153.89 | 239.76 | 121.4 | 155.09 | 84.83 | 257.92 | 2709.69
|  | Labor Total |  | 500.6 | 500.34 | 86.4 | 170.44 | 260.67 | 178.35 | 153.89 | 239.76 | 121.4 | 155.09 | 84.83 | 257.92 | 2709.69
| Labor - Other Total |  |  | 500.6 | 500.34 | 86.4 | 170.44 | 260.67 | 178.35 | 153.89 | 239.76 | 121.4 | 155.09 | 84.83 | 257.92 | 2709.69
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -26 | -26
|  | Overhead Total | [12 empty] | -26 | -26
| Overhead Correction Total | [13 empty] | -26 | -26
4. Allocated Total |  |  |  | 515.4 | 500.42 | 88.53 | 170.44 | 260.67 | 178.35 | 153.93 | 240 | 121.4 | 155.09 | 84.83 | 231.92 | 2700.98
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 23400.44 | 1422.64 | [6 empty] | 24313.24 | 49136.32
|  | Non Budgeted Total |  |  |  |  | 23400.44 | 1422.64 | [6 empty] | 24313.24 | 49136.32
| Non Budget - Other Total | [5 empty] | 23400.44 | 1422.64 | [6 empty] | 24313.24 | 49136.32
5. Corporate Overhead Total | [6 empty] | 23400.44 | 1422.64 | [6 empty] | 24313.24 | 49136.32
Grand Total |  |  |  | 59426.17 | 2963168.85 | 3393.31 | 26849.39 | 2998 | 3399.79 | 918.1 | 1376.41 | 980.75 | 1357.19 | 1035.22 | 28024.37 | 3092927.55

## EITP
WO | SumOfYTD2012 | Order | Project
900344623- Eldorado-Ivanpah No. 2 (Nevada) | 74629589.6 | 900344623 | Eldorado-Ivanpah (EITP)
900344621- Eldorado-Ivanpah No. 2 (California) | 11993222.6 | 900344621 | Eldorado-Ivanpah (EITP)
900316934- I: Eldorado SS Upgrades, EITP | 4363673.4 | 900316934 | Eldorado-Ivanpah (EITP)
900316933- Ivanpah: Construct a New Substation, EIT | 25867129.3 | 900316933 | Eldorado-Ivanpah (EITP)
800586667- ACQ/Eldorado-Ivanpah Project: Primm Priv | 38509.55 | 800586667 | Eldorado-Ivanpah (EITP)
800063786- 8363-8201--Ivanpah: Licensing Phase - Si | 274130.4 | 800063786 | Eldorado-Ivanpah (EITP)

## 900344623
Pin: 6551 | Project: Eldorado-Ivanpah (EITP)
Order: 900344623 | 900344623- Eldorado-Ivanpah No. 2 (Nevada)
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 45.17 |  | 64.42 |  |  |  |  | 109.59
|  | Labor Total | [6 empty] | 45.17 |  | 64.42 |  |  |  |  | 109.59
| BP&FM Total | [7 empty] | 45.17 |  | 64.42 |  |  |  |  | 109.59
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 | [8 empty] | 2232.5 |  |  |  | 2232.5
|  | Contract Total | [9 empty] | 2232.5 |  |  |  | 2232.5
| Building/Facility Repairs & Maintenance Total | [10 empty] | 2232.5 |  |  |  | 2232.5
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 |  |  |  |  | 58.5 | [7 empty] | 58.5
|  | Contract Total | [5 empty] | 58.5 | [7 empty] | 58.5
| Cleaning / Janitorial Services Total | [6 empty] | 58.5 | [7 empty] | 58.5
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  | 127.75 | 317.36 |  |  | 351.84 |  |  | 156.18 |  | 953.13
|  | Contract Total |  |  |  |  | 127.75 | 317.36 |  |  | 351.84 |  |  | 156.18 |  | 953.13
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [5 empty] | 127.75 | 317.36 |  |  | 351.84 |  |  | 156.18 |  | 953.13
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 3708398.05 |  |  | 3708398.05
|  |  | Contract Entries <$50,000 | [8 empty] | -3708398.05 |  |  |  | -3708398.05
|  | Contract Total | [9 empty] | -3708398.05 | 3708398.05 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -3708398.05 | 3708398.05 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | 16167.2 | 25818.88 | 41615.7 |  | 49654.69 | 2473.22 | 341 | 20515.37 | 9966.42 | 11824.09 | 9053.01 | 6276.79 | 193706.37
|  | Contract Total |  | 16167.2 | 25818.88 | 41615.7 |  | 49654.69 | 2473.22 | 341 | 20515.37 | 9966.42 | 11824.09 | 9053.01 | 6276.79 | 193706.37
| Contract Consult/Contract Ord to Ord Total |  |  | 16167.2 | 25818.88 | 41615.7 |  | 49654.69 | 2473.22 | 341 | 20515.37 | 9966.42 | 11824.09 | 9053.01 | 6276.79 | 193706.37
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 21071.78 | 21071.78
|  | Labor Total | [12 empty] | 21071.78 | 21071.78
| ELEC SYS PLANNING Total | [13 empty] | 21071.78 | 21071.78
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | [7 empty] | 708.35 |  |  | 436.22 | 453.94 | 1598.51
|  | Labor Total | [8 empty] | 708.35 |  |  | 436.22 | 453.94 | 1598.51
| ENG ADVANCEMENT Total | [9 empty] | 708.35 |  |  | 436.22 | 453.94 | 1598.51
| ENGINEERING | Labor | Anly Prg/Prj |  |  | 6258.28 | [9 empty] | 6258.28
|  |  | Engineer Sr | 5090.04 | 5372.82 | 11248.36 | 5998.86 | 5713.2 | 5998.86 |  | 5427.54 |  |  | 5427.54 |  | 50277.22
|  |  | Labor Entries <$5,000 | 16388.54 | 9825.8 | 9842.48 | 21237.51 | 22197.4 | 26112.6 | 28703.43 | 25586.15 | 25651.26 | 25606.92 | 23646.26 | 825.68 | 235624.03
|  |  | Mgr-Prj/Prod |  | 5757.84 | 7328.16 | 5829.12 |  | 7153.92 |  | 5829.12 | 5299.2 |  |  |  | 37197.36
|  | Labor Total |  | 21478.58 | 20956.46 | 34677.28 | 33065.49 | 27910.6 | 39265.38 | 28703.43 | 36842.81 | 30950.46 | 25606.92 | 29073.8 | 825.68 | 329356.89
| ENGINEERING Total |  |  | 21478.58 | 20956.46 | 34677.28 | 33065.49 | 27910.6 | 39265.38 | 28703.43 | 36842.81 | 30950.46 | 25606.92 | 29073.8 | 825.68 | 329356.89
| Engineering/Technical Professional Servi | Contract | BUREAU VERITAS NORTH AMERICA INC | [10 empty] | 137944.8 | 276348.2 | 414293
|  |  | Contract Entries <$50,000 |  | 14352.61 |  | 37235.36 | 18690.5 | 17661 | 31604 | 13909.37 | 1500 | 37326.9 | 68062.81 | 37967.35 | 278309.9
|  |  | POWER ENGINEERS INCORPORATED |  | 86105 | [5 empty] | 77958 |  |  |  |  | 164063
|  | Contract Total |  |  | 100457.61 |  | 37235.36 | 18690.5 | 17661 | 31604 | 91867.37 | 1500 | 37326.9 | 206007.61 | 314315.55 | 856665.9
| Engineering/Technical Professional Servi Total |  |  |  | 100457.61 |  | 37235.36 | 18690.5 | 17661 | 31604 | 91867.37 | 1500 | 37326.9 | 206007.61 | 314315.55 | 856665.9
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 17959.97 |  | 34498.15 | 50213.66 | 22941.25 | 25517.37 | 0 | 24094.65 | 21547.32 | 14992.02 | 16330.2 | 18326.85 | 246421.44
|  | Contract Total |  | 17959.97 |  | 34498.15 | 50213.66 | 22941.25 | 25517.37 | 0 | 24094.65 | 21547.32 | 14992.02 | 16330.2 | 18326.85 | 246421.44
| Environmental/Safety Professional Servic Total |  |  | 17959.97 |  | 34498.15 | 50213.66 | 22941.25 | 25517.37 | 0 | 24094.65 | 21547.32 | 14992.02 | 16330.2 | 18326.85 | 246421.44
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 26352.43 | 12434.49 | 25554.83 | 14633.61 | 22925.71 | 25258.71 | 20034.81 | 9878.31 | 5569968.88 | -5536971.43 | -40362.6 | -31127.38 | 118580.37
|  | IMM Correction Total |  | 26352.43 | 12434.49 | 25554.83 | 14633.61 | 22925.71 | 25258.71 | 20034.81 | 9878.31 | 5569968.88 | -5536971.43 | -40362.6 | -31127.38 | 118580.37
| IMM/Allocated - Correction Total |  |  | 26352.43 | 12434.49 | 25554.83 | 14633.61 | 22925.71 | 25258.71 | 20034.81 | 9878.31 | 5569968.88 | -5536971.43 | -40362.6 | -31127.38 | 118580.37
| ITBI (HCC) | Labor | Labor Entries <$5,000 | 338.85 | [11 empty] | 338.85
|  | Labor Total |  | 338.85 | [11 empty] | 338.85
| ITBI (HCC) Total |  |  | 338.85 | [11 empty] | 338.85
| Labor - Other | Labor | Labor - Other | [9 empty] | 43474.83 |  | 8673.84 | 52148.67
|  |  | Labor Correction | [9 empty] | 216292.77 |  |  | 216292.77
|  |  | Labor Entries <$5,000 | 2283.11 | 7205.91 | -1954.48 | 910.83 | 7838.96 | -10855.64 | 540.81 | 2051.24 | 509013.95 | -761691.92 | -6135.18 | 4898.09 | -245894.32
|  | Labor Total |  | 2283.11 | 7205.91 | -1954.48 | 910.83 | 7838.96 | -10855.64 | 540.81 | 2051.24 | 509013.95 | -501924.32 | -6135.18 | 13571.93 | 22547.12
| Labor - Other Total |  |  | 2283.11 | 7205.91 | -1954.48 | 910.83 | 7838.96 | -10855.64 | 540.81 | 2051.24 | 509013.95 | -501924.32 | -6135.18 | 13571.93 | 22547.12
| Legal Professional Services (OC & Attys) | Contract | Contract Entries <$50,000 |  |  |  | 5672.5 |  |  |  | 3032 |  | 0 |  |  | 8704.5
|  | Contract Total |  |  |  |  | 5672.5 |  |  |  | 3032 |  | 0 |  |  | 8704.5
| Legal Professional Services (OC & Attys) Total | [5 empty] | 5672.5 |  |  |  | 3032 |  | 0 |  |  | 8704.5
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 1424.71 | 1035.66 | 3507.45 | 2686.04 | 3273.91 | 4408.15 | 2327.54 | 3139.38 | 2966.98 | 3333.95 | 2571.42 | 2915.82 | 33591.01
|  | Labor Total |  | 1424.71 | 1035.66 | 3507.45 | 2686.04 | 3273.91 | 4408.15 | 2327.54 | 3139.38 | 2966.98 | 3333.95 | 2571.42 | 2915.82 | 33591.01
| MAJOR PROJECT ORG Total |  |  | 1424.71 | 1035.66 | 3507.45 | 2686.04 | 3273.91 | 4408.15 | 2327.54 | 3139.38 | 2966.98 | 3333.95 | 2571.42 | 2915.82 | 33591.01
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 |  |  | 184.7 | 756.93 | [8 empty] | 941.63
|  | Labor Total |  |  |  | 184.7 | 756.93 | [8 empty] | 941.63
| NORTH GRIDMGMTCENTER Total |  |  |  |  | 184.7 | 756.93 | [8 empty] | 941.63
| Other | Other | Other | 4113.91 | 315399.25 | -220167.68 | -64679.32 | 36289.72 | 61572.14 | 24865.3 | 48288.12 | 267649.02 | 10844465.47 | 4028861.4 | 12843521.71 | 28190179.04
|  | Other Total |  | 4113.91 | 315399.25 | -220167.68 | -64679.32 | 36289.72 | 61572.14 | 24865.3 | 48288.12 | 267649.02 | 10844465.47 | 4028861.4 | 12843521.71 | 28190179.04
| Other Total |  |  | 4113.91 | 315399.25 | -220167.68 | -64679.32 | 36289.72 | 61572.14 | 24865.3 | 48288.12 | 267649.02 | 10844465.47 | 4028861.4 | 12843521.71 | 28190179.04
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 |  |  |  |  | 816.84 |  | 1222.02 | [5 empty] | 2038.86
|  | Labor Total | [5 empty] | 816.84 |  | 1222.02 | [5 empty] | 2038.86
| TEC SRVCS SUMMARY Total | [6 empty] | 816.84 |  | 1222.02 | [5 empty] | 2038.86
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -73288.34 |  |  |  | -73288.34
|  |  | Temporary / Supplemental - Correction | [9 empty] | 73288.34 |  |  | 73288.34
|  | Contract Total | [9 empty] | -73288.34 | 73288.34 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -73288.34 | 73288.34 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 12284.86 | 12069.81 | 7810.26 | 7325.88 | 752.64 |  |  | 2871.02 | 13564.19 | 3593.28 | 11137.34 | 6507.66 | 77916.94
|  | Contract Total |  | 12284.86 | 12069.81 | 7810.26 | 7325.88 | 752.64 |  |  | 2871.02 | 13564.19 | 3593.28 | 11137.34 | 6507.66 | 77916.94
| Temporary/Supplementary - Technical/Prof Total |  |  | 12284.86 | 12069.81 | 7810.26 | 7325.88 | 752.64 |  |  | 2871.02 | 13564.19 | 3593.28 | 11137.34 | 6507.66 | 77916.94
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1488.82 | 3493.39 | 1347.63 | 1772.73 | 555.21 | 3206.08 | 292.16 |  | 436.58 | 355.86 |  | 786 | 13734.46
|  | Contract Total |  | 1488.82 | 3493.39 | 1347.63 | 1772.73 | 555.21 | 3206.08 | 292.16 |  | 436.58 | 355.86 |  | 786 | 13734.46
| Temporary/Supplementary - Trade/Labor Total |  |  | 1488.82 | 3493.39 | 1347.63 | 1772.73 | 555.21 | 3206.08 | 292.16 |  | 436.58 | 355.86 |  | 786 | 13734.46
| TRANSMISSION | Labor | Labor Entries <$5,000 | [9 empty] | 1322.08 |  | 6064.12 | 7386.2
|  | Labor Total | [10 empty] | 1322.08 |  | 6064.12 | 7386.2
| TRANSMISSION Total | [11 empty] | 1322.08 |  | 6064.12 | 7386.2
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 9323.09 | 9099.22 | 5970.35 | 9931.38 | 9665.16 | 5691.81 | 4148.58 | 6996.02 | 6169.7 | 3581.21 | 7768.87 | -401.89 | 77943.5
|  |  | Mgr-Prj/Prod | 5915.87 | 11679.4 | 21810.06 | 6195.6 |  | 6608.64 |  | 6608.64 | 7434.72 | 10636.12 | 6312.2 |  | 83201.25
|  | Labor Total |  | 15238.96 | 20778.62 | 27780.41 | 16126.98 | 9665.16 | 12300.45 | 4148.58 | 13604.66 | 13604.42 | 14217.33 | 14081.07 | -401.89 | 161144.75
| TRNS CAPITAL Total |  |  | 15238.96 | 20778.62 | 27780.41 | 16126.98 | 9665.16 | 12300.45 | 4148.58 | 13604.66 | 13604.42 | 14217.33 | 14081.07 | -401.89 | 161144.75
| TSD-Aircraft - Fixed | Labor | Labor Entries <$5,000 |  |  |  | 4473.4 | 2930.4 |  |  |  |  | 3428.2 | 4595.4 |  | 15427.4
|  | Labor Total |  |  |  |  | 4473.4 | 2930.4 |  |  |  |  | 3428.2 | 4595.4 |  | 15427.4
| TSD-Aircraft - Fixed Total | [5 empty] | 4473.4 | 2930.4 |  |  |  |  | 3428.2 | 4595.4 |  | 15427.4
1. Project Support Total |  |  |  | 119131.4 | 519650.08 | -45145.75 | 110321.84 | 204621.45 | 180852.03 | 114079.65 | 257309.54 | 2661714.33 | 8703256.74 | 4275805.87 | 13203108.56 | 30304705.74
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 285.7 |  | 214.99 | 828.6 | 1496.02 | 67.52 | 476.59 |  | 82.78 | 3452.2
|  | Material - Direct Purchase Total |  |  |  |  | 285.7 |  | 214.99 | 828.6 | 1496.02 | 67.52 | 476.59 |  | 82.78 | 3452.2
| Building, Shop & Industrial Products/Eqp Total | [5 empty] | 285.7 |  | 214.99 | 828.6 | 1496.02 | 67.52 | 476.59 |  | 82.78 | 3452.2
| Insulators & Bushings-DP | Material - Direct Purchase | ONESOURCE SUPPLY SOLUTIONS, LLC | [8 empty] | 210077.15 |  | 100318.78 |  | 310395.93
|  | Material - Direct Purchase Total | [9 empty] | 210077.15 |  | 100318.78 |  | 310395.93
| Insulators & Bushings-DP Total | [10 empty] | 210077.15 |  | 100318.78 |  | 310395.93
| Labor - Other | Labor | Labor Entries <$5,000 |  | 7188.35 | -1367.66 | [9 empty] | 5820.69
|  |  | SUBORDER*IT-Eldorado-Ivanpah OPGW Cable | [9 empty] | 30464.12 |  |  | 30464.12
|  | Labor Total |  |  | 7188.35 | -1367.66 | [6 empty] | 30464.12 |  |  | 36284.81
| Labor - Other Total |  |  |  | 7188.35 | -1367.66 | [6 empty] | 30464.12 |  |  | 36284.81
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -1197.44 | 1197.44 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -1197.44 | 1197.44 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -1197.44 | 1197.44 |  |  | 0
| Material - Inventory | Material | Material - Inventory | [6 empty] | 6983.03 |  | -1 | 1 |  |  | 6983.03
|  | Material Total | [7 empty] | 6983.03 |  | -1 | 1 |  |  | 6983.03
| Material - Inventory Total | [8 empty] | 6983.03 |  | -1 | 1 |  |  | 6983.03
| Material - Other | Material | Material - Other | 224318.71 | 36076.6 | 163551.11 | 232.18 | -4.22 | 45.59 | 132934.71 | 8324.82 | 103646.07 | 271836.07 | 388926.85 | 201167.12 | 1531055.61
|  | Material Total |  | 224318.71 | 36076.6 | 163551.11 | 232.18 | -4.22 | 45.59 | 132934.71 | 8324.82 | 103646.07 | 271836.07 | 388926.85 | 201167.12 | 1531055.61
| Material - Other Total |  |  | 224318.71 | 36076.6 | 163551.11 | 232.18 | -4.22 | 45.59 | 132934.71 | 8324.82 | 103646.07 | 271836.07 | 388926.85 | 201167.12 | 1531055.61
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 1170.09 | 2879.22 | 95.28 |  |  |  | 536.47 | 398.77 | 801.67 |  |  | 5881.5
|  | Material - Direct Purchase Total |  |  | 1170.09 | 2879.22 | 95.28 |  |  |  | 536.47 | 398.77 | 801.67 |  |  | 5881.5
| Office & Office Support Products-DP Total |  |  |  | 1170.09 | 2879.22 | 95.28 |  |  |  | 536.47 | 398.77 | 801.67 |  |  | 5881.5
| Other Consumables-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 1437.14 |  | 1437.14
|  | Material - Direct Purchase Total | [11 empty] | 1437.14 |  | 1437.14
| Other Consumables-DP Total | [12 empty] | 1437.14 |  | 1437.14
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 3642.4 |  |  | 3642.4
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [10 empty] | 1520480.36 | 217396.89 | 1737877.25
|  |  | Pole Line Hdwe & Connectors-DP | [11 empty] | 31195.2 | 31195.2
|  | Material - Direct Purchase Total | [10 empty] | 3642.4 | 1520480.36 | 248592.09 | 1772714.85
| Pole Line Hdwe & Connectors-DP Total | [11 empty] | 3642.4 | 1520480.36 | 248592.09 | 1772714.85
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | FORMET | [6 empty] | 1245786.12 | 69399.6 | 260293.8 | 2189868.66 | 2539584.61 |  | 6304932.79
|  |  | Material Entries <$5,000 | [9 empty] | -299432.05 | -262399.11 |  | -561831.16
|  |  | Steel Lattice Towers (T/S)-DP | [8 empty] | 41367.18 | 50133.86 | 350744.64 | 1284255.53 | 1726501.21
|  | Material - Direct Purchase Total | [7 empty] | 1245786.12 | 69399.6 | 301660.98 | 1940570.47 | 2627930.14 | 1284255.53 | 7469602.84
| Steel Lattice Towers (T/S)-DP Total | [8 empty] | 1245786.12 | 69399.6 | 301660.98 | 1940570.47 | 2627930.14 | 1284255.53 | 7469602.84
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | -155008 | -14375 |  | -169383
|  |  | VALMONT INDUSTRIES INC | [8 empty] | 221440 | 442880 | 43125 |  | 707445
|  | Material - Direct Purchase Total | [9 empty] | 221440 | 287872 | 28750 |  | 538062
| Towers/Poles, Steel & Concrete-DP Total | [10 empty] | 221440 | 287872 | 28750 |  | 538062
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 1687.86 | 26.95 |  | 9.05 | 51.65 | 8.69 | 472.47 |  |  | 21.01 | 2277.68
|  | Material - Direct Purchase Total |  |  |  | 1687.86 | 26.95 |  | 9.05 | 51.65 | 8.69 | 472.47 |  |  | 21.01 | 2277.68
| Transportation & Mobile Equip-DP Total |  |  |  |  | 1687.86 | 26.95 |  | 9.05 | 51.65 | 8.69 | 472.47 |  |  | 21.01 | 2277.68
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | AFL TELECOMMUNICATIONS LLC | [10 empty] | 172966.56 | 210691.3 | 383657.86
|  |  | Material Entries <$5,000 | -70398 | -356900 |  |  |  | 33.8 | 33.99 | [5 empty] | -427230.21
|  |  | SOUTHWIRE COMPANY | 1971144 | 351574.08 | 1388114.38 | [6 empty] | 15600 |  | 225207.42 | 3951639.88
|  | Material - Direct Purchase Total |  | 1900746 | -5325.92 | 1388114.38 |  |  | 33.8 | 33.99 |  |  | 15600 | 172966.56 | 435898.72 | 3908067.53
| Wire, Cable & Bus Bar-DP Total |  |  | 1900746 | -5325.92 | 1388114.38 |  |  | 33.8 | 33.99 |  |  | 15600 | 172966.56 | 435898.72 | 3908067.53
2. Material Total |  |  |  | 2125064.71 | 39109.12 | 1554864.91 | 640.11 | -4.22 | 303.43 | 1386618.1 | 79765.6 | 836564.52 | 2552461.76 | 4840809.83 | 2170017.25 | 15586215.12
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  | 7599.15 |  |  | 87.5 | 7998.12 | 4506.7 |  |  | 10402.69 | 3125.4 | 76468.29 | 110187.85
|  | Contract Total |  |  | 7599.15 |  |  | 87.5 | 7998.12 | 4506.7 |  |  | 10402.69 | 3125.4 | 76468.29 | 110187.85
| Construction Management Services Total |  |  |  | 7599.15 |  |  | 87.5 | 7998.12 | 4506.7 |  |  | 10402.69 | 3125.4 | 76468.29 | 110187.85
| Construction Services - Other | Contract | Construction Services - Other | [8 empty] | 115000 |  |  |  | 115000
|  |  | Contract Entries <$50,000 | [5 empty] | 179.54 | [5 empty] | 40000 | 40179.54
|  | Contract Total | [6 empty] | 179.54 |  |  | 115000 |  |  | 40000 | 155179.54
| Construction Services - Other Total | [7 empty] | 179.54 |  |  | 115000 |  |  | 40000 | 155179.54
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 |  |  | 14579.98 |  | 4844.38 |  | 398.4 |  | 1222.71 | 93.02 | 0.01 |  | 21138.5
|  | Contract Total |  |  |  | 14579.98 |  | 4844.38 |  | 398.4 |  | 1222.71 | 93.02 | 0.01 |  | 21138.5
| Construction, Civil/Structural Total |  |  |  |  | 14579.98 |  | 4844.38 |  | 398.4 |  | 1222.71 | 93.02 | 0.01 |  | 21138.5
| Construction, Earthwork | Contract | Contract Entries <$50,000 |  |  |  | 4383.16 | 1500 |  |  | 19253.49 |  |  |  |  | 25136.65
|  |  | UNION ENGINEERING CO INC |  |  | 322085 | 417188.5 | [8 empty] | 739273.5
|  | Contract Total |  |  |  | 322085 | 421571.66 | 1500 |  |  | 19253.49 |  |  |  |  | 764410.15
| Construction, Earthwork Total |  |  |  |  | 322085 | 421571.66 | 1500 |  |  | 19253.49 |  |  |  |  | 764410.15
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 | [9 empty] | 1000 | 2419.8 |  | 3419.8
|  | Contract Total | [10 empty] | 1000 | 2419.8 |  | 3419.8
| Decontamination & Waste Disposal Service Total | [11 empty] | 1000 | 2419.8 |  | 3419.8
| Electrical Construction, Transmission Li | Contract | PAR ELECTRICAL CONTRACTORS INC | [11 empty] | 1547908.7 | 1547908.7
|  | Contract Total | [12 empty] | 1547908.7 | 1547908.7
| Electrical Construction, Transmission Li Total | [13 empty] | 1547908.7 | 1547908.7
| ENGINEERING | Labor | Labor Entries <$5,000 | [10 empty] | 162.87 |  | 162.87
|  | Labor Total | [11 empty] | 162.87 |  | 162.87
| ENGINEERING Total | [12 empty] | 162.87 |  | 162.87
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 |  | 3186.58 | 2698.73 | 94.43 | [5 empty] | 1075.05 |  |  | 7054.79
|  | Labor Total |  |  | 3186.58 | 2698.73 | 94.43 | [5 empty] | 1075.05 |  |  | 7054.79
| N/W SUBSMTCETEST&APP Total |  |  |  | 3186.58 | 2698.73 | 94.43 | [5 empty] | 1075.05 |  |  | 7054.79
| Security / Protection Services | Contract | Contract Entries <$50,000 | [7 empty] | 10736.46 | 27271.68 | 15552.52 | 15526.2 | 23470.74 | 92557.6
|  | Contract Total | [8 empty] | 10736.46 | 27271.68 | 15552.52 | 15526.2 | 23470.74 | 92557.6
| Security / Protection Services Total | [9 empty] | 10736.46 | 27271.68 | 15552.52 | 15526.2 | 23470.74 | 92557.6
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 17589 | 30173.42 | 84402.77 | 15643.58 | 37516.74 | 1518.51 | 91518.24 | 47782.23 | 22831.57 | 53215.34 | 117636.21 | 30528.44 | 550356.05
|  |  | GANNETT FLEMING, INC. | [10 empty] | 58682 |  | 58682
|  | Contract Total |  | 17589 | 30173.42 | 84402.77 | 15643.58 | 37516.74 | 1518.51 | 91518.24 | 47782.23 | 22831.57 | 53215.34 | 176318.21 | 30528.44 | 609038.05
| Short Term Equipment Rent Total |  |  | 17589 | 30173.42 | 84402.77 | 15643.58 | 37516.74 | 1518.51 | 91518.24 | 47782.23 | 22831.57 | 53215.34 | 176318.21 | 30528.44 | 609038.05
| TRANSMISSION | Labor | Labor Entries <$5,000 |  |  | 1490.18 | 577.9 |  |  |  |  | 852.73 | 2267.48 |  | 691.83 | 5880.12
|  | Labor Total |  |  |  | 1490.18 | 577.9 |  |  |  |  | 852.73 | 2267.48 |  | 691.83 | 5880.12
| TRANSMISSION Total |  |  |  |  | 1490.18 | 577.9 |  |  |  |  | 852.73 | 2267.48 |  | 691.83 | 5880.12
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 4368.32 | 5834.67 | 9673.93 | 3327.27 | 5491.11 | 6735.32 | 4290.17 | 3939.6 | 2968.14 | 4215.51 | 1726.15 |  | 52570.19
|  | Labor Total |  | 4368.32 | 5834.67 | 9673.93 | 3327.27 | 5491.11 | 6735.32 | 4290.17 | 3939.6 | 2968.14 | 4215.51 | 1726.15 |  | 52570.19
| TRNS CAPITAL Total |  |  | 4368.32 | 5834.67 | 9673.93 | 3327.27 | 5491.11 | 6735.32 | 4290.17 | 3939.6 | 2968.14 | 4215.51 | 1726.15 |  | 52570.19
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | 82 | 82 | 123 | 164 | 369 | 41 | 41 | 328 | 410 | 287 | 1107 | 1189 | 4223
|  | Labor Total |  | 82 | 82 | 123 | 164 | 369 | 41 | 41 | 328 | 410 | 287 | 1107 | 1189 | 4223
| TSD-HERC - Rental Total |  |  | 82 | 82 | 123 | 164 | 369 | 41 | 41 | 328 | 410 | 287 | 1107 | 1189 | 4223
3. Construction Total |  |  |  | 22039.32 | 46875.82 | 435053.59 | 441378.84 | 49808.73 | 16472.49 | 100754.51 | 82039.78 | 170556.83 | 88108.61 | 200385.64 | 1720257 | 3373731.16
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -97865.6 | 20724.29 | 22863.1 | 25845.95 | -839501.47 | -709460.8 | 13737.11 | -14752.94 | 781372.91 | -843816.12 | 25464.49 | -522769.63 | -2138158.71
|  |  | EITP -- OWNERS ENGINEER | 117801.42 | 202188.26 | 558759.99 | 623049.46 | 343139.45 | 785573.02 | 76328 | 379679.1 | 644330.48 | 343303.5 | 1303786.26 | 1478838.62 | 6856777.56
|  |  | EITP (MPO/BPFM) | 17904.64 | 28631.15 | 75431.75 | 67980.63 | 59362.64 | 105713.36 | 153001.19 | 39880.04 | 166087.08 | 66998.97 | 61981.47 | 164590.11 | 1007563.03
|  |  | PDP-Trans Eldorado IvanPah 220kv NV T&D | 161024.29 | 82905.73 | 425428.05 | 1032930.02 | 980226.95 | 869643.2 | 1901864.29 | 980845.23 |  | 3348273.53 | 2972850.48 | 2808081.64 | 15564073.41
|  |  | PROCUREMENT TDBU | 13917.94 |  | 11718.82 |  |  |  | 8473.02 |  |  | 40362.6 | 31127.38 | 26390.38 | 131990.14
|  |  | TDBU Vehicle Cost | [9 empty] | 14906.32 |  |  | 14906.32
|  | Chargeback Total |  | 212782.69 | 334449.43 | 1094201.71 | 1749806.06 | 543227.57 | 1051468.78 | 2153403.61 | 1385651.43 | 1591790.47 | 2970028.8 | 4395210.08 | 3955131.12 | 21437151.75
| Chargebacks Total |  |  | 212782.69 | 334449.43 | 1094201.71 | 1749806.06 | 543227.57 | 1051468.78 | 2153403.61 | 1385651.43 | 1591790.47 | 2970028.8 | 4395210.08 | 3955131.12 | 21437151.75
| Labor - Other | Labor | Division Overhead | 54320.71 |  | 68087.89 | 13880.06 |  |  | 57588.13 |  |  | 341111.28 | 49518.28 | 49758.34 | 634264.69
|  |  | Labor Entries <$5,000 | 2629.84 | 11108.88 | 8087.9 | 6926.1 | 8859.79 | 6747.54 | 3044.17 | 18019.57 | -132440.95 | 5112.26 | 3984.97 | 5319.76 | -52600.17
|  |  | Paid Absence | 8326.06 | 9352.49 | 11759.1 | 10025.46 | 10473.6 | 9980.93 | 7969.84 | 11349.21 |  | 53001.37 | 6659.66 | 8561.42 | 147459.14
|  | Labor Total |  | 65276.61 | 20461.37 | 87934.89 | 30831.62 | 19333.39 | 16728.47 | 68602.14 | 29368.78 | -132440.95 | 399224.91 | 60162.91 | 63639.52 | 729123.66
| Labor - Other Total |  |  | 65276.61 | 20461.37 | 87934.89 | 30831.62 | 19333.39 | 16728.47 | 68602.14 | 29368.78 | -132440.95 | 399224.91 | 60162.91 | 63639.52 | 729123.66
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -88501.63 | 88501.63 |  |  | 0
|  | Overhead Total | [9 empty] | -88501.63 | 88501.63 |  |  | 0
| Overhead Correction Total | [10 empty] | -88501.63 | 88501.63 |  |  | 0
4. Allocated Total |  |  |  | 278059.3 | 354910.8 | 1182136.6 | 1780637.68 | 562560.96 | 1068197.25 | 2222005.75 | 1415020.21 | 1370847.89 | 3457755.34 | 4455372.99 | 4018770.64 | 22166275.41
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 110839.41 | 7098.17 | [6 empty] | 495213.62 | 613151.2
|  |  | Capitalized Overhead - A&G | 141995.92 | 19132.29 | 121349.74 | 84024.75 | 65968.89 | 43171.64 | 134973.06 | 52810.2 | 150817.85 | 140785.64 | 258156.06 | 232896.76 | 1446082.8
|  |  | Capitalized Overhead - Inj & Damages | 2097.88 | 420.83 | 2884.91 | 1069.96 | -5230.25 | -542.14 | 2821.62 | 806.98 | 6016.7 | -5203.15 | 11463.11 | 3028.62 | 19635.07
|  |  | Capitalized Overhead - P&B/Payroll Tax | 56116.46 | 119750.2 | 122690.64 | 123929.25 | 164222.23 | 139484.73 | 108633.9 | 90851.95 | -260210.65 | 183859.15 | 69015.84 | 201449.4 | 1119793.1
|  | Non Budgeted Total |  | 200210.26 | 139303.32 | 246925.29 | 319863.37 | 232059.04 | 182114.23 | 246428.58 | 144469.13 | -103376.1 | 319441.64 | 338635.01 | 932588.4 | 3198662.17
| Non Budget - Other Total |  |  | 200210.26 | 139303.32 | 246925.29 | 319863.37 | 232059.04 | 182114.23 | 246428.58 | 144469.13 | -103376.1 | 319441.64 | 338635.01 | 932588.4 | 3198662.17
5. Corporate Overhead Total |  |  |  | 200210.26 | 139303.32 | 246925.29 | 319863.37 | 232059.04 | 182114.23 | 246428.58 | 144469.13 | -103376.1 | 319441.64 | 338635.01 | 932588.4 | 3198662.17
Grand Total |  |  |  | 2744504.99 | 1099849.14 | 3373834.64 | 2652841.84 | 1049045.96 | 1447939.43 | 4069886.59 | 1978604.26 | 4936307.47 | 15121024.09 | 14111009.34 | 22044741.85 | 74629589.6

## 900344621
Pin: 6551 | Project: Eldorado-Ivanpah (EITP)
Order: 900344621 | 900344621- Eldorado-Ivanpah No. 2 (California)
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 | [8 empty] | 1312 |  |  |  | 1312
|  | Contract Total | [9 empty] | 1312 |  |  |  | 1312
| Building/Facility Repairs & Maintenance Total | [10 empty] | 1312 |  |  |  | 1312
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  | 127.75 | 317.37 |  |  | 351.84 |  |  | 156.18 |  | 953.14
|  | Contract Total |  |  |  |  | 127.75 | 317.37 |  |  | 351.84 |  |  | 156.18 |  | 953.14
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [5 empty] | 127.75 | 317.37 |  |  | 351.84 |  |  | 156.18 |  | 953.14
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 785446.93 |  |  | 785446.93
|  |  | Contract Entries <$50,000 | [8 empty] | -785446.93 |  |  |  | -785446.93
|  | Contract Total | [9 empty] | -785446.93 | 785446.93 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -785446.93 | 785446.93 |  |  | 0
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  | 25818.87 | 41615.69 |  | 44141.93 | 2473.21 | 11148.8 | 4829.42 | 9869.49 | 11525 | 5046.05 | 5093.5 | 161561.96
|  | Contract Total |  |  | 25818.87 | 41615.69 |  | 44141.93 | 2473.21 | 11148.8 | 4829.42 | 9869.49 | 11525 | 5046.05 | 5093.5 | 161561.96
| Contract Consult/Contract Ord to Ord Total |  |  |  | 25818.87 | 41615.69 |  | 44141.93 | 2473.21 | 11148.8 | 4829.42 | 9869.49 | 11525 | 5046.05 | 5093.5 | 161561.96
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 |  | 561.04 | 444.73 | 112.54 | 1243.64 | 895.83 | 3353.19 | 1874.69 | 679.14 | 112.09 | 1240.04 | 18275.18 | 28792.11
|  | Labor Total |  |  | 561.04 | 444.73 | 112.54 | 1243.64 | 895.83 | 3353.19 | 1874.69 | 679.14 | 112.09 | 1240.04 | 18275.18 | 28792.11
| ELEC SYS PLANNING Total |  |  |  | 561.04 | 444.73 | 112.54 | 1243.64 | 895.83 | 3353.19 | 1874.69 | 679.14 | 112.09 | 1240.04 | 18275.18 | 28792.11
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | [7 empty] | 354.18 |  |  |  | 281.01 | 635.19
|  | Labor Total | [8 empty] | 354.18 |  |  |  | 281.01 | 635.19
| ENG ADVANCEMENT Total | [9 empty] | 354.18 |  |  |  | 281.01 | 635.19
| ENGINEERING | Labor | Labor Entries <$5,000 | 17265.96 | 15090.81 | 21980.16 | 22904.25 | 20275.06 | 24434.32 | 19485.91 | 26974.17 | 18859.24 | 18056.14 | 23573.46 | 825.68 | 229725.16
|  | Labor Total |  | 17265.96 | 15090.81 | 21980.16 | 22904.25 | 20275.06 | 24434.32 | 19485.91 | 26974.17 | 18859.24 | 18056.14 | 23573.46 | 825.68 | 229725.16
| ENGINEERING Total |  |  | 17265.96 | 15090.81 | 21980.16 | 22904.25 | 20275.06 | 24434.32 | 19485.91 | 26974.17 | 18859.24 | 18056.14 | 23573.46 | 825.68 | 229725.16
| Engineering/Technical Professional Servi | Contract | BUREAU VERITAS NORTH AMERICA INC | [11 empty] | 55840.05 | 55840.05
|  |  | Contract Entries <$50,000 |  | 2495 | 16869 | 22128 | 15115 | 24317.5 | 11685.82 | 17946 |  | 11796.5 | 56215.4 | 23939.41 | 202507.63
|  | Contract Total |  |  | 2495 | 16869 | 22128 | 15115 | 24317.5 | 11685.82 | 17946 |  | 11796.5 | 56215.4 | 79779.46 | 258347.68
| Engineering/Technical Professional Servi Total |  |  |  | 2495 | 16869 | 22128 | 15115 | 24317.5 | 11685.82 | 17946 |  | 11796.5 | 56215.4 | 79779.46 | 258347.68
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 865.02 |  | 22343.5 | 39370.94 | 17214.49 | 45483.92 | 0 | 48869.17 | 21864.45 | 17334.06 | 17098.91 | 18197.78 | 248642.24
|  | Contract Total |  | 865.02 |  | 22343.5 | 39370.94 | 17214.49 | 45483.92 | 0 | 48869.17 | 21864.45 | 17334.06 | 17098.91 | 18197.78 | 248642.24
| Environmental/Safety Professional Servic Total |  |  | 865.02 |  | 22343.5 | 39370.94 | 17214.49 | 45483.92 | 0 | 48869.17 | 21864.45 | 17334.06 | 17098.91 | 18197.78 | 248642.24
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 8282.19 | 8260.05 | 5816.86 | 7735.4 | 6658.84 | 7782 | 5790.96 | 4609.85 | 2127853.26 | -2117632.16 | -6534.56 | -3912.64 | 54710.05
|  | IMM Correction Total |  | 8282.19 | 8260.05 | 5816.86 | 7735.4 | 6658.84 | 7782 | 5790.96 | 4609.85 | 2127853.26 | -2117632.16 | -6534.56 | -3912.64 | 54710.05
| IMM/Allocated - Correction Total |  |  | 8282.19 | 8260.05 | 5816.86 | 7735.4 | 6658.84 | 7782 | 5790.96 | 4609.85 | 2127853.26 | -2117632.16 | -6534.56 | -3912.64 | 54710.05
| ITBI (HCC) | Labor | Labor Entries <$5,000 | 290.44 | [11 empty] | 290.44
|  | Labor Total |  | 290.44 | [11 empty] | 290.44
| ITBI (HCC) Total |  |  | 290.44 | [11 empty] | 290.44
| Labor - Other | Labor | Labor - Other | [9 empty] | 14755.31 |  |  | 14755.31
|  |  | Labor Correction | [9 empty] | 73409.47 |  |  | 73409.47
|  |  | Labor Entries <$5,000 | 1361.05 | 2385.54 | -1915.44 | 1079.01 | 5180.27 | -5572.3 | -465.58 | 1575.19 | 78632.68 | -162479.97 | -3458.95 | 4166.79 | -79511.71
|  | Labor Total |  | 1361.05 | 2385.54 | -1915.44 | 1079.01 | 5180.27 | -5572.3 | -465.58 | 1575.19 | 78632.68 | -74315.19 | -3458.95 | 4166.79 | 8653.07
| Labor - Other Total |  |  | 1361.05 | 2385.54 | -1915.44 | 1079.01 | 5180.27 | -5572.3 | -465.58 | 1575.19 | 78632.68 | -74315.19 | -3458.95 | 4166.79 | 8653.07
| Legal Professional Services (OC & Attys) | Contract | Contract Entries <$50,000 |  |  | 8445 |  |  | 1930 |  | 758 |  |  |  |  | 11133
|  | Contract Total |  |  |  | 8445 |  |  | 1930 |  | 758 |  |  |  |  | 11133
| Legal Professional Services (OC & Attys) Total |  |  |  |  | 8445 |  |  | 1930 |  | 758 |  |  |  |  | 11133
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | [9 empty] | 597.17 |  |  | 597.17
|  | Labor Total | [10 empty] | 597.17 |  |  | 597.17
| MAJOR PROJECT ORG Total | [11 empty] | 597.17 |  |  | 597.17
| Other | Other | Other | -75801.78 | 121781.5 | -47150.54 | 1684768.2 | -1652713.84 | -24667.35 | 17146.53 | 45938.49 | -1083219.05 | 2593903.25 | 1901998.52 | -1105585.85 | 2376398.08
|  | Other Total |  | -75801.78 | 121781.5 | -47150.54 | 1684768.2 | -1652713.84 | -24667.35 | 17146.53 | 45938.49 | -1083219.05 | 2593903.25 | 1901998.52 | -1105585.85 | 2376398.08
| Other Total |  |  | -75801.78 | 121781.5 | -47150.54 | 1684768.2 | -1652713.84 | -24667.35 | 17146.53 | 45938.49 | -1083219.05 | 2593903.25 | 1901998.52 | -1105585.85 | 2376398.08
| SC&M | Labor | Labor Entries <$5,000 |  | 350.41 | [10 empty] | 350.41
|  | Labor Total |  |  | 350.41 | [10 empty] | 350.41
| SC&M Total |  |  |  | 350.41 | [10 empty] | 350.41
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -14709.93 | 14709.93 |  |  | 0
|  | Contract Total | [9 empty] | -14709.93 | 14709.93 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -14709.93 | 14709.93 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 1495.01 | 9939.2 | 10415.75 | 13412.86 | 564.48 | 3693.58 | 2268.51 | 4101.3 | 6955.32 | 9581.52 | 2861.65 | 10840.98 | 76130.16
|  | Contract Total |  | 1495.01 | 9939.2 | 10415.75 | 13412.86 | 564.48 | 3693.58 | 2268.51 | 4101.3 | 6955.32 | 9581.52 | 2861.65 | 10840.98 | 76130.16
| Temporary/Supplementary - Technical/Prof Total |  |  | 1495.01 | 9939.2 | 10415.75 | 13412.86 | 564.48 | 3693.58 | 2268.51 | 4101.3 | 6955.32 | 9581.52 | 2861.65 | 10840.98 | 76130.16
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 271.04 | 1654.8 | 696.71 | 633.77 | 250.15 | 104 |  |  | 1204.08 | 439.19 | 1314 |  | 6567.74
|  | Contract Total |  | 271.04 | 1654.8 | 696.71 | 633.77 | 250.15 | 104 |  |  | 1204.08 | 439.19 | 1314 |  | 6567.74
| Temporary/Supplementary - Trade/Labor Total |  |  | 271.04 | 1654.8 | 696.71 | 633.77 | 250.15 | 104 |  |  | 1204.08 | 439.19 | 1314 |  | 6567.74
| TRANSMISSION | Labor | Labor Entries <$5,000 | [11 empty] | 466.78 | 466.78
|  | Labor Total | [12 empty] | 466.78 | 466.78
| TRANSMISSION Total | [13 empty] | 466.78 | 466.78
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 1052.47 | 1186 | 2481.52 | 1738 | 715.05 | 746 |  | 1913.13 | 3487.64 | 319.97 | 1413.32 |  | 15053.1
|  | Labor Total |  | 1052.47 | 1186 | 2481.52 | 1738 | 715.05 | 746 |  | 1913.13 | 3487.64 | 319.97 | 1413.32 |  | 15053.1
| TRNS CAPITAL Total |  |  | 1052.47 | 1186 | 2481.52 | 1738 | 715.05 | 746 |  | 1913.13 | 3487.64 | 319.97 | 1413.32 |  | 15053.1
1. Project Support Total |  |  |  | -44918.6 | 189523.22 | 82042.94 | 1794010.72 | -1541037.56 | 81620.71 | 70414.14 | 160095.43 | 387341.39 | 1271874.4 | 2000924.02 | -971571.33 | 3480319.48
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  |  | 1005 | 103.51 |  |  |  | 433.06 |  | 844.75 |  | 105.47 | 2491.79
|  | Material - Direct Purchase Total |  |  |  | 1005 | 103.51 |  |  |  | 433.06 |  | 844.75 |  | 105.47 | 2491.79
| Building, Shop & Industrial Products/Eqp Total |  |  |  |  | 1005 | 103.51 |  |  |  | 433.06 |  | 844.75 |  | 105.47 | 2491.79
| Insulators & Bushings-DP | Material - Direct Purchase | Material Entries <$5,000 | 444.4 | [9 empty] | 1013.44 |  | 1457.84
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [9 empty] | 54971.73 | 100133.69 |  | 155105.42
|  | Material - Direct Purchase Total |  | 444.4 | [8 empty] | 54971.73 | 101147.13 |  | 156563.26
| Insulators & Bushings-DP Total |  |  | 444.4 | [8 empty] | 54971.73 | 101147.13 |  | 156563.26
| Labor - Other | Labor | Labor Entries <$5,000 | [9 empty] | 13649.65 |  | -11180.23 | 2469.42
|  |  | SUBORDER*IT-Eldorado-Ivanpah OPGW Cable | [9 empty] | 5511.83 |  |  | 5511.83
|  | Labor Total | [10 empty] | 19161.48 |  | -11180.23 | 7981.25
| Labor - Other Total | [11 empty] | 19161.48 |  | -11180.23 | 7981.25
| Material - Other | Material | Material - Other | 4134.81 | 19837.95 | 8378.21 | 383.28 |  | 840.68 | 16016.85 | 1491.03 | 5636.85 | 15874.51 | 43589.26 | 13934.85 | 130118.28
|  | Material Total |  | 4134.81 | 19837.95 | 8378.21 | 383.28 |  | 840.68 | 16016.85 | 1491.03 | 5636.85 | 15874.51 | 43589.26 | 13934.85 | 130118.28
| Material - Other Total |  |  | 4134.81 | 19837.95 | 8378.21 | 383.28 |  | 840.68 | 16016.85 | 1491.03 | 5636.85 | 15874.51 | 43589.26 | 13934.85 | 130118.28
| Mechanical Systems and Components-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 261.6 | [9 empty] | 261.6
|  | Material - Direct Purchase Total |  |  |  | 261.6 | [9 empty] | 261.6
| Mechanical Systems and Components-DP Total |  |  |  |  | 261.6 | [9 empty] | 261.6
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 1015.2 | 4121.61 | 224.1 |  |  |  | 1998.96 | 861.21 | 1153.61 |  |  | 9374.69
|  |  | SHAMROCK VALCAT INC | [5 empty] | 6984.6 | [6 empty] | 6984.6
|  | Material - Direct Purchase Total |  |  | 1015.2 | 4121.61 | 224.1 |  | 6984.6 |  | 1998.96 | 861.21 | 1153.61 |  |  | 16359.29
| Office & Office Support Products-DP Total |  |  |  | 1015.2 | 4121.61 | 224.1 |  | 6984.6 |  | 1998.96 | 861.21 | 1153.61 |  |  | 16359.29
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 226 |  | 2780.39 | 3006.39
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [10 empty] | 104541.67 |  | 104541.67
|  | Material - Direct Purchase Total | [10 empty] | 226 | 104541.67 | 2780.39 | 107548.06
| Pole Line Hdwe & Connectors-DP Total | [11 empty] | 226 | 104541.67 | 2780.39 | 107548.06
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | FORMET | [6 empty] | 151495.56 | 5515.2 |  | 58443.76 | 284991.68 |  | 500446.2
|  |  | Material Entries <$5,000 | [8 empty] | 4596.79 |  |  | 776.45 | 5373.24
|  |  | Steel Lattice Towers (T/S)-DP | [11 empty] | 73091.45 | 73091.45
|  | Material - Direct Purchase Total | [7 empty] | 151495.56 | 5515.2 | 4596.79 | 58443.76 | 284991.68 | 73867.9 | 578910.89
| Steel Lattice Towers (T/S)-DP Total | [8 empty] | 151495.56 | 5515.2 | 4596.79 | 58443.76 | 284991.68 | 73867.9 | 578910.89
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 9.51 |  | 9.51
|  | Material - Direct Purchase Total | [11 empty] | 9.51 |  | 9.51
| Transportation & Mobile Equip-DP Total | [12 empty] | 9.51 |  | 9.51
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | AFL TELECOMMUNICATIONS LLC | [11 empty] | 71865.62 | 71865.62
|  |  | Material Entries <$5,000 | -0.89 | [9 empty] | 1708.29 | 3.6 | 1711
|  |  | Wire, Cable & Bus Bar-DP |  | 356900 | [10 empty] | 356900
|  | Material - Direct Purchase Total |  | -0.89 | 356900 | [8 empty] | 1708.29 | 71869.22 | 430476.62
| Wire, Cable & Bus Bar-DP Total |  |  | -0.89 | 356900 | [8 empty] | 1708.29 | 71869.22 | 430476.62
2. Material Total |  |  |  | 4578.32 | 377753.15 | 13766.42 | 710.89 |  | 7825.28 | 167512.41 | 9438.25 | 11094.85 | 150675.84 | 535987.54 | 151377.6 | 1430720.55
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [5 empty] | 8222.93 | 4195.34 |  |  | 9348.21 | 2702.04 | 32387.15 | 56855.67
|  | Contract Total | [6 empty] | 8222.93 | 4195.34 |  |  | 9348.21 | 2702.04 | 32387.15 | 56855.67
| Construction Management Services Total | [7 empty] | 8222.93 | 4195.34 |  |  | 9348.21 | 2702.04 | 32387.15 | 56855.67
| Construction Services - Other | Contract | Contract Entries <$50,000 | [11 empty] | 10000 | 10000
|  | Contract Total | [12 empty] | 10000 | 10000
| Construction Services - Other Total | [13 empty] | 10000 | 10000
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 |  |  | 20373.69 |  |  |  | 398.41 |  | 668.18 |  | -0.01 |  | 21440.27
|  | Contract Total |  |  |  | 20373.69 |  |  |  | 398.41 |  | 668.18 |  | -0.01 |  | 21440.27
| Construction, Civil/Structural Total |  |  |  |  | 20373.69 |  |  |  | 398.41 |  | 668.18 |  | -0.01 |  | 21440.27
| Construction, Earthwork | Contract | Contract Entries <$50,000 |  |  |  | 4383.16 |  |  |  | 7406 | 154.77 | 13400 |  |  | 25343.93
|  |  | UNION ENGINEERING CO INC |  |  |  | 157567 | [8 empty] | 157567
|  | Contract Total |  |  |  |  | 161950.16 |  |  |  | 7406 | 154.77 | 13400 |  |  | 182910.93
| Construction, Earthwork Total | [5 empty] | 161950.16 |  |  |  | 7406 | 154.77 | 13400 |  |  | 182910.93
| Construction, Paving/Fencing | Contract | Contract Entries <$50,000 | [9 empty] | 2345 |  |  | 2345
|  | Contract Total | [10 empty] | 2345 |  |  | 2345
| Construction, Paving/Fencing Total | [11 empty] | 2345 |  |  | 2345
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 | [10 empty] | 1559 |  | 1559
|  | Contract Total | [11 empty] | 1559 |  | 1559
| Decontamination & Waste Disposal Service Total | [12 empty] | 1559 |  | 1559
| Electrical Construction, Transmission Li | Contract | PAR ELECTRICAL CONTRACTORS INC | [11 empty] | 386977 | 386977
|  | Contract Total | [12 empty] | 386977 | 386977
| Electrical Construction, Transmission Li Total | [13 empty] | 386977 | 386977
| ENGINEERING | Labor | Labor Entries <$5,000 | [10 empty] | 244.3 |  | 244.3
|  | Labor Total | [11 empty] | 244.3 |  | 244.3
| ENGINEERING Total | [12 empty] | 244.3 |  | 244.3
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | [10 empty] | 98.9 |  | 98.9
|  | Contract Total | [11 empty] | 98.9 |  | 98.9
| Hauling / Industrial Moving Services Total | [12 empty] | 98.9 |  | 98.9
| SC&M | Labor | Labor Entries <$5,000 |  | 243.86 |  |  | 1334.96 | [7 empty] | 1578.82
|  | Labor Total |  |  | 243.86 |  |  | 1334.96 | [7 empty] | 1578.82
| SC&M Total |  |  |  | 243.86 |  |  | 1334.96 | [7 empty] | 1578.82
| Security / Protection Services | Contract | Contract Entries <$50,000 |  |  | 6720.14 | 8139.32 | 5490.04 | 5023.24 | 5024.36 | 5443.94 | 8014.17 | 9872.14 | 11731.63 | 14033.14 | 79492.12
|  | Contract Total |  |  |  | 6720.14 | 8139.32 | 5490.04 | 5023.24 | 5024.36 | 5443.94 | 8014.17 | 9872.14 | 11731.63 | 14033.14 | 79492.12
| Security / Protection Services Total |  |  |  |  | 6720.14 | 8139.32 | 5490.04 | 5023.24 | 5024.36 | 5443.94 | 8014.17 | 9872.14 | 11731.63 | 14033.14 | 79492.12
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 689 |  | 8969.08 | 24121.42 | 36061.5 | 549.3 | 58435.65 | 26284.43 | 18060.52 | 18578 | 56228.6 | 810.23 | 248787.73
|  |  | GANNETT FLEMING, INC. | [9 empty] | 143252.94 |  |  | 143252.94
|  | Contract Total |  | 689 |  | 8969.08 | 24121.42 | 36061.5 | 549.3 | 58435.65 | 26284.43 | 18060.52 | 161830.94 | 56228.6 | 810.23 | 392040.67
| Short Term Equipment Rent Total |  |  | 689 |  | 8969.08 | 24121.42 | 36061.5 | 549.3 | 58435.65 | 26284.43 | 18060.52 | 161830.94 | 56228.6 | 810.23 | 392040.67
| TRANSMISSION | Labor | Labor Entries <$5,000 | [11 empty] | 1833.57 | 1833.57
|  | Labor Total | [12 empty] | 1833.57 | 1833.57
| TRANSMISSION Total | [13 empty] | 1833.57 | 1833.57
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 3940.82 | 6637.22 | 2734.49 | 2340.26 | 4154.61 | 4244.78 | 1803.15 | 2452.69 | 1433.84 | 2092.86 | 2066.57 |  | 33901.29
|  | Labor Total |  | 3940.82 | 6637.22 | 2734.49 | 2340.26 | 4154.61 | 4244.78 | 1803.15 | 2452.69 | 1433.84 | 2092.86 | 2066.57 |  | 33901.29
| TRNS CAPITAL Total |  |  | 3940.82 | 6637.22 | 2734.49 | 2340.26 | 4154.61 | 4244.78 | 1803.15 | 2452.69 | 1433.84 | 2092.86 | 2066.57 |  | 33901.29
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 |  |  | 41 |  | 41 | 41 | 41 | 164 | 164 | 82 | 205 | 123 | 902
|  | Labor Total |  |  |  | 41 |  | 41 | 41 | 41 | 164 | 164 | 82 | 205 | 123 | 902
| TSD-HERC - Rental Total |  |  |  |  | 41 |  | 41 | 41 | 41 | 164 | 164 | 82 | 205 | 123 | 902
3. Construction Total |  |  |  | 4629.82 | 6881.08 | 38838.4 | 196551.16 | 47082.11 | 18081.25 | 69897.91 | 41751.06 | 28495.48 | 198971.15 | 74836.03 | 446164.09 | 1172179.54
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -13609.02 | 19575.49 | -188704.58 | 24347.01 | -159219.72 | -967032.66 | 15778.46 | 11955.96 | 3036.91 | -888346.85 | 21649.73 | -43987.32 | -2164556.59
|  |  | EITP -- OWNERS ENGINEER | 29450.36 | 48748.25 | 139690 | 154088.8 | 82200.9 | 196393.25 | 19082 | 91181.34 | 158997.06 | 81591.28 | 324441.86 | 367296.74 | 1693161.84
|  |  | EITP (MPO/BPFM) |  |  | 13366.86 | 7939.8 | 13181.56 | 17907.52 | 31308.6 | 6071.37 | 34400.44 | 11779.49 | 10789.24 | 33381.68 | 180126.56
|  |  | PDP-Trans Eldorado IvanPah 220kv-TDBU | 24315.13 | 254405.69 | 51054.83 | 272786.22 | 1081270.15 | 187339.62 | 249640.81 | 1142089.71 |  | 634186.48 | 578168.08 | 546274.63 | 5021531.35
|  |  | PROCUREMENT TDBU | [9 empty] | 6534.56 |  |  | 6534.56
|  |  | TDBU Vehicle Cost | [9 empty] | 5260.11 |  |  | 5260.11
|  |  | WW-Eldorado IVanPah Transm, CA-TDBU |  | 8669.05 | [10 empty] | 8669.05
|  | Chargeback Total |  | 40156.47 | 331398.48 | 15407.11 | 459161.83 | 1017432.89 | -565392.27 | 315809.87 | 1251298.38 | 196434.41 | -148994.93 | 935048.91 | 902965.73 | 4750726.88
| Chargebacks Total |  |  | 40156.47 | 331398.48 | 15407.11 | 459161.83 | 1017432.89 | -565392.27 | 315809.87 | 1251298.38 | 196434.41 | -148994.93 | 935048.91 | 902965.73 | 4750726.88
| Labor - Other | Labor | Division Overhead |  | 5922.18 | [7 empty] | 60175.69 |  |  | 66097.87
|  |  | Labor Entries <$5,000 | 5671.79 | 14642.06 | 10510.99 | 10509.16 | 6472.93 | 11260.79 | 16502.11 | 8328.77 | -35383.25 | 11241.98 | 12464.22 | 9000.06 | 81221.61
|  |  | Paid Absence |  |  |  | 5220.19 | 6021.11 |  |  | 6468.45 |  | 19156.91 |  | 6060.95 | 42927.61
|  | Labor Total |  | 5671.79 | 20564.24 | 10510.99 | 15729.35 | 12494.04 | 11260.79 | 16502.11 | 14797.22 | -35383.25 | 90574.58 | 12464.22 | 15061.01 | 190247.09
| Labor - Other Total |  |  | 5671.79 | 20564.24 | 10510.99 | 15729.35 | 12494.04 | 11260.79 | 16502.11 | 14797.22 | -35383.25 | 90574.58 | 12464.22 | 15061.01 | 190247.09
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -19218.47 | 19218.47 |  |  | 0
|  | Overhead Total | [9 empty] | -19218.47 | 19218.47 |  |  | 0
| Overhead Correction Total | [10 empty] | -19218.47 | 19218.47 |  |  | 0
4. Allocated Total |  |  |  | 45828.26 | 351962.72 | 25918.1 | 474891.18 | 1029926.93 | -554131.48 | 332311.98 | 1266095.6 | 141832.69 | -39201.88 | 947513.13 | 918026.74 | 4940973.97
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 44828.51 | 2625.14 | [6 empty] | 94149.5 | 141603.15
|  |  | Capitalized Overhead - A&G | 4841.38 | 24080.04 | 9257.14 | 26527.81 | 99799.44 | -14794.35 | 23604.01 | 41788.18 | 20556.46 | 5703.14 | 44472.4 | 46878.49 | 332714.14
|  |  | Capitalized Overhead - Inj & Damages | 27.12 | 1230.3 | 85.59 | 314.59 | 7366.94 | -1130.02 | 450.81 | 1490.22 | 1021.23 | -4251.25 | 1740.73 | 413.3 | 8759.56
|  |  | Capitalized Overhead - P&B/Payroll Tax | 22272.34 | 43023.15 | 41919.24 | 52749.94 | 71577.03 | 53950.69 | 48430.48 | 42031.07 | -79774.73 | 64004.42 | 32914.08 | 92854.5 | 485952.21
|  | Non Budgeted Total |  | 27140.84 | 68333.49 | 51261.97 | 124420.85 | 181368.55 | 38026.32 | 72485.3 | 85309.47 | -58197.04 | 65456.31 | 79127.21 | 234295.79 | 969029.06
| Non Budget - Other Total |  |  | 27140.84 | 68333.49 | 51261.97 | 124420.85 | 181368.55 | 38026.32 | 72485.3 | 85309.47 | -58197.04 | 65456.31 | 79127.21 | 234295.79 | 969029.06
5. Corporate Overhead Total |  |  |  | 27140.84 | 68333.49 | 51261.97 | 124420.85 | 181368.55 | 38026.32 | 72485.3 | 85309.47 | -58197.04 | 65456.31 | 79127.21 | 234295.79 | 969029.06
Grand Total |  |  |  | 37258.64 | 994453.66 | 211827.83 | 2590584.8 | -282659.97 | -408577.92 | 712621.74 | 1562689.81 | 510567.37 | 1647775.82 | 3638387.93 | 778292.89 | 11993222.6

## 900316934
Pin: 6551 | Project: Eldorado-Ivanpah (EITP)
Order: 900316934 | 900316934- I: Eldorado SS Upgrades, EITP
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 | [11 empty] | 14573.16 | 14573.16
|  | Contract Total | [12 empty] | 14573.16 | 14573.16
| Building/Facility Repairs & Maintenance Total | [13 empty] | 14573.16 | 14573.16
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [11 empty] | 22.37 | 22.37
|  | Contract Total | [12 empty] | 22.37 | 22.37
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [13 empty] | 22.37 | 22.37
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 230059.7 |  |  | 230059.7
|  |  | Contract Entries <$50,000 | [8 empty] | -230059.7 |  |  |  | -230059.7
|  | Contract Total | [9 empty] | -230059.7 | 230059.7 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -230059.7 | 230059.7 |  |  | 0
| Contract - Other - Correction | Contract | Contract Entries <$50,000 | [7 empty] | 298 |  |  |  |  | 298
|  | Contract Total | [8 empty] | 298 |  |  |  |  | 298
| Contract - Other - Correction Total | [9 empty] | 298 |  |  |  |  | 298
| Data Processing Services/Computer Mainte | Contract | Contract Entries <$50,000 | [9 empty] | 557.17 |  |  | 557.17
|  | Contract Total | [10 empty] | 557.17 |  |  | 557.17
| Data Processing Services/Computer Mainte Total | [11 empty] | 557.17 |  |  | 557.17
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 338.89 | 338.89
|  | Labor Total | [12 empty] | 338.89 | 338.89
| ELEC SYS PLANNING Total | [13 empty] | 338.89 | 338.89
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 71.5 | 48.54 | 24.14 |  |  | 84.38 | 169.21 | 338.44 | 332.72 | 235.29 | 190.89 | 1495.11
|  | Labor Total |  |  | 71.5 | 48.54 | 24.14 |  |  | 84.38 | 169.21 | 338.44 | 332.72 | 235.29 | 190.89 | 1495.11
| ENG ADVANCEMENT Total |  |  |  | 71.5 | 48.54 | 24.14 |  |  | 84.38 | 169.21 | 338.44 | 332.72 | 235.29 | 190.89 | 1495.11
| ENGINEERING | Labor | Labor Entries <$5,000 | 1924.36 | 598.49 | 251.01 | 450.32 | 628.61 | 4710.39 | 4805.9 | 2243.18 | 1245.99 | 1326.32 | 1683.06 |  | 19867.63
|  | Labor Total |  | 1924.36 | 598.49 | 251.01 | 450.32 | 628.61 | 4710.39 | 4805.9 | 2243.18 | 1245.99 | 1326.32 | 1683.06 |  | 19867.63
| ENGINEERING Total |  |  | 1924.36 | 598.49 | 251.01 | 450.32 | 628.61 | 4710.39 | 4805.9 | 2243.18 | 1245.99 | 1326.32 | 1683.06 |  | 19867.63
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  | 2052 | 12762 | 15010 | 8404.5 |  |  | 30009.75 | 47456.61 | 25630 | 8753.6 |  | 150078.46
|  |  | ORSA CONSULTING ENGINEERS INC | [6 empty] | 53868.31 | [5 empty] | 53868.31
|  | Contract Total |  |  | 2052 | 12762 | 15010 | 8404.5 |  | 53868.31 | 30009.75 | 47456.61 | 25630 | 8753.6 |  | 203946.77
| Engineering/Technical Professional Servi Total |  |  |  | 2052 | 12762 | 15010 | 8404.5 |  | 53868.31 | 30009.75 | 47456.61 | 25630 | 8753.6 |  | 203946.77
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | [5 empty] | 244 | [6 empty] | 244
|  | Contract Total | [6 empty] | 244 | [6 empty] | 244
| Environmental/Safety Professional Servic Total | [7 empty] | 244 | [6 empty] | 244
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 18070.24 | 18067.02 | 13043.67 | 17284.41 | 15916.43 | 17052.17 | 13982.42 | 12217.48 | 344316.68 | -321053.1 | -6197.93 | -758.33 | 141941.16
|  | IMM Correction Total |  | 18070.24 | 18067.02 | 13043.67 | 17284.41 | 15916.43 | 17052.17 | 13982.42 | 12217.48 | 344316.68 | -321053.1 | -6197.93 | -758.33 | 141941.16
| IMM/Allocated - Correction Total |  |  | 18070.24 | 18067.02 | 13043.67 | 17284.41 | 15916.43 | 17052.17 | 13982.42 | 12217.48 | 344316.68 | -321053.1 | -6197.93 | -758.33 | 141941.16
| Labor - Other | Labor | ASSIST El Dorado Maint/switching for pro | [11 empty] | 19097.67 | 19097.67
|  |  | Labor Entries <$5,000 | -56.07 | 218.79 | -100.29 | -57.8 | 172.14 | -543.15 | 224.49 | 6713.56 | 44774.41 | -42666.84 | -299.69 | 3931.39 | 12310.94
|  | Labor Total |  | -56.07 | 218.79 | -100.29 | -57.8 | 172.14 | -543.15 | 224.49 | 6713.56 | 44774.41 | -42666.84 | -299.69 | 23029.06 | 31408.61
| Labor - Other Total |  |  | -56.07 | 218.79 | -100.29 | -57.8 | 172.14 | -543.15 | 224.49 | 6713.56 | 44774.41 | -42666.84 | -299.69 | 23029.06 | 31408.61
| Other | Other | Other |  | 11152.11 | 424034 | -386778.98 | -48407.13 |  | 55.2 | 2755.76 | -86458.32 | 93725.78 | 33576.12 | -28905.92 | 14748.62
|  | Other Total |  |  | 11152.11 | 424034 | -386778.98 | -48407.13 |  | 55.2 | 2755.76 | -86458.32 | 93725.78 | 33576.12 | -28905.92 | 14748.62
| Other Total |  |  |  | 11152.11 | 424034 | -386778.98 | -48407.13 |  | 55.2 | 2755.76 | -86458.32 | 93725.78 | 33576.12 | -28905.92 | 14748.62
| SC&M | Labor | Labor Entries <$5,000 |  | 502.96 |  | 244.15 | [5 empty] | 1640.51 | 1505.96 | 1217.45 | 5111.03
|  | Labor Total |  |  | 502.96 |  | 244.15 | [5 empty] | 1640.51 | 1505.96 | 1217.45 | 5111.03
| SC&M Total |  |  |  | 502.96 |  | 244.15 | [5 empty] | 1640.51 | 1505.96 | 1217.45 | 5111.03
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -2503.15 | 2503.15 |  |  | 0
|  | Contract Total | [9 empty] | -2503.15 | 2503.15 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -2503.15 | 2503.15 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 447.91 | 1275.42 | 2708.14 | 1603.54 | 1885.06 | 97.06 |  | 2877 | 1341 | 1262.1 | 2059.04 | 5147.95 | 20704.22
|  | Contract Total |  | 447.91 | 1275.42 | 2708.14 | 1603.54 | 1885.06 | 97.06 |  | 2877 | 1341 | 1262.1 | 2059.04 | 5147.95 | 20704.22
| Temporary/Supplementary - Trade/Labor Total |  |  | 447.91 | 1275.42 | 2708.14 | 1603.54 | 1885.06 | 97.06 |  | 2877 | 1341 | 1262.1 | 2059.04 | 5147.95 | 20704.22
| TRANSMISSION | Labor | Labor Entries <$5,000 | [6 empty] | 450.33 | -459.31 |  |  |  |  | -8.98
|  | Labor Total | [7 empty] | 450.33 | -459.31 |  |  |  |  | -8.98
| TRANSMISSION Total | [8 empty] | 450.33 | -459.31 |  |  |  |  | -8.98
1. Project Support Total |  |  |  | 20386.44 | 33938.29 | 452747.07 | -352220.22 | -21400.39 | 21560.47 | 73471.03 | 56824.63 | 120451.96 | -6682.49 | 41315.45 | 14855.52 | 455247.76
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | ABB INC |  | 658032 | [10 empty] | 658032
|  |  | Material Entries <$5,000 | 0 | [11 empty] | 0
|  | Material - Direct Purchase Total |  | 0 | 658032 | [10 empty] | 658032
| Breakers - Circuit-DP Total |  |  | 0 | 658032 | [10 empty] | 658032
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 3660 | 3660
|  | Material - Direct Purchase Total | [12 empty] | 3660 | 3660
| Building, Shop & Industrial Products/Eqp Total | [13 empty] | 3660 | 3660
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Cabinets, Panels and Switchboards-DP | [11 empty] | 43859.06 | 43859.06
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [9 empty] | 18300 |  |  | 18300
|  | Material - Direct Purchase Total | [10 empty] | 18300 |  | 43859.06 | 62159.06
| Cabinets, Panels and Switchboards-DP Total | [11 empty] | 18300 |  | 43859.06 | 62159.06
| Capacitors and Regulators-DP | Material - Direct Purchase | Capacitors and Regulators-DP | [10 empty] | 58750 | 18710 | 77460
|  |  | HAEFELY TRENCH LIMITED |  |  | 89928 | [9 empty] | 89928
|  |  | Material Entries <$5,000 | [11 empty] | 0 | 0
|  | Material - Direct Purchase Total |  |  |  | 89928 | [7 empty] | 58750 | 18710 | 167388
| Capacitors and Regulators-DP Total |  |  |  |  | 89928 | [7 empty] | 58750 | 18710 | 167388
| Communication Systems and Equipment -DP | Material - Direct Purchase | DAQ ELECTRONICS, LLC | [9 empty] | 7875 |  |  | 7875
|  | Material - Direct Purchase Total | [10 empty] | 7875 |  |  | 7875
| Communication Systems and Equipment -DP Total | [11 empty] | 7875 |  |  | 7875
| Electric Wiring and Components-DP | Material - Direct Purchase | ABB INC | [10 empty] | 6494.4 |  | 6494.4
|  |  | Material Entries <$5,000 |  |  |  |  | 1077.48 |  | 1372.6 |  |  | 6440.27 | 1528.48 | 1618.36 | 12037.19
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [10 empty] | 7136.24 |  | 7136.24
|  | Material - Direct Purchase Total | [5 empty] | 1077.48 |  | 1372.6 |  |  | 6440.27 | 15159.12 | 1618.36 | 25667.83
| Electric Wiring and Components-DP Total | [6 empty] | 1077.48 |  | 1372.6 |  |  | 6440.27 | 15159.12 | 1618.36 | 25667.83
| Line Switches & Switchgear-DP | Material - Direct Purchase | SOUTHERN STATES LLC |  | 95808 |  | 304154 |  |  |  |  | 23952 |  |  |  | 423914
|  | Material - Direct Purchase Total |  |  | 95808 |  | 304154 |  |  |  |  | 23952 |  |  |  | 423914
| Line Switches & Switchgear-DP Total |  |  |  | 95808 |  | 304154 |  |  |  |  | 23952 |  |  |  | 423914
| Material - Inventory | Material | Material - Inventory | [10 empty] | 19853.17 | 10374.27 | 30227.44
|  | Material Total | [11 empty] | 19853.17 | 10374.27 | 30227.44
| Material - Inventory Total | [12 empty] | 19853.17 | 10374.27 | 30227.44
| Material - Other | Material | Material - Other | 0 | 62429.49 | 7371.03 | 24748.38 | 5187.5 | 0.01 | 113.06 | 1842.8 | 23.53 | 55398.99 | 11473.64 | 20406.67 | 188995.1
|  | Material Total |  | 0 | 62429.49 | 7371.03 | 24748.38 | 5187.5 | 0.01 | 113.06 | 1842.8 | 23.53 | 55398.99 | 11473.64 | 20406.67 | 188995.1
| Material - Other Total |  |  | 0 | 62429.49 | 7371.03 | 24748.38 | 5187.5 | 0.01 | 113.06 | 1842.8 | 23.53 | 55398.99 | 11473.64 | 20406.67 | 188995.1
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 312.76 | 312.76
|  | Material - Direct Purchase Total | [12 empty] | 312.76 | 312.76
| Metals & Fabricated Metal Products-DP Total | [13 empty] | 312.76 | 312.76
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 150.14 |  |  | 150.14
|  |  | RONAN ENGINEERING COMPANY | [9 empty] | 16001 |  |  | 16001
|  | Material - Direct Purchase Total | [10 empty] | 16151.14 |  |  | 16151.14
| Meters, Monitor and Warnings-DP Total | [11 empty] | 16151.14 |  |  | 16151.14
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 167.06 | 167.06
|  | Material - Direct Purchase Total | [12 empty] | 167.06 | 167.06
| Office & Office Support Products-DP Total | [13 empty] | 167.06 | 167.06
| Other Consumables-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 120 |  |  |  | 120
|  | Material - Direct Purchase Total | [9 empty] | 120 |  |  |  | 120
| Other Consumables-DP Total | [10 empty] | 120 |  |  |  | 120
| Protection and Test-DP | Material - Direct Purchase | GE CONSUMER AND INDUSTRIAL |  |  |  |  | 62343.48 | [7 empty] | 62343.48
|  |  | Material Entries <$5,000 | [9 empty] | 172.76 |  |  | 172.76
|  |  | SCHWEITZER ENGINEERING LABS INC | [9 empty] | 8820 | 11668.44 |  | 20488.44
|  | Material - Direct Purchase Total | [5 empty] | 62343.48 |  |  |  |  | 8992.76 | 11668.44 |  | 83004.68
| Protection and Test-DP Total | [6 empty] | 62343.48 |  |  |  |  | 8992.76 | 11668.44 |  | 83004.68
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 722 |  | 722
|  |  | Steel / Fabricated / Structural-DP | [11 empty] | 91531.81 | 91531.81
|  |  | WASHINGTON ORNAMENTAL | [9 empty] | 619325.9 | 17539.2 |  | 636865.1
|  |  | WESTMONT INDUSTRIES | [7 empty] | 22494.96 |  |  |  |  | 22494.96
|  | Material - Direct Purchase Total | [8 empty] | 22494.96 |  | 619325.9 | 18261.2 | 91531.81 | 751613.87
| Steel / Fabricated / Structural-DP Total | [9 empty] | 22494.96 |  | 619325.9 | 18261.2 | 91531.81 | 751613.87
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 4434.53 | 2618.88 |  | 432.98 |  |  |  | 14.88 | 6.89 | 132.62 | 197.64 | 7838.42
|  |  | Transportation & Mobile Equip-DP |  |  | 11047.92 | 5566.78 | [8 empty] | 16614.7
|  | Material - Direct Purchase Total |  |  | 4434.53 | 13666.8 | 5566.78 | 432.98 |  |  |  | 14.88 | 6.89 | 132.62 | 197.64 | 24453.12
| Transportation & Mobile Equip-DP Total |  |  |  | 4434.53 | 13666.8 | 5566.78 | 432.98 |  |  |  | 14.88 | 6.89 | 132.62 | 197.64 | 24453.12
2. Material Total |  |  |  | 0 | 820704.02 | 110965.83 | 334469.16 | 69041.44 | 0.01 | 1485.66 | 24337.76 | 24110.41 | 732490.95 | 135298.19 | 190837.63 | 2443741.06
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [5 empty] | 257.6 | 257.6 |  |  | 1856 |  | 3889.42 | 6260.62
|  | Contract Total | [6 empty] | 257.6 | 257.6 |  |  | 1856 |  | 3889.42 | 6260.62
| Construction Management Services Total | [7 empty] | 257.6 | 257.6 |  |  | 1856 |  | 3889.42 | 6260.62
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [9 empty] | 120 |  |  | 120
|  | Contract Total | [10 empty] | 120 |  |  | 120
| Construction, Civil/Structural Total | [11 empty] | 120 |  |  | 120
| Decontamination & Waste Disposal Service | Contract | Contract Entries <$50,000 | [11 empty] | 35691 | 35691
|  | Contract Total | [12 empty] | 35691 | 35691
| Decontamination & Waste Disposal Service Total | [13 empty] | 35691 | 35691
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 166.86 | 166.86
|  | Labor Total | [12 empty] | 166.86 | 166.86
| ELEC SYS PLANNING Total | [13 empty] | 166.86 | 166.86
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  |  | 307.31 | 292.02 | 83.35 | 333.74 | 500.62 | 333.74 |  | 166.86 |  | 2017.64
|  | Labor Total |  |  |  |  | 307.31 | 292.02 | 83.35 | 333.74 | 500.62 | 333.74 |  | 166.86 |  | 2017.64
| ENGINEERING Total | [5 empty] | 307.31 | 292.02 | 83.35 | 333.74 | 500.62 | 333.74 |  | 166.86 |  | 2017.64
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 |  |  |  |  | 1397 | [5 empty] | 114.8 | 229.6 | 1741.4
|  | Contract Total | [5 empty] | 1397 | [5 empty] | 114.8 | 229.6 | 1741.4
| Hauling / Industrial Moving Services Total | [6 empty] | 1397 | [5 empty] | 114.8 | 229.6 | 1741.4
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [11 empty] | 21672 | 21672
|  | Contract Total | [12 empty] | 21672 | 21672
| Major Construction, Turnkey, Trans/Subs Total | [13 empty] | 21672 | 21672
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | [10 empty] | 2065.28 |  | 2065.28
|  | Labor Total | [11 empty] | 2065.28 |  | 2065.28
| N/W SUBSMTCETEST&APP Total | [12 empty] | 2065.28 |  | 2065.28
| SC&M | Labor | Labor Entries <$5,000 |  |  | 499.08 |  | 869.71 | 432.9 |  | 573.46 | 1167.36 | 447.49 | 1129.05 | 2351.79 | 7470.84
|  | Labor Total |  |  |  | 499.08 |  | 869.71 | 432.9 |  | 573.46 | 1167.36 | 447.49 | 1129.05 | 2351.79 | 7470.84
| SC&M Total |  |  |  |  | 499.08 |  | 869.71 | 432.9 |  | 573.46 | 1167.36 | 447.49 | 1129.05 | 2351.79 | 7470.84
| SCM HOME CENTER | Labor | Labor Entries <$5,000 | [10 empty] | 117.3 | 206.35 | 323.65
|  | Labor Total | [11 empty] | 117.3 | 206.35 | 323.65
| SCM HOME CENTER Total | [12 empty] | 117.3 | 206.35 | 323.65
| TRANSMISSION | Labor | Labor Entries <$5,000 | [6 empty] | 480.22 | -475.04 |  |  |  |  | 5.18
|  | Labor Total | [7 empty] | 480.22 | -475.04 |  |  |  |  | 5.18
| TRANSMISSION Total | [8 empty] | 480.22 | -475.04 |  |  |  |  | 5.18
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 |  |  |  |  | 82 | [7 empty] | 82
|  | Labor Total | [5 empty] | 82 | [7 empty] | 82
| TSD-HERC - Crane Svs Total | [6 empty] | 82 | [7 empty] | 82
3. Construction Total | [5 empty] | 499.08 | 307.31 | 2640.73 | 773.85 | 1071.56 | 599.04 | 1501.1 | 2423.49 | 3593.29 | 64207.02 | 77616.47
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 1433.68 | 1915.48 | 4064.97 | 6257.59 | -5140.97 | -41756.15 | 7107.83 | 4326.07 | 51254.4 | -39054.51 | 11016.46 | -26919.69 | -25494.84
|  |  | PDP- Sub Eldorado S UpgradesEITP-T&D | 7912.11 |  | 24161.78 | 63956.79 | 58982.41 | 51075.84 | 117141.53 | 58189.64 |  | 202580.84 | 184562.28 | 178194.57 | 946757.79
|  |  | PROCUREMENT TDBU |  | 5026.57 | [7 empty] | 6197.93 |  |  | 11224.5
|  | Chargeback Total |  | 9345.79 | 6942.05 | 28226.75 | 70214.38 | 53841.44 | 9319.69 | 124249.36 | 62515.71 | 51254.4 | 169724.26 | 195578.74 | 151274.88 | 932487.45
| Chargebacks Total |  |  | 9345.79 | 6942.05 | 28226.75 | 70214.38 | 53841.44 | 9319.69 | 124249.36 | 62515.71 | 51254.4 | 169724.26 | 195578.74 | 151274.88 | 932487.45
| Labor - Other | Labor | Division Overhead |  | 69305.77 |  | 15468.25 | [5 empty] | 76535.02 |  |  | 161309.04
|  |  | Labor Entries <$5,000 | 736.63 | 495.03 | 9279.46 | 9292.02 | 5865.92 | 1503.45 | 6272.92 | 7707.16 | -9505.5 | 3713.05 | 5039.71 | 19042.97 | 59442.82
|  | Labor Total |  | 736.63 | 69800.8 | 9279.46 | 24760.27 | 5865.92 | 1503.45 | 6272.92 | 7707.16 | -9505.5 | 80248.07 | 5039.71 | 19042.97 | 220751.86
| Labor - Other Total |  |  | 736.63 | 69800.8 | 9279.46 | 24760.27 | 5865.92 | 1503.45 | 6272.92 | 7707.16 | -9505.5 | 80248.07 | 5039.71 | 19042.97 | 220751.86
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -5191.95 | 5191.95 |  |  | 0
|  | Overhead Total | [9 empty] | -5191.95 | 5191.95 |  |  | 0
| Overhead Correction Total | [10 empty] | -5191.95 | 5191.95 |  |  | 0
4. Allocated Total |  |  |  | 10082.42 | 76742.85 | 37506.21 | 94974.65 | 59707.36 | 10823.14 | 130522.28 | 70222.87 | 36556.95 | 255164.28 | 200618.45 | 170317.85 | 1153239.31
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax | [11 empty] | 15619.82 | 15619.82
|  |  | Capitalized Overhead - A&G | 1700.45 | 26959.31 | 6333.49 | 16557.56 | 13183.24 | 1183.4 | 7252.59 | 4298.93 | 7915.99 | 25377.34 | 9187.35 | 13235.07 | 133184.72
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1698.65 | 2163.15 | 1283.56 | 2732.19 | 5049.33 | 8225.34 | 8993.43 | 7775.82 | 1704.97 | 4439.26 | 6600.89 | 56656.5 | 107323.09
|  |  | Corporate Overheads Correction |  |  |  |  | -22298.83 | [7 empty] | -22298.83
|  | Non Budgeted Total |  | 3399.1 | 29122.46 | 7617.05 | 19289.75 | -4066.26 | 9408.74 | 16246.02 | 12074.75 | 9620.96 | 29816.6 | 15788.24 | 85511.39 | 233828.8
| Non Budget - Other Total |  |  | 3399.1 | 29122.46 | 7617.05 | 19289.75 | -4066.26 | 9408.74 | 16246.02 | 12074.75 | 9620.96 | 29816.6 | 15788.24 | 85511.39 | 233828.8
5. Corporate Overhead Total |  |  |  | 3399.1 | 29122.46 | 7617.05 | 19289.75 | -4066.26 | 9408.74 | 16246.02 | 12074.75 | 9620.96 | 29816.6 | 15788.24 | 85511.39 | 233828.8
Grand Total |  |  |  | 33867.96 | 960507.62 | 609335.24 | 96820.65 | 105922.88 | 42566.21 | 222796.55 | 164059.05 | 192241.38 | 1013212.83 | 396613.62 | 525729.41 | 4363673.4

## 900316933
Pin: 6551 | Project: Eldorado-Ivanpah (EITP)
Order: 900316933 | 900316933- Ivanpah: Construct a New Substation, EIT
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [10 empty] | 189.58 |  | 189.58
|  | Labor Total | [11 empty] | 189.58 |  | 189.58
| BP&FM Total | [12 empty] | 189.58 |  | 189.58
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [7 empty] | 103.34 |  | 282.72 |  |  | 386.06
|  | Contract Total | [8 empty] | 103.34 |  | 282.72 |  |  | 386.06
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [9 empty] | 103.34 |  | 282.72 |  |  | 386.06
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 230059.74 |  |  | 230059.74
|  |  | Contract Entries <$50,000 | [8 empty] | -230059.74 |  |  |  | -230059.74
|  | Contract Total | [9 empty] | -230059.74 | 230059.74 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -230059.74 | 230059.74 |  |  | 0
| Contract - Other - Correction | Contract | Contract Entries <$50,000 | [7 empty] | 298 |  |  |  |  | 298
|  | Contract Total | [8 empty] | 298 |  |  |  |  | 298
| Contract - Other - Correction Total | [9 empty] | 298 |  |  |  |  | 298
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | [7 empty] | 1319.01 | 6748.01 | 26352.15 | 4456.78 | 10197.61 | 49073.56
|  | Contract Total | [8 empty] | 1319.01 | 6748.01 | 26352.15 | 4456.78 | 10197.61 | 49073.56
| Contract Consult/Contract Ord to Ord Total | [9 empty] | 1319.01 | 6748.01 | 26352.15 | 4456.78 | 10197.61 | 49073.56
| Corporate Security | Labor | Labor Entries <$5,000 | [9 empty] | 1056.17 | 1050.25 | 792.13 | 2898.55
|  | Labor Total | [10 empty] | 1056.17 | 1050.25 | 792.13 | 2898.55
| Corporate Security Total | [11 empty] | 1056.17 | 1050.25 | 792.13 | 2898.55
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [6 empty] | 47.78 |  |  |  |  | 13807.01 | 13854.79
|  | Labor Total | [7 empty] | 47.78 |  |  |  |  | 13807.01 | 13854.79
| ELEC SYS PLANNING Total | [8 empty] | 47.78 |  |  |  |  | 13807.01 | 13854.79
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 71.5 |  | 24.14 | 48.46 | 38.78 | 205.18 | 367.63 | 338.44 | 253.37 | 300.72 | 205.22 | 1853.44
|  | Labor Total |  |  | 71.5 |  | 24.14 | 48.46 | 38.78 | 205.18 | 367.63 | 338.44 | 253.37 | 300.72 | 205.22 | 1853.44
| ENG ADVANCEMENT Total |  |  |  | 71.5 |  | 24.14 | 48.46 | 38.78 | 205.18 | 367.63 | 338.44 | 253.37 | 300.72 | 205.22 | 1853.44
| ENGINEERING | Labor | Labor Entries <$5,000 | 4195.48 | 9850.98 | 16066.58 | 8271.62 | 10212.81 | 11385.62 | 18091.87 | 15370.23 | 16453.61 | 18211.03 | 21137.04 |  | 149246.87
|  | Labor Total |  | 4195.48 | 9850.98 | 16066.58 | 8271.62 | 10212.81 | 11385.62 | 18091.87 | 15370.23 | 16453.61 | 18211.03 | 21137.04 |  | 149246.87
| ENGINEERING Total |  |  | 4195.48 | 9850.98 | 16066.58 | 8271.62 | 10212.81 | 11385.62 | 18091.87 | 15370.23 | 16453.61 | 18211.03 | 21137.04 |  | 149246.87
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 24000 |  | 6480 | 45993.5 | 43218.5 |  |  | 17272 | 48355.4 | 25017.5 | 49226.25 | 64958.98 | 324522.13
|  |  | ORSA CONSULTING ENGINEERS INC |  |  | 141874 |  |  |  | 150922.73 | 107995 |  |  |  |  | 400791.73
|  | Contract Total |  | 24000 |  | 148354 | 45993.5 | 43218.5 |  | 150922.73 | 125267 | 48355.4 | 25017.5 | 49226.25 | 64958.98 | 725313.86
| Engineering/Technical Professional Servi Total |  |  | 24000 |  | 148354 | 45993.5 | 43218.5 |  | 150922.73 | 125267 | 48355.4 | 25017.5 | 49226.25 | 64958.98 | 725313.86
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 2002.46 |  | 527 |  |  | 282 | 0 | [5 empty] | 2811.46
|  | Contract Total |  | 2002.46 |  | 527 |  |  | 282 | 0 | [5 empty] | 2811.46
| Environmental/Safety Professional Servic Total |  |  | 2002.46 |  | 527 |  |  | 282 | 0 | [5 empty] | 2811.46
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 19576.09 | 6586.73 | 19323.81 | 18544.9 | 10458.07 | 18010.09 | 14149.27 | 8993.43 | 339533.71 | -332101.42 | -9966.85 | -26300.07 | 86807.76
|  | IMM Correction Total |  | 19576.09 | 6586.73 | 19323.81 | 18544.9 | 10458.07 | 18010.09 | 14149.27 | 8993.43 | 339533.71 | -332101.42 | -9966.85 | -26300.07 | 86807.76
| IMM/Allocated - Correction Total |  |  | 19576.09 | 6586.73 | 19323.81 | 18544.9 | 10458.07 | 18010.09 | 14149.27 | 8993.43 | 339533.71 | -332101.42 | -9966.85 | -26300.07 | 86807.76
| Labor - Other | Labor | Labor Entries <$5,000 | -11 | 2086.66 | -1948.37 | -44.21 | 2998.42 | -3562.31 | 383.72 | 6628.15 | 44766.82 | -38652.94 | -7395.88 | 5732.59 | 10981.65
|  | Labor Total |  | -11 | 2086.66 | -1948.37 | -44.21 | 2998.42 | -3562.31 | 383.72 | 6628.15 | 44766.82 | -38652.94 | -7395.88 | 5732.59 | 10981.65
| Labor - Other Total |  |  | -11 | 2086.66 | -1948.37 | -44.21 | 2998.42 | -3562.31 | 383.72 | 6628.15 | 44766.82 | -38652.94 | -7395.88 | 5732.59 | 10981.65
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 5085.58 | -331.99 | 3272.21 | 1456.03 | 2789.67 | -116.81 | 4547.51 | -106.09 | -144.61 | -53.59 | -65.21 | -59.78 | 16272.92
|  |  | MAJOR PROJECT ORG / Mgr-Prj/Prod |  | 6270.54 |  |  |  | 6131.72 |  | 5227.04 | 7036.4 | 5428.08 | 8242.64 | 6232.24 | 44568.66
|  | Labor Total |  | 5085.58 | 5938.55 | 3272.21 | 1456.03 | 2789.67 | 6014.91 | 4547.51 | 5120.95 | 6891.79 | 5374.49 | 8177.43 | 6172.46 | 60841.58
| MAJOR PROJECT ORG Total |  |  | 5085.58 | 5938.55 | 3272.21 | 1456.03 | 2789.67 | 6014.91 | 4547.51 | 5120.95 | 6891.79 | 5374.49 | 8177.43 | 6172.46 | 60841.58
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [7 empty] | 278.99 | 437.66 | 435.92 |  |  | 1152.57
|  | Labor Total | [8 empty] | 278.99 | 437.66 | 435.92 |  |  | 1152.57
| NORTH GRIDMGMTCENTER Total | [9 empty] | 278.99 | 437.66 | 435.92 |  |  | 1152.57
| Other | Other | Other | -6672 | 70730.61 | -70730.61 | 670.75 | 1560.48 | 65882.06 | 962757.12 | -862439.07 | 439389.17 | 1793461.43 | -858421.89 | -926027.63 | 610160.42
|  | Other Total |  | -6672 | 70730.61 | -70730.61 | 670.75 | 1560.48 | 65882.06 | 962757.12 | -862439.07 | 439389.17 | 1793461.43 | -858421.89 | -926027.63 | 610160.42
| Other Total |  |  | -6672 | 70730.61 | -70730.61 | 670.75 | 1560.48 | 65882.06 | 962757.12 | -862439.07 | 439389.17 | 1793461.43 | -858421.89 | -926027.63 | 610160.42
| SC&M | Labor | Labor Entries <$5,000 | 1439.6 | 769.11 | 377.75 | 3205.98 | 3272.57 | 3501.26 | 2678.73 | 9741.22 | 7826.82 | 9686.48 | 8642.53 | 5093.65 | 56235.7
|  |  | SC&M / Mgr-Prj/Prod | [10 empty] | 6003.92 |  | 6003.92
|  | Labor Total |  | 1439.6 | 769.11 | 377.75 | 3205.98 | 3272.57 | 3501.26 | 2678.73 | 9741.22 | 7826.82 | 9686.48 | 14646.45 | 5093.65 | 62239.62
| SC&M Total |  |  | 1439.6 | 769.11 | 377.75 | 3205.98 | 3272.57 | 3501.26 | 2678.73 | 9741.22 | 7826.82 | 9686.48 | 14646.45 | 5093.65 | 62239.62
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  |  | 484.33 | 1056.97 | 1400.64 | 1761.61 | 1944.74 | 1541.41 | 1673.54 | 2362.84 | 1527.75 | 13753.83
|  | Labor Total |  |  |  |  | 484.33 | 1056.97 | 1400.64 | 1761.61 | 1944.74 | 1541.41 | 1673.54 | 2362.84 | 1527.75 | 13753.83
| SCM HOME CENTER Total | [5 empty] | 484.33 | 1056.97 | 1400.64 | 1761.61 | 1944.74 | 1541.41 | 1673.54 | 2362.84 | 1527.75 | 13753.83
| Software License Via Electronic Delivery | Contract | Contract Entries <$50,000 | [11 empty] | 7810.6 | 7810.6
|  | Contract Total | [12 empty] | 7810.6 | 7810.6
| Software License Via Electronic Delivery Total | [13 empty] | 7810.6 | 7810.6
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 | [8 empty] | 207.17 |  | 208.05 |  | 415.22
|  | Labor Total | [9 empty] | 207.17 |  | 208.05 |  | 415.22
| TEC SRVCS SUMMARY Total | [10 empty] | 207.17 |  | 208.05 |  | 415.22
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -2041.35 | 2041.35 |  |  | 0
|  | Contract Total | [9 empty] | -2041.35 | 2041.35 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -2041.35 | 2041.35 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 340 | [11 empty] | 340
|  | Contract Total |  | 340 | [11 empty] | 340
| Temporary/Supplementary - Technical/Prof Total |  |  | 340 | [11 empty] | 340
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 775.96 | 1709.86 | 2912.21 | 10083.26 | 4129.55 | 7733.55 | 4850.56 | 4411.72 | 1503.12 | 6648.26 | 4625.14 | 9357.29 | 58740.48
|  | Contract Total |  | 775.96 | 1709.86 | 2912.21 | 10083.26 | 4129.55 | 7733.55 | 4850.56 | 4411.72 | 1503.12 | 6648.26 | 4625.14 | 9357.29 | 58740.48
| Temporary/Supplementary - Trade/Labor Total |  |  | 775.96 | 1709.86 | 2912.21 | 10083.26 | 4129.55 | 7733.55 | 4850.56 | 4411.72 | 1503.12 | 6648.26 | 4625.14 | 9357.29 | 58740.48
1. Project Support Total |  |  |  | 50732.17 | 97744 | 118154.58 | 88690.3 | 79745.5 | 110686.6 | 1160396.08 | -682594.66 | 681892.04 | 1749799.79 | -769404.09 | -826672.41 | 1859169.9
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | Material Entries <$5,000 | 0 | [11 empty] | 0
|  |  | MITSUBISHI ELECTRIC | 1739717 | [11 empty] | 1739717
|  | Material - Direct Purchase Total |  | 1739717 | [11 empty] | 1739717
| Breakers - Circuit-DP Total |  |  | 1739717 | [11 empty] | 1739717
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp | [6 empty] | 41213.48 |  |  | 13610.18 | 11705.16 |  | 66528.82
|  |  | JENSEN PRECAST | [9 empty] | 179687.06 |  | 34091.04 | 213778.1
|  |  | Material Entries <$5,000 | [7 empty] | 3750.93 | 687.53 |  | 338 | 1121.84 | 5898.3
|  | Material - Direct Purchase Total | [7 empty] | 41213.48 | 3750.93 | 687.53 | 193297.24 | 12043.16 | 35212.88 | 286205.22
| Building, Shop & Industrial Products/Eqp Total | [8 empty] | 41213.48 | 3750.93 | 687.53 | 193297.24 | 12043.16 | 35212.88 | 286205.22
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | CROWN TECHNICAL SYSTEMS |  |  |  | 696114 |  |  | 177426 |  |  |  |  | 6122.74 | 879662.74
|  |  | Material Entries <$5,000 | [9 empty] | 249.98 | 249.98 |  | 499.96
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [7 empty] | 167716 | 57007 |  |  |  | 224723
|  | Material - Direct Purchase Total |  |  |  |  | 696114 |  |  | 177426 | 167716 | 57007 | 249.98 | 249.98 | 6122.74 | 1104885.7
| Cabinets, Panels and Switchboards-DP Total | [5 empty] | 696114 |  |  | 177426 | 167716 | 57007 | 249.98 | 249.98 | 6122.74 | 1104885.7
| Communication Systems and Equipment -DP | Material - Direct Purchase | Communication Systems and Equipment -DP | [11 empty] | 42966 | 42966
|  |  | DAQ ELECTRONICS, LLC | [11 empty] | 15525 | 15525
|  |  | Material Entries <$5,000 | [6 empty] | 3052.57 | [5 empty] | 3052.57
|  | Material - Direct Purchase Total | [7 empty] | 3052.57 |  |  |  |  | 58491 | 61543.57
| Communication Systems and Equipment -DP Total | [8 empty] | 3052.57 |  |  |  |  | 58491 | 61543.57
| Electric Wiring and Components-DP | Material - Direct Purchase | CROSS BROTHERS INC | [11 empty] | 8778 | 8778
|  |  | Electric Wiring and Components-DP | [10 empty] | 65228.49 | 34953.78 | 100182.27
|  |  | Material Entries <$5,000 |  |  |  |  | 1137.52 |  | 996.86 |  | 1996.42 | 4587.83 | 1972 |  | 10690.63
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [5 empty] | 34320.94 | 19007.46 | 67027.55 |  |  | 6652.66 | 13797.22 | 140805.83
|  |  | SOUTHWIRE COMPANY | [10 empty] | 28290 |  | 28290
|  | Material - Direct Purchase Total | [5 empty] | 1137.52 | 34320.94 | 20004.32 | 67027.55 | 1996.42 | 4587.83 | 102143.15 | 57529 | 288746.73
| Electric Wiring and Components-DP Total | [6 empty] | 1137.52 | 34320.94 | 20004.32 | 67027.55 | 1996.42 | 4587.83 | 102143.15 | 57529 | 288746.73
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | AIRGAS WEST | [10 empty] | 8928.74 |  | 8928.74
|  | Material - Direct Purchase Total | [11 empty] | 8928.74 |  | 8928.74
| Fuels, Chemicals & Petrochem-DP Total | [12 empty] | 8928.74 |  | 8928.74
| Insulators & Bushings-DP | Material - Direct Purchase | Insulators & Bushings-DP | [8 empty] | 5899.49 |  | 121741.2 |  | 127640.69
|  |  | Material Entries <$5,000 | [9 empty] | 1178.21 |  |  | 1178.21
|  | Material - Direct Purchase Total | [9 empty] | 5899.49 | 1178.21 | 121741.2 |  | 128818.9
| Insulators & Bushings-DP Total | [10 empty] | 5899.49 | 1178.21 | 121741.2 |  | 128818.9
| Material - Inventory | Material | Material - Inventory | [6 empty] | 129378.44 | 157132.37 | 844302.51 | 275378.71 | 136370.47 | 134776.5 | 1677339
|  | Material Total | [7 empty] | 129378.44 | 157132.37 | 844302.51 | 275378.71 | 136370.47 | 134776.5 | 1677339
| Material - Inventory Total | [8 empty] | 129378.44 | 157132.37 | 844302.51 | 275378.71 | 136370.47 | 134776.5 | 1677339
| Material - Other | Material | Material - Other | 136755 | 55.21 | 0.04 | 97667.06 | 7827.7 | 10413.63 | 55375.26 | 79490.96 | 218871.75 | 72706.78 | 208089.91 | 88538.05 | 975791.35
|  | Material Total |  | 136755 | 55.21 | 0.04 | 97667.06 | 7827.7 | 10413.63 | 55375.26 | 79490.96 | 218871.75 | 72706.78 | 208089.91 | 88538.05 | 975791.35
| Material - Other Total |  |  | 136755 | 55.21 | 0.04 | 97667.06 | 7827.7 | 10413.63 | 55375.26 | 79490.96 | 218871.75 | 72706.78 | 208089.91 | 88538.05 | 975791.35
| Material Handling Services | Contract | Contract Entries <$50,000 | [9 empty] | 8940 |  | 2980 | 11920
|  | Contract Total | [10 empty] | 8940 |  | 2980 | 11920
| Material Handling Services Total | [11 empty] | 8940 |  | 2980 | 11920
| Mechanical Systems and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 156.96 | [5 empty] | 156.96
|  | Material - Direct Purchase Total | [7 empty] | 156.96 | [5 empty] | 156.96
| Mechanical Systems and Components-DP Total | [8 empty] | 156.96 | [5 empty] | 156.96
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | DAHL TAYLOR & ASSOCIATES, INC. |  |  |  | 571818 | [8 empty] | 571818
|  |  | Material Entries <$5,000 |  |  |  |  | -1240 |  | 177.16 |  | 3520.53 | 2195.4 | 3200.01 | 1140.62 | 8993.72
|  | Material - Direct Purchase Total |  |  |  |  | 571818 | -1240 |  | 177.16 |  | 3520.53 | 2195.4 | 3200.01 | 1140.62 | 580811.72
| Metals & Fabricated Metal Products-DP Total | [5 empty] | 571818 | -1240 |  | 177.16 |  | 3520.53 | 2195.4 | 3200.01 | 1140.62 | 580811.72
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | MAGNETIC INSTRUMENTATION INC | [7 empty] | 192435 |  |  |  |  | 192435
|  |  | Material Entries <$5,000 | [6 empty] | 0 | [5 empty] | 0
|  |  | RONAN ENGINEERING COMPANY | [6 empty] | 48499 | [5 empty] | 48499
|  | Material - Direct Purchase Total | [7 empty] | 48499 | 192435 |  |  |  |  | 240934
| Meters, Monitor and Warnings-DP Total | [8 empty] | 48499 | 192435 |  |  |  |  | 240934
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 1000.64 |  | 1299.86 |  |  |  | 2300.5
|  | Material - Direct Purchase Total | [7 empty] | 1000.64 |  | 1299.86 |  |  |  | 2300.5
| Office & Office Support Products-DP Total | [8 empty] | 1000.64 |  | 1299.86 |  |  |  | 2300.5
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 1105 | 311.86 | 317.01 | 816.56 | 2550.43
|  | Material - Direct Purchase Total | [9 empty] | 1105 | 311.86 | 317.01 | 816.56 | 2550.43
| Pipe/Tubing, Fittings and Gaskets-DP Total | [10 empty] | 1105 | 311.86 | 317.01 | 816.56 | 2550.43
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 3428 |  |  | 3178.52 | 421.27 |  |  |  | 2392.77 | 9420.56
|  |  | Pole Line Hdwe & Connectors-DP | [8 empty] | 8630.77 | 10572.85 | 7341.72 |  | 26545.34
|  |  | POWER-GLASS INC. | [5 empty] | 56220.09 | [6 empty] | 56220.09
|  | Material - Direct Purchase Total |  |  |  |  | 3428 |  | 56220.09 | 3178.52 | 421.27 | 8630.77 | 10572.85 | 7341.72 | 2392.77 | 92185.99
| Pole Line Hdwe & Connectors-DP Total | [5 empty] | 3428 |  | 56220.09 | 3178.52 | 421.27 | 8630.77 | 10572.85 | 7341.72 | 2392.77 | 92185.99
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | BENNING POWER ELECTRONICS INC | [6 empty] | 10531 | [5 empty] | 10531
|  |  | ENERSYS DELAWARE INC | [6 empty] | 55104.6 | [5 empty] | 55104.6
|  |  | Power Systems, Batteries and Light-DP | [11 empty] | 146300 | 146300
|  | Material - Direct Purchase Total | [7 empty] | 65635.6 |  |  |  |  | 146300 | 211935.6
| Power Systems, Batteries and Light-DP Total | [8 empty] | 65635.6 |  |  |  |  | 146300 | 211935.6
| Protection and Test-DP | Material - Direct Purchase | ABB INC |  |  |  |  | 98861.14 | [7 empty] | 98861.14
|  |  | Material Entries <$5,000 | [8 empty] | 1074.47 | 1612.19 |  |  | 2686.66
|  | Material - Direct Purchase Total | [5 empty] | 98861.14 |  |  |  | 1074.47 | 1612.19 |  |  | 101547.8
| Protection and Test-DP Total | [6 empty] | 98861.14 |  |  |  | 1074.47 | 1612.19 |  |  | 101547.8
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 1080 |  | 1080
|  |  | PARCELL STEEL CO | [7 empty] | 52460.75 | 33688.45 |  |  |  | 86149.2
|  |  | Steel / Fabricated / Structural-DP | [8 empty] | 351569.9 |  |  | 23147.5 | 374717.4
|  |  | WASHINGTON ORNAMENTAL | [5 empty] | 41900.26 | 163515.81 |  | 34051.95 | 25101 | 423519 |  | 688088.02
|  | Material - Direct Purchase Total | [6 empty] | 41900.26 | 163515.81 | 52460.75 | 419310.3 | 25101 | 424599 | 23147.5 | 1150034.62
| Steel / Fabricated / Structural-DP Total | [7 empty] | 41900.26 | 163515.81 | 52460.75 | 419310.3 | 25101 | 424599 | 23147.5 | 1150034.62
| Transformers - Distribution-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 1662 |  |  | 1662
|  | Material - Direct Purchase Total | [10 empty] | 1662 |  |  | 1662
| Transformers - Distribution-DP Total | [11 empty] | 1662 |  |  | 1662
| Transformers - Power Substation-DP | Material - Direct Purchase | HYUNDAI CORPORATION USA | [8 empty] | 941866.5 |  | 1506986.4 | 470933.25 | 2919786.15
|  | Material - Direct Purchase Total | [9 empty] | 941866.5 |  | 1506986.4 | 470933.25 | 2919786.15
| Transformers - Power Substation-DP Total | [10 empty] | 941866.5 |  | 1506986.4 | 470933.25 | 2919786.15
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 478.2 | 478.2
|  | Material - Direct Purchase Total | [12 empty] | 478.2 | 478.2
| Transformers CT/PT/INSTR-DP Total | [13 empty] | 478.2 | 478.2
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 1834.18 | 5502.55 |  |  |  | 446.45 | 47.77 | 3267.98 | 140.89 | 29.2 | 169.65 | 378.11 | 11816.78
|  |  | Transportation & Mobile Equip-DP | 27339.67 | 27555.57 | [10 empty] | 54895.24
|  | Material - Direct Purchase Total |  | 29173.85 | 33058.12 |  |  |  | 446.45 | 47.77 | 3267.98 | 140.89 | 29.2 | 169.65 | 378.11 | 66712.02
| Transportation & Mobile Equip-DP Total |  |  | 29173.85 | 33058.12 |  |  |  | 446.45 | 47.77 | 3267.98 | 140.89 | 29.2 | 169.65 | 378.11 | 66712.02
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | ANIXTER INC | [8 empty] | 51280 |  |  |  | 51280
|  |  | Material Entries <$5,000 | [7 empty] | 384.8 | 434.64 | 21.74 |  |  | 841.18
|  |  | Wire, Cable & Bus Bar-DP |  |  |  | 43852.5 |  |  |  | 20382.78 |  |  | 5325.21 | 51408.53 | 120969.02
|  | Material - Direct Purchase Total |  |  |  |  | 43852.5 |  |  |  | 20767.58 | 51714.64 | 21.74 | 5325.21 | 51408.53 | 173090.2
| Wire, Cable & Bus Bar-DP Total | [5 empty] | 43852.5 |  |  |  | 20767.58 | 51714.64 | 21.74 | 5325.21 | 51408.53 | 173090.2
2. Material Total |  |  |  | 1905645.85 | 33113.33 | 0.04 | 1412879.56 | 106586.36 | 143301.37 | 708661.53 | 744470.39 | 2557427.66 | 597844.99 | 2537505.61 | 1080645.71 | 11828082.4
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 6672 | 1112 | 4448 | 10229.04 | 5896.86 | 6862.32 | 23194.66 | 13704.74 |  | 88964.39 | 112762.91 | 287250.65 | 561097.57
|  | Contract Total |  | 6672 | 1112 | 4448 | 10229.04 | 5896.86 | 6862.32 | 23194.66 | 13704.74 |  | 88964.39 | 112762.91 | 287250.65 | 561097.57
| Construction Management Services Total |  |  | 6672 | 1112 | 4448 | 10229.04 | 5896.86 | 6862.32 | 23194.66 | 13704.74 |  | 88964.39 | 112762.91 | 287250.65 | 561097.57
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [7 empty] | 10690.78 |  |  |  |  | 10690.78
|  |  | DAHL TAYLOR & ASSOCIATES, INC. | [10 empty] | 600507.62 |  | 600507.62
|  | Contract Total | [8 empty] | 10690.78 |  |  | 600507.62 |  | 611198.4
| Construction, Civil/Structural Total | [9 empty] | 10690.78 |  |  | 600507.62 |  | 611198.4
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 667.42 | 667.42
|  | Labor Total | [12 empty] | 667.42 | 667.42
| ELEC SYS PLANNING Total | [13 empty] | 667.42 | 667.42
| Electrical Construction, Substations | Contract | Contract Entries <$50,000 | [9 empty] | 0 |  |  | 0
|  |  | PROFESSIONAL ELECTRICAL CONSTRUCTIO | [8 empty] | 769177 | 901839 | 1012941 | 3314208 | 5998165
|  | Contract Total | [9 empty] | 769177 | 901839 | 1012941 | 3314208 | 5998165
| Electrical Construction, Substations Total | [10 empty] | 769177 | 901839 | 1012941 | 3314208 | 5998165
| Electrical Services | Contract | Contract Entries <$50,000 | [5 empty] | 4147.5 | [6 empty] | 4147.5
|  | Contract Total | [6 empty] | 4147.5 | [6 empty] | 4147.5
| Electrical Services Total | [7 empty] | 4147.5 | [6 empty] | 4147.5
| ENGINEERING | Labor | Labor Entries <$5,000 | 677.63 | 405.71 | 487.42 | 167.72 | 478.83 | 166.69 | 250.3 | 333.75 | 667.47 |  | 667.46 |  | 4302.98
|  | Labor Total |  | 677.63 | 405.71 | 487.42 | 167.72 | 478.83 | 166.69 | 250.3 | 333.75 | 667.47 |  | 667.46 |  | 4302.98
| ENGINEERING Total |  |  | 677.63 | 405.71 | 487.42 | 167.72 | 478.83 | 166.69 | 250.3 | 333.75 | 667.47 |  | 667.46 |  | 4302.98
| GRID OPS | Labor | Labor Entries <$5,000 | [8 empty] | 369.24 |  |  | 4110.7 | 4479.94
|  | Labor Total | [9 empty] | 369.24 |  |  | 4110.7 | 4479.94
| GRID OPS Total | [10 empty] | 369.24 |  |  | 4110.7 | 4479.94
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | 1397 | 1397 | [5 empty] | 5280.64 | 1397 | 1593.82 | 114.8 |  | 11180.26
|  | Contract Total |  | 1397 | 1397 | [5 empty] | 5280.64 | 1397 | 1593.82 | 114.8 |  | 11180.26
| Hauling / Industrial Moving Services Total |  |  | 1397 | 1397 | [5 empty] | 5280.64 | 1397 | 1593.82 | 114.8 |  | 11180.26
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [10 empty] | 9800 | 53146 | 62946
|  | Contract Total | [11 empty] | 9800 | 53146 | 62946
| Major Construction, Turnkey, Trans/Subs Total | [12 empty] | 9800 | 53146 | 62946
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | [8 empty] | 539.06 | 3266.13 | 2190.33 |  | 5995.52
|  | Labor Total | [9 empty] | 539.06 | 3266.13 | 2190.33 |  | 5995.52
| N/W SUBSMTCETEST&APP Total | [10 empty] | 539.06 | 3266.13 | 2190.33 |  | 5995.52
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [9 empty] | 377.1 |  |  | 377.1
|  | Labor Total | [10 empty] | 377.1 |  |  | 377.1
| NORTH GRIDMGMTCENTER Total | [11 empty] | 377.1 |  |  | 377.1
| SC&M | Labor | Labor Entries <$5,000 | 435.96 |  | 433.26 | 437.23 |  | 651.38 | 433.02 | 901.61 | 572.15 | 244.09 | 1151.42 |  | 5260.12
|  | Labor Total |  | 435.96 |  | 433.26 | 437.23 |  | 651.38 | 433.02 | 901.61 | 572.15 | 244.09 | 1151.42 |  | 5260.12
| SC&M Total |  |  | 435.96 |  | 433.26 | 437.23 |  | 651.38 | 433.02 | 901.61 | 572.15 | 244.09 | 1151.42 |  | 5260.12
| SCM HOME CENTER | Labor | Labor Entries <$5,000 | [5 empty] | 124.24 |  |  |  |  | 234.61 | 206.35 | 565.2
|  | Labor Total | [6 empty] | 124.24 |  |  |  |  | 234.61 | 206.35 | 565.2
| SCM HOME CENTER Total | [7 empty] | 124.24 |  |  |  |  | 234.61 | 206.35 | 565.2
| Security / Protection Services | Contract | Contract Entries <$50,000 |  | 947.5 | [10 empty] | 947.5
|  | Contract Total |  |  | 947.5 | [10 empty] | 947.5
| Security / Protection Services Total |  |  |  | 947.5 | [10 empty] | 947.5
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [7 empty] | 11392 | 18325.84 | 63894.04 | 61620.36 | 31729.56 | 186961.8
|  |  | GANNETT FLEMING, INC. | [8 empty] | 78750.85 | 54978 |  |  | 133728.85
|  | Contract Total | [8 empty] | 11392 | 97076.69 | 118872.04 | 61620.36 | 31729.56 | 320690.65
| Short Term Equipment Rent Total | [9 empty] | 11392 | 97076.69 | 118872.04 | 61620.36 | 31729.56 | 320690.65
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | 1120 | 2724.7 | [5 empty] | 82 | 82 | 82 |  |  | 4090.7
|  | Labor Total |  | 1120 | 2724.7 | [5 empty] | 82 | 82 | 82 |  |  | 4090.7
| TSD-HERC - Crane Svs Total |  |  | 1120 | 2724.7 | [5 empty] | 82 | 82 | 82 |  |  | 4090.7
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | [10 empty] | 82 | 82 | 164
|  | Labor Total | [11 empty] | 82 | 82 | 164
| TSD-HERC - Rental Total | [12 empty] | 82 | 82 | 164
3. Construction Total |  |  |  | 10302.59 | 6586.91 | 5368.68 | 10833.99 | 6375.69 | 11952.13 | 23877.98 | 42385.52 | 869880.61 | 1115238.57 | 1802072.51 | 3691400.68 | 7596275.86
4. Allocated | Chargebacks | Chargeback | BR Reprographics / DWG MGMT REPRGRAPHC | [9 empty] | 6504.03 |  |  | 6504.03
|  |  | Chargeback Entries <$5,000 | 3500.58 | 5764.82 | 10819.58 | 14110.81 | 2616.18 | -39584.67 | 16251.3 | 19003.4 | 59300.01 | -31604.4 | 192636.85 | -203494.91 | 49319.55
|  |  | EITP (MPO/BPFM) | [5 empty] | 5969.17 | 6885.41 |  | 8170.87 |  |  | 7439.31 | 28464.76
|  |  | Ivanpah Substation Security System Insta | [11 empty] | 605229.77 | 605229.77
|  |  | MATERIAL MANAGEM | [6 empty] | 24193.77 | 20505.77 | 152565.46 | 32246.85 | 23155.71 | 18100.48 | 270768.04
|  |  | PDP-Substransmision 115KV TL Ivanpah-T&D | 7912.12 |  | 24161.78 | 63956.79 | 58982.41 | 51075.86 | 117141.55 | 58189.63 |  | 202582.99 | 184521.52 | 172561.87 | 941086.52
|  |  | PROCUREMENT TDBU | 12989.36 |  |  | 9118.02 |  |  |  |  | 13752.47 | 9966.85 | 26300.07 | 30363.32 | 102490.09
|  | Chargeback Total |  | 24402.06 | 5764.82 | 34981.36 | 87185.62 | 61598.59 | 17460.36 | 164472.03 | 97698.8 | 233788.81 | 219696.32 | 426614.15 | 630199.84 | 2003862.76
| Chargebacks Total |  |  | 24402.06 | 5764.82 | 34981.36 | 87185.62 | 61598.59 | 17460.36 | 164472.03 | 97698.8 | 233788.81 | 219696.32 | 426614.15 | 630199.84 | 2003862.76
| Labor - Other | Labor | Division Overhead | 174995.58 |  | 5155.96 | 103525.97 |  |  | 59447.02 | 62484.69 | 197265.15 | 155837.24 | 103451.84 | 173198.85 | 1035362.3
|  |  | Labor Entries <$5,000 | 9069.91 | 10280.3 | 12868.64 | 4496.42 | 17054.87 | 16179.45 | 8257.8 | 4341.21 | 3806.68 | 7149.92 | 4713.09 | 2819.72 | 101038.01
|  |  | Paid Absence | [6 empty] | 5456.28 | 6594.45 | 6588.26 | 9321.6 | 8674.01 | 8071.05 | 44705.65
|  | Labor Total |  | 184065.49 | 10280.3 | 18024.6 | 108022.39 | 17054.87 | 16179.45 | 73161.1 | 73420.35 | 207660.09 | 172308.76 | 116838.94 | 184089.62 | 1181105.96
| Labor - Other Total |  |  | 184065.49 | 10280.3 | 18024.6 | 108022.39 | 17054.87 | 16179.45 | 73161.1 | 73420.35 | 207660.09 | 172308.76 | 116838.94 | 184089.62 | 1181105.96
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -5161.44 | 5161.44 |  |  | 0
|  | Overhead Total | [9 empty] | -5161.44 | 5161.44 |  |  | 0
| Overhead Correction Total | [10 empty] | -5161.44 | 5161.44 |  |  | 0
4. Allocated Total |  |  |  | 208467.55 | 16045.12 | 53005.96 | 195208.01 | 78653.46 | 33639.81 | 237633.13 | 171119.15 | 436287.46 | 397166.52 | 543453.09 | 814289.46 | 3184968.72
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 44788.69 | 2808.58 | [6 empty] | 171682.27 | 219279.54
|  |  | Capitalized Overhead - A&G | 121766.38 | 2424.52 | 8813.49 | 60894.44 | 22569.13 | 8415.76 | 41062.94 | 32475.45 | 180340 | 56445.02 | 131816.3 | 160173.83 | 827197.26
|  |  | Capitalized Overhead - Inj & Damages | 1999.96 | 131.02 | 79.97 | 1343.9 | 1392.04 | 205.26 | 866.69 | 1224.42 | 3102.62 | 2222.54 | 5048.91 | 1315.66 | 18932.99
|  |  | Capitalized Overhead - P&B/Payroll Tax | 9148.1 | 23948.23 | 21051.49 | 19478.45 | 35111.07 | 28960.39 | 38807.1 | 33093.52 | 50220.47 | 24530.43 | 39326.99 | 90656.24 | 414332.48
|  |  | Corporate Overheads Correction |  |  |  |  | -81109.85 | [7 empty] | -81109.85
|  | Non Budgeted Total |  | 132914.44 | 26503.77 | 29944.95 | 126505.48 | -19229.03 | 37581.41 | 80736.73 | 66793.39 | 233663.09 | 83197.99 | 176192.2 | 423828 | 1398632.42
| Non Budget - Other Total |  |  | 132914.44 | 26503.77 | 29944.95 | 126505.48 | -19229.03 | 37581.41 | 80736.73 | 66793.39 | 233663.09 | 83197.99 | 176192.2 | 423828 | 1398632.42
5. Corporate Overhead Total |  |  |  | 132914.44 | 26503.77 | 29944.95 | 126505.48 | -19229.03 | 37581.41 | 80736.73 | 66793.39 | 233663.09 | 83197.99 | 176192.2 | 423828 | 1398632.42
Grand Total |  |  |  | 2308062.6 | 179993.13 | 206474.21 | 1834117.34 | 252131.98 | 337161.32 | 2211305.45 | 342173.79 | 4779150.86 | 3943247.86 | 4289819.32 | 5183491.44 | 25867129.3

## 800586667
Pin: 6551 | Project: Eldorado-Ivanpah (EITP)
Order: 800586667 | 800586667- ACQ/Eldorado-Ivanpah Project: Primm Priv
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -307.88 | 307.88 |  |  | 0
|  | Contract Total | [9 empty] | -307.88 | 307.88 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -307.88 | 307.88 |  |  | 0
| HRealProp | Labor | Labor Entries <$5,000 | 2879.51 | 1329.42 | 1257.37 | 838.63 | 94.03 | 1990.83 |  | 1157.47 | 146 |  |  |  | 9693.26
|  | Labor Total |  | 2879.51 | 1329.42 | 1257.37 | 838.63 | 94.03 | 1990.83 |  | 1157.47 | 146 |  |  |  | 9693.26
| HRealProp Total |  |  | 2879.51 | 1329.42 | 1257.37 | 838.63 | 94.03 | 1990.83 |  | 1157.47 | 146 |  |  |  | 9693.26
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -0.02 | -3.36 | -3.85 | -6.71 | -5.64 | -2.55 |  | 305.62 | -307.88 | -6.98 |  | -31.37
|  | IMM Correction Total |  |  | -0.02 | -3.36 | -3.85 | -6.71 | -5.64 | -2.55 |  | 305.62 | -307.88 | -6.98 |  | -31.37
| IMM/Allocated - Correction Total |  |  |  | -0.02 | -3.36 | -3.85 | -6.71 | -5.64 | -2.55 |  | 305.62 | -307.88 | -6.98 |  | -31.37
| Information System Professional Services | Contract | Contract Entries <$50,000 | 3.19 | [11 empty] | 3.19
|  | Contract Total |  | 3.19 | [11 empty] | 3.19
| Information System Professional Services Total |  |  | 3.19 | [11 empty] | 3.19
| Labor - Other | Labor | Labor Entries <$5,000 | -27.66 | 336.34 | -310.93 | 33.09 | -6.62 | -46.22 | 22 | -11.02 | 6.51 | 4.66 | 83.2 | 11.59 | 94.94
|  | Labor Total |  | -27.66 | 336.34 | -310.93 | 33.09 | -6.62 | -46.22 | 22 | -11.02 | 6.51 | 4.66 | 83.2 | 11.59 | 94.94
| Labor - Other Total |  |  | -27.66 | 336.34 | -310.93 | 33.09 | -6.62 | -46.22 | 22 | -11.02 | 6.51 | 4.66 | 83.2 | 11.59 | 94.94
| Other | Other | Other | 1387 | 560 | 582.95 |  | 15044 | 187.95 |  |  |  | 750 |  |  | 18511.9
|  | Other Total |  | 1387 | 560 | 582.95 |  | 15044 | 187.95 |  |  |  | 750 |  |  | 18511.9
| Other Total |  |  | 1387 | 560 | 582.95 |  | 15044 | 187.95 |  |  |  | 750 |  |  | 18511.9
| RR | Labor | Labor Entries <$5,000 |  |  |  |  | 711.88 | 252.2 | 172.36 | 27.36 | 0.46 | 1.26 | 2.26 |  | 1167.78
|  | Labor Total | [5 empty] | 711.88 | 252.2 | 172.36 | 27.36 | 0.46 | 1.26 | 2.26 |  | 1167.78
| RR Total | [6 empty] | 711.88 | 252.2 | 172.36 | 27.36 | 0.46 | 1.26 | 2.26 |  | 1167.78
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  |  |  | 1016.4 | 762.3 | 386 |  | 342.9 |  |  |  |  | 2507.6
|  | Contract Total |  |  |  |  | 1016.4 | 762.3 | 386 |  | 342.9 |  |  |  |  | 2507.6
| Temporary/Supplementary - Trade/Labor Total | [5 empty] | 1016.4 | 762.3 | 386 |  | 342.9 |  |  |  |  | 2507.6
1. Project Support Total |  |  |  | 4242.04 | 2225.74 | 1526.03 | 1884.27 | 16598.88 | 2765.12 | 191.81 | 1516.71 | 150.71 | 755.92 | 78.48 | 11.59 | 31947.3
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 9.43 |  |  | 47.85 | [7 empty] | 57.28
|  | Material - Direct Purchase Total |  |  | 9.43 |  |  | 47.85 | [7 empty] | 57.28
| Transportation & Mobile Equip-DP Total |  |  |  | 9.43 |  |  | 47.85 | [7 empty] | 57.28
2. Material Total |  |  |  |  | 9.43 |  |  | 47.85 | [7 empty] | 57.28
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 0.02 | 3.36 | 3.85 | 6.71 | 193.26 | 49.12 | 73.69 | 2.26 | -2.03 | 6.98 |  |  | 337.22
|  | Chargeback Total |  | 0.02 | 3.36 | 3.85 | 6.71 | 193.26 | 49.12 | 73.69 | 2.26 | -2.03 | 6.98 |  |  | 337.22
| Chargebacks Total |  |  | 0.02 | 3.36 | 3.85 | 6.71 | 193.26 | 49.12 | 73.69 | 2.26 | -2.03 | 6.98 |  |  | 337.22
| Labor - Other | Labor | Labor Entries <$5,000 | 646.88 | 382.67 | 223.88 | 216.76 | 38.28 | 398.48 | 4.9 | 263.21 | 27.23 | 54.03 |  |  | 2256.32
|  | Labor Total |  | 646.88 | 382.67 | 223.88 | 216.76 | 38.28 | 398.48 | 4.9 | 263.21 | 27.23 | 54.03 |  |  | 2256.32
| Labor - Other Total |  |  | 646.88 | 382.67 | 223.88 | 216.76 | 38.28 | 398.48 | 4.9 | 263.21 | 27.23 | 54.03 |  |  | 2256.32
| Overhead Correction | Overhead | Overhead Correction | [11 empty] | -29.91 | -29.91
|  | Overhead Total | [12 empty] | -29.91 | -29.91
| Overhead Correction Total | [13 empty] | -29.91 | -29.91
4. Allocated Total |  |  |  | 646.9 | 386.03 | 227.73 | 223.47 | 231.54 | 447.6 | 78.59 | 265.47 | 25.2 | 61.01 |  | -29.91 | 2563.63
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 1811.94 | 115.98 | [6 empty] | 2013.42 | 3941.34
|  | Non Budgeted Total |  |  |  |  | 1811.94 | 115.98 | [6 empty] | 2013.42 | 3941.34
| Non Budget - Other Total | [5 empty] | 1811.94 | 115.98 | [6 empty] | 2013.42 | 3941.34
5. Corporate Overhead Total | [6 empty] | 1811.94 | 115.98 | [6 empty] | 2013.42 | 3941.34
Grand Total |  |  |  | 4888.94 | 2621.2 | 1753.76 | 3919.68 | 16994.25 | 3212.72 | 270.4 | 1782.18 | 175.91 | 816.93 | 78.48 | 1995.1 | 38509.55

## 800063786
Pin: 6551 | Project: Eldorado-Ivanpah (EITP)
Order: 800063786 | 800063786- 8363-8201--Ivanpah: Licensing Phase - Si
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [5 empty] | 90.35 | [6 empty] | 90.35
|  | Labor Total | [6 empty] | 90.35 | [6 empty] | 90.35
| BP&FM Total | [7 empty] | 90.35 | [6 empty] | 90.35
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  |  | 5922.28 | 6616.44 | 9.57 |  |  |  | 10.92 | 74.06 | 12633.27
|  | Contract Total | [5 empty] | 5922.28 | 6616.44 | 9.57 |  |  |  | 10.92 | 74.06 | 12633.27
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [6 empty] | 5922.28 | 6616.44 | 9.57 |  |  |  | 10.92 | 74.06 | 12633.27
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 263341.5 |  |  | 263341.5
|  |  | Contract Entries <$50,000 | [8 empty] | -263341.5 |  |  |  | -263341.5
|  | Contract Total | [9 empty] | -263341.5 | 263341.5 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -263341.5 | 263341.5 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 889.41 | 889.41
|  | Labor Total | [12 empty] | 889.41 | 889.41
| ELEC SYS PLANNING Total | [13 empty] | 889.41 | 889.41
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  |  | 281.04 | 1715.26 | 900.94 | 92.4 | [6 empty] | 2989.64
|  | Labor Total |  |  |  | 281.04 | 1715.26 | 900.94 | 92.4 | [6 empty] | 2989.64
| ENG ADVANCEMENT Total |  |  |  |  | 281.04 | 1715.26 | 900.94 | 92.4 | [6 empty] | 2989.64
| ENGINEERING | Labor | Labor Entries <$5,000 | 2476.14 | 2976.25 | 1664.8 | 2763.07 | 2232.55 | 3553.05 | 2052.61 | 1738.34 | 428.99 | 389.23 | 356.36 |  | 20631.39
|  | Labor Total |  | 2476.14 | 2976.25 | 1664.8 | 2763.07 | 2232.55 | 3553.05 | 2052.61 | 1738.34 | 428.99 | 389.23 | 356.36 |  | 20631.39
| ENGINEERING Total |  |  | 2476.14 | 2976.25 | 1664.8 | 2763.07 | 2232.55 | 3553.05 | 2052.61 | 1738.34 | 428.99 | 389.23 | 356.36 |  | 20631.39
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  | 51191.65 | [10 empty] | 51191.65
|  |  | CONVERSE CONSULTANTS |  | 125478.75 | [10 empty] | 125478.75
|  | Contract Total |  |  | 176670.4 | [10 empty] | 176670.4
| Engineering/Technical Professional Servi Total |  |  |  | 176670.4 | [10 empty] | 176670.4
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  | -47.05 | -1225.81 | -36.1 | -4.35 | -5.79 | -28.9 | -13.93 | 263660.92 | -263666.37 | -1747.99 | -7.64 | -3123.01
|  | IMM Correction Total |  |  | -47.05 | -1225.81 | -36.1 | -4.35 | -5.79 | -28.9 | -13.93 | 263660.92 | -263666.37 | -1747.99 | -7.64 | -3123.01
| IMM/Allocated - Correction Total |  |  |  | -47.05 | -1225.81 | -36.1 | -4.35 | -5.79 | -28.9 | -13.93 | 263660.92 | -263666.37 | -1747.99 | -7.64 | -3123.01
| Labor - Other | Labor | ACQ/Eldorado Ivanpah Trans Project(EITP) |  | 5278.34 |  |  | 6319.81 | 5791.09 | 9676.03 | 16912.65 | 16516.76 | 19768.78 | 19167.27 | 16482.77 | 115913.5
|  |  | GOV-MP-ACQ EL DORADO-IVANPAH-BLM09 |  |  |  | 9634.28 | 39747.91 |  |  | 6095.62 | 5473.31 | 9841.65 |  | 6655.85 | 77448.62
|  |  | Labor Entries <$5,000 | 6418.11 | 8154.52 | 7303.5 | 7711.32 | 4100.63 | 5093.35 | 6661.1 | 5160.67 | 4277.56 | 8079.01 | 12359.47 | 8271.33 | 83590.57
|  | Labor Total |  | 6418.11 | 13432.86 | 7303.5 | 17345.6 | 50168.35 | 10884.44 | 16337.13 | 28168.94 | 26267.63 | 37689.44 | 31526.74 | 31409.95 | 276952.69
| Labor - Other Total |  |  | 6418.11 | 13432.86 | 7303.5 | 17345.6 | 50168.35 | 10884.44 | 16337.13 | 28168.94 | 26267.63 | 37689.44 | 31526.74 | 31409.95 | 276952.69
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 58.77 | -40.37 | -20.82 | 2971.3 | 2735.19 | -18.68 | -15.67 | -24.82 | 3952.54 | -23.01 | -17.88 | 4198.22 | 13754.77
|  |  | MAJOR PROJECT ORG / Mgr-Prj/Prod | 5216.4 | 5464.8 | 5713.2 |  |  | 7185.04 | 5202.96 | 6441.76 |  | 5202.96 | 5946.24 |  | 46373.36
|  | Labor Total |  | 5275.17 | 5424.43 | 5692.38 | 2971.3 | 2735.19 | 7166.36 | 5187.29 | 6416.94 | 3952.54 | 5179.95 | 5928.36 | 4198.22 | 60128.13
| MAJOR PROJECT ORG Total |  |  | 5275.17 | 5424.43 | 5692.38 | 2971.3 | 2735.19 | 7166.36 | 5187.29 | 6416.94 | 3952.54 | 5179.95 | 5928.36 | 4198.22 | 60128.13
| Other | Other | Other | 8000 | 30274.43 | 18840.91 | 4517.17 | 10017.63 | 10520.35 | 4354.88 | 6409.09 | 9225.52 | 4013.49 | 3545 | 9854.64 | 119573.11
|  | Other Total |  | 8000 | 30274.43 | 18840.91 | 4517.17 | 10017.63 | 10520.35 | 4354.88 | 6409.09 | 9225.52 | 4013.49 | 3545 | 9854.64 | 119573.11
| Other Total |  |  | 8000 | 30274.43 | 18840.91 | 4517.17 | 10017.63 | 10520.35 | 4354.88 | 6409.09 | 9225.52 | 4013.49 | 3545 | 9854.64 | 119573.11
| SC&M | Labor | Labor Entries <$5,000 | [7 empty] | 151.87 |  |  |  |  | 151.87
|  | Labor Total | [8 empty] | 151.87 |  |  |  |  | 151.87
| SC&M Total | [9 empty] | 151.87 |  |  |  |  | 151.87
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -2.31 | 2.31 |  |  | 0
|  | Contract Total | [9 empty] | -2.31 | 2.31 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -2.31 | 2.31 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 6534.45 | 5867.83 | 5367.28 | 659.45 | 797.39 | 3810.29 | 2092.75 | 825.64 | 98.01 | 1077.72 | 163.35 | 1811.38 | 29105.54
|  | Contract Total |  | 6534.45 | 5867.83 | 5367.28 | 659.45 | 797.39 | 3810.29 | 2092.75 | 825.64 | 98.01 | 1077.72 | 163.35 | 1811.38 | 29105.54
| Temporary/Supplementary - Trade/Labor Total |  |  | 6534.45 | 5867.83 | 5367.28 | 659.45 | 797.39 | 3810.29 | 2092.75 | 825.64 | 98.01 | 1077.72 | 163.35 | 1811.38 | 29105.54
| WEBEX | Labor | Labor Entries <$5,000 |  | 14.4 | 14.4 | [9 empty] | 28.8
|  | Labor Total |  |  | 14.4 | 14.4 | [9 empty] | 28.8
| WEBEX Total |  |  |  | 14.4 | 14.4 | [9 empty] | 28.8
1. Project Support Total |  |  |  | 28703.87 | 234613.55 | 37938.5 | 29935.75 | 72769.98 | 42727.89 | 30005.33 | 43696.89 | 40289.8 | 48027.27 | 39782.74 | 48230.02 | 696721.59
2. Material | Material - Other | Material | Material - Other | 9.44 | 8.91 | 8.82 |  |  | -19.28 |  |  |  |  | 16.25 | 34.91 | 59.05
|  | Material Total |  | 9.44 | 8.91 | 8.82 |  |  | -19.28 |  |  |  |  | 16.25 | 34.91 | 59.05
| Material - Other Total |  |  | 9.44 | 8.91 | 8.82 |  |  | -19.28 |  |  |  |  | 16.25 | 34.91 | 59.05
2. Material Total |  |  |  | 9.44 | 8.91 | 8.82 |  |  | -19.28 |  |  |  |  | 16.25 | 34.91 | 59.05
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [5 empty] | 568 |  |  | 284 | 426 | 994 | 2698 | 4970
|  | Contract Total | [6 empty] | 568 |  |  | 284 | 426 | 994 | 2698 | 4970
| Construction Management Services Total | [7 empty] | 568 |  |  | 284 | 426 | 994 | 2698 | 4970
| GRID OPS | Labor | Labor Entries <$5,000 | 338.68 | 352.3 | 463.33 | 879.25 | 2771.44 | 1990.1 | 1624.7 | 2294.6 | 2129.98 | 2421.56 | 4256.84 | 2135.77 | 21658.55
|  | Labor Total |  | 338.68 | 352.3 | 463.33 | 879.25 | 2771.44 | 1990.1 | 1624.7 | 2294.6 | 2129.98 | 2421.56 | 4256.84 | 2135.77 | 21658.55
| GRID OPS Total |  |  | 338.68 | 352.3 | 463.33 | 879.25 | 2771.44 | 1990.1 | 1624.7 | 2294.6 | 2129.98 | 2421.56 | 4256.84 | 2135.77 | 21658.55
3. Construction Total |  |  |  | 338.68 | 352.3 | 463.33 | 879.25 | 2771.44 | 2558.1 | 1624.7 | 2294.6 | 2413.98 | 2847.56 | 5250.84 | 4833.77 | 26628.55
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 1282.19 | 2070.64 | 652.11 | 811.17 | 896.32 | 1303.7 | 3319.13 | 919.93 | -1006.23 | 2605.52 | 993.2 | 803.99 | 14651.67
|  |  | Law/TD-Eldorado Ivanpah Trns Project |  | 28549.5 | 27516.56 | 12352.89 | 23054.32 | 78702.71 | 72734.52 | 20431 |  | 5071.95 | 225049.15 | 104541.73 | 598004.33
|  | Chargeback Total |  | 1282.19 | 30620.14 | 28168.67 | 13164.06 | 23950.64 | 80006.41 | 76053.65 | 21350.93 | -1006.23 | 7677.47 | 226042.35 | 105345.72 | 612656
| Chargebacks Total |  |  | 1282.19 | 30620.14 | 28168.67 | 13164.06 | 23950.64 | 80006.41 | 76053.65 | 21350.93 | -1006.23 | 7677.47 | 226042.35 | 105345.72 | 612656
| Labor - Other | Labor | Division Overhead |  | 5238.51 | [7 empty] | 8851.7 |  |  | 14090.21
|  |  | Labor Entries <$5,000 | 4589.72 | 15411.51 | 3289.76 | 3444.05 | 4623.65 | 4490.59 | 11405.63 | 4558.99 | -14240.12 | 17315.6 | 3540.31 | 1467.2 | 59896.89
|  | Labor Total |  | 4589.72 | 20650.02 | 3289.76 | 3444.05 | 4623.65 | 4490.59 | 11405.63 | 4558.99 | -14240.12 | 26167.3 | 3540.31 | 1467.2 | 73987.1
| Labor - Other Total |  |  | 4589.72 | 20650.02 | 3289.76 | 3444.05 | 4623.65 | 4490.59 | 11405.63 | 4558.99 | -14240.12 | 26167.3 | 3540.31 | 1467.2 | 73987.1
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -5.85 | 5.85 |  |  | 0
|  | Overhead Total | [9 empty] | -5.85 | 5.85 |  |  | 0
| Overhead Correction Total | [10 empty] | -5.85 | 5.85 |  |  | 0
4. Allocated Total |  |  |  | 5871.91 | 51270.16 | 31458.43 | 16608.11 | 28574.29 | 84497 | 87459.28 | 25909.92 | -15252.2 | 33850.62 | 229582.66 | 106812.92 | 686643.1
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 79827.08 | 4903.03 | [6 empty] | 80171.43 | 164901.54
|  |  | Capitalized Overhead - A&G | 1949.09 | 7617.16 | 3425.76 | 1691.14 | 8665.5 | 4631.3 | 4181.57 | 2033.75 | 1229.8 | 2189.03 | 7257.78 | 4298.37 | 49170.25
|  |  | Capitalized Overhead - Inj & Damages | 26.55 | 76.27 | 66.54 | 28.53 | 649.64 | -16163.15 | 40.46 | 65.92 | 263.03 | -585.14 | 79.62 | 83.46 | -15368.27
|  |  | Capitalized Overhead - P&B/Payroll Tax | 9350.35 | 21785.78 | 14291.28 | 29300.5 | 74506.4 | -1667027.06 | 29083.12 | 27676.51 | 40437.03 | 19250.15 | 31086.62 | 74661.22 | -1295598.1
|  |  | Corporate Overheads Correction |  |  |  |  | -39027.31 | [7 empty] | -39027.31
|  | Non Budgeted Total |  | 11325.99 | 29479.21 | 17783.58 | 110847.25 | 49697.26 | -1678558.91 | 33305.15 | 29776.18 | 41929.86 | 20854.04 | 38424.02 | 159214.48 | -1135921.89
| Non Budget - Other Total |  |  | 11325.99 | 29479.21 | 17783.58 | 110847.25 | 49697.26 | -1678558.91 | 33305.15 | 29776.18 | 41929.86 | 20854.04 | 38424.02 | 159214.48 | -1135921.89
5. Corporate Overhead Total |  |  |  | 11325.99 | 29479.21 | 17783.58 | 110847.25 | 49697.26 | -1678558.91 | 33305.15 | 29776.18 | 41929.86 | 20854.04 | 38424.02 | 159214.48 | -1135921.89
Grand Total |  |  |  | 46249.89 | 315724.13 | 87652.66 | 158270.36 | 153812.97 | -1548795.2 | 152394.46 | 101677.59 | 69381.44 | 105579.49 | 313056.51 | 319126.1 | 274130.4

## Lugo-Pisgah
WO | SumOfYTD2012 | Order | Project
800499057- Pisgah Sub: Siting Study for new sub | -7284.21 | 800499057 | Lugo-Pisgah

## 800499057
Pin: 7018 | Project: Lugo-Pisgah
Order: 800499057 | 800499057- Pisgah Sub: Siting Study for new sub
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [6 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 5 | 6 | 9 | 10 | 11
1. Project Support | 3rd Party Billable A&G - Collectible Ord | WO Postings / Contributions | 3rd Party Billable A&G - Collectible Ord | 257.47 | -2.9 |  | 71.16 | -15.83 | 16.17 | 1.94 | 328.01
|  | WO Postings / Contributions Total |  | 257.47 | -2.9 |  | 71.16 | -15.83 | 16.17 | 1.94 | 328.01
| 3rd Party Billable A&G - Collectible Ord Total |  |  | 257.47 | -2.9 |  | 71.16 | -15.83 | 16.17 | 1.94 | 328.01
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  |  |  | 324.87 | -324.87 |  | 0
|  | IMM Correction Total | [5 empty] | 324.87 | -324.87 |  | 0
| IMM/Allocated - Correction Total | [6 empty] | 324.87 | -324.87 |  | 0
| Labor - Other | Labor | Labor Entries <$5,000 | 14.34 | -14.34 |  | 355.46 | -316.71 | 316.71 |  | 355.46
|  | Labor Total |  | 14.34 | -14.34 |  | 355.46 | -316.71 | 316.71 |  | 355.46
| Labor - Other Total |  |  | 14.34 | -14.34 |  | 355.46 | -316.71 | 316.71 |  | 355.46
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 1004.79 | [6 empty] | 1004.79
|  | Labor Total |  | 1004.79 | [6 empty] | 1004.79
| MAJOR PROJECT ORG Total |  |  | 1004.79 | [6 empty] | 1004.79
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 |  |  |  |  | -2.31 | 2.31 |  | 0
|  | Contract Total | [5 empty] | -2.31 | 2.31 |  | 0
| Temporary / Supplemental - Correction Total | [6 empty] | -2.31 | 2.31 |  | 0
1. Project Support Total |  |  |  | 1276.6 | -17.24 |  | 426.62 | -9.98 | 10.32 | 1.94 | 1688.26
2. Material | Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 13.4 | 13.4
|  | Material - Direct Purchase Total | [7 empty] | 13.4 | 13.4
| Transportation & Mobile Equip-DP Total | [8 empty] | 13.4 | 13.4
2. Material Total | [9 empty] | 13.4 | 13.4
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 438.54 | -1.23 |  | 40.63 | -30.5 | 25.51 | 0.09 | 473.04
|  | Chargeback Total |  | 438.54 | -1.23 |  | 40.63 | -30.5 | 25.51 | 0.09 | 473.04
| Chargebacks Total |  |  | 438.54 | -1.23 |  | 40.63 | -30.5 | 25.51 | 0.09 | 473.04
| Labor - Other | Labor | Labor Entries <$5,000 | 377.49 | -5.1 |  | 111.12 | -82.33 | 89.75 | 0.33 | 491.26
|  | Labor Total |  | 377.49 | -5.1 |  | 111.12 | -82.33 | 89.75 | 0.33 | 491.26
| Labor - Other Total |  |  | 377.49 | -5.1 |  | 111.12 | -82.33 | 89.75 | 0.33 | 491.26
| Overhead Correction | Overhead | Overhead Correction |  |  |  |  | -5.85 | 5.85 |  | 0
|  | Overhead Total | [5 empty] | -5.85 | 5.85 |  | 0
| Overhead Correction Total | [6 empty] | -5.85 | 5.85 |  | 0
4. Allocated Total |  |  |  | 816.03 | -6.33 |  | 151.75 | -118.68 | 121.11 | 0.42 | 964.3
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - Inj & Damages | 1.71 | -0.04 |  | 0.66 | -0.1 | 0.36 | 0.02 | 2.61
|  |  | Capitalized Overhead - P&B/Payroll Tax | 874.91 | -16.59 |  | 475.81 | -441.06 | 150.45 |  | 1043.52
|  |  | Corporate Overheads Correction |  |  | -10996.3 |  |  |  |  | -10996.3
|  | Non Budgeted Total |  | 876.62 | -16.63 | -10996.3 | 476.47 | -441.16 | 150.81 | 0.02 | -9950.17
| Non Budget - Other Total |  |  | 876.62 | -16.63 | -10996.3 | 476.47 | -441.16 | 150.81 | 0.02 | -9950.17
5. Corporate Overhead Total |  |  |  | 876.62 | -16.63 | -10996.3 | 476.47 | -441.16 | 150.81 | 0.02 | -9950.17
Grand Total |  |  |  | 2969.25 | -40.2 | -10996.3 | 1054.84 | -569.82 | 282.24 | 15.78 | -7284.21

## Coolwater-Lugo
WO | SumOfYTD2012 | Order | Project
900473253- New Coolwater-Lugo 220 kV Transmission | 7561193.42 | 900473253 | Coolwater-Lugo
900295954- I:Install New Jasper: Engineer and Construct. | 650657.19 | 900295954 | Coolwater-Lugo

## 900473253
Pin: 7091 | Project: Coolwater-Lugo
Order: 900473253 | 900473253- New Coolwater-Lugo 220 kV Transmission
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Con - Consults/Prof Srvcs/Out Ord to Ord |  |  | 101171.65 | 285390.1 |  |  | 250992 | 214116.87 |  | 111262.09 |  | 130544.47 | 1093477.18
|  |  | Contract Entries <$50,000 | 184 | 141.79 |  |  | 136.17 | 6108.13 |  |  | 13131.98 |  | 48699.33 |  | 68401.4
|  | Contract Total |  | 184 | 141.79 | 101171.65 | 285390.1 | 136.17 | 6108.13 | 250992 | 214116.87 | 13131.98 | 111262.09 | 48699.33 | 130544.47 | 1161878.58
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 184 | 141.79 | 101171.65 | 285390.1 | 136.17 | 6108.13 | 250992 | 214116.87 | 13131.98 | 111262.09 | 48699.33 | 130544.47 | 1161878.58
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 750864.57 |  |  | 750864.57
|  |  | Contract Entries <$50,000 | [8 empty] | -750864.57 |  |  |  | -750864.57
|  | Contract Total | [9 empty] | -750864.57 | 750864.57 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -750864.57 | 750864.57 |  |  | 0
| Contract - Other - Correction | Contract | Contract Entries <$50,000 | [10 empty] | 23313 |  | 23313
|  | Contract Total | [11 empty] | 23313 |  | 23313
| Contract - Other - Correction Total | [12 empty] | 23313 |  | 23313
| ELEC SYS PLANNING | Labor | ELEC SYS PLANNING / Engineer | [11 empty] | 5294.4 | 5294.4
|  |  | Labor Entries <$5,000 |  |  |  |  | 55.99 | [6 empty] | 6787.87 | 6843.86
|  | Labor Total | [5 empty] | 55.99 | [6 empty] | 12082.27 | 12138.26
| ELEC SYS PLANNING Total | [6 empty] | 55.99 | [6 empty] | 12082.27 | 12138.26
| ENGINEERING | Labor | Engineer | 5004.04 |  | 5925.8 | 6811.4 |  | 13282.08 | 5789.69 | 6470.83 | 5789.69 | 6130.26 | 7151.97 |  | 62355.76
|  |  | Engineer Sr |  |  |  | 5205.36 | [8 empty] | 5205.36
|  |  | Labor Entries <$5,000 | 7804.49 | 9911.51 | 9932.17 | 5342.47 | 16787.85 | 12102.47 | 9546.26 | 10395.8 | 9995.96 | 4734.37 | 8330.03 |  | 104883.38
|  | Labor Total |  | 12808.53 | 9911.51 | 15857.97 | 17359.23 | 16787.85 | 25384.55 | 15335.95 | 16866.63 | 15785.65 | 10864.63 | 15482 |  | 172444.5
| ENGINEERING Total |  |  | 12808.53 | 9911.51 | 15857.97 | 17359.23 | 16787.85 | 25384.55 | 15335.95 | 16866.63 | 15785.65 | 10864.63 | 15482 |  | 172444.5
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  |  | 35235 |  | 30735.78 |  |  | 3763.08 |  |  |  | 56223.7 | 125957.56
|  |  | MESA ASSOCIATES INC. | [7 empty] | 128770.65 |  |  |  |  | 128770.65
|  | Contract Total |  |  |  | 35235 |  | 30735.78 |  |  | 132533.73 |  |  |  | 56223.7 | 254728.21
| Engineering/Technical Professional Servi Total |  |  |  |  | 35235 |  | 30735.78 |  |  | 132533.73 |  |  |  | 56223.7 | 254728.21
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 948095.71 | -948095.71 |  |  | 0
|  | IMM Correction Total | [9 empty] | 948095.71 | -948095.71 |  |  | 0
| IMM/Allocated - Correction Total | [10 empty] | 948095.71 | -948095.71 |  |  | 0
| Labor - Other | Labor | ACQ/Cool Water-Lugo | 7962.06 | 21379.51 | 12952.71 | 12031.34 | 15970.52 | 11818.23 | 15121.06 | 34291.43 | 17442.81 | 18225.1 | 39511.27 | 45076.82 | 251782.86
|  |  | Labor - Other | [9 empty] | 27543.81 |  |  | 27543.81
|  |  | Labor Correction | [9 empty] | 137033.93 |  |  | 137033.93
|  |  | Labor Entries <$5,000 | 5214.34 | 15315.6 | 6044.83 | 6528.29 | 10289.41 | 1996.4 | 7030.03 | 6327.3 | -110749.18 | -34650.13 | 5328.12 | 6650.17 | -74674.82
|  | Labor Total |  | 13176.4 | 36695.11 | 18997.54 | 18559.63 | 26259.93 | 13814.63 | 22151.09 | 40618.73 | -93306.37 | 148152.71 | 44839.39 | 51726.99 | 341685.78
| Labor - Other Total |  |  | 13176.4 | 36695.11 | 18997.54 | 18559.63 | 26259.93 | 13814.63 | 22151.09 | 40618.73 | -93306.37 | 148152.71 | 44839.39 | 51726.99 | 341685.78
| Legal Professional Services (OC & Attys) | Contract | Contract Entries <$50,000 |  | 3530 | [7 empty] | 2031.25 |  |  | 5561.25
|  | Contract Total |  |  | 3530 | [7 empty] | 2031.25 |  |  | 5561.25
| Legal Professional Services (OC & Attys) Total |  |  |  | 3530 | [7 empty] | 2031.25 |  |  | 5561.25
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 502.4 | 739.69 | [10 empty] | 1242.09
|  | Labor Total |  | 502.4 | 739.69 | [10 empty] | 1242.09
| MAJOR PROJECT ORG Total |  |  | 502.4 | 739.69 | [10 empty] | 1242.09
| Other | Other | Other | -4864.22 | 11641.56 | 8518.07 | 49961.98 | -26235.18 | 130470.25 | 42277.59 | -67380.17 | -6539.63 | 12897.67 | 3595.72 | 16019.08 | 170362.72
|  | Other Total |  | -4864.22 | 11641.56 | 8518.07 | 49961.98 | -26235.18 | 130470.25 | 42277.59 | -67380.17 | -6539.63 | 12897.67 | 3595.72 | 16019.08 | 170362.72
| Other Total |  |  | -4864.22 | 11641.56 | 8518.07 | 49961.98 | -26235.18 | 130470.25 | 42277.59 | -67380.17 | -6539.63 | 12897.67 | 3595.72 | 16019.08 | 170362.72
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -1718.02 | 1718.02 |  |  | 0
|  | Contract Total | [9 empty] | -1718.02 | 1718.02 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -1718.02 | 1718.02 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 454.96 | 796.18 | 2524.06 | 4691.73 | 2843.5 | 7498.8 | 4851.53 | 2138.3 | 1627.75 | 4050.24 | 1829.53 | 5701 | 39007.58
|  | Contract Total |  | 454.96 | 796.18 | 2524.06 | 4691.73 | 2843.5 | 7498.8 | 4851.53 | 2138.3 | 1627.75 | 4050.24 | 1829.53 | 5701 | 39007.58
| Temporary/Supplementary - Trade/Labor Total |  |  | 454.96 | 796.18 | 2524.06 | 4691.73 | 2843.5 | 7498.8 | 4851.53 | 2138.3 | 1627.75 | 4050.24 | 1829.53 | 5701 | 39007.58
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 954.99 | 1419.54 | 1281.64 | 1122.87 | 826.09 | 3826.21 | 2450.54 | 411.2 |  |  |  |  | 12293.08
|  | Labor Total |  | 954.99 | 1419.54 | 1281.64 | 1122.87 | 826.09 | 3826.21 | 2450.54 | 411.2 |  |  |  |  | 12293.08
| TRNS CAPITAL Total |  |  | 954.99 | 1419.54 | 1281.64 | 1122.87 | 826.09 | 3826.21 | 2450.54 | 411.2 |  |  |  |  | 12293.08
1. Project Support Total |  |  |  | 23217.06 | 64875.38 | 183585.93 | 377085.54 | 51410.13 | 187102.57 | 338058.7 | 339305.29 | 126212.5 | 93745.47 | 137758.97 | 272297.51 | 2194655.05
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -23.33 | 23.33 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -23.33 | 23.33 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -23.33 | 23.33 |  |  | 0
| Material - Other | Material | Material - Other |  |  | 206.42 |  |  |  | 0.61 |  | 1443.57 | 1276.31 |  | 1669.9 | 4596.81
|  | Material Total |  |  |  | 206.42 |  |  |  | 0.61 |  | 1443.57 | 1276.31 |  | 1669.9 | 4596.81
| Material - Other Total |  |  |  |  | 206.42 |  |  |  | 0.61 |  | 1443.57 | 1276.31 |  | 1669.9 | 4596.81
2. Material Total | [5 empty] | 206.42 |  |  |  | 0.61 |  | 1420.24 | 1299.64 |  | 1669.9 | 4596.81
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 4865 | 540 | 3510 | 12015 | 7830 | 19456 | 10006 |  | 11205 | 11745 | 7894 | 17443 | 106509
|  | Contract Total |  | 4865 | 540 | 3510 | 12015 | 7830 | 19456 | 10006 |  | 11205 | 11745 | 7894 | 17443 | 106509
| Construction Management Services Total |  |  | 4865 | 540 | 3510 | 12015 | 7830 | 19456 | 10006 |  | 11205 | 11745 | 7894 | 17443 | 106509
3. Construction Total |  |  |  | 4865 | 540 | 3510 | 12015 | 7830 | 19456 | 10006 |  | 11205 | 11745 | 7894 | 17443 | 106509
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 14527.73 | 18559.95 | 18524.99 | 13973.63 | 16966.95 | -2484.51 | -62982.17 | -17375.06 | 153497.41 | -192196.41 | 10211.28 | -99774.44 | -128550.65
|  |  | Law - New Cool Water-Lugo 220 kV Trans | 16995.24 |  |  | 5214.77 |  | 8158.45 | 12028.01 | 14665.31 |  | 28013.13 | 10150.32 | 21775.55 | 117000.78
|  |  | PDP-Coolwater-Lugo-MPO | 7482.11 | 43612.95 | 36947.42 | 55462.85 | 136466.56 | 111175.47 | 209775.24 | 285500.95 |  | 411703.49 | 287075.58 | 289201.55 | 1874404.17
|  |  | TDBU Licensing | 35717.51 | 38005.28 | 24624.95 | 49640.97 | 93343.96 | 142393.39 | 249444.19 | 153538.72 | 245059.96 | 293952.01 | 181203.45 | 238751.95 | 1745676.34
|  |  | TDBU Vehicle Cost | [9 empty] | 8145.02 |  |  | 8145.02
|  | Chargeback Total |  | 74722.59 | 100178.18 | 80097.36 | 124292.22 | 246777.47 | 259242.8 | 408265.27 | 436329.92 | 398557.37 | 549617.24 | 488640.63 | 449954.61 | 3616675.66
| Chargebacks Total |  |  | 74722.59 | 100178.18 | 80097.36 | 124292.22 | 246777.47 | 259242.8 | 408265.27 | 436329.92 | 398557.37 | 549617.24 | 488640.63 | 449954.61 | 3616675.66
| Labor - Other | Labor | ACQ/Cool Water-Lugo |  |  |  | 6537.37 |  |  | 5847.3 | 5460.72 |  | 6528.33 |  |  | 24373.72
|  |  | Division Overhead | [9 empty] | 39985.45 |  |  | 39985.45
|  |  | Labor Entries <$5,000 | 4021.46 | 4967.41 | 9117.72 | 7811.56 | 7986.56 | 8634.64 | 12302.22 | 11888.35 | -53443.55 | 14516.17 | 8359.27 | 3372.42 | 39534.23
|  |  | Paid Absence | [9 empty] | 30029.32 |  |  | 30029.32
|  | Labor Total |  | 4021.46 | 4967.41 | 9117.72 | 14348.93 | 7986.56 | 8634.64 | 18149.52 | 17349.07 | -53443.55 | 91059.27 | 8359.27 | 3372.42 | 133922.72
| Labor - Other Total |  |  | 4021.46 | 4967.41 | 9117.72 | 14348.93 | 7986.56 | 8634.64 | 18149.52 | 17349.07 | -53443.55 | 91059.27 | 8359.27 | 3372.42 | 133922.72
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -18630.58 | 18630.58 |  |  | 0
|  | Overhead Total | [9 empty] | -18630.58 | 18630.58 |  |  | 0
| Overhead Correction Total | [10 empty] | -18630.58 | 18630.58 |  |  | 0
4. Allocated Total |  |  |  | 78744.05 | 105145.59 | 89215.08 | 138641.15 | 254764.03 | 267877.44 | 426414.79 | 453678.99 | 326483.24 | 659307.09 | 496999.9 | 453327.03 | 3750598.38
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 15317.06 | 1107.59 | [6 empty] | 51485.72 | 67910.37
|  |  | Capitalized Overhead - A&G | 6263.57 | 4761.46 | 10142.68 | 17069.58 | 28379.85 | 17721.33 | 24703.71 | 24436.07 | 20845.83 | 19793.5 | 16983.54 | 20723.81 | 211824.93
|  |  | Capitalized Overhead - Inj & Damages | 79.93 | 223.9 | 121.93 | 110.39 | 1532.88 | 455 | 82.32 | 202.02 | 989.68 | -2259.51 | 378.19 | 225.94 | 2142.67
|  |  | Capitalized Overhead - P&B/Payroll Tax | 44235.99 | 113397.2 | 76516.57 | 121703.65 | 164457.61 | 144442.89 | 118575.43 | 99652.68 | -109145.52 | 133913.71 | 97478.77 | 217727.23 | 1222956.21
|  | Non Budgeted Total |  | 50579.49 | 118382.56 | 86781.18 | 154200.68 | 195477.93 | 162619.22 | 143361.46 | 124290.77 | -87310.01 | 151447.7 | 114840.5 | 290162.7 | 1504834.18
| Non Budget - Other Total |  |  | 50579.49 | 118382.56 | 86781.18 | 154200.68 | 195477.93 | 162619.22 | 143361.46 | 124290.77 | -87310.01 | 151447.7 | 114840.5 | 290162.7 | 1504834.18
5. Corporate Overhead Total |  |  |  | 50579.49 | 118382.56 | 86781.18 | 154200.68 | 195477.93 | 162619.22 | 143361.46 | 124290.77 | -87310.01 | 151447.7 | 114840.5 | 290162.7 | 1504834.18
Grand Total |  |  |  | 157405.6 | 288943.53 | 363298.61 | 681942.37 | 509482.09 | 637055.23 | 917841.56 | 917275.05 | 378010.97 | 917544.9 | 757493.37 | 1034900.14 | 7561193.42

## 900295954
Pin: 6902 | Project: Coolwater-Lugo
Order: 900295954 | 900295954- I:Install New Jasper: Engineer and Construct.
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | 3rd Party Billable A&G - Collectible Ord | WO Postings / Contributions | 3rd Party Billable A&G - Collectible Ord | 5363.89 | 7654.05 | [10 empty] | 13017.94
|  | WO Postings / Contributions Total |  | 5363.89 | 7654.05 | [10 empty] | 13017.94
| 3rd Party Billable A&G - Collectible Ord Total |  |  | 5363.89 | 7654.05 | [10 empty] | 13017.94
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  | 6653.51 | 78.77 | 2219.67 | 10685 |  |  |  | -5783.88 | 5783.88 |  |  | 19636.95
|  | Contract Total |  |  | 6653.51 | 78.77 | 2219.67 | 10685 |  |  |  | -5783.88 | 5783.88 |  |  | 19636.95
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  | 6653.51 | 78.77 | 2219.67 | 10685 |  |  |  | -5783.88 | 5783.88 |  |  | 19636.95
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -18776.81 | 18776.81 |  |  | 0
|  | Contract Total | [9 empty] | -18776.81 | 18776.81 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -18776.81 | 18776.81 |  |  | 0
| Contract - Other - Correction | Contract | Contract Entries <$50,000 | [10 empty] | 23370 |  | 23370
|  | Contract Total | [11 empty] | 23370 |  | 23370
| Contract - Other - Correction Total | [12 empty] | 23370 |  | 23370
| Customer Advance (for advances billed) | WO Postings / Contributions | Customer Advance (for advances billed) | [9 empty] | -5000 | -7000 | -15000 | -27000
|  | WO Postings / Contributions Total | [10 empty] | -5000 | -7000 | -15000 | -27000
| Customer Advance (for advances billed) Total | [11 empty] | -5000 | -7000 | -15000 | -27000
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 |  | 33.72 | 563.24 | 136.05 | 640 | 285.03 | 342.59 | 183.2 | 349.21 | 356.67 | 210.53 | 4553.51 | 7653.75
|  | Labor Total |  |  | 33.72 | 563.24 | 136.05 | 640 | 285.03 | 342.59 | 183.2 | 349.21 | 356.67 | 210.53 | 4553.51 | 7653.75
| ELEC SYS PLANNING Total |  |  |  | 33.72 | 563.24 | 136.05 | 640 | 285.03 | 342.59 | 183.2 | 349.21 | 356.67 | 210.53 | 4553.51 | 7653.75
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  |  |  | 441.88 | 1769.92 | 442.98 | 241.67 | 194.05 | 40.23 |  | 331.3 | 341.39 | 3803.42
|  | Labor Total |  |  |  |  | 441.88 | 1769.92 | 442.98 | 241.67 | 194.05 | 40.23 |  | 331.3 | 341.39 | 3803.42
| ENG ADVANCEMENT Total | [5 empty] | 441.88 | 1769.92 | 442.98 | 241.67 | 194.05 | 40.23 |  | 331.3 | 341.39 | 3803.42
| ENGINEERING | Labor | Labor Entries <$5,000 | 6625.32 | 4569.02 | 5516.23 | 1801.18 | 1439.08 | 2802.5 | 1130.74 | 2503.04 | 1664.55 | 1721.72 | 2761.9 |  | 32535.28
|  | Labor Total |  | 6625.32 | 4569.02 | 5516.23 | 1801.18 | 1439.08 | 2802.5 | 1130.74 | 2503.04 | 1664.55 | 1721.72 | 2761.9 |  | 32535.28
| ENGINEERING Total |  |  | 6625.32 | 4569.02 | 5516.23 | 1801.18 | 1439.08 | 2802.5 | 1130.74 | 2503.04 | 1664.55 | 1721.72 | 2761.9 |  | 32535.28
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  |  | 9011.5 |  | 18023 | [7 empty] | 27034.5
|  | Contract Total |  |  |  | 9011.5 |  | 18023 | [7 empty] | 27034.5
| Engineering/Technical Professional Servi Total |  |  |  |  | 9011.5 |  | 18023 | [7 empty] | 27034.5
| GIS-RES America Granite Mountain | Labor | Labor Entries <$5,000 | [8 empty] | 70.26 | 480.08 | -2.97 |  | 547.37
|  | Labor Total | [9 empty] | 70.26 | 480.08 | -2.97 |  | 547.37
| GIS-RES America Granite Mountain Total | [10 empty] | 70.26 | 480.08 | -2.97 |  | 547.37
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 10026.87 | 9999.39 | 10014.4 | -98.72 | -7.13 | -143.93 | -25.59 | -12.58 | 36305.23 | -36305.92 | -151.3 | -173.16 | 29427.56
|  | IMM Correction Total |  | 10026.87 | 9999.39 | 10014.4 | -98.72 | -7.13 | -143.93 | -25.59 | -12.58 | 36305.23 | -36305.92 | -151.3 | -173.16 | 29427.56
| IMM/Allocated - Correction Total |  |  | 10026.87 | 9999.39 | 10014.4 | -98.72 | -7.13 | -143.93 | -25.59 | -12.58 | 36305.23 | -36305.92 | -151.3 | -173.16 | 29427.56
| ITBI (HCC) | Labor | Labor Entries <$5,000 | [6 empty] | 389.54 | [5 empty] | 389.54
|  | Labor Total | [7 empty] | 389.54 | [5 empty] | 389.54
| ITBI (HCC) Total | [8 empty] | 389.54 | [5 empty] | 389.54
| Labor - Other | Labor | ACQ/Jasper Sub-Lugo Pisgah |  | 6332.09 | 18115.13 | 5021.73 |  | 9453.19 | [6 empty] | 38922.14
|  |  | Labor Correction | [9 empty] | 12517.88 |  |  | 12517.88
|  |  | Labor Entries <$5,000 | 1841.96 | 5731.35 | 6511.49 | 572.88 | 7076.29 | -836.82 | 5685.37 | 1084.9 | -12310.47 | 2357.3 | 994.13 | 5108.3 | 23816.68
|  | Labor Total |  | 1841.96 | 12063.44 | 24626.62 | 5594.61 | 7076.29 | 8616.37 | 5685.37 | 1084.9 | -12310.47 | 14875.18 | 994.13 | 5108.3 | 75256.7
| Labor - Other Total |  |  | 1841.96 | 12063.44 | 24626.62 | 5594.61 | 7076.29 | 8616.37 | 5685.37 | 1084.9 | -12310.47 | 14875.18 | 994.13 | 5108.3 | 75256.7
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 2221.37 | 415.53 | 1219.74 | 347.67 | 350.72 | 701.46 | 876.83 | 175.32 | 350 | 172 | 351.04 | 1053.36 | 8235.04
|  | Labor Total |  | 2221.37 | 415.53 | 1219.74 | 347.67 | 350.72 | 701.46 | 876.83 | 175.32 | 350 | 172 | 351.04 | 1053.36 | 8235.04
| MAJOR PROJECT ORG Total |  |  | 2221.37 | 415.53 | 1219.74 | 347.67 | 350.72 | 701.46 | 876.83 | 175.32 | 350 | 172 | 351.04 | 1053.36 | 8235.04
| Other | Other | Other | -3582 | 9011.5 | -9011.5 |  | 136 |  | 21.09 |  | -189.82 | 189.82 |  | 1511.09 | -1913.82
|  | Other Total |  | -3582 | 9011.5 | -9011.5 |  | 136 |  | 21.09 |  | -189.82 | 189.82 |  | 1511.09 | -1913.82
| Other Total |  |  | -3582 | 9011.5 | -9011.5 |  | 136 |  | 21.09 |  | -189.82 | 189.82 |  | 1511.09 | -1913.82
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -1582.02 | 1582.02 |  |  | 0
|  | Contract Total | [9 empty] | -1582.02 | 1582.02 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -1582.02 | 1582.02 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 1314 |  | 343.88 |  |  | 97.06 |  | 104 |  |  |  |  | 1858.94
|  | Contract Total |  | 1314 |  | 343.88 |  |  | 97.06 |  | 104 |  |  |  |  | 1858.94
| Temporary/Supplementary - Trade/Labor Total |  |  | 1314 |  | 343.88 |  |  | 97.06 |  | 104 |  |  |  |  | 1858.94
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 1422.58 | 419.27 | 781.69 | 104.45 | 720.61 | 56.96 | 103.07 | -2081.68 |  |  |  |  | 1526.95
|  | Labor Total |  | 1422.58 | 419.27 | 781.69 | 104.45 | 720.61 | 56.96 | 103.07 | -2081.68 |  |  |  |  | 1526.95
| TRNS CAPITAL Total |  |  | 1422.58 | 419.27 | 781.69 | 104.45 | 720.61 | 56.96 | 103.07 | -2081.68 |  |  |  |  | 1526.95
| WEBEX | Labor | Labor Entries <$5,000 |  | 16.8 | 16.8 | [9 empty] | 33.6
|  | Labor Total |  |  | 16.8 | 16.8 | [9 empty] | 33.6
| WEBEX Total |  |  |  | 16.8 | 16.8 | [9 empty] | 33.6
1. Project Support Total |  |  |  | 25233.99 | 50836.23 | 43161.37 | 10546.79 | 40833.49 | 12858.43 | 8765.31 | 2150.25 | 136.48 | 2632.26 | 20864.63 | -2605.51 | 215413.72
2. Material | Material - Other | Material | Material - Other |  |  | 0.02 | [9 empty] | 0.02
|  | Material Total |  |  |  | 0.02 | [9 empty] | 0.02
| Material - Other Total |  |  |  |  | 0.02 | [9 empty] | 0.02
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 26.83 | [9 empty] | 26.83
|  | Material - Direct Purchase Total |  |  |  | 26.83 | [9 empty] | 26.83
| Transportation & Mobile Equip-DP Total |  |  |  |  | 26.83 | [9 empty] | 26.83
2. Material Total | [5 empty] | 26.85 | [9 empty] | 26.85
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 2502 | 1890 | 5575 | 1080 | 3784 | 3780 | 1906 |  | 2025 | 2565 | 2867 | 5130 | 33104
|  | Contract Total |  | 2502 | 1890 | 5575 | 1080 | 3784 | 3780 | 1906 |  | 2025 | 2565 | 2867 | 5130 | 33104
| Construction Management Services Total |  |  | 2502 | 1890 | 5575 | 1080 | 3784 | 3780 | 1906 |  | 2025 | 2565 | 2867 | 5130 | 33104
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | [11 empty] | 750 | 750
|  | Contract Total | [12 empty] | 750 | 750
| Contract Consult/Contract Ord to Ord Total | [13 empty] | 750 | 750
| Labor - Other | Labor | Labor Entries <$5,000 | [5 empty] | 97.91 | 123.79 | 3161.93 | 1070.94 | 112.92 | 1619.8 | 5000.72 | 11188.01
|  | Labor Total | [6 empty] | 97.91 | 123.79 | 3161.93 | 1070.94 | 112.92 | 1619.8 | 5000.72 | 11188.01
| Labor - Other Total | [7 empty] | 97.91 | 123.79 | 3161.93 | 1070.94 | 112.92 | 1619.8 | 5000.72 | 11188.01
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 |  |  |  |  | 82 | [7 empty] | 82
|  | Labor Total | [5 empty] | 82 | [7 empty] | 82
| TSD-HERC - Rental Total | [6 empty] | 82 | [7 empty] | 82
3. Construction Total |  |  |  | 2502 | 1890 | 5575 | 1080 | 3866 | 3877.91 | 2029.79 | 3161.93 | 3095.94 | 2677.92 | 4486.8 | 10880.72 | 45124.01
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 7934.76 | 5626.46 | 9118.91 | 6365.01 | 5928.2 | 6133.04 | 12298.28 | 6624.69 | 5819.55 | 13255.55 | 7689.75 | 11276.42 | 98070.62
|  |  | JASPER - TDBU LICENSING |  | 5009.87 |  |  | 5545.74 | 5198.93 |  | 5752.99 |  |  |  |  | 21507.53
|  |  | PDP-Jasper Substation-MPO |  | 5579.37 | [5 empty] | 8825.5 |  |  | 17749.49 | 11346.73 | 43501.09
|  | Chargeback Total |  | 7934.76 | 16215.7 | 9118.91 | 6365.01 | 11473.94 | 11331.97 | 12298.28 | 21203.18 | 5819.55 | 13255.55 | 25439.24 | 22623.15 | 163079.24
| Chargebacks Total |  |  | 7934.76 | 16215.7 | 9118.91 | 6365.01 | 11473.94 | 11331.97 | 12298.28 | 21203.18 | 5819.55 | 13255.55 | 25439.24 | 22623.15 | 163079.24
| GIS-RES America Granite Mountain | Labor | Labor Entries <$5,000 | [9 empty] | 2.97 |  |  | 2.97
|  | Labor Total | [10 empty] | 2.97 |  |  | 2.97
| GIS-RES America Granite Mountain Total | [11 empty] | 2.97 |  |  | 2.97
| Labor - Other | Labor | Labor Entries <$5,000 | 4342.7 | 2278.48 | 3883.26 | 1225.69 | 3689.59 | 1688.92 | 2194.2 | 1336.03 | 2191.07 | 1146.52 | 1982.68 | 3623.47 | 29582.61
|  | Labor Total |  | 4342.7 | 2278.48 | 3883.26 | 1225.69 | 3689.59 | 1688.92 | 2194.2 | 1336.03 | 2191.07 | 1146.52 | 1982.68 | 3623.47 | 29582.61
| Labor - Other Total |  |  | 4342.7 | 2278.48 | 3883.26 | 1225.69 | 3689.59 | 1688.92 | 2194.2 | 1336.03 | 2191.07 | 1146.52 | 1982.68 | 3623.47 | 29582.61
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -723.29 | 723.29 |  |  | 0
|  | Overhead Total | [9 empty] | -723.29 | 723.29 |  |  | 0
| Overhead Correction Total | [10 empty] | -723.29 | 723.29 |  |  | 0
4. Allocated Total |  |  |  | 12277.46 | 18494.18 | 13002.17 | 7590.7 | 15163.53 | 13020.89 | 14492.48 | 22539.21 | 7287.33 | 15128.33 | 27421.92 | 26246.62 | 192664.82
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 7046.05 | 454.82 | [6 empty] | 9525.64 | 17026.51
|  |  | AFUDC - Debt/Equity |  |  | -45.01 |  |  | -2.87 | 2.87 | [5 empty] | -45.01
|  |  | Capitalized Overhead - A&G |  |  | 2522.82 | 685.31 | 4982.37 | 1062.04 | 887.92 | 787.79 | 471.27 | 657.25 | 1579.64 | 1348.7 | 14985.11
|  |  | Capitalized Overhead - Inj & Damages | 29.31 | 57.95 | 43.5 | 8.39 | 200.03 | 19.03 | 16.72 | 22.94 | 29.97 | -25.3 | 23.53 | 30.64 | 456.71
|  |  | Capitalized Overhead - P&B/Payroll Tax | 9796.11 | 19536.77 | 23037.69 | 9077.21 | 21857.83 | 13294.19 | 15722.2 | 9825.02 | -13372.9 | 12912.6 | 7806.89 | 45843.51 | 175337.12
|  |  | Corporate Overheads Correction |  |  |  |  | -10332.65 | [7 empty] | -10332.65
|  | Non Budgeted Total |  | 9825.42 | 19594.72 | 25559 | 16816.96 | 17162.4 | 14372.39 | 16629.71 | 10635.75 | -12871.66 | 13544.55 | 9410.06 | 56748.49 | 197427.79
| Non Budget - Other Total |  |  | 9825.42 | 19594.72 | 25559 | 16816.96 | 17162.4 | 14372.39 | 16629.71 | 10635.75 | -12871.66 | 13544.55 | 9410.06 | 56748.49 | 197427.79
5. Corporate Overhead Total |  |  |  | 9825.42 | 19594.72 | 25559 | 16816.96 | 17162.4 | 14372.39 | 16629.71 | 10635.75 | -12871.66 | 13544.55 | 9410.06 | 56748.49 | 197427.79
Grand Total |  |  |  | 49838.87 | 90815.13 | 87324.39 | 36034.45 | 77025.42 | 44129.62 | 41917.29 | 38487.14 | -2351.91 | 33983.06 | 62183.41 | 91270.32 | 650657.19

## Whirlwind
WO | SumOfYTD2012 | Order | Project
900692361- Whirlwind: Install 2nd AA transformer ba | 1613683.13 | 900692361 | Whirlwind Expansion
900642439- Whirlwind (NU): Equip one 220kV position | 817656.89 | 900642439 | Whirlwind Expansion
900615314- Whirlwind (NU): Equip one 220kV position | 825403.06 | 900615314 | Whirlwind Expansion
900397857- Whirlwind: Plan of Service Reliability N | 1657989.62 | 900397857 | Whirlwind Expansion
900389180- Whirlwind Sub: Extension of positions 9- | 4150286.31 | 900389180 | Whirlwind Expansion

## 900692361
Pin: 7067 | Project: Whirlwind Expansion
Order: 900692361 | 900692361- Whirlwind: Install 2nd AA transformer ba
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [8 empty] | 2012 Total
SubCategory | Prime | Group | Details | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | 890.89 | 3580.56 | 1206.05 | 1283.11 | 953.5 | 190.84 | 756.66 | 947.91 | 754.28 | 10563.8
|  | Labor Total |  | 890.89 | 3580.56 | 1206.05 | 1283.11 | 953.5 | 190.84 | 756.66 | 947.91 | 754.28 | 10563.8
| BP&FM Total |  |  | 890.89 | 3580.56 | 1206.05 | 1283.11 | 953.5 | 190.84 | 756.66 | 947.91 | 754.28 | 10563.8
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [5 empty] | -480 | 480 |  |  | 0
|  | Contract Total | [6 empty] | -480 | 480 |  |  | 0
| Consultants / Prof Services - Correction Total | [7 empty] | -480 | 480 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 |  | 83.98 | 55.99 | 391.21 | 56.81 | 84.89 | 364.3 | 394.56 | 16575.92 | 18007.66
|  | Labor Total |  |  | 83.98 | 55.99 | 391.21 | 56.81 | 84.89 | 364.3 | 394.56 | 16575.92 | 18007.66
| ELEC SYS PLANNING Total |  |  |  | 83.98 | 55.99 | 391.21 | 56.81 | 84.89 | 364.3 | 394.56 | 16575.92 | 18007.66
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  |  |  |  | 51.54 |  |  |  |  | 51.54
|  | Labor Total | [5 empty] | 51.54 |  |  |  |  | 51.54
| ENG ADVANCEMENT Total | [6 empty] | 51.54 |  |  |  |  | 51.54
| ENGINEERING | Labor | Engineer Sr |  | 5014.92 | 12473.82 | 5808.42 | 7204.98 |  |  |  |  | 30502.14
|  |  | Labor Entries <$5,000 |  | 2616.16 | 6691.59 | 7212.42 | 18578.81 | 11614.48 | 11535.24 | 14352.88 | 1751.54 | 74353.12
|  | Labor Total |  |  | 7631.08 | 19165.41 | 13020.84 | 25783.79 | 11614.48 | 11535.24 | 14352.88 | 1751.54 | 104855.26
| ENGINEERING Total |  |  |  | 7631.08 | 19165.41 | 13020.84 | 25783.79 | 11614.48 | 11535.24 | 14352.88 | 1751.54 | 104855.26
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 |  |  | 396 |  | 468 | 936 | 4695 |  | 1620 | 8115
|  | Contract Total |  |  |  | 396 |  | 468 | 936 | 4695 |  | 1620 | 8115
| Engineering/Technical Professional Servi Total |  |  |  |  | 396 |  | 468 | 936 | 4695 |  | 1620 | 8115
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [5 empty] | 3389.42 | -3389.42 |  |  | 0
|  | IMM Correction Total | [6 empty] | 3389.42 | -3389.42 |  |  | 0
| IMM/Allocated - Correction Total | [7 empty] | 3389.42 | -3389.42 |  |  | 0
| Labor - Other | Labor | Labor Entries <$5,000 |  | 2468.43 | -3365.91 | 493.92 | 573.88 | -2094.2 | 4757.99 | -770.14 | 3169.28 | 5233.25
|  | Labor Total |  |  | 2468.43 | -3365.91 | 493.92 | 573.88 | -2094.2 | 4757.99 | -770.14 | 3169.28 | 5233.25
| Labor - Other Total |  |  |  | 2468.43 | -3365.91 | 493.92 | 573.88 | -2094.2 | 4757.99 | -770.14 | 3169.28 | 5233.25
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 |  | 1134.82 | 678.8 | 720.76 | 898.22 | 1247.44 | 736.57 | 237.43 | 975.28 | 6629.32
|  | Labor Total |  |  | 1134.82 | 678.8 | 720.76 | 898.22 | 1247.44 | 736.57 | 237.43 | 975.28 | 6629.32
| MAJOR PROJECT ORG Total |  |  |  | 1134.82 | 678.8 | 720.76 | 898.22 | 1247.44 | 736.57 | 237.43 | 975.28 | 6629.32
| Other | Other | Other |  |  | 127.79 | 148.74 |  | -128.76 | 147.08 | 1096.81 | 1831.77 | 3223.43
|  | Other Total |  |  |  | 127.79 | 148.74 |  | -128.76 | 147.08 | 1096.81 | 1831.77 | 3223.43
| Other Total |  |  |  |  | 127.79 | 148.74 |  | -128.76 | 147.08 | 1096.81 | 1831.77 | 3223.43
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [5 empty] | -232.98 | 232.98 |  |  | 0
|  | Contract Total | [6 empty] | -232.98 | 232.98 |  |  | 0
| Temporary / Supplemental - Correction Total | [7 empty] | -232.98 | 232.98 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  | 386 | 3752.89 | 5078.87 | 279.12 | 1923 | 1255.52 | 2725.52 | 271.04 | 15671.96
|  | Contract Total |  |  | 386 | 3752.89 | 5078.87 | 279.12 | 1923 | 1255.52 | 2725.52 | 271.04 | 15671.96
| Temporary/Supplementary - Trade/Labor Total |  |  |  | 386 | 3752.89 | 5078.87 | 279.12 | 1923 | 1255.52 | 2725.52 | 271.04 | 15671.96
1. Project Support Total |  |  |  | 890.89 | 15284.87 | 22017.02 | 21137.45 | 29064.86 | 16450.13 | 21571.92 | 18984.97 | 26949.11 | 172351.22
2. Material | Line Switches & Switchgear-DP | Material - Direct Purchase | Line Switches & Switchgear-DP | [7 empty] | 10681 |  | 10681
|  | Material - Direct Purchase Total | [8 empty] | 10681 |  | 10681
| Line Switches & Switchgear-DP Total | [9 empty] | 10681 |  | 10681
| Material - Other | Material | Material - Other | [6 empty] | 224.2 | 4.09 | 73069.62 | 73297.91
|  | Material Total | [7 empty] | 224.2 | 4.09 | 73069.62 | 73297.91
| Material - Other Total | [8 empty] | 224.2 | 4.09 | 73069.62 | 73297.91
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 3058 | 9.14 |  | 3067.14
|  | Material - Direct Purchase Total | [7 empty] | 3058 | 9.14 |  | 3067.14
| Office & Office Support Products-DP Total | [8 empty] | 3058 | 9.14 |  | 3067.14
| Transformers - Power Substation-DP | Material - Direct Purchase | Transformers - Power Substation-DP | [8 empty] | 990000 | 990000
|  | Material - Direct Purchase Total | [9 empty] | 990000 | 990000
| Transformers - Power Substation-DP Total | [10 empty] | 990000 | 990000
2. Material Total | [9 empty] | 3282.2 | 10694.23 | 1063069.62 | 1077046.05
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  | 684 | 3116 |  | 456 | 1368 | 1368 | 2280 | 9272
|  | Contract Total |  |  |  | 684 | 3116 |  | 456 | 1368 | 1368 | 2280 | 9272
| Construction Management Services Total |  |  |  |  | 684 | 3116 |  | 456 | 1368 | 1368 | 2280 | 9272
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [8 empty] | 333.71 | 333.71
|  | Labor Total | [9 empty] | 333.71 | 333.71
| ELEC SYS PLANNING Total | [10 empty] | 333.71 | 333.71
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 662.57 | 1159.18 | 747.31 | 486.03 | 323.63 | 333.73 |  | 3712.45
|  | Labor Total |  |  |  | 662.57 | 1159.18 | 747.31 | 486.03 | 323.63 | 333.73 |  | 3712.45
| ENGINEERING Total |  |  |  |  | 662.57 | 1159.18 | 747.31 | 486.03 | 323.63 | 333.73 |  | 3712.45
3. Construction Total | [5 empty] | 1346.57 | 4275.18 | 747.31 | 942.03 | 1691.63 | 1701.73 | 2613.71 | 13318.16
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 84.54 | 1793.51 | 2648.17 | 3610.24 | 3487.24 | 1518.25 | 1738.57 | 2702.27 | 2372.94 | 19955.73
|  |  | PROCUREMENT TDBU | [8 empty] | 6561.53 | 6561.53
|  | Chargeback Total |  | 84.54 | 1793.51 | 2648.17 | 3610.24 | 3487.24 | 1518.25 | 1738.57 | 2702.27 | 8934.47 | 26517.26
| Chargebacks Total |  |  | 84.54 | 1793.51 | 2648.17 | 3610.24 | 3487.24 | 1518.25 | 1738.57 | 2702.27 | 8934.47 | 26517.26
| Labor - Other | Labor | Division Overhead | [8 empty] | 30223.03 | 30223.03
|  |  | Labor Entries <$5,000 | 292.47 | 4768.95 | 6079.16 | 6207.24 | 3669.58 | 3820.11 | 6746.02 | 3767.23 | 7266.89 | 42617.65
|  |  | Paid Absence |  |  |  |  | 5779.3 |  |  |  | 5451.11 | 11230.41
|  | Labor Total |  | 292.47 | 4768.95 | 6079.16 | 6207.24 | 9448.88 | 3820.11 | 6746.02 | 3767.23 | 42941.03 | 84071.09
| Labor - Other Total |  |  | 292.47 | 4768.95 | 6079.16 | 6207.24 | 9448.88 | 3820.11 | 6746.02 | 3767.23 | 42941.03 | 84071.09
| Overhead Correction | Overhead | Overhead Correction | [5 empty] | -61.23 | 61.23 |  |  | 0
|  | Overhead Total | [6 empty] | -61.23 | 61.23 |  |  | 0
| Overhead Correction Total | [7 empty] | -61.23 | 61.23 |  |  | 0
4. Allocated Total |  |  |  | 377.01 | 6562.46 | 8727.33 | 9817.48 | 12936.12 | 5277.13 | 8545.82 | 6469.5 | 51875.5 | 110588.35
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax | [8 empty] | 9498.12 | 9498.12
|  |  | Capitalized Overhead - A&G | 45.21 | 1818.34 | 1145.33 | 1237.03 | 1209.15 | 1015.56 | 906.65 | 1000.28 | 32082.43 | 40459.98
|  |  | Capitalized Overhead - Inj & Damages | 1.05 | 191.54 | 35.22 | 24.66 | 53.91 | 18.18 | 85.5 | 54.46 | 1281.13 | 1745.65
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1144.87 | 23023.42 | 25159.79 | 23438.67 | 23776.94 | 16563.84 | 8972.2 | 13082.03 | 53513.84 | 188675.6
|  | Non Budgeted Total |  | 1191.13 | 25033.3 | 26340.34 | 24700.36 | 25040 | 17597.58 | 9964.35 | 14136.77 | 96375.52 | 240379.35
| Non Budget - Other Total |  |  | 1191.13 | 25033.3 | 26340.34 | 24700.36 | 25040 | 17597.58 | 9964.35 | 14136.77 | 96375.52 | 240379.35
5. Corporate Overhead Total |  |  |  | 1191.13 | 25033.3 | 26340.34 | 24700.36 | 25040 | 17597.58 | 9964.35 | 14136.77 | 96375.52 | 240379.35
Grand Total |  |  |  | 2459.03 | 46880.63 | 58431.26 | 59930.47 | 67788.29 | 40266.87 | 45055.92 | 51987.2 | 1240883.46 | 1613683.13

## 900642439
Pin: 7069 | Project: Whirlwind Expansion
Order: 900642439 | 900642439- Whirlwind (NU): Equip one 220kV position
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [10 empty] | 2012 Total
SubCategory | Prime | Group | Details | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  |  | 181.29 | 189.18 | 186.63 | [5 empty] | 557.1
|  | Labor Total |  |  |  |  | 181.29 | 189.18 | 186.63 | [5 empty] | 557.1
| BP&FM Total | [5 empty] | 181.29 | 189.18 | 186.63 | [5 empty] | 557.1
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [10 empty] | 3269.68 | 3269.68
|  | Labor Total | [11 empty] | 3269.68 | 3269.68
| ELEC SYS PLANNING Total | [12 empty] | 3269.68 | 3269.68
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | [5 empty] | 84.38 | 169.21 | 338.44 | 337.82 |  |  | 929.85
|  | Labor Total | [6 empty] | 84.38 | 169.21 | 338.44 | 337.82 |  |  | 929.85
| ENG ADVANCEMENT Total | [7 empty] | 84.38 | 169.21 | 338.44 | 337.82 |  |  | 929.85
| ENGINEERING | Labor | Labor Entries <$5,000 |  | 469.16 | 2893.7 | 1758.18 | 2993.98 | 2997.81 | 4172.85 | 5659.48 | 4585.66 | 3778.67 |  | 29309.49
|  | Labor Total |  |  | 469.16 | 2893.7 | 1758.18 | 2993.98 | 2997.81 | 4172.85 | 5659.48 | 4585.66 | 3778.67 |  | 29309.49
| ENGINEERING Total |  |  |  | 469.16 | 2893.7 | 1758.18 | 2993.98 | 2997.81 | 4172.85 | 5659.48 | 4585.66 | 3778.67 |  | 29309.49
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | [8 empty] | 4455 |  |  | 4455
|  | Contract Total | [9 empty] | 4455 |  |  | 4455
| Engineering/Technical Professional Servi Total | [10 empty] | 4455 |  |  | 4455
| Labor - Other | Labor | Labor Entries <$5,000 | 76.4 | -3.86 | 68.45 | 179.64 | -332.03 | 20.99 | -6 | -43.99 | 543.78 | -745.66 | 465.68 | 223.4
|  | Labor Total |  | 76.4 | -3.86 | 68.45 | 179.64 | -332.03 | 20.99 | -6 | -43.99 | 543.78 | -745.66 | 465.68 | 223.4
| Labor - Other Total |  |  | 76.4 | -3.86 | 68.45 | 179.64 | -332.03 | 20.99 | -6 | -43.99 | 543.78 | -745.66 | 465.68 | 223.4
| Other | Other | Other | [10 empty] | 3925.62 | 3925.62
|  | Other Total | [11 empty] | 3925.62 | 3925.62
| Other Total | [12 empty] | 3925.62 | 3925.62
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  |  |  |  | 186.34 |  | 438 |  |  |  | 3153.8 | 3778.14
|  | Contract Total | [5 empty] | 186.34 |  | 438 |  |  |  | 3153.8 | 3778.14
| Temporary/Supplementary - Trade/Labor Total | [6 empty] | 186.34 |  | 438 |  |  |  | 3153.8 | 3778.14
1. Project Support Total |  |  |  | 76.4 | 465.3 | 2962.15 | 2119.11 | 3037.47 | 3289.81 | 4774.06 | 5953.93 | 9922.26 | 3033.01 | 10814.78 | 46448.28
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | MITSUBISHI ELECTRIC | [7 empty] | 341056 |  |  |  | 341056
|  | Material - Direct Purchase Total | [8 empty] | 341056 |  |  |  | 341056
| Breakers - Circuit-DP Total | [9 empty] | 341056 |  |  |  | 341056
| Line Switches & Switchgear-DP | Material - Direct Purchase | Line Switches & Switchgear-DP |  |  |  |  | 42724 | [6 empty] | 42724
|  |  | SOUTHERN STATES LLC | [8 empty] | 191906 |  |  | 191906
|  | Material - Direct Purchase Total | [5 empty] | 42724 |  |  |  | 191906 |  |  | 234630
| Line Switches & Switchgear-DP Total | [6 empty] | 42724 |  |  |  | 191906 |  |  | 234630
| Material - Other | Material | Material - Other |  |  |  |  | 44.58 |  |  | 25083.75 | 14069.28 | 3.31 |  | 39200.92
|  | Material Total | [5 empty] | 44.58 |  |  | 25083.75 | 14069.28 | 3.31 |  | 39200.92
| Material - Other Total | [6 empty] | 44.58 |  |  | 25083.75 | 14069.28 | 3.31 |  | 39200.92
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 4744.32 |  | 4744.32
|  |  | Transportation & Mobile Equip-DP | [9 empty] | 5588.19 |  | 5588.19
|  | Material - Direct Purchase Total | [10 empty] | 10332.51 |  | 10332.51
| Transportation & Mobile Equip-DP Total | [11 empty] | 10332.51 |  | 10332.51
2. Material Total | [7 empty] | 42768.58 |  |  | 366139.75 | 205975.28 | 10335.82 |  | 625219.43
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  | 760 | 760 | 988 | 988 |  | 608 | 456 | 760 | 1520 | 6840
|  | Contract Total |  |  |  | 760 | 760 | 988 | 988 |  | 608 | 456 | 760 | 1520 | 6840
| Construction Management Services Total |  |  |  |  | 760 | 760 | 988 | 988 |  | 608 | 456 | 760 | 1520 | 6840
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 460.96 | 155.98 | 166.69 |  | 166.87 | 324.02 | 166.87 |  |  | 1441.39
|  | Labor Total |  |  |  | 460.96 | 155.98 | 166.69 |  | 166.87 | 324.02 | 166.87 |  |  | 1441.39
| ENGINEERING Total |  |  |  |  | 460.96 | 155.98 | 166.69 |  | 166.87 | 324.02 | 166.87 |  |  | 1441.39
3. Construction Total | [5 empty] | 1220.96 | 915.98 | 1154.69 | 988 | 166.87 | 932.02 | 622.87 | 760 | 1520 | 8281.39
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 |  | 42.51 | 329.89 | 210.92 | 634.67 | 429.26 | 380.22 | 2980.72 | 1843.8 | 405.88 | 370.77 | 7628.64
|  | Chargeback Total |  |  | 42.51 | 329.89 | 210.92 | 634.67 | 429.26 | 380.22 | 2980.72 | 1843.8 | 405.88 | 370.77 | 7628.64
| Chargebacks Total |  |  |  | 42.51 | 329.89 | 210.92 | 634.67 | 429.26 | 380.22 | 2980.72 | 1843.8 | 405.88 | 370.77 | 7628.64
| Labor - Other | Labor | Division Overhead | [7 empty] | 9908.26 | 6514.64 |  |  | 16422.9
|  |  | Labor Entries <$5,000 |  | 157.32 | 1180.73 | 776.58 | 3831.88 | 1167.52 | 1503.55 | 14290.27 | 11439.29 | 1021.31 | 1295.88 | 36664.33
|  | Labor Total |  |  | 157.32 | 1180.73 | 776.58 | 3831.88 | 1167.52 | 1503.55 | 24198.53 | 17953.93 | 1021.31 | 1295.88 | 53087.23
| Labor - Other Total |  |  |  | 157.32 | 1180.73 | 776.58 | 3831.88 | 1167.52 | 1503.55 | 24198.53 | 17953.93 | 1021.31 | 1295.88 | 53087.23
4. Allocated Total |  |  |  |  | 199.83 | 1510.62 | 987.5 | 4466.55 | 1596.78 | 1883.77 | 27179.25 | 19797.73 | 1427.19 | 1666.65 | 60715.87
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax | [10 empty] | 4812.72 | 4812.72
|  |  | Capitalized Overhead - A&G | 2.24 | 23.71 | 203.04 | 334.8 | 1835.45 | 206.27 | 193.04 | 17928.71 | 6105.7 | 411.1 | 282.89 | 27526.95
|  |  | Capitalized Overhead - Inj & Damages | 0.13 | 0.7 | 4.09 | 29.12 | 64.93 | 4.47 | 8.32 | 361.92 | 731.16 | 24.33 | 6.08 | 1235.25
|  |  | Capitalized Overhead - P&B/Payroll Tax | 73.6 | 479.03 | 4398.99 | 3432.35 | 4039.59 | 4260.29 | 3660.57 | 8994.87 | 2753.67 | 2587.16 | 8736.88 | 43417
|  | Non Budgeted Total |  | 75.97 | 503.44 | 4606.12 | 3796.27 | 5939.97 | 4471.03 | 3861.93 | 27285.5 | 9590.53 | 3022.59 | 13838.57 | 76991.92
| Non Budget - Other Total |  |  | 75.97 | 503.44 | 4606.12 | 3796.27 | 5939.97 | 4471.03 | 3861.93 | 27285.5 | 9590.53 | 3022.59 | 13838.57 | 76991.92
5. Corporate Overhead Total |  |  |  | 75.97 | 503.44 | 4606.12 | 3796.27 | 5939.97 | 4471.03 | 3861.93 | 27285.5 | 9590.53 | 3022.59 | 13838.57 | 76991.92
Grand Total |  |  |  | 152.37 | 1168.57 | 10299.85 | 7818.86 | 57367.26 | 10345.62 | 10686.63 | 427490.45 | 245908.67 | 18578.61 | 27840 | 817656.89

## 900615314
Pin: 7068 | Project: Whirlwind Expansion
Order: 900615314 | 900615314- Whirlwind (NU): Equip one 220kV position
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | 3rd Party Billable A&G - Collectible Ord | WO Postings / Contributions | 3rd Party Billable A&G - Collectible Ord | 35.21 | 64.62 | [10 empty] | 99.83
|  | WO Postings / Contributions Total |  | 35.21 | 64.62 | [10 empty] | 99.83
| 3rd Party Billable A&G - Collectible Ord Total |  |  | 35.21 | 64.62 | [10 empty] | 99.83
| BP&FM | Labor | Labor Entries <$5,000 |  |  |  | 182.75 | 362.59 | 945.92 | 373.27 | 190.7 |  |  |  |  | 2055.23
|  | Labor Total |  |  |  |  | 182.75 | 362.59 | 945.92 | 373.27 | 190.7 |  |  |  |  | 2055.23
| BP&FM Total | [5 empty] | 182.75 | 362.59 | 945.92 | 373.27 | 190.7 |  |  |  |  | 2055.23
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 2232.63 | 2232.63
|  | Labor Total | [12 empty] | 2232.63 | 2232.63
| ELEC SYS PLANNING Total | [13 empty] | 2232.63 | 2232.63
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 169.37 | 163.9 | 159.92 |  |  | 207.91 | 238.26 | 169.21 | 338.44 | 337.82 |  |  | 1784.83
|  | Labor Total |  | 169.37 | 163.9 | 159.92 |  |  | 207.91 | 238.26 | 169.21 | 338.44 | 337.82 |  |  | 1784.83
| ENG ADVANCEMENT Total |  |  | 169.37 | 163.9 | 159.92 |  |  | 207.91 | 238.26 | 169.21 | 338.44 | 337.82 |  |  | 1784.83
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 52.13 | 3012.1 | 1333.96 | 3368.46 | 2855.51 | 5250.89 | 5188.35 | 6388.93 | 6016.72 | 111.14 | 33578.19
|  | Labor Total |  |  |  | 52.13 | 3012.1 | 1333.96 | 3368.46 | 2855.51 | 5250.89 | 5188.35 | 6388.93 | 6016.72 | 111.14 | 33578.19
| ENGINEERING Total |  |  |  |  | 52.13 | 3012.1 | 1333.96 | 3368.46 | 2855.51 | 5250.89 | 5188.35 | 6388.93 | 6016.72 | 111.14 | 33578.19
| Labor - Other | Labor | Labor Entries <$5,000 |  | 32.42 | -32.42 | 95.17 | 108.01 | -323.29 | 68.7 | -17.52 | 25.9 | 701.2 | -971.3 | 369.96 | 56.83
|  | Labor Total |  |  | 32.42 | -32.42 | 95.17 | 108.01 | -323.29 | 68.7 | -17.52 | 25.9 | 701.2 | -971.3 | 369.96 | 56.83
| Labor - Other Total |  |  |  | 32.42 | -32.42 | 95.17 | 108.01 | -323.29 | 68.7 | -17.52 | 25.9 | 701.2 | -971.3 | 369.96 | 56.83
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 |  | 123.28 | [10 empty] | 123.28
|  | Labor Total |  |  | 123.28 | [10 empty] | 123.28
| MAJOR PROJECT ORG Total |  |  |  | 123.28 | [10 empty] | 123.28
| Other | Other | Other | [8 empty] | 371129.99 | -371129.99 |  | 5067.55 | 5067.55
|  | Other Total | [9 empty] | 371129.99 | -371129.99 |  | 5067.55 | 5067.55
| Other Total | [10 empty] | 371129.99 | -371129.99 |  | 5067.55 | 5067.55
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | [5 empty] | 271.04 |  | 328.5 |  | 219 |  | 2203.2 | 3021.74
|  | Contract Total | [6 empty] | 271.04 |  | 328.5 |  | 219 |  | 2203.2 | 3021.74
| Temporary/Supplementary - Trade/Labor Total | [7 empty] | 271.04 |  | 328.5 |  | 219 |  | 2203.2 | 3021.74
1. Project Support Total |  |  |  | 204.58 | 384.22 | 179.63 | 3290.02 | 1804.56 | 4470.04 | 3535.74 | 5921.78 | 376682.68 | -363483.04 | 5045.42 | 9984.48 | 48020.11
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | MITSUBISHI ELECTRIC | [9 empty] | 341056 |  |  | 341056
|  | Material - Direct Purchase Total | [10 empty] | 341056 |  |  | 341056
| Breakers - Circuit-DP Total | [11 empty] | 341056 |  |  | 341056
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 1813.36 | 1813.36
|  | Material - Direct Purchase Total | [12 empty] | 1813.36 | 1813.36
| Electric Wiring and Components-DP Total | [13 empty] | 1813.36 | 1813.36
| Line Switches & Switchgear-DP | Material - Direct Purchase | Line Switches & Switchgear-DP | [5 empty] | 42724 | [6 empty] | 42724
|  |  | SOUTHERN STATES LLC | [9 empty] | 191906 |  |  | 191906
|  | Material - Direct Purchase Total | [6 empty] | 42724 |  |  |  | 191906 |  |  | 234630
| Line Switches & Switchgear-DP Total | [7 empty] | 42724 |  |  |  | 191906 |  |  | 234630
| Material - Other | Material | Material - Other | [5 empty] | 44.58 |  |  |  | 39073.25 | 3.31 | 133.84 | 39254.98
|  | Material Total | [6 empty] | 44.58 |  |  |  | 39073.25 | 3.31 | 133.84 | 39254.98
| Material - Other Total | [7 empty] | 44.58 |  |  |  | 39073.25 | 3.31 | 133.84 | 39254.98
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 4744.33 |  | 4744.33
|  |  | Transportation & Mobile Equip-DP | [10 empty] | 5588.19 |  | 5588.19
|  | Material - Direct Purchase Total | [11 empty] | 10332.52 |  | 10332.52
| Transportation & Mobile Equip-DP Total | [12 empty] | 10332.52 |  | 10332.52
2. Material Total | [8 empty] | 42768.58 |  |  |  | 572035.25 | 10335.83 | 1947.2 | 627086.86
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  |  | 760 | 608 | 1444 | 988 |  | 608 | 608 | 760 | 1064 | 6840
|  | Contract Total |  |  |  |  | 760 | 608 | 1444 | 988 |  | 608 | 608 | 760 | 1064 | 6840
| Construction Management Services Total | [5 empty] | 760 | 608 | 1444 | 988 |  | 608 | 608 | 760 | 1064 | 6840
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  |  | 537.79 | 155.98 | 166.69 |  | 166.87 | 166.87 | 328.68 |  |  | 1522.88
|  | Labor Total |  |  |  |  | 537.79 | 155.98 | 166.69 |  | 166.87 | 166.87 | 328.68 |  |  | 1522.88
| ENGINEERING Total | [5 empty] | 537.79 | 155.98 | 166.69 |  | 166.87 | 166.87 | 328.68 |  |  | 1522.88
3. Construction Total | [6 empty] | 1297.79 | 763.98 | 1610.69 | 988 | 166.87 | 774.87 | 936.68 | 760 | 1064 | 8362.88
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 18.89 | 27.3 | 16.03 | 368.28 | 181.43 | 792.3 | 460.87 | 484.86 | 665.19 | 4273.08 | 614.8 | 280.49 | 8183.52
|  | Chargeback Total |  | 18.89 | 27.3 | 16.03 | 368.28 | 181.43 | 792.3 | 460.87 | 484.86 | 665.19 | 4273.08 | 614.8 | 280.49 | 8183.52
| Chargebacks Total |  |  | 18.89 | 27.3 | 16.03 | 368.28 | 181.43 | 792.3 | 460.87 | 484.86 | 665.19 | 4273.08 | 614.8 | 280.49 | 8183.52
| Labor - Other | Labor | Division Overhead | [9 empty] | 39286.88 |  |  | 39286.88
|  |  | Labor Entries <$5,000 | 62.73 | 113.69 | 59.3 | 1313.58 | 665.98 | 4288.81 | 1249.12 | 1906.19 | 1821.78 | 6851.08 | 1512.73 | 1002.63 | 20847.62
|  | Labor Total |  | 62.73 | 113.69 | 59.3 | 1313.58 | 665.98 | 4288.81 | 1249.12 | 1906.19 | 1821.78 | 46137.96 | 1512.73 | 1002.63 | 60134.5
| Labor - Other Total |  |  | 62.73 | 113.69 | 59.3 | 1313.58 | 665.98 | 4288.81 | 1249.12 | 1906.19 | 1821.78 | 46137.96 | 1512.73 | 1002.63 | 60134.5
4. Allocated Total |  |  |  | 81.62 | 140.99 | 75.33 | 1681.86 | 847.41 | 5081.11 | 1709.99 | 2391.05 | 2486.97 | 50411.04 | 2127.53 | 1283.12 | 68318.02
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax | [11 empty] | 4858.32 | 4858.32
|  |  | Capitalized Overhead - A&G |  |  | 9.09 | 223.58 | 284.31 | 1924.79 | 218.88 | 239.85 | 394.88 | 16303.79 | 482.79 | 258.62 | 20340.58
|  |  | Capitalized Overhead - Inj & Damages | 0.23 | 0.8 | 0.27 | 4.57 | 25.06 | 67.46 | 4.8 | 10.62 | 7.43 | 1991.19 | 28.79 | 6.69 | 2147.91
|  |  | Capitalized Overhead - P&B/Payroll Tax | 115.51 | 369.77 | 184.19 | 4919.06 | 2957.8 | 5843.82 | 4578.77 | 4682.6 | 8194.82 | 3791.03 | 4303.74 | 6347.32 | 46288.43
|  |  | Corporate Overheads Correction |  |  |  |  | -20.05 | [7 empty] | -20.05
|  | Non Budgeted Total |  | 115.74 | 370.57 | 193.55 | 5147.21 | 3247.12 | 7836.07 | 4802.45 | 4933.07 | 8597.13 | 22086.01 | 4815.32 | 11470.95 | 73615.19
| Non Budget - Other Total |  |  | 115.74 | 370.57 | 193.55 | 5147.21 | 3247.12 | 7836.07 | 4802.45 | 4933.07 | 8597.13 | 22086.01 | 4815.32 | 11470.95 | 73615.19
5. Corporate Overhead Total |  |  |  | 115.74 | 370.57 | 193.55 | 5147.21 | 3247.12 | 7836.07 | 4802.45 | 4933.07 | 8597.13 | 22086.01 | 4815.32 | 11470.95 | 73615.19
Grand Total |  |  |  | 401.94 | 895.78 | 448.51 | 11416.88 | 6663.07 | 61766.49 | 11036.18 | 13412.77 | 388541.65 | 281985.94 | 23084.1 | 25749.75 | 825403.06

## 900397857
Pin: 7054 | Project: Whirlwind Expansion
Order: 900397857 | 900397857- Whirlwind: Plan of Service Reliability N
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [7 empty] | 381.4 | 166.98 |  |  |  | 548.38
|  | Labor Total | [8 empty] | 381.4 | 166.98 |  |  |  | 548.38
| BP&FM Total | [9 empty] | 381.4 | 166.98 |  |  |  | 548.38
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 105.3 | 105.3
|  | Labor Total | [12 empty] | 105.3 | 105.3
| ELEC SYS PLANNING Total | [13 empty] | 105.3 | 105.3
| ENGINEERING | Labor | Labor Entries <$5,000 | 419.65 | 856.03 | 1005.48 | 676.92 | 462.65 | 155.76 |  | 1149.39 | 858.75 | 313.32 | 207.86 |  | 6105.81
|  | Labor Total |  | 419.65 | 856.03 | 1005.48 | 676.92 | 462.65 | 155.76 |  | 1149.39 | 858.75 | 313.32 | 207.86 |  | 6105.81
| ENGINEERING Total |  |  | 419.65 | 856.03 | 1005.48 | 676.92 | 462.65 | 155.76 |  | 1149.39 | 858.75 | 313.32 | 207.86 |  | 6105.81
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 3691 | [7 empty] | 419.86 |  | 5114.52 | 541.5 | 9766.88
|  | Contract Total |  | 3691 | [7 empty] | 419.86 |  | 5114.52 | 541.5 | 9766.88
| Engineering/Technical Professional Servi Total |  |  | 3691 | [7 empty] | 419.86 |  | 5114.52 | 541.5 | 9766.88
| Labor - Other | Labor | Labor Entries <$5,000 | -1.14 | 121.91 | -156.36 | 42.45 | 200.01 | -329.57 | 122.7 | 1559.05 | -307.35 | -1002.34 | 110.08 | 301.7 | 661.14
|  | Labor Total |  | -1.14 | 121.91 | -156.36 | 42.45 | 200.01 | -329.57 | 122.7 | 1559.05 | -307.35 | -1002.34 | 110.08 | 301.7 | 661.14
| Labor - Other Total |  |  | -1.14 | 121.91 | -156.36 | 42.45 | 200.01 | -329.57 | 122.7 | 1559.05 | -307.35 | -1002.34 | 110.08 | 301.7 | 661.14
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [9 empty] | 245.17 | 1773.38 |  | 2018.55
|  | Labor Total | [10 empty] | 245.17 | 1773.38 |  | 2018.55
| NORTH GRIDMGMTCENTER Total | [11 empty] | 245.17 | 1773.38 |  | 2018.55
| Other | Other | Other | [6 empty] | 56192.28 | -52578.25 | 4760.72 | 6888 | 95.46 | 133671.63 | 149029.84
|  | Other Total | [7 empty] | 56192.28 | -52578.25 | 4760.72 | 6888 | 95.46 | 133671.63 | 149029.84
| Other Total | [8 empty] | 56192.28 | -52578.25 | 4760.72 | 6888 | 95.46 | 133671.63 | 149029.84
| SC&M | Labor | Labor Entries <$5,000 | 261.62 | 384.56 | 242.55 |  | 259.74 | 369.13 |  | 1879.28 | 3677.33 | -170.95 |  |  | 6903.26
|  | Labor Total |  | 261.62 | 384.56 | 242.55 |  | 259.74 | 369.13 |  | 1879.28 | 3677.33 | -170.95 |  |  | 6903.26
| SC&M Total |  |  | 261.62 | 384.56 | 242.55 |  | 259.74 | 369.13 |  | 1879.28 | 3677.33 | -170.95 |  |  | 6903.26
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  | 590.55 | 572.39 | 132.12 | 218.85 | [6 empty] | 1513.91
|  | Labor Total |  |  |  | 590.55 | 572.39 | 132.12 | 218.85 | [6 empty] | 1513.91
| SCM HOME CENTER Total |  |  |  |  | 590.55 | 572.39 | 132.12 | 218.85 | [6 empty] | 1513.91
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 232.58 |  | 97.06 | [5 empty] | 96.8 | 707.2 |  |  | 1133.64
|  | Contract Total |  | 232.58 |  | 97.06 | [5 empty] | 96.8 | 707.2 |  |  | 1133.64
| Temporary/Supplementary - Trade/Labor Total |  |  | 232.58 |  | 97.06 | [5 empty] | 96.8 | 707.2 |  |  | 1133.64
1. Project Support Total |  |  |  | 4603.71 | 1362.5 | 1779.28 | 1291.76 | 1054.52 | 414.17 | 56314.98 | -47609.13 | 9673.09 | 6980.4 | 7301.3 | 134620.13 | 177786.71
2. Material | Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Material Entries <$5,000 |  |  | 626.63 | [9 empty] | 626.63
|  | Material - Direct Purchase Total |  |  |  | 626.63 | [9 empty] | 626.63
| Building, Shop & Industrial Products/Eqp Total |  |  |  |  | 626.63 | [9 empty] | 626.63
| Electric Wiring and Components-DP | Material - Direct Purchase | ANIXTER INC | [7 empty] | 48555 |  |  |  |  | 48555
|  |  | Electric Wiring and Components-DP | [6 empty] | 20349.4 | 6299.81 |  |  |  |  | 26649.21
|  |  | Material Entries <$5,000 | 66.24 | 1453.57 |  | 239.54 |  | 939.6 |  |  |  |  | 1294.8 |  | 3993.75
|  |  | SOUTHWIRE COMPANY |  |  |  |  | 67749 | [7 empty] | 67749
|  | Material - Direct Purchase Total |  | 66.24 | 1453.57 |  | 239.54 | 67749 | 939.6 | 20349.4 | 54854.81 |  |  | 1294.8 |  | 146946.96
| Electric Wiring and Components-DP Total |  |  | 66.24 | 1453.57 |  | 239.54 | 67749 | 939.6 | 20349.4 | 54854.81 |  |  | 1294.8 |  | 146946.96
| Material - Inventory | Material | Material - Inventory | 417.44 | 3106.35 | 67484.71 | [9 empty] | 71008.5
|  | Material Total |  | 417.44 | 3106.35 | 67484.71 | [9 empty] | 71008.5
| Material - Inventory Total |  |  | 417.44 | 3106.35 | 67484.71 | [9 empty] | 71008.5
| Material - Other | Material | Material - Other | 671.05 | 233.2 | 7582.8 | 122.87 | 5762.68 | 2465.97 | 1502.99 | 5671.01 | 224.7 |  | 94.32 |  | 24331.59
|  | Material Total |  | 671.05 | 233.2 | 7582.8 | 122.87 | 5762.68 | 2465.97 | 1502.99 | 5671.01 | 224.7 |  | 94.32 |  | 24331.59
| Material - Other Total |  |  | 671.05 | 233.2 | 7582.8 | 122.87 | 5762.68 | 2465.97 | 1502.99 | 5671.01 | 224.7 |  | 94.32 |  | 24331.59
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 201.36 |  |  |  |  | 781.07 |  |  |  |  | 982.43
|  | Material - Direct Purchase Total |  |  |  | 201.36 |  |  |  |  | 781.07 |  |  |  |  | 982.43
| Metals & Fabricated Metal Products-DP Total |  |  |  |  | 201.36 |  |  |  |  | 781.07 |  |  |  |  | 982.43
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 6.72 | [9 empty] | 6.72
|  | Material - Direct Purchase Total |  |  |  | 6.72 | [9 empty] | 6.72
| Monitor Equipment, Gauges and Hoses-DP Total |  |  |  |  | 6.72 | [9 empty] | 6.72
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 2.26 |  |  |  |  | 76.89 |  |  |  |  | 79.15
|  | Material - Direct Purchase Total |  |  |  | 2.26 |  |  |  |  | 76.89 |  |  |  |  | 79.15
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  |  |  | 2.26 |  |  |  |  | 76.89 |  |  |  |  | 79.15
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | AGILE SOURCING PARTNERS INC | 6600 | [11 empty] | 6600
|  |  | Material Entries <$5,000 |  |  | 287.89 |  |  |  |  | 1609.41 |  |  |  |  | 1897.3
|  | Material - Direct Purchase Total |  | 6600 |  | 287.89 |  |  |  |  | 1609.41 |  |  |  |  | 8497.3
| Pole Line Hdwe & Connectors-DP Total |  |  | 6600 |  | 287.89 |  |  |  |  | 1609.41 |  |  |  |  | 8497.3
| Protection and Test-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 190.43 |  |  |  |  | 217.53 |  |  |  |  | 407.96
|  | Material - Direct Purchase Total |  |  |  | 190.43 |  |  |  |  | 217.53 |  |  |  |  | 407.96
| Protection and Test-DP Total |  |  |  |  | 190.43 |  |  |  |  | 217.53 |  |  |  |  | 407.96
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 3954.48 |  | 3592 | [7 empty] | 7546.48
|  | Material - Direct Purchase Total |  |  |  | 3954.48 |  | 3592 | [7 empty] | 7546.48
| Steel / Fabricated / Structural-DP Total |  |  |  |  | 3954.48 |  | 3592 | [7 empty] | 7546.48
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Wire, Cable & Bus Bar-DP | [7 empty] | 10920 |  |  |  |  | 10920
|  | Material - Direct Purchase Total | [8 empty] | 10920 |  |  |  |  | 10920
| Wire, Cable & Bus Bar-DP Total | [9 empty] | 10920 |  |  |  |  | 10920
2. Material Total |  |  |  | 7754.73 | 4793.12 | 80337.28 | 362.41 | 77103.68 | 3405.57 | 21852.39 | 74130.72 | 224.7 |  | 1389.12 |  | 271353.72
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  | 1144 | 456 | 3528 | 3099.2 | 4453.12 | 7507.27 | 760 | 44124.42 | 54348 | 73353.45 | 192773.46
|  | Contract Total |  |  |  | 1144 | 456 | 3528 | 3099.2 | 4453.12 | 7507.27 | 760 | 44124.42 | 54348 | 73353.45 | 192773.46
| Construction Management Services Total |  |  |  |  | 1144 | 456 | 3528 | 3099.2 | 4453.12 | 7507.27 | 760 | 44124.42 | 54348 | 73353.45 | 192773.46
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 312.14 |  |  |  |  | 163.25 |  |  |  |  | 475.39
|  | Labor Total |  |  |  | 312.14 |  |  |  |  | 163.25 |  |  |  |  | 475.39
| ENGINEERING Total |  |  |  |  | 312.14 |  |  |  |  | 163.25 |  |  |  |  | 475.39
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  |  | 9371 | [8 empty] | 13427.8 | 22798.8
|  |  | KINDNESS GENERAL CONTRACTORS INC | [9 empty] | 549986 |  |  | 549986
|  | Contract Total |  |  |  | 9371 | [6 empty] | 549986 |  | 13427.8 | 572784.8
| Major Construction, Turnkey, Trans/Subs Total |  |  |  |  | 9371 | [6 empty] | 549986 |  | 13427.8 | 572784.8
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | [6 empty] | 5613.89 | 26405.63 | 13863.36 | 188.18 |  |  | 46071.06
|  |  | Sub Stn Elect | [7 empty] | 5402.33 |  |  |  |  | 5402.33
|  | Labor Total | [7 empty] | 5613.89 | 31807.96 | 13863.36 | 188.18 |  |  | 51473.39
| N/W SUBSMTCETEST&APP Total | [8 empty] | 5613.89 | 31807.96 | 13863.36 | 188.18 |  |  | 51473.39
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [7 empty] | 2300.04 |  |  |  |  | 2300.04
|  |  | Sub Elect Apr | [7 empty] | 14101.98 |  |  |  |  | 14101.98
|  | Labor Total | [8 empty] | 16402.02 |  |  |  |  | 16402.02
| S/E SUBS MTCETST&APP Total | [9 empty] | 16402.02 |  |  |  |  | 16402.02
| SC&M | Labor | Labor Entries <$5,000 | 230.75 | 129.37 | 131.64 |  |  |  |  | 8060.33 | 27975.46 | 20.89 |  |  | 36548.44
|  | Labor Total |  | 230.75 | 129.37 | 131.64 |  |  |  |  | 8060.33 | 27975.46 | 20.89 |  |  | 36548.44
| SC&M Total |  |  | 230.75 | 129.37 | 131.64 |  |  |  |  | 8060.33 | 27975.46 | 20.89 |  |  | 36548.44
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [6 empty] | 205.36 |  | 19735.26 | 12895.43 |  | 1266.8 | 34102.85
|  | Contract Total | [7 empty] | 205.36 |  | 19735.26 | 12895.43 |  | 1266.8 | 34102.85
| Short Term Equipment Rent Total | [8 empty] | 205.36 |  | 19735.26 | 12895.43 |  | 1266.8 | 34102.85
3. Construction Total |  |  |  | 230.75 | 129.37 | 10958.78 | 456 | 3528 | 3099.2 | 10272.37 | 63940.83 | 62334.08 | 607214.92 | 54348 | 88048.05 | 904560.35
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 353.35 | 871.61 | 294.47 | 127.17 | 589.58 | 74 | 913.79 | 5646.92 | 5357.62 | 3908.39 | 587.52 | 585.92 | 19310.34
|  |  | MATERIAL MANAGEM |  |  | 16446.02 | [9 empty] | 16446.02
|  | Chargeback Total |  | 353.35 | 871.61 | 16740.49 | 127.17 | 589.58 | 74 | 913.79 | 5646.92 | 5357.62 | 3908.39 | 587.52 | 585.92 | 35756.36
| Chargebacks Total |  |  | 353.35 | 871.61 | 16740.49 | 127.17 | 589.58 | 74 | 913.79 | 5646.92 | 5357.62 | 3908.39 | 587.52 | 585.92 | 35756.36
| Labor - Other | Labor | Division Overhead | [9 empty] | 45234.63 |  |  | 45234.63
|  |  | Labor Entries <$5,000 | 1433.73 | 945.61 | 7037.68 | 476.18 | 5501.6 | 378.67 | 3439.07 | 20649.53 | 14399.26 | 4719.34 | 1836.37 | 3410.58 | 64227.62
|  | Labor Total |  | 1433.73 | 945.61 | 7037.68 | 476.18 | 5501.6 | 378.67 | 3439.07 | 20649.53 | 14399.26 | 49953.97 | 1836.37 | 3410.58 | 109462.25
| Labor - Other Total |  |  | 1433.73 | 945.61 | 7037.68 | 476.18 | 5501.6 | 378.67 | 3439.07 | 20649.53 | 14399.26 | 49953.97 | 1836.37 | 3410.58 | 109462.25
4. Allocated Total |  |  |  | 1787.08 | 1817.22 | 23778.17 | 603.35 | 6091.18 | 452.67 | 4352.86 | 26296.45 | 19756.88 | 53862.36 | 2423.89 | 3996.5 | 145218.61
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 6858.16 | 444.84 | [7 empty] | 7303
|  |  | Capitalized Overhead - A&G | 802.33 | 237.36 | 4165.2 | 96.77 | 7305.67 | 263.09 | 1353.96 | 4836.54 | 4120.99 | 17260.47 | 1729.99 | 2735.93 | 44908.3
|  |  | Capitalized Overhead - Inj & Damages | 9.78 | 13.99 | 112.09 | 1.87 | 751.94 | 5.52 | 29.4 | 213.06 | 81.54 | 231.41 | 9.87 | 11.4 | 1471.87
|  |  | Capitalized Overhead - P&B/Payroll Tax | 621.23 | 1726.05 | 2179.89 | 1660.02 | 1590.92 | 530.07 | 6474.01 | 44501.55 | 60668.45 | -205.17 | 1561.19 | 815.37 | 122123.58
|  |  | Corporate Overheads Correction |  |  |  |  | -16736.52 | [7 empty] | -16736.52
|  | Non Budgeted Total |  | 1433.34 | 1977.4 | 6457.18 | 8616.82 | -6643.15 | 798.68 | 7857.37 | 49551.15 | 64870.98 | 17286.71 | 3301.05 | 3562.7 | 159070.23
| Non Budget - Other Total |  |  | 1433.34 | 1977.4 | 6457.18 | 8616.82 | -6643.15 | 798.68 | 7857.37 | 49551.15 | 64870.98 | 17286.71 | 3301.05 | 3562.7 | 159070.23
5. Corporate Overhead Total |  |  |  | 1433.34 | 1977.4 | 6457.18 | 8616.82 | -6643.15 | 798.68 | 7857.37 | 49551.15 | 64870.98 | 17286.71 | 3301.05 | 3562.7 | 159070.23
Grand Total |  |  |  | 15809.61 | 10079.61 | 123310.69 | 11330.34 | 81134.23 | 8170.29 | 100649.97 | 166310.02 | 156859.73 | 685344.39 | 68763.36 | 230227.38 | 1657989.62

## 900389180
Pin: 7066 | Project: Whirlwind Expansion
Order: 900389180 | 900389180- Whirlwind Sub: Extension of positions 9-
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | 3rd Party Billable A&G - Collectible Ord | WO Postings / Contributions | 3rd Party Billable A&G - Collectible Ord | 47838.44 | 1060.95 | 152019.3 | [9 empty] | 200918.69
|  | WO Postings / Contributions Total |  | 47838.44 | 1060.95 | 152019.3 | [9 empty] | 200918.69
| 3rd Party Billable A&G - Collectible Ord Total |  |  | 47838.44 | 1060.95 | 152019.3 | [9 empty] | 200918.69
| BP&FM | Labor | Labor Entries <$5,000 | 193.64 | [6 empty] | 977.34 | 214.69 |  |  |  | 1385.67
|  | Labor Total |  | 193.64 | [6 empty] | 977.34 | 214.69 |  |  |  | 1385.67
| BP&FM Total |  |  | 193.64 | [6 empty] | 977.34 | 214.69 |  |  |  | 1385.67
| CORP COMM SVP | Labor | Labor Entries <$5,000 | [7 empty] | 62.39 |  |  |  |  | 62.39
|  | Labor Total | [8 empty] | 62.39 |  |  |  |  | 62.39
| CORP COMM SVP Total | [9 empty] | 62.39 |  |  |  |  | 62.39
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 157.94 | 157.94
|  | Labor Total | [12 empty] | 157.94 | 157.94
| ELEC SYS PLANNING Total | [13 empty] | 157.94 | 157.94
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 508.11 | 163.9 | 159.92 | [9 empty] | 831.93
|  | Labor Total |  | 508.11 | 163.9 | 159.92 | [9 empty] | 831.93
| ENG ADVANCEMENT Total |  |  | 508.11 | 163.9 | 159.92 | [9 empty] | 831.93
| ENGINEERING | Labor | Labor Entries <$5,000 | 891.65 | 731.36 | 1597.94 | 891.63 | 215.05 | 683.01 | 938.84 | 5514.14 | 1981.19 | 854.01 | 155.9 |  | 14454.72
|  | Labor Total |  | 891.65 | 731.36 | 1597.94 | 891.63 | 215.05 | 683.01 | 938.84 | 5514.14 | 1981.19 | 854.01 | 155.9 |  | 14454.72
| ENGINEERING Total |  |  | 891.65 | 731.36 | 1597.94 | 891.63 | 215.05 | 683.01 | 938.84 | 5514.14 | 1981.19 | 854.01 | 155.9 |  | 14454.72
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 16894.41 | [7 empty] | 419.86 |  | 5114.52 | 541.5 | 22970.29
|  | Contract Total |  | 16894.41 | [7 empty] | 419.86 |  | 5114.52 | 541.5 | 22970.29
| Engineering/Technical Professional Servi Total |  |  | 16894.41 | [7 empty] | 419.86 |  | 5114.52 | 541.5 | 22970.29
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 |  | 600 | 3094.5 | 1372.5 | 959.9 | 322.5 | 521.43 | 2249.64 | 1603.1 | 1386.45 | 348.6 |  | 12458.62
|  | Contract Total |  |  | 600 | 3094.5 | 1372.5 | 959.9 | 322.5 | 521.43 | 2249.64 | 1603.1 | 1386.45 | 348.6 |  | 12458.62
| Environmental/Safety Professional Servic Total |  |  |  | 600 | 3094.5 | 1372.5 | 959.9 | 322.5 | 521.43 | 2249.64 | 1603.1 | 1386.45 | 348.6 |  | 12458.62
| Labor - Other | Labor | Labor Entries <$5,000 | 6.89 | 198.75 | -270.52 | 53.72 | 202.05 | -313.04 | 82.98 | 5152.76 | -559.21 | -3933.8 | -609.89 | 430.67 | 441.36
|  | Labor Total |  | 6.89 | 198.75 | -270.52 | 53.72 | 202.05 | -313.04 | 82.98 | 5152.76 | -559.21 | -3933.8 | -609.89 | 430.67 | 441.36
| Labor - Other Total |  |  | 6.89 | 198.75 | -270.52 | 53.72 | 202.05 | -313.04 | 82.98 | 5152.76 | -559.21 | -3933.8 | -609.89 | 430.67 | 441.36
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | [5 empty] | 1482.7 | 494.03 | 493.61 |  |  |  |  | 2470.34
|  | Labor Total | [6 empty] | 1482.7 | 494.03 | 493.61 |  |  |  |  | 2470.34
| MAJOR PROJECT ORG Total | [7 empty] | 1482.7 | 494.03 | 493.61 |  |  |  |  | 2470.34
| NORTH GRIDMGMTCENTER | Labor | Labor Entries <$5,000 | [8 empty] | 418.23 | 91.04 |  |  | 509.27
|  | Labor Total | [9 empty] | 418.23 | 91.04 |  |  | 509.27
| NORTH GRIDMGMTCENTER Total | [10 empty] | 418.23 | 91.04 |  |  | 509.27
| Other | Other | Other | -99119.55 | 1011.08 | 303.14 | -1279.44 | 2055.87 | -2049.8 | 155.33 | 29720.37 | 41886.32 | 29976.07 | 3334.4 | 117016.91 | 123010.7
|  | Other Total |  | -99119.55 | 1011.08 | 303.14 | -1279.44 | 2055.87 | -2049.8 | 155.33 | 29720.37 | 41886.32 | 29976.07 | 3334.4 | 117016.91 | 123010.7
| Other Total |  |  | -99119.55 | 1011.08 | 303.14 | -1279.44 | 2055.87 | -2049.8 | 155.33 | 29720.37 | 41886.32 | 29976.07 | 3334.4 | 117016.91 | 123010.7
| SC&M | Labor | Labor Entries <$5,000 | 575.56 | 1105.6 | 388.09 |  | 259.74 |  |  | 8466.24 | 26981.18 | 789.89 | 392.52 |  | 38958.82
|  |  | SC&M / Spl Cbl Subs | [7 empty] | 13625.9 |  |  |  |  | 13625.9
|  |  | SC&M / Spl Trnf | [7 empty] | 5931.64 |  |  |  |  | 5931.64
|  | Labor Total |  | 575.56 | 1105.6 | 388.09 |  | 259.74 |  |  | 28023.78 | 26981.18 | 789.89 | 392.52 |  | 58516.36
| SC&M Total |  |  | 575.56 | 1105.6 | 388.09 |  | 259.74 |  |  | 28023.78 | 26981.18 | 789.89 | 392.52 |  | 58516.36
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  | 635.98 | 484.33 | 264.24 | 393.93 | 660.6 | 605.03 | 220.2 | 264.24 |  |  | 3528.55
|  | Labor Total |  |  |  | 635.98 | 484.33 | 264.24 | 393.93 | 660.6 | 605.03 | 220.2 | 264.24 |  |  | 3528.55
| SCM HOME CENTER Total |  |  |  |  | 635.98 | 484.33 | 264.24 | 393.93 | 660.6 | 605.03 | 220.2 | 264.24 |  |  | 3528.55
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 |  |  | 880 | [9 empty] | 880
|  | Contract Total |  |  |  | 880 | [9 empty] | 880
| Temporary/Supplementary - Technical/Prof Total |  |  |  |  | 880 | [9 empty] | 880
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 65.5 | 97.06 | 97.06 | 429 |  | 290.4 |  |  |  | 96.8 |  |  | 1075.82
|  | Contract Total |  | 65.5 | 97.06 | 97.06 | 429 |  | 290.4 |  |  |  | 96.8 |  |  | 1075.82
| Temporary/Supplementary - Trade/Labor Total |  |  | 65.5 | 97.06 | 97.06 | 429 |  | 290.4 |  |  |  | 96.8 |  |  | 1075.82
1. Project Support Total |  |  |  | -32145.35 | 4968.7 | 158905.41 | 1951.74 | 3956.85 | 809.7 | 2853.21 | 72799.06 | 73165.56 | 29524.7 | 8736.05 | 118147.02 | 443672.65
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | MITSUBISHI ELECTRIC |  |  | 285000 | [9 empty] | 285000
|  | Material - Direct Purchase Total |  |  |  | 285000 | [9 empty] | 285000
| Breakers - Circuit-DP Total |  |  |  |  | 285000 | [9 empty] | 285000
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp | [6 empty] | 6473.11 | [5 empty] | 6473.11
|  |  | JENSEN PRECAST |  |  | 115575.54 | [9 empty] | 115575.54
|  |  | Material Entries <$5,000 | 1581.12 |  | 3219.1 |  | 5.81 |  |  | 2130.12 | 2857.29 | 8.09 | 328.95 |  | 10130.48
|  | Material - Direct Purchase Total |  | 1581.12 |  | 118794.64 |  | 5.81 |  | 6473.11 | 2130.12 | 2857.29 | 8.09 | 328.95 |  | 132179.13
| Building, Shop & Industrial Products/Eqp Total |  |  | 1581.12 |  | 118794.64 |  | 5.81 |  | 6473.11 | 2130.12 | 2857.29 | 8.09 | 328.95 |  | 132179.13
| Capacitors and Regulators-DP | Material - Direct Purchase | HAEFELY TRENCH LIMITED | 114378 | [11 empty] | 114378
|  | Material - Direct Purchase Total |  | 114378 | [11 empty] | 114378
| Capacitors and Regulators-DP Total |  |  | 114378 | [11 empty] | 114378
| Electric Wiring and Components-DP | Material - Direct Purchase | Electric Wiring and Components-DP |  |  |  |  | 5494.28 | [7 empty] | 5494.28
|  |  | Material Entries <$5,000 | 4739.27 | 1436.4 | 174.73 | 1175.87 | 571.3 | 3153.24 |  | 2121.93 | 1210.85 |  | 799.67 |  | 15383.26
|  |  | ONE SOURCE DISTRIBUTORS INC | 60282.76 | [11 empty] | 60282.76
|  | Material - Direct Purchase Total |  | 65022.03 | 1436.4 | 174.73 | 1175.87 | 6065.58 | 3153.24 |  | 2121.93 | 1210.85 |  | 799.67 |  | 81160.3
| Electric Wiring and Components-DP Total |  |  | 65022.03 | 1436.4 | 174.73 | 1175.87 | 6065.58 | 3153.24 |  | 2121.93 | 1210.85 |  | 799.67 |  | 81160.3
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 2.97 |  |  |  |  | 1801.88 |  | 1488.89 |  |  | 3293.74
|  | Material - Direct Purchase Total |  |  |  | 2.97 |  |  |  |  | 1801.88 |  | 1488.89 |  |  | 3293.74
| Fuels, Chemicals & Petrochem-DP Total |  |  |  |  | 2.97 |  |  |  |  | 1801.88 |  | 1488.89 |  |  | 3293.74
| Material - Inventory | Material | Material - Inventory | 7730.19 |  | 362521.87 |  |  | 72.56 |  | 445.41 |  |  |  |  | 370770.03
|  | Material Total |  | 7730.19 |  | 362521.87 |  |  | 72.56 |  | 445.41 |  |  |  |  | 370770.03
| Material - Inventory Total |  |  | 7730.19 |  | 362521.87 |  |  | 72.56 |  | 445.41 |  |  |  |  | 370770.03
| Material - Other | Material | Material - Other | 19320.61 | 518.68 | 83072.43 | 1883.7 | 2729.41 | 1810.54 | 967.3 | 3869.29 | 1140.45 | 1257.44 | 0.45 | 1135.15 | 117705.45
|  | Material Total |  | 19320.61 | 518.68 | 83072.43 | 1883.7 | 2729.41 | 1810.54 | 967.3 | 3869.29 | 1140.45 | 1257.44 | 0.45 | 1135.15 | 117705.45
| Material - Other Total |  |  | 19320.61 | 518.68 | 83072.43 | 1883.7 | 2729.41 | 1810.54 | 967.3 | 3869.29 | 1140.45 | 1257.44 | 0.45 | 1135.15 | 117705.45
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 2411.03 |  |  |  | 146.02 | [5 empty] | 2557.05
|  |  | Metals & Fabricated Metal Products-DP | 78500 | [11 empty] | 78500
|  | Material - Direct Purchase Total |  | 78500 |  | 2411.03 |  |  |  | 146.02 | [5 empty] | 81057.05
| Metals & Fabricated Metal Products-DP Total |  |  | 78500 |  | 2411.03 |  |  |  | 146.02 | [5 empty] | 81057.05
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 61.56 | [9 empty] | 61.56
|  | Material - Direct Purchase Total |  |  |  | 61.56 | [9 empty] | 61.56
| Monitor Equipment, Gauges and Hoses-DP Total |  |  |  |  | 61.56 | [9 empty] | 61.56
| Other Consumables-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 75.87 |  |  |  |  | 75.87
|  | Material - Direct Purchase Total | [8 empty] | 75.87 |  |  |  |  | 75.87
| Other Consumables-DP Total | [9 empty] | 75.87 |  |  |  |  | 75.87
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 24.87 | [5 empty] | 1656.53 | 78.68 | 260.6 |  | 2020.68
|  | Material - Direct Purchase Total |  |  |  | 24.87 | [5 empty] | 1656.53 | 78.68 | 260.6 |  | 2020.68
| Pipe/Tubing, Fittings and Gaskets-DP Total |  |  |  |  | 24.87 | [5 empty] | 1656.53 | 78.68 | 260.6 |  | 2020.68
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 897.07 | 1770.31 | 345.7 |  |  |  | 3013.08
|  |  | Pole Line Hdwe & Connectors-DP |  |  | 7388.88 | [9 empty] | 7388.88
|  | Material - Direct Purchase Total |  |  |  | 7388.88 |  |  |  | 897.07 | 1770.31 | 345.7 |  |  |  | 10401.96
| Pole Line Hdwe & Connectors-DP Total |  |  |  |  | 7388.88 |  |  |  | 897.07 | 1770.31 | 345.7 |  |  |  | 10401.96
| Poles & Wood Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 805.1 |  |  |  |  | 805.1
|  | Material - Direct Purchase Total | [8 empty] | 805.1 |  |  |  |  | 805.1
| Poles & Wood Products-DP Total | [9 empty] | 805.1 |  |  |  |  | 805.1
| Protection and Test-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 190.43 |  |  |  |  | 48.26 |  |  |  |  | 238.69
|  | Material - Direct Purchase Total |  |  |  | 190.43 |  |  |  |  | 48.26 |  |  |  |  | 238.69
| Protection and Test-DP Total |  |  |  |  | 190.43 |  |  |  |  | 48.26 |  |  |  |  | 238.69
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 929.04 | [6 empty] | 3840 |  | 1680 | 6449.04
|  |  | PARCELL STEEL CO |  |  | 27885.98 | [9 empty] | 27885.98
|  | Material - Direct Purchase Total |  |  |  | 28815.02 | [6 empty] | 3840 |  | 1680 | 34335.02
| Steel / Fabricated / Structural-DP Total |  |  |  |  | 28815.02 | [6 empty] | 3840 |  | 1680 | 34335.02
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 184.28 |  |  |  |  | 184.28
|  | Material - Direct Purchase Total | [8 empty] | 184.28 |  |  |  |  | 184.28
| Transformers CT/PT/INSTR-DP Total | [9 empty] | 184.28 |  |  |  |  | 184.28
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | 5.93 |  |  |  | 21.47 | 147.9 | 159.54 | 552.82 | 1181.21 | 405.72 |  |  | 2474.59
|  | Material - Direct Purchase Total |  | 5.93 |  |  |  | 21.47 | 147.9 | 159.54 | 552.82 | 1181.21 | 405.72 |  |  | 2474.59
| Transportation & Mobile Equip-DP Total |  |  | 5.93 |  |  |  | 21.47 | 147.9 | 159.54 | 552.82 | 1181.21 | 405.72 |  |  | 2474.59
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 1004.53 |  |  | 1004.53
|  |  | Wire, Cable & Bus Bar-DP | [7 empty] | 10232.57 |  |  |  |  | 10232.57
|  | Material - Direct Purchase Total | [8 empty] | 10232.57 |  | 1004.53 |  |  | 11237.1
| Wire, Cable & Bus Bar-DP Total | [9 empty] | 10232.57 |  | 1004.53 |  |  | 11237.1
2. Material Total |  |  |  | 286537.88 | 1955.08 | 888458.43 | 3059.57 | 8822.27 | 5184.24 | 8643.04 | 24037.84 | 8392.03 | 8083.35 | 1389.67 | 2815.15 | 1247378.55
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  | 3676 |  | 8560.44 | 17404.8 | 13633.24 | 10148.26 | 1368 | 70035.22 | 74974.25 | 93906.31 | 293706.52
|  | Contract Total |  |  |  | 3676 |  | 8560.44 | 17404.8 | 13633.24 | 10148.26 | 1368 | 70035.22 | 74974.25 | 93906.31 | 293706.52
| Construction Management Services Total |  |  |  |  | 3676 |  | 8560.44 | 17404.8 | 13633.24 | 10148.26 | 1368 | 70035.22 | 74974.25 | 93906.31 | 293706.52
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [8 empty] | 329.98 |  |  |  | 329.98
|  | Contract Total | [9 empty] | 329.98 |  |  |  | 329.98
| Construction, Civil/Structural Total | [10 empty] | 329.98 |  |  |  | 329.98
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 468.2 |  |  |  |  | 163.25 |  |  |  |  | 631.45
|  | Labor Total |  |  |  | 468.2 |  |  |  |  | 163.25 |  |  |  |  | 631.45
| ENGINEERING Total |  |  |  |  | 468.2 |  |  |  |  | 163.25 |  |  |  |  | 631.45
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 |  |  | 6757.8 | 3222.13 |  |  |  | 16925.68 | 4733.75 | 108.2 |  | 424.98 | 32172.54
|  | Contract Total |  |  |  | 6757.8 | 3222.13 |  |  |  | 16925.68 | 4733.75 | 108.2 |  | 424.98 | 32172.54
| Hauling / Industrial Moving Services Total |  |  |  |  | 6757.8 | 3222.13 |  |  |  | 16925.68 | 4733.75 | 108.2 |  | 424.98 | 32172.54
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  |  | 20718 | [6 empty] | 1176 |  | 56983.38 | 78877.38
|  |  | KINDNESS GENERAL CONTRACTORS INC | [9 empty] | 494753 |  |  | 494753
|  | Contract Total |  |  |  | 20718 | [6 empty] | 495929 |  | 56983.38 | 573630.38
| Major Construction, Turnkey, Trans/Subs Total |  |  |  |  | 20718 | [6 empty] | 495929 |  | 56983.38 | 573630.38
| N/W SUBSMTCETEST&APP | Labor | Labor Entries <$5,000 | [6 empty] | 9233.69 | 51316.24 | 36917.02 | 4120.66 | 938.53 |  | 102526.14
|  |  | Sub Stn Elect | [7 empty] | 47366.68 |  |  |  |  | 47366.68
|  | Labor Total | [7 empty] | 9233.69 | 98682.92 | 36917.02 | 4120.66 | 938.53 |  | 149892.82
| N/W SUBSMTCETEST&APP Total | [8 empty] | 9233.69 | 98682.92 | 36917.02 | 4120.66 | 938.53 |  | 149892.82
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [6 empty] | 5322.18 | 10734.12 | 5843.66 | 706.17 | 382.67 |  | 22988.8
|  |  | Sub Elect Apr | [7 empty] | 5650.1 |  |  |  |  | 5650.1
|  |  | Sub Stn Elect | [7 empty] | 5541.13 |  |  |  |  | 5541.13
|  | Labor Total | [7 empty] | 5322.18 | 21925.35 | 5843.66 | 706.17 | 382.67 |  | 34180.03
| S/E SUBS MTCETST&APP Total | [8 empty] | 5322.18 | 21925.35 | 5843.66 | 706.17 | 382.67 |  | 34180.03
| SC&M | Labor | Labor Entries <$5,000 | 369.2 | 646.83 |  |  |  | 651.38 |  | 140528.96 | 75003.49 |  |  | 1015.59 | 218215.45
|  |  | SC&M / Elct Apr Const | [7 empty] | 5047.46 |  |  |  |  | 5047.46
|  |  | SC&M / Electn Constrn | [7 empty] | 25333 |  |  |  |  | 25333
|  |  | SC&M / Supervisor | [7 empty] | 16637.43 |  |  |  |  | 16637.43
|  | Labor Total |  | 369.2 | 646.83 |  |  |  | 651.38 |  | 187546.85 | 75003.49 |  |  | 1015.59 | 265233.34
| SC&M Total |  |  | 369.2 | 646.83 |  |  |  | 651.38 |  | 187546.85 | 75003.49 |  |  | 1015.59 | 265233.34
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [8 empty] | 38865 | 34223.32 | 17672.6 | 1229.54 | 91990.46
|  | Contract Total | [9 empty] | 38865 | 34223.32 | 17672.6 | 1229.54 | 91990.46
| Short Term Equipment Rent Total | [10 empty] | 38865 | 34223.32 | 17672.6 | 1229.54 | 91990.46
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 |  |  | 164 | 82 |  |  |  | 328 | 82 |  |  |  | 656
|  | Labor Total |  |  |  | 164 | 82 |  |  |  | 328 | 82 |  |  |  | 656
| TSD-HERC - Crane Svs Total |  |  |  |  | 164 | 82 |  |  |  | 328 | 82 |  |  |  | 656
3. Construction Total |  |  |  | 369.2 | 646.83 | 31784 | 3304.13 | 8560.44 | 18056.18 | 28189.11 | 335720.31 | 163142.9 | 605122.57 | 93968.05 | 153559.8 | 1442423.52
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 5682.91 | 856.83 | 3451.03 | 176.59 | 188.22 | 484.88 | 2294.18 | 1292.51 | 611.98 | 4123.12 | 679.5 | 1160.02 | 21001.77
|  |  | MATERIAL MANAGEM |  |  | 88346.58 | [9 empty] | 88346.58
|  |  | TDBU Vehicle Cost | [7 empty] | 28350.77 | 16495.69 |  |  |  | 44846.46
|  | Chargeback Total |  | 5682.91 | 856.83 | 91797.61 | 176.59 | 188.22 | 484.88 | 2294.18 | 29643.28 | 17107.67 | 4123.12 | 679.5 | 1160.02 | 154194.81
| Chargebacks Total |  |  | 5682.91 | 856.83 | 91797.61 | 176.59 | 188.22 | 484.88 | 2294.18 | 29643.28 | 17107.67 | 4123.12 | 679.5 | 1160.02 | 154194.81
| Labor - Other | Labor | Division Overhead | 17079.05 |  | 63888.96 |  |  |  |  | 40291.61 | 7248.11 | 52009.31 |  |  | 180517.04
|  |  | Labor Entries <$5,000 | 12167.68 | 1206.61 | 983.56 | 933.7 | 1376.85 | 2313.86 | 7097.51 | 9387.32 | 19465.66 | 657.96 | 2967.1 | 8087.93 | 66645.74
|  |  | OH Tool Expenses | [7 empty] | 10348.87 | 5326.07 |  |  |  | 15674.94
|  |  | Paid Absence | [7 empty] | 33933.45 | 13017.96 |  |  |  | 46951.41
|  |  | TOOL EXPENSE | [7 empty] | 7071.81 |  |  |  |  | 7071.81
|  | Labor Total |  | 29246.73 | 1206.61 | 64872.52 | 933.7 | 1376.85 | 2313.86 | 7097.51 | 101033.06 | 45057.8 | 52667.27 | 2967.1 | 8087.93 | 316860.94
| Labor - Other Total |  |  | 29246.73 | 1206.61 | 64872.52 | 933.7 | 1376.85 | 2313.86 | 7097.51 | 101033.06 | 45057.8 | 52667.27 | 2967.1 | 8087.93 | 316860.94
4. Allocated Total |  |  |  | 34929.64 | 2063.44 | 156670.13 | 1110.29 | 1565.07 | 2798.74 | 9391.69 | 130676.34 | 62165.47 | 56790.39 | 3646.6 | 9247.95 | 471055.75
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 19864.72 | 1205.32 | [7 empty] | 21070.04
|  |  | Capitalized Overhead - A&G |  |  |  | 381.75 | 1735.23 | 1031.62 | 1717.78 | 15901.26 | 13801.68 | 18073.38 | 2847.28 | 6153.24 | 61643.22
|  |  | Capitalized Overhead - Inj & Damages | 303.04 | 11.85 | 1106.02 | 4.71 | 101.11 | 14.06 | 31.8 | 693.86 | 270.21 | 413.39 | 44.9 | 75.68 | 3070.63
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1735.75 | 3293.24 | 3055.14 | 1837.26 | 1419.78 | 3879.17 | 20337.73 | 259298.77 | 190922.97 | 1160.86 | 1038.85 | 3607.17 | 491586.69
|  |  | Corporate Overheads Correction |  |  |  |  | -31614.74 | [7 empty] | -31614.74
|  | Non Budgeted Total |  | 2038.79 | 3305.09 | 4161.16 | 22088.44 | -27153.3 | 4924.85 | 22087.31 | 275893.89 | 204994.86 | 19647.63 | 3931.03 | 9836.09 | 545755.84
| Non Budget - Other Total |  |  | 2038.79 | 3305.09 | 4161.16 | 22088.44 | -27153.3 | 4924.85 | 22087.31 | 275893.89 | 204994.86 | 19647.63 | 3931.03 | 9836.09 | 545755.84
5. Corporate Overhead Total |  |  |  | 2038.79 | 3305.09 | 4161.16 | 22088.44 | -27153.3 | 4924.85 | 22087.31 | 275893.89 | 204994.86 | 19647.63 | 3931.03 | 9836.09 | 545755.84
Grand Total |  |  |  | 291730.16 | 12939.14 | 1239979.13 | 31514.17 | -4248.67 | 31773.71 | 71164.36 | 839127.44 | 511860.82 | 719168.64 | 111671.4 | 293606.01 | 4150286.31

## Red Bluff
WO | SumOfYTD2012 | Order | Project
900389804- Red Bluff 500/230kV Substation: Transmis | 818.54 | 900389804 | Red Bluff
900342200- Devers - Colorado River #2 500 kV T/L: L | 7560506.87 | 900342200 | Red Bluff
900312870- Devers-Palo Verde 500 kV Line: Loop the | 8638259.33 | 900312870 | Red Bluff
900248417- Red Bluff Sub: Construct a new 2000 by 2 | 118867166.17 | 900248417 | Red Bluff
900247848- Devers: Modify Existing CA Series Capaci | 638176.45 | 900247848 | Red Bluff
800380461- Red Bluff: Commence the Siting Study for | 117687.76 | 800380461 | Red Bluff

## 900389804
Pin: 6929 | Project: Red Bluff
Order: 900389804 | 900389804- Red Bluff 500/230kV Substation: Transmis
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | 2012 Total
SubCategory | Prime | Group | Details | 12
1. Project Support | Other | Other | Other | 780 | 780
|  | Other Total |  | 780 | 780
| Other Total |  |  | 780 | 780
1. Project Support Total |  |  |  | 780 | 780
2. Material | Material - Other | Material | Material - Other | 37.45 | 37.45
|  | Material Total |  | 37.45 | 37.45
| Material - Other Total |  |  | 37.45 | 37.45
2. Material Total |  |  |  | 37.45 | 37.45
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - A&G | 1.05 | 1.05
|  |  | Capitalized Overhead - Inj & Damages | 0.04 | 0.04
|  | Non Budgeted Total |  | 1.09 | 1.09
| Non Budget - Other Total |  |  | 1.09 | 1.09
5. Corporate Overhead Total |  |  |  | 1.09 | 1.09
Grand Total |  |  |  | 818.54 | 818.54

## 900342200
Pin: 6929 | Project: Red Bluff
Order: 900342200 | 900342200- Devers - Colorado River #2 500 kV T/L: L
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 2749.42 |  |  |  |  | 1305 | 389.48 | -389.48 |  |  |  |  | 4054.42
|  | Contract Total |  | 2749.42 |  |  |  |  | 1305 | 389.48 | -389.48 |  |  |  |  | 4054.42
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 2749.42 |  |  |  |  | 1305 | 389.48 | -389.48 |  |  |  |  | 4054.42
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -35050.95 | 35050.95 |  |  | 0
|  | Contract Total | [9 empty] | -35050.95 | 35050.95 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -35050.95 | 35050.95 |  |  | 0
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 176.47 | [11 empty] | 176.47
|  | Labor Total |  | 176.47 | [11 empty] | 176.47
| ENG ADVANCEMENT Total |  |  | 176.47 | [11 empty] | 176.47
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 20280.45 | 15245.54 | 6452.1 | [8 empty] | 14730.62 | 56708.71
|  |  | PAR ELECTRICAL CONTRACTORS INC |  | 81705.6 |  | 198555.3 | 453804.3 |  |  | 246845.7 | 1084914.9 |  |  | 1383829.86 | 3449655.66
|  | Contract Total |  | 20280.45 | 96951.14 | 6452.1 | 198555.3 | 453804.3 |  |  | 246845.7 | 1084914.9 |  |  | 1398560.48 | 3506364.37
| Engineering/Technical Professional Servi Total |  |  | 20280.45 | 96951.14 | 6452.1 | 198555.3 | 453804.3 |  |  | 246845.7 | 1084914.9 |  |  | 1398560.48 | 3506364.37
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  | -2028.88 | -2885.94 | -4598.49 | -3571.02 |  |  | 109049.36 | -119839.81 | -231.34 | -986.07 | -25092.19
|  | IMM Correction Total |  |  |  | -2028.88 | -2885.94 | -4598.49 | -3571.02 |  |  | 109049.36 | -119839.81 | -231.34 | -986.07 | -25092.19
| IMM/Allocated - Correction Total |  |  |  |  | -2028.88 | -2885.94 | -4598.49 | -3571.02 |  |  | 109049.36 | -119839.81 | -231.34 | -986.07 | -25092.19
| Labor - Other | Labor | Labor Entries <$5,000 |  | 311.11 |  |  |  | 254.95 | 784.83 | 66.02 | 58084.52 | -58082.27 |  |  | 1419.16
|  | Labor Total |  |  | 311.11 |  |  |  | 254.95 | 784.83 | 66.02 | 58084.52 | -58082.27 |  |  | 1419.16
| Labor - Other Total |  |  |  | 311.11 |  |  |  | 254.95 | 784.83 | 66.02 | 58084.52 | -58082.27 |  |  | 1419.16
| Other | Other | Other | -2976.01 | 359.55 | -26762.09 | 568626 | 411507 | -840616 | 1254406 | -376110.8 | -864426.54 | 677210.64 | 270633.9 | -156723.81 | 915127.84
|  | Other Total |  | -2976.01 | 359.55 | -26762.09 | 568626 | 411507 | -840616 | 1254406 | -376110.8 | -864426.54 | 677210.64 | 270633.9 | -156723.81 | 915127.84
| Other Total |  |  | -2976.01 | 359.55 | -26762.09 | 568626 | 411507 | -840616 | 1254406 | -376110.8 | -864426.54 | 677210.64 | 270633.9 | -156723.81 | 915127.84
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 50.82 | 271.04 | [10 empty] | 321.86
|  | Contract Total |  | 50.82 | 271.04 | [10 empty] | 321.86
| Temporary/Supplementary - Trade/Labor Total |  |  | 50.82 | 271.04 | [10 empty] | 321.86
1. Project Support Total |  |  |  | 20281.15 | 97892.84 | -22338.87 | 764295.36 | 860712.81 | -842627.07 | 1255580.31 | -129588.56 | 352571.29 | 534339.51 | 270402.56 | 1240850.6 | 4402371.93
2. Material | Material - Other | Material | Material - Other | 4684.6 | 23058.32 | 48276.15 | 55919.44 | -4561.56 |  |  | 36762.43 |  |  | 13055.29 | 778 | 177972.67
|  | Material Total |  | 4684.6 | 23058.32 | 48276.15 | 55919.44 | -4561.56 |  |  | 36762.43 |  |  | 13055.29 | 778 | 177972.67
| Material - Other Total |  |  | 4684.6 | 23058.32 | 48276.15 | 55919.44 | -4561.56 |  |  | 36762.43 |  |  | 13055.29 | 778 | 177972.67
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  | -1.5 | [10 empty] | -1.5
|  |  | ONE SOURCE DISTRIBUTORS INC | 41129.9 | 53098.5 | 34367.2 | 81996.3 | [8 empty] | 210591.9
|  | Material - Direct Purchase Total |  | 41129.9 | 53097 | 34367.2 | 81996.3 | [8 empty] | 210590.4
| Pole Line Hdwe & Connectors-DP Total |  |  | 41129.9 | 53097 | 34367.2 | 81996.3 | [8 empty] | 210590.4
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | -6450.12 |  | -534362.43 | [7 empty] | -540812.55
|  |  | SAE TOWERS |  | 147042.81 | 402895.11 | 416189.67 | 591403.59 | [5 empty] | 149404.92 | 7613.62 | 1714549.72
|  | Material - Direct Purchase Total |  |  | 147042.81 | 396444.99 | 416189.67 | 57041.16 | [5 empty] | 149404.92 | 7613.62 | 1173737.17
| Steel Lattice Towers (T/S)-DP Total |  |  |  | 147042.81 | 396444.99 | 416189.67 | 57041.16 | [5 empty] | 149404.92 | 7613.62 | 1173737.17
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | SABRE COMMUNICATIONS CORPORATION |  |  |  |  | 30218 |  |  | 338208 |  |  |  |  | 368426
|  | Material - Direct Purchase Total | [5 empty] | 30218 |  |  | 338208 |  |  |  |  | 368426
| Towers/Poles, Steel & Concrete-DP Total | [6 empty] | 30218 |  |  | 338208 |  |  |  |  | 368426
2. Material Total |  |  |  | 45814.5 | 223198.13 | 479088.34 | 554105.41 | 82697.6 |  |  | 374970.43 |  |  | 162460.21 | 8391.62 | 1930726.24
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 8209.36 | 10044.14 | [9 empty] | 22864.69 | 41118.19
|  | Contract Total |  | 8209.36 | 10044.14 | [9 empty] | 22864.69 | 41118.19
| Construction Management Services Total |  |  | 8209.36 | 10044.14 | [9 empty] | 22864.69 | 41118.19
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 329.79 | [11 empty] | 329.79
|  | Labor Total |  | 329.79 | [11 empty] | 329.79
| TRNS CAPITAL Total |  |  | 329.79 | [11 empty] | 329.79
3. Construction Total |  |  |  | 8539.15 | 10044.14 | [9 empty] | 22864.69 | 41447.98
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 722.27 | 10609.98 | 10440.22 | 13033.05 | 9529.18 | 14570.92 | 10688.77 | -47493.96 | -28340.66 | 43816.94 | 11474.61 | 7418.13 | 56469.45
|  |  | DPV2/DCR Project OE T/L Work | [8 empty] | 5030.27 |  |  |  | 5030.27
|  |  | PDP-RED Bluff Loop In(DPV2 Loop In)MPO |  |  |  |  | 10500 | 72100 | 85272.98 |  |  | 230668.71 | 92319.02 | 139829.49 | 630690.2
|  |  | PROCUREMENT TDBU | [8 empty] | 6929.1 |  |  | 9431.66 | 16360.76
|  | Chargeback Total |  | 722.27 | 10609.98 | 10440.22 | 13033.05 | 20029.18 | 86670.92 | 95961.75 | -47493.96 | -16381.29 | 274485.65 | 103793.63 | 156679.28 | 708550.68
| Chargebacks Total |  |  | 722.27 | 10609.98 | 10440.22 | 13033.05 | 20029.18 | 86670.92 | 95961.75 | -47493.96 | -16381.29 | 274485.65 | 103793.63 | 156679.28 | 708550.68
| Labor - Other | Labor | Division Overhead |  |  | 6427.79 | 17836.58 | 15907.27 |  |  | 20418.37 | 29501.18 |  |  | 15147.81 | 105239
|  |  | Labor Entries <$5,000 | 2082.39 | 11343.28 | 9488.63 | 4528.82 | 7683.1 | 8.61 | 3.84 | 3568.83 | 3884.5 | 1819.15 | 1598.63 | 4001.31 | 50011.09
|  | Labor Total |  | 2082.39 | 11343.28 | 15916.42 | 22365.4 | 23590.37 | 8.61 | 3.84 | 23987.2 | 33385.68 | 1819.15 | 1598.63 | 19149.12 | 155250.09
| Labor - Other Total |  |  | 2082.39 | 11343.28 | 15916.42 | 22365.4 | 23590.37 | 8.61 | 3.84 | 23987.2 | 33385.68 | 1819.15 | 1598.63 | 19149.12 | 155250.09
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -771.12 | 771.12 |  |  | 0
|  | Overhead Total | [9 empty] | -771.12 | 771.12 |  |  | 0
| Overhead Correction Total | [10 empty] | -771.12 | 771.12 |  |  | 0
4. Allocated Total |  |  |  | 2804.66 | 21953.26 | 26356.64 | 35398.45 | 43619.55 | 86679.53 | 95965.59 | -23506.76 | 16233.27 | 277075.92 | 105392.26 | 175828.4 | 863800.77
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 18719.05 | 1497.99 | [6 empty] | 49925.8 | 70142.84
|  |  | Capitalized Overhead - A&G | 4334.51 | 10333.61 | 18174.08 | 27999.74 | 47900.48 | 3021.84 | 3410.86 | 16920.48 | 51793.83 | 5459.15 | 7072.49 | 45053.02 | 241474.09
|  |  | Capitalized Overhead - Inj & Damages | 43.37 | 412.29 | 522.63 | 480.53 | 1017.17 | 93.22 | 55.61 | 448.52 | 89.85 | 198.24 | 364.38 | 105.27 | 3831.08
|  |  | Capitalized Overhead - P&B/Payroll Tax | 345.28 | 858.57 | 501.6 | 465.7 | 707.31 | 759.17 | 1084.81 | 424.31 | 423.26 | 170.5 | 234.07 | 737.36 | 6711.94
|  | Non Budgeted Total |  | 4723.16 | 11604.47 | 19198.31 | 47665.02 | 51122.95 | 3874.23 | 4551.28 | 17793.31 | 52306.94 | 5827.89 | 7670.94 | 95821.45 | 322159.95
| Non Budget - Other Total |  |  | 4723.16 | 11604.47 | 19198.31 | 47665.02 | 51122.95 | 3874.23 | 4551.28 | 17793.31 | 52306.94 | 5827.89 | 7670.94 | 95821.45 | 322159.95
5. Corporate Overhead Total |  |  |  | 4723.16 | 11604.47 | 19198.31 | 47665.02 | 51122.95 | 3874.23 | 4551.28 | 17793.31 | 52306.94 | 5827.89 | 7670.94 | 95821.45 | 322159.95
Grand Total |  |  |  | 82162.62 | 364692.84 | 502304.42 | 1401464.24 | 1038152.91 | -752073.31 | 1356097.18 | 239668.42 | 421111.5 | 817243.32 | 545925.97 | 1543756.76 | 7560506.87

## 900312870
Pin: 6929 | Project: Red Bluff
Order: 900312870 | 900312870- Devers-Palo Verde 500 kV Line: Loop the
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | 3399.03 | [11 empty] | 3399.03
|  | Contract Total |  | 3399.03 | [11 empty] | 3399.03
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  | 3399.03 | [11 empty] | 3399.03
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -33322.3 | 33322.3 |  |  | 0
|  | Contract Total | [9 empty] | -33322.3 | 33322.3 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -33322.3 | 33322.3 |  |  | 0
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 1437 | [11 empty] | 1437
|  | Labor Total |  | 1437 | [11 empty] | 1437
| ENG ADVANCEMENT Total |  |  | 1437 | [11 empty] | 1437
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 28206.13 | 29678.21 | 9668.7 | 3222.9 | [7 empty] | 20487.41 | 91263.35
|  |  | PAR ELECTRICAL CONTRACTORS INC |  |  |  |  | 1430049.6 |  |  |  | 1310485.5 | 350611.2 |  | 2384874.68 | 5476020.98
|  | Contract Total |  | 28206.13 | 29678.21 | 9668.7 | 3222.9 | 1430049.6 |  |  |  | 1310485.5 | 350611.2 |  | 2405362.09 | 5567284.33
| Engineering/Technical Professional Servi Total |  |  | 28206.13 | 29678.21 | 9668.7 | 3222.9 | 1430049.6 |  |  |  | 1310485.5 | 350611.2 |  | 2405362.09 | 5567284.33
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  | -1404.92 | -3266.29 | -231.57 | -9693.34 | -96.19 | -1.67 | 45448.47 | -56177.12 | -2533.96 | -982.11 | -28938.7
|  | IMM Correction Total |  |  |  | -1404.92 | -3266.29 | -231.57 | -9693.34 | -96.19 | -1.67 | 45448.47 | -56177.12 | -2533.96 | -982.11 | -28938.7
| IMM/Allocated - Correction Total |  |  |  |  | -1404.92 | -3266.29 | -231.57 | -9693.34 | -96.19 | -1.67 | 45448.47 | -56177.12 | -2533.96 | -982.11 | -28938.7
| Labor - Other | Labor | Labor Entries <$5,000 |  |  |  | 1570.07 |  |  | 784.84 | 20.81 | 2850.5 | -2863 |  |  | 2363.22
|  | Labor Total |  |  |  |  | 1570.07 |  |  | 784.84 | 20.81 | 2850.5 | -2863 |  |  | 2363.22
| Labor - Other Total | [5 empty] | 1570.07 |  |  | 784.84 | 20.81 | 2850.5 | -2863 |  |  | 2363.22
| Other | Other | Other | -2748.99 | 500.08 | -33639.85 | 2132951 | -1743383 | -6939 | 393149 | 530637.2 | -619116.35 | -126344.65 | 1402550 | -1348138.03 | 579477.41
|  | Other Total |  | -2748.99 | 500.08 | -33639.85 | 2132951 | -1743383 | -6939 | 393149 | 530637.2 | -619116.35 | -126344.65 | 1402550 | -1348138.03 | 579477.41
| Other Total |  |  | -2748.99 | 500.08 | -33639.85 | 2132951 | -1743383 | -6939 | 393149 | 530637.2 | -619116.35 | -126344.65 | 1402550 | -1348138.03 | 579477.41
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 | 111.35 | [11 empty] | 111.35
|  | Labor Total |  | 111.35 | [11 empty] | 111.35
| TEC SRVCS SUMMARY Total |  |  | 111.35 | [11 empty] | 111.35
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | [5 empty] | 1280.54 | 253 | [5 empty] | 1533.54
|  | Contract Total | [6 empty] | 1280.54 | 253 | [5 empty] | 1533.54
| Temporary/Supplementary - Trade/Labor Total | [7 empty] | 1280.54 | 253 | [5 empty] | 1533.54
1. Project Support Total |  |  |  | 30404.52 | 30178.29 | -25376.07 | 2134477.68 | -313564.97 | -15351.8 | 394090.65 | 530656.34 | 706345.82 | 198548.73 | 1400016.04 | 1056241.95 | 6126667.18
2. Material | Material - Other | Material | Material - Other | 4030.26 | 19495.79 | 54373.4 | 3576.47 | -2019.89 | 1455.04 |  | 37456.94 |  |  | 13002.78 | 779.01 | 132149.8
|  | Material Total |  | 4030.26 | 19495.79 | 54373.4 | 3576.47 | -2019.89 | 1455.04 |  | 37456.94 |  |  | 13002.78 | 779.01 | 132149.8
| Material - Other Total |  |  | 4030.26 | 19495.79 | 54373.4 | 3576.47 | -2019.89 | 1455.04 |  | 37456.94 |  |  | 13002.78 | 779.01 | 132149.8
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 4104.8 | [8 empty] | 4104.8
|  |  | ONE SOURCE DISTRIBUTORS INC | 35385 | 30342 | 77046.85 | [9 empty] | 142773.85
|  | Material - Direct Purchase Total |  | 35385 | 30342 | 77046.85 | 4104.8 | [8 empty] | 146878.65
| Pole Line Hdwe & Connectors-DP Total |  |  | 35385 | 30342 | 77046.85 | 4104.8 | [8 empty] | 146878.65
| Steel Lattice Towers (T/S)-DP | Material - Direct Purchase | Material Entries <$5,000 |  | 359.16 | 4536.24 | 2447.7 | -523570.41 | [7 empty] | -516227.31
|  |  | SAE TOWERS |  | 138517.68 | 403640.49 | 25310.25 | 531990.99 | 13293.84 |  | 10181.94 |  |  | 148804.18 | 7623.42 | 1279362.79
|  | Material - Direct Purchase Total |  |  | 138876.84 | 408176.73 | 27757.95 | 8420.58 | 13293.84 |  | 10181.94 |  |  | 148804.18 | 7623.42 | 763135.48
| Steel Lattice Towers (T/S)-DP Total |  |  |  | 138876.84 | 408176.73 | 27757.95 | 8420.58 | 13293.84 |  | 10181.94 |  |  | 148804.18 | 7623.42 | 763135.48
| Towers/Poles, Steel & Concrete-DP | Material - Direct Purchase | SABRE COMMUNICATIONS CORPORATION |  |  |  |  | 30218 |  |  | 338208 |  |  |  |  | 368426
|  | Material - Direct Purchase Total | [5 empty] | 30218 |  |  | 338208 |  |  |  |  | 368426
| Towers/Poles, Steel & Concrete-DP Total | [6 empty] | 30218 |  |  | 338208 |  |  |  |  | 368426
2. Material Total |  |  |  | 39415.26 | 188714.63 | 539596.98 | 35439.22 | 36618.69 | 14748.88 |  | 385846.88 |  |  | 161806.96 | 8402.43 | 1410589.93
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 11417.62 | 13969.44 | [9 empty] | 31800.32 | 57187.38
|  | Contract Total |  | 11417.62 | 13969.44 | [9 empty] | 31800.32 | 57187.38
| Construction Management Services Total |  |  | 11417.62 | 13969.44 | [9 empty] | 31800.32 | 57187.38
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 329.79 | [11 empty] | 329.79
|  | Labor Total |  | 329.79 | [11 empty] | 329.79
| TRNS CAPITAL Total |  |  | 329.79 | [11 empty] | 329.79
3. Construction Total |  |  |  | 11747.41 | 13969.44 | [9 empty] | 31800.32 | 57517.17
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 673.79 | 13339.57 | 2842.94 | 6724.26 | 2330.19 | 11320.67 | 13325.28 | 7655.37 | -9538.8 | 20964.23 | 6875.14 | 6830.41 | 83343.05
|  |  | DPV2/DCR Project OE T/L Work |  |  | 10856.77 | 5305.44 | 5956.35 | 6408.04 | 5552.93 | 5200.87 | 6996.12 | 5908.96 | 6710.18 | 5924.06 | 64819.72
|  |  | PDP-RED Bluff Loop In(DPV1 Loop In)MPO |  |  |  |  | 9450 |  | 31236.3 |  |  | 22604.09 | 154823.37 | 18199.84 | 236313.6
|  |  | PROCUREMENT TDBU |  |  |  |  | 9693.34 |  |  |  | 8429.28 |  |  | 16135.59 | 34258.21
|  | Chargeback Total |  | 673.79 | 13339.57 | 13699.71 | 12029.7 | 27429.88 | 17728.71 | 50114.51 | 12856.24 | 5886.6 | 49477.28 | 168408.69 | 47089.9 | 418734.58
| Chargebacks Total |  |  | 673.79 | 13339.57 | 13699.71 | 12029.7 | 27429.88 | 17728.71 | 50114.51 | 12856.24 | 5886.6 | 49477.28 | 168408.69 | 47089.9 | 418734.58
| Labor - Other | Labor | Division Overhead |  |  | 12372.31 |  | 64034.8 |  |  | 5086.49 | 35888.28 | 12631.41 |  | 25914.73 | 155928.02
|  |  | Labor Entries <$5,000 | 2576.24 | 7854.77 | 5641.77 | 1129.12 |  | 650.02 | 11.8 | 9197.5 | 4725.5 | 7294.73 | 1592.21 | 6845.4 | 47519.06
|  | Labor Total |  | 2576.24 | 7854.77 | 18014.08 | 1129.12 | 64034.8 | 650.02 | 11.8 | 14283.99 | 40613.78 | 19926.14 | 1592.21 | 32760.13 | 203447.08
| Labor - Other Total |  |  | 2576.24 | 7854.77 | 18014.08 | 1129.12 | 64034.8 | 650.02 | 11.8 | 14283.99 | 40613.78 | 19926.14 | 1592.21 | 32760.13 | 203447.08
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -733.09 | 733.09 |  |  | 0
|  | Overhead Total | [9 empty] | -733.09 | 733.09 |  |  | 0
| Overhead Correction Total | [10 empty] | -733.09 | 733.09 |  |  | 0
4. Allocated Total |  |  |  | 3250.03 | 21194.34 | 31713.79 | 13158.82 | 91464.68 | 18378.73 | 50126.31 | 27140.23 | 45767.29 | 70136.51 | 170000.9 | 79850.03 | 622181.66
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 21928.51 | 1313.94 | [6 empty] | 54983.97 | 78226.42
|  |  | Capitalized Overhead - A&G | 4751.2 | 7428.24 | 20658.74 | 1787.48 | 129663.33 | 882.08 | 1793.14 | 11688.27 | 60816.07 | 10560.08 | 8701.8 | 70876.94 | 329607.37
|  |  | Capitalized Overhead - Inj & Damages | 39.38 | 346.38 | 589.45 | 30.43 | 1044.87 | 16.55 | 9.57 | 525.92 | 63.89 | 24.61 | 490.36 | 66.92 | 3248.33
|  |  | Capitalized Overhead - P&B/Payroll Tax | 1280.91 | 777.29 | 697.68 | 1861.65 | 983.61 | 660.56 | 1259.31 | 542.11 | 570.11 | 237.13 | 325.56 | 1025.35 | 10221.27
|  | Non Budgeted Total |  | 6071.49 | 8551.91 | 21945.87 | 25608.07 | 133005.75 | 1559.19 | 3062.02 | 12756.3 | 61450.07 | 10821.82 | 9517.72 | 126953.18 | 421303.39
| Non Budget - Other Total |  |  | 6071.49 | 8551.91 | 21945.87 | 25608.07 | 133005.75 | 1559.19 | 3062.02 | 12756.3 | 61450.07 | 10821.82 | 9517.72 | 126953.18 | 421303.39
5. Corporate Overhead Total |  |  |  | 6071.49 | 8551.91 | 21945.87 | 25608.07 | 133005.75 | 1559.19 | 3062.02 | 12756.3 | 61450.07 | 10821.82 | 9517.72 | 126953.18 | 421303.39
Grand Total |  |  |  | 90888.71 | 262608.61 | 567880.57 | 2208683.79 | -52475.85 | 19335 | 447278.98 | 956399.75 | 813563.18 | 279507.06 | 1741341.62 | 1303247.91 | 8638259.33

## 900248417
Pin: 6929 | Project: Red Bluff
Order: 900248417 | 900248417- Red Bluff Sub: Construct a new 2000 by 2
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | BP&FM / Techn Spl/Scientist | 7259.52 |  |  |  |  | 7735 | [6 empty] | 14994.52
|  |  | Labor Entries <$5,000 | 98.77 | 3300.01 | 162.01 | 114.52 | 2085 | 40.95 | 886.52 | 924.2 | 548.66 | 283.75 | 94.79 |  | 8539.18
|  | Labor Total |  | 7358.29 | 3300.01 | 162.01 | 114.52 | 2085 | 7775.95 | 886.52 | 924.2 | 548.66 | 283.75 | 94.79 |  | 23533.7
| BP&FM Total |  |  | 7358.29 | 3300.01 | 162.01 | 114.52 | 2085 | 7775.95 | 886.52 | 924.2 | 548.66 | 283.75 | 94.79 |  | 23533.7
| BSVHCC | Labor | Labor Entries <$5,000 | [8 empty] | 788.4 | 572.01 |  |  | 1360.41
|  | Labor Total | [9 empty] | 788.4 | 572.01 |  |  | 1360.41
| BSVHCC Total | [10 empty] | 788.4 | 572.01 |  |  | 1360.41
| Building/Facility Repairs & Maintenance | Contract | Contract Entries <$50,000 | [10 empty] | 2238.98 |  | 2238.98
|  | Contract Total | [11 empty] | 2238.98 |  | 2238.98
| Building/Facility Repairs & Maintenance Total | [12 empty] | 2238.98 |  | 2238.98
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 | [5 empty] | 2953.76 | 1620.9 | 1620.9 | 1304.4 | 1620.9 | 1620.9 | 1620.9 | 12362.66
|  | Contract Total | [6 empty] | 2953.76 | 1620.9 | 1620.9 | 1304.4 | 1620.9 | 1620.9 | 1620.9 | 12362.66
| Cleaning / Janitorial Services Total | [7 empty] | 2953.76 | 1620.9 | 1620.9 | 1304.4 | 1620.9 | 1620.9 | 1620.9 | 12362.66
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 |  | 20325.34 |  | 10860.6 |  | 107.44 |  | 329.35 | 3159 |  |  |  | 34781.73
|  | Contract Total |  |  | 20325.34 |  | 10860.6 |  | 107.44 |  | 329.35 | 3159 |  |  |  | 34781.73
| Con - Consults/Prof Srvcs/Out Ord to Ord Total |  |  |  | 20325.34 |  | 10860.6 |  | 107.44 |  | 329.35 | 3159 |  |  |  | 34781.73
| Consultants - Strategic Planning/Develop | Contract | Contract Entries <$50,000 |  | -1761.5 | [10 empty] | -1761.5
|  | Contract Total |  |  | -1761.5 | [10 empty] | -1761.5
| Consultants - Strategic Planning/Develop Total |  |  |  | -1761.5 | [10 empty] | -1761.5
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 2329544.25 |  |  | 2329544.25
|  |  | Contract Entries <$50,000 |  | -38744.66 | [6 empty] | -2329544.25 |  |  |  | -2368288.91
|  | Contract Total |  |  | -38744.66 | [6 empty] | -2329544.25 | 2329544.25 |  |  | -38744.66
| Consultants / Prof Services - Correction Total |  |  |  | -38744.66 | [6 empty] | -2329544.25 | 2329544.25 |  |  | -38744.66
| Contract - Other - Correction | Contract | Contract Entries <$50,000 |  | -6685.99 | [10 empty] | -6685.99
|  | Contract Total |  |  | -6685.99 | [10 empty] | -6685.99
| Contract - Other - Correction Total |  |  |  | -6685.99 | [10 empty] | -6685.99
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 |  |  |  |  | 4629.17 | 23240.79 |  | 6715.37 |  |  |  |  | 34585.33
|  | Contract Total | [5 empty] | 4629.17 | 23240.79 |  | 6715.37 |  |  |  |  | 34585.33
| Contract Consult/Contract Ord to Ord Total | [6 empty] | 4629.17 | 23240.79 |  | 6715.37 |  |  |  |  | 34585.33
| EAST GRID MGMTCENTER | Labor | Labor Entries <$5,000 | [10 empty] | 262.35 |  | 262.35
|  | Labor Total | [11 empty] | 262.35 |  | 262.35
| EAST GRID MGMTCENTER Total | [12 empty] | 262.35 |  | 262.35
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 17121.52 | 17121.52
|  | Labor Total | [12 empty] | 17121.52 | 17121.52
| ELEC SYS PLANNING Total | [13 empty] | 17121.52 | 17121.52
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 5886.36 | 1090.14 | 772.87 | 207.1 | 375.82 | 616.89 | 539.79 | 541.15 | 40.23 | 79.35 | 38.99 | 197.92 | 10386.61
|  |  | Techn Spl/Scientist | 6113.28 | [11 empty] | 6113.28
|  | Labor Total |  | 11999.64 | 1090.14 | 772.87 | 207.1 | 375.82 | 616.89 | 539.79 | 541.15 | 40.23 | 79.35 | 38.99 | 197.92 | 16499.89
| ENG ADVANCEMENT Total |  |  | 11999.64 | 1090.14 | 772.87 | 207.1 | 375.82 | 616.89 | 539.79 | 541.15 | 40.23 | 79.35 | 38.99 | 197.92 | 16499.89
| ENGINEERING | Labor | Engineer | 6467.84 | [6 empty] | 7151.76 | 6130.08 | 6130.08 | 11475.12 |  | 37354.88
|  |  | Labor Entries <$5,000 | 29705.41 | 39313.87 | 22489.47 | 13471.26 | 17463.56 | 28059.55 | 18652.43 | 19295.96 | 18644.65 | 10678.63 | 15027.82 |  | 232802.61
|  |  | Techn Spl/Scientist | [9 empty] | 8238.42 |  |  | 8238.42
|  | Labor Total |  | 36173.25 | 39313.87 | 22489.47 | 13471.26 | 17463.56 | 28059.55 | 18652.43 | 26447.72 | 24774.73 | 25047.13 | 26502.94 |  | 278395.91
| ENGINEERING Total |  |  | 36173.25 | 39313.87 | 22489.47 | 13471.26 | 17463.56 | 28059.55 | 18652.43 | 26447.72 | 24774.73 | 25047.13 | 26502.94 |  | 278395.91
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 34003.48 | -37508.84 |  | 7348.39 | 9632 | 20766.3 | 9668 | 42927.22 | 20682.55 | 36262.83 | 19441.97 | 103815.71 | 267039.61
|  |  | MONTANA GEOTECHNICAL I | [5 empty] | 158331.7 |  | 260667.93 | 121288.2 |  | 158640.15 |  | 698927.98
|  |  | S & L ENGINEERS, LTD. |  |  | 104441.25 | 114248.44 | 276606.27 | 90602 |  |  | 115049.59 |  |  |  | 700947.55
|  | Contract Total |  | 34003.48 | -37508.84 | 104441.25 | 121596.83 | 286238.27 | 269700 | 9668 | 303595.15 | 257020.34 | 36262.83 | 178082.12 | 103815.71 | 1666915.14
| Engineering/Technical Professional Servi Total |  |  | 34003.48 | -37508.84 | 104441.25 | 121596.83 | 286238.27 | 269700 | 9668 | 303595.15 | 257020.34 | 36262.83 | 178082.12 | 103815.71 | 1666915.14
| Environmental/Safety Professional Servic | Contract | Contract Entries <$50,000 | 25443.67 | 55607.08 | 1347.21 | 34603.68 | 10515.69 | 6140.02 | 4574.1 | 8254.24 | 15690.76 | 6982.19 | 7779.77 | 22612.05 | 199550.46
|  |  | GEOSCIENCE SUPPORT SERVICES |  |  |  | 74494 | [8 empty] | 74494
|  | Contract Total |  | 25443.67 | 55607.08 | 1347.21 | 109097.68 | 10515.69 | 6140.02 | 4574.1 | 8254.24 | 15690.76 | 6982.19 | 7779.77 | 22612.05 | 274044.46
| Environmental/Safety Professional Servic Total |  |  | 25443.67 | 55607.08 | 1347.21 | 109097.68 | 10515.69 | 6140.02 | 4574.1 | 8254.24 | 15690.76 | 6982.19 | 7779.77 | 22612.05 | 274044.46
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | 13673 | 9187.83 | -3640.45 | -12271.49 | -13375.92 | -38013.92 | -38012.99 | 366.83 | 7644212.08 | -7673072.67 | -87774.87 | -84085.33 | -282807.9
|  | IMM Correction Total |  | 13673 | 9187.83 | -3640.45 | -12271.49 | -13375.92 | -38013.92 | -38012.99 | 366.83 | 7644212.08 | -7673072.67 | -87774.87 | -84085.33 | -282807.9
| IMM/Allocated - Correction Total |  |  | 13673 | 9187.83 | -3640.45 | -12271.49 | -13375.92 | -38013.92 | -38012.99 | 366.83 | 7644212.08 | -7673072.67 | -87774.87 | -84085.33 | -282807.9
| Information System Professional Services | Contract | Contract Entries <$50,000 | [6 empty] | 569.63 | [5 empty] | 569.63
|  | Contract Total | [7 empty] | 569.63 | [5 empty] | 569.63
| Information System Professional Services Total | [8 empty] | 569.63 | [5 empty] | 569.63
| Labor - Other | Labor | Labor - Other | [9 empty] | 9668.57 |  |  | 9668.57
|  |  | Labor Correction | [9 empty] | 48102.22 |  |  | 48102.22
|  |  | Labor Entries <$5,000 | 974.71 | -18504.03 | -4352.79 | 1303.11 | 4889.84 | -6192.16 | 453.56 | 476.61 | 484211.51 | -538806.14 | -4707.45 | 4895.65 | -75357.58
|  | Labor Total |  | 974.71 | -18504.03 | -4352.79 | 1303.11 | 4889.84 | -6192.16 | 453.56 | 476.61 | 484211.51 | -481035.35 | -4707.45 | 4895.65 | -17586.79
| Labor - Other Total |  |  | 974.71 | -18504.03 | -4352.79 | 1303.11 | 4889.84 | -6192.16 | 453.56 | 476.61 | 484211.51 | -481035.35 | -4707.45 | 4895.65 | -17586.79
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 6562.17 | 6042.73 | 3583.25 | 2384.77 | 2978.76 | 2221.18 | [6 empty] | 23772.86
|  | Labor Total |  | 6562.17 | 6042.73 | 3583.25 | 2384.77 | 2978.76 | 2221.18 | [6 empty] | 23772.86
| MAJOR PROJECT ORG Total |  |  | 6562.17 | 6042.73 | 3583.25 | 2384.77 | 2978.76 | 2221.18 | [6 empty] | 23772.86
| Marketing Professional Services | Contract | Contract Entries <$50,000 |  | -700.18 | [10 empty] | -700.18
|  | Contract Total |  |  | -700.18 | [10 empty] | -700.18
| Marketing Professional Services Total |  |  |  | -700.18 | [10 empty] | -700.18
| Other | Other | Other | -551991.09 | 1087156.55 | 1266331.81 | 3010639.04 | 981742.01 | 4177146.13 | 1270794.77 | 2485622.72 | -6589524.37 | 10923089.98 | -5979918.56 | -10827461.06 | 1253627.93
|  | Other Total |  | -551991.09 | 1087156.55 | 1266331.81 | 3010639.04 | 981742.01 | 4177146.13 | 1270794.77 | 2485622.72 | -6589524.37 | 10923089.98 | -5979918.56 | -10827461.06 | 1253627.93
| Other Total |  |  | -551991.09 | 1087156.55 | 1266331.81 | 3010639.04 | 981742.01 | 4177146.13 | 1270794.77 | 2485622.72 | -6589524.37 | 10923089.98 | -5979918.56 | -10827461.06 | 1253627.93
| PLGHCC | Labor | Labor Entries <$5,000 | [11 empty] | 204.88 | 204.88
|  | Labor Total | [12 empty] | 204.88 | 204.88
| PLGHCC Total | [13 empty] | 204.88 | 204.88
| RURALS | Labor | Labor Entries <$5,000 |  |  | 325.49 | 247.7 |  | 167.39 | [6 empty] | 740.58
|  | Labor Total |  |  |  | 325.49 | 247.7 |  | 167.39 | [6 empty] | 740.58
| RURALS Total |  |  |  |  | 325.49 | 247.7 |  | 167.39 | [6 empty] | 740.58
| SC&M | Labor | Labor Entries <$5,000 | 2014.96 | 7394.02 | 5495.91 | 1347.67 | 3631.09 | 4812.93 | 834.79 | 3908.98 | 343.82 | 2116.14 | 1893.55 | 3294.71 | 37088.57
|  |  | SC&M / Mgr-Prj/Prod | 5865.6 | [11 empty] | 5865.6
|  | Labor Total |  | 7880.56 | 7394.02 | 5495.91 | 1347.67 | 3631.09 | 4812.93 | 834.79 | 3908.98 | 343.82 | 2116.14 | 1893.55 | 3294.71 | 42954.17
| SC&M Total |  |  | 7880.56 | 7394.02 | 5495.91 | 1347.67 | 3631.09 | 4812.93 | 834.79 | 3908.98 | 343.82 | 2116.14 | 1893.55 | 3294.71 | 42954.17
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  | 1090.25 | 836.58 | 1453.34 | 1619.49 | 1761.61 | 1037.2 | 1585.45 | 1893.74 | 2541.17 | 1417.05 | 15235.88
|  | Labor Total |  |  |  | 1090.25 | 836.58 | 1453.34 | 1619.49 | 1761.61 | 1037.2 | 1585.45 | 1893.74 | 2541.17 | 1417.05 | 15235.88
| SCM HOME CENTER Total |  |  |  |  | 1090.25 | 836.58 | 1453.34 | 1619.49 | 1761.61 | 1037.2 | 1585.45 | 1893.74 | 2541.17 | 1417.05 | 15235.88
| Software License Via Electronic Delivery | Contract | Contract Entries <$50,000 | [11 empty] | 7810.6 | 7810.6
|  | Contract Total | [12 empty] | 7810.6 | 7810.6
| Software License Via Electronic Delivery Total | [13 empty] | 7810.6 | 7810.6
| TEC SRVCS SUMMARY | Labor | Labor Entries <$5,000 |  | 207.47 | 201.47 | 424.97 | 848.1 | 212.02 | 422.54 | 206.4 | 207.17 | 203.41 |  |  | 2933.55
|  | Labor Total |  |  | 207.47 | 201.47 | 424.97 | 848.1 | 212.02 | 422.54 | 206.4 | 207.17 | 203.41 |  |  | 2933.55
| TEC SRVCS SUMMARY Total |  |  |  | 207.47 | 201.47 | 424.97 | 848.1 | 212.02 | 422.54 | 206.4 | 207.17 | 203.41 |  |  | 2933.55
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 |  | -442.26 | [6 empty] | -5524.85 | 5524.85 |  |  | -442.26
|  | Contract Total |  |  | -442.26 | [6 empty] | -5524.85 | 5524.85 |  |  | -442.26
| Temporary / Supplemental - Correction Total |  |  |  | -442.26 | [6 empty] | -5524.85 | 5524.85 |  |  | -442.26
| Temporary/Supplementary - Admin/Non-Tech | Contract | Contract Entries <$50,000 |  | -18.5 | [10 empty] | -18.5
|  | Contract Total |  |  | -18.5 | [10 empty] | -18.5
| Temporary/Supplementary - Admin/Non-Tech Total |  |  |  | -18.5 | [10 empty] | -18.5
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 340 | -478.13 | [10 empty] | -138.13
|  | Contract Total |  | 340 | -478.13 | [10 empty] | -138.13
| Temporary/Supplementary - Technical/Prof Total |  |  | 340 | -478.13 | [10 empty] | -138.13
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 4766.82 | 3467.51 | 2451.79 | 7930.38 | 4587.68 | 7137.88 | 13120.95 | 3427.85 | 3369.98 | 4532.09 | 14038.07 | 29370.32 | 98201.32
|  | Contract Total |  | 4766.82 | 3467.51 | 2451.79 | 7930.38 | 4587.68 | 7137.88 | 13120.95 | 3427.85 | 3369.98 | 4532.09 | 14038.07 | 29370.32 | 98201.32
| Temporary/Supplementary - Trade/Labor Total |  |  | 4766.82 | 3467.51 | 2451.79 | 7930.38 | 4587.68 | 7137.88 | 13120.95 | 3427.85 | 3369.98 | 4532.09 | 14038.07 | 29370.32 | 98201.32
| Training - Skills/Technical - Outside Se | Contract | Contract Entries <$50,000 |  | -6.78 | [10 empty] | -6.78
|  | Contract Total |  |  | -6.78 | [10 empty] | -6.78
| Training - Skills/Technical - Outside Se Total |  |  |  | -6.78 | [10 empty] | -6.78
1. Project Support Total |  |  |  | -402815.5 | 1128241.68 | 1400699.54 | 3268190.72 | 1308062.41 | 4487705.34 | 1285886.6 | 2843474.67 | -487336.94 | 5183644.6 | -5837307.25 | -10719185.08 | 3459260.79
2. Material | Animal Guards And Deterrents-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 2448 | [7 empty] | 2448
|  |  | PRO TOOL AND EQUIPMENT |  |  |  | 37332 | [5 empty] | 37800 |  |  | 75132
|  | Material - Direct Purchase Total |  |  |  |  | 37332 | 2448 |  |  |  |  | 37800 |  |  | 77580
| Animal Guards And Deterrents-DP Total | [5 empty] | 37332 | 2448 |  |  |  |  | 37800 |  |  | 77580
| Breakers - Circuit-DP | Material - Direct Purchase | MITSUBISHI ELECTRIC |  |  | 2344630 | 937852 | 1577306 | 682112 | [6 empty] | 5541900
|  | Material - Direct Purchase Total |  |  |  | 2344630 | 937852 | 1577306 | 682112 | [6 empty] | 5541900
| Breakers - Circuit-DP Total |  |  |  |  | 2344630 | 937852 | 1577306 | 682112 | [6 empty] | 5541900
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp |  |  |  | 110713 | 15485.33 |  | 5974.52 | 18126.1 | 6746.38 |  | 13547.56 | 131070.48 | 301663.37
|  |  | CAL-DUCT INC | [8 empty] | 8880 |  |  |  | 8880
|  |  | COMPASS POWER SERVICES CO |  |  |  | 8672.9 | [6 empty] | 5329.3 |  | 14002.2
|  |  | JENSEN PRECAST | [5 empty] | 260281.31 | 33170.7 |  |  |  | 30525 |  | 323977.01
|  |  | Material Entries <$5,000 |  |  | 193.53 | 340.34 | 752.4 | 2000.57 | 888 | 409.6 | 3185 | 5963.16 |  | 2336.5 | 16069.1
|  |  | MCNICHOLS COMPANY | [7 empty] | 5669.92 |  |  |  |  | 5669.92
|  |  | OLD CASTLE PRECAST | [9 empty] | 102807 | 16742 |  | 119549
|  | Material - Direct Purchase Total |  |  |  | 193.53 | 119726.24 | 16237.73 | 262281.88 | 40033.22 | 24205.62 | 18811.38 | 108770.16 | 66143.86 | 133406.98 | 789810.6
| Building, Shop & Industrial Products/Eqp Total |  |  |  |  | 193.53 | 119726.24 | 16237.73 | 262281.88 | 40033.22 | 24205.62 | 18811.38 | 108770.16 | 66143.86 | 133406.98 | 789810.6
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Cabinets, Panels and Switchboards-DP | [11 empty] | 249858 | 249858
|  |  | CROWN TECHNICAL SYSTEMS |  |  |  |  | 1144632.02 | [5 empty] | 10284.51 | 143414.1 | 1298330.63
|  |  | GRAYBAR ELECTRIC COMPANY INC | [10 empty] | 13559.77 |  | 13559.77
|  |  | NORTON & NORTON ELECTRIC CO LTD | [9 empty] | 152912 |  | 194139 | 347051
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [5 empty] | 216287 |  |  |  |  | 41420 |  | 257707
|  | Material - Direct Purchase Total | [5 empty] | 1144632.02 | 216287 |  |  |  | 152912 | 65264.28 | 587411.1 | 2166506.4
| Cabinets, Panels and Switchboards-DP Total | [6 empty] | 1144632.02 | 216287 |  |  |  | 152912 | 65264.28 | 587411.1 | 2166506.4
| Capacitors and Regulators-DP | Material - Direct Purchase | HAEFELY TRENCH LIMITED | 322854 |  | 256800 | [9 empty] | 579654
|  | Material - Direct Purchase Total |  | 322854 |  | 256800 | [9 empty] | 579654
| Capacitors and Regulators-DP Total |  |  | 322854 |  | 256800 | [9 empty] | 579654
| Communication Systems and Equipment -DP | Material - Direct Purchase | Communication Systems and Equipment -DP | [11 empty] | 42966 | 42966
|  | Material - Direct Purchase Total | [12 empty] | 42966 | 42966
| Communication Systems and Equipment -DP Total | [13 empty] | 42966 | 42966
| Electric Wiring and Components-DP | Material - Direct Purchase | CROSS BROTHERS INC | [6 empty] | 8920 |  |  |  |  | 27210 | 36130
|  |  | Electric Wiring and Components-DP | [11 empty] | 18960.6 | 18960.6
|  |  | M & M POWER PRODUCTS | [7 empty] | 200613.51 | 28328.8 | 58044.84 |  |  | 286987.15
|  |  | Material Entries <$5,000 |  |  | 3333.16 |  | 2859 |  | 4227.4 | 1514.32 | 1517.35 | 781.46 | 8837.04 | 677.42 | 23747.15
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC | [5 empty] | 17872.14 | 162286.4 | [5 empty] | 180158.54
|  |  | WALKER AND ASSOCIATES INC | [5 empty] | 8181.44 | [6 empty] | 8181.44
|  | Material - Direct Purchase Total |  |  |  | 3333.16 |  | 2859 | 26053.58 | 175433.8 | 202127.83 | 29846.15 | 58826.3 | 8837.04 | 46848.02 | 554164.88
| Electric Wiring and Components-DP Total |  |  |  |  | 3333.16 |  | 2859 | 26053.58 | 175433.8 | 202127.83 | 29846.15 | 58826.3 | 8837.04 | 46848.02 | 554164.88
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | COMPASS POWER SERVICES CO |  |  |  | 11321.4 | 6777 | [7 empty] | 18098.4
|  |  | Material Entries <$5,000 |  |  |  |  | 303.39 | [5 empty] | 174.71 |  | 478.1
|  | Material - Direct Purchase Total |  |  |  |  | 11321.4 | 7080.39 | [5 empty] | 174.71 |  | 18576.5
| Fuels, Chemicals & Petrochem-DP Total | [5 empty] | 11321.4 | 7080.39 | [5 empty] | 174.71 |  | 18576.5
| Insulators & Bushings-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 4946.38 | 566.95 | 5513.33
|  | Material - Direct Purchase Total | [11 empty] | 4946.38 | 566.95 | 5513.33
| Insulators & Bushings-DP Total | [12 empty] | 4946.38 | 566.95 | 5513.33
| Line Switches & Switchgear-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | -213245 | [7 empty] | -213245
|  |  | SOUTHERN STATES LLC |  |  |  |  | 320055 | 2786930 | 9147 | [5 empty] | 3116132
|  | Material - Direct Purchase Total | [5 empty] | 106810 | 2786930 | 9147 | [5 empty] | 2902887
| Line Switches & Switchgear-DP Total | [6 empty] | 106810 | 2786930 | 9147 | [5 empty] | 2902887
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 |  | -81.16 | [6 empty] | -293.35 | 293.35 |  |  | -81.16
|  | Material - Direct Purchase Total |  |  | -81.16 | [6 empty] | -293.35 | 293.35 |  |  | -81.16
| Material - Direct Purchase - Correction Total |  |  |  | -81.16 | [6 empty] | -293.35 | 293.35 |  |  | -81.16
| Material - Inventory | Material | Material - Inventory | 444924.07 |  | 4776 |  | 879051.01 |  | 505446.61 | 6489.29 | 1176.26 | 1042662.33 | 864559.45 | 1185318.66 | 4934403.68
|  | Material Total |  | 444924.07 |  | 4776 |  | 879051.01 |  | 505446.61 | 6489.29 | 1176.26 | 1042662.33 | 864559.45 | 1185318.66 | 4934403.68
| Material - Inventory Total |  |  | 444924.07 |  | 4776 |  | 879051.01 |  | 505446.61 | 6489.29 | 1176.26 | 1042662.33 | 864559.45 | 1185318.66 | 4934403.68
| Material - Other | Material | Material - Other | 60340.21 | 196213.66 | 216635.23 | 125215.09 | 368396.7 | 379524.35 | 164173.73 | 45308.78 | 117332.53 | 277247.43 | 545555.78 | 568721.2 | 3064664.69
|  | Material Total |  | 60340.21 | 196213.66 | 216635.23 | 125215.09 | 368396.7 | 379524.35 | 164173.73 | 45308.78 | 117332.53 | 277247.43 | 545555.78 | 568721.2 | 3064664.69
| Material - Other Total |  |  | 60340.21 | 196213.66 | 216635.23 | 125215.09 | 368396.7 | 379524.35 | 164173.73 | 45308.78 | 117332.53 | 277247.43 | 545555.78 | 568721.2 | 3064664.69
| Mechanical Systems and Components-DP | Material - Direct Purchase | GENERATOR SERVICES CO INC |  |  |  |  | 118600 | [5 empty] | 6600 |  | 125200
|  |  | Material Entries <$5,000 |  |  |  |  | 3020 | [7 empty] | 3020
|  | Material - Direct Purchase Total | [5 empty] | 121620 | [5 empty] | 6600 |  | 128220
| Mechanical Systems and Components-DP Total | [6 empty] | 121620 | [5 empty] | 6600 |  | 128220
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 887.98 |  | 22.14 |  | 88.44 |  | 3305 | 1310.4 | 5613.96
|  |  | Metals & Fabricated Metal Products-DP | [9 empty] | 27265.12 |  |  | 27265.12
|  | Material - Direct Purchase Total | [5 empty] | 887.98 |  | 22.14 |  | 88.44 | 27265.12 | 3305 | 1310.4 | 32879.08
| Metals & Fabricated Metal Products-DP Total | [6 empty] | 887.98 |  | 22.14 |  | 88.44 | 27265.12 | 3305 | 1310.4 | 32879.08
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | MAGNETIC INSTRUMENTATION INC | [5 empty] | 187715 | [6 empty] | 187715
|  |  | Meters, Monitor and Warnings-DP | [8 empty] | 67900 |  |  |  | 67900
|  | Material - Direct Purchase Total | [6 empty] | 187715 |  |  | 67900 |  |  |  | 255615
| Meters, Monitor and Warnings-DP Total | [7 empty] | 187715 |  |  | 67900 |  |  |  | 255615
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 447.2 |  |  | 447.2
|  | Material - Direct Purchase Total | [10 empty] | 447.2 |  |  | 447.2
| Monitor Equipment, Gauges and Hoses-DP Total | [11 empty] | 447.2 |  |  | 447.2
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 795.44 |  | 1397.54 | 446 | 2638.98
|  | Material - Direct Purchase Total | [9 empty] | 795.44 |  | 1397.54 | 446 | 2638.98
| Office & Office Support Products-DP Total | [10 empty] | 795.44 |  | 1397.54 | 446 | 2638.98
| Other Consumables-DP | Material - Direct Purchase | Material Entries <$5,000 | [6 empty] | 166.13 |  | 194.87 |  |  |  | 361
|  | Material - Direct Purchase Total | [7 empty] | 166.13 |  | 194.87 |  |  |  | 361
| Other Consumables-DP Total | [8 empty] | 166.13 |  | 194.87 |  |  |  | 361
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 4764.74 |  | 3550 |  |  |  | 102.71 |  | 8417.45
|  |  | Pipe/Tubing, Fittings and Gaskets-DP | [9 empty] | 6258.44 |  | 15721.74 | 21980.18
|  | Material - Direct Purchase Total | [5 empty] | 4764.74 |  | 3550 |  |  | 6258.44 | 102.71 | 15721.74 | 30397.63
| Pipe/Tubing, Fittings and Gaskets-DP Total | [6 empty] | 4764.74 |  | 3550 |  |  | 6258.44 | 102.71 | 15721.74 | 30397.63
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | JENSEN PRECAST | [8 empty] | 10150 |  |  |  | 10150
|  |  | Material Entries <$5,000 | [5 empty] | 1047.76 |  |  | 4278.54 |  |  |  | 5326.3
|  |  | Pole Line Hdwe & Connectors-DP |  |  |  |  | 8936.08 |  | 26497.47 | 5156.19 |  | 8789.91 | 8756.25 | 18619.74 | 76755.64
|  | Material - Direct Purchase Total | [5 empty] | 8936.08 | 1047.76 | 26497.47 | 5156.19 | 14428.54 | 8789.91 | 8756.25 | 18619.74 | 92231.94
| Pole Line Hdwe & Connectors-DP Total | [6 empty] | 8936.08 | 1047.76 | 26497.47 | 5156.19 | 14428.54 | 8789.91 | 8756.25 | 18619.74 | 92231.94
| Poles & Wood Products-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 320.5 | [9 empty] | 320.5
|  | Material - Direct Purchase Total |  |  |  | 320.5 | [9 empty] | 320.5
| Poles & Wood Products-DP Total |  |  |  |  | 320.5 | [9 empty] | 320.5
| Power Systems, Batteries and Light-DP | Material - Direct Purchase | BENNING POWER ELECTRONICS INC | [5 empty] | 21194 | [6 empty] | 21194
|  |  | C&D TECHNOLOGIES |  |  |  |  | 69000 | [7 empty] | 69000
|  |  | M & M POWER PRODUCTS | [10 empty] | 450100 | 125320 | 575420
|  |  | Material Entries <$5,000 | [5 empty] | 3600 | [6 empty] | 3600
|  | Material - Direct Purchase Total | [5 empty] | 69000 | 24794 |  |  |  |  | 450100 | 125320 | 669214
| Power Systems, Batteries and Light-DP Total | [6 empty] | 69000 | 24794 |  |  |  |  | 450100 | 125320 | 669214
| Protection and Test-DP | Material - Direct Purchase | ABB INC | [6 empty] | 98501.94 | [5 empty] | 98501.94
|  |  | Protection and Test-DP | [9 empty] | 7038.02 |  | 34059.37 | 41097.39
|  | Material - Direct Purchase Total | [7 empty] | 98501.94 |  |  | 7038.02 |  | 34059.37 | 139599.33
| Protection and Test-DP Total | [8 empty] | 98501.94 |  |  | 7038.02 |  | 34059.37 | 139599.33
| Reactors and Line Traps-DP | Material - Direct Purchase | HAEFELY TRENCH LIMITED |  | 40395 |  |  | 18450 | [7 empty] | 58845
|  |  | Material Entries <$5,000 |  | 0 | [9 empty] | -450600 | -450600
|  |  | Reactors and Line Traps-DP | [11 empty] | 1351800 | 1351800
|  | Material - Direct Purchase Total |  |  | 40395 |  |  | 18450 | [6 empty] | 901200 | 960045
| Reactors and Line Traps-DP Total |  |  |  | 40395 |  |  | 18450 | [6 empty] | 901200 | 960045
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO |  | 2432739.74 | 150344.95 | 380270.73 | 139000 |  | 167490 | 144064.68 | 768773.76 | 1030200.23 | 156584 |  | 5369468.09
|  |  | Material Entries <$5,000 | [7 empty] | 2060.95 |  |  | 24.7 | -160550 | -158464.35
|  |  | PARCELL STEEL CO |  |  |  |  | 50739.79 | 135568.8 | 67678.56 |  | 74483.46 | 84507.15 |  |  | 412977.76
|  |  | WASHINGTON ORNAMENTAL | [8 empty] | 139904 | 164967 |  | 24985 | 329856
|  | Material - Direct Purchase Total |  |  | 2432739.74 | 150344.95 | 380270.73 | 189739.79 | 135568.8 | 235168.56 | 146125.63 | 983161.22 | 1279674.38 | 156608.7 | -135565 | 5953837.5
| Steel / Fabricated / Structural-DP Total |  |  |  | 2432739.74 | 150344.95 | 380270.73 | 189739.79 | 135568.8 | 235168.56 | 146125.63 | 983161.22 | 1279674.38 | 156608.7 | -135565 | 5953837.5
| Transformers - Distribution-DP | Material - Direct Purchase | HOWARD INDUSTRIES INC | [6 empty] | 17269 | [5 empty] | 17269
|  |  | Material Entries <$5,000 | [8 empty] | 3732 |  | 2937 |  | 6669
|  | Material - Direct Purchase Total | [7 empty] | 17269 |  | 3732 |  | 2937 |  | 23938
| Transformers - Distribution-DP Total | [8 empty] | 17269 |  | 3732 |  | 2937 |  | 23938
| Transformers - Power Substation-DP | Material - Direct Purchase | HYUNDAI CORPORATION USA | [6 empty] | 402280 |  |  |  | 3960000 | 3463250 | 7825530
|  | Material - Direct Purchase Total | [7 empty] | 402280 |  |  |  | 3960000 | 3463250 | 7825530
| Transformers - Power Substation-DP Total | [8 empty] | 402280 |  |  |  | 3960000 | 3463250 | 7825530
| Transformers CT/PT/INSTR-DP | Material - Direct Purchase | ABB INC | [7 empty] | 15534 |  |  |  |  | 15534
|  | Material - Direct Purchase Total | [8 empty] | 15534 |  |  |  |  | 15534
| Transformers CT/PT/INSTR-DP Total | [9 empty] | 15534 |  |  |  |  | 15534
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  | 14.12 | 221.51 | 1639.84 | 31836.05 | 326.11 | 1152.84 | 3622.32 | 4717.77 | 1172.28 | 7669.94 | 52372.78
|  |  | Transportation & Mobile Equip-DP |  |  |  |  | 27701.42 | 118538.45 | [6 empty] | 146239.87
|  | Material - Direct Purchase Total |  |  |  | 14.12 | 221.51 | 29341.26 | 150374.5 | 326.11 | 1152.84 | 3622.32 | 4717.77 | 1172.28 | 7669.94 | 198612.65
| Transportation & Mobile Equip-DP Total |  |  |  |  | 14.12 | 221.51 | 29341.26 | 150374.5 | 326.11 | 1152.84 | 3622.32 | 4717.77 | 1172.28 | 7669.94 | 198612.65
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  |  | 222.55 |  | 1118.86 |  |  |  |  | 148 | 1489.41
|  |  | Wire, Cable & Bus Bar-DP | [11 empty] | 8600.13 | 8600.13
|  | Material - Direct Purchase Total | [5 empty] | 222.55 |  | 1118.86 |  |  |  |  | 8748.13 | 10089.54
| Wire, Cable & Bus Bar-DP Total | [6 empty] | 222.55 |  | 1118.86 |  |  |  |  | 8748.13 | 10089.54
2. Material Total |  |  |  | 828118.28 | 2669267.24 | 2977047.49 | 1611938.97 | 4547783.25 | 4852688.87 | 1679134.57 | 446100.18 | 1240795.8 | 3012702.41 | 6146460.98 | 7006019.23 | 37018057.27
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | 123222.58 | 72812 | 96710.49 | 6750.99 | 22268.78 | 2588 | 2505.88 | 2018.75 | 780 | 23590.69 | 28039.8 | 38702.22 | 419990.18
|  |  | UTILITY LINE MANAGEMENT SERVICES |  | 66201.85 | 131117.34 | 124248.89 | [8 empty] | 321568.08
|  | Contract Total |  | 123222.58 | 139013.85 | 227827.83 | 130999.88 | 22268.78 | 2588 | 2505.88 | 2018.75 | 780 | 23590.69 | 28039.8 | 38702.22 | 741558.26
| Construction Management Services Total |  |  | 123222.58 | 139013.85 | 227827.83 | 130999.88 | 22268.78 | 2588 | 2505.88 | 2018.75 | 780 | 23590.69 | 28039.8 | 38702.22 | 741558.26
| Construction Services - Other | Contract | Contract Entries <$50,000 | [7 empty] | 1576.7 | 2423.25 |  |  |  | 3999.95
|  | Contract Total | [8 empty] | 1576.7 | 2423.25 |  |  |  | 3999.95
| Construction Services - Other Total | [9 empty] | 1576.7 | 2423.25 |  |  |  | 3999.95
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | 368 | 2077.46 | 1849.14 | 6862.6 | 1056 | -1171.39 | 7968.89 | 6888.66 | 7153.59 | 16210.42 | 11756.77 | 13679.14 | 74699.28
|  | Contract Total |  | 368 | 2077.46 | 1849.14 | 6862.6 | 1056 | -1171.39 | 7968.89 | 6888.66 | 7153.59 | 16210.42 | 11756.77 | 13679.14 | 74699.28
| Construction, Civil/Structural Total |  |  | 368 | 2077.46 | 1849.14 | 6862.6 | 1056 | -1171.39 | 7968.89 | 6888.66 | 7153.59 | 16210.42 | 11756.77 | 13679.14 | 74699.28
| Construction, Earthwork | Contract | Contract Entries <$50,000 | [7 empty] | 24400 | 5900 | 5420 | 4460 |  | 40180
|  |  | ZIM INDUSTRIES, INC. |  |  | 507293 |  |  |  | 288762 | [5 empty] | 796055
|  | Contract Total |  |  |  | 507293 |  |  |  | 288762 | 24400 | 5900 | 5420 | 4460 |  | 836235
| Construction, Earthwork Total |  |  |  |  | 507293 |  |  |  | 288762 | 24400 | 5900 | 5420 | 4460 |  | 836235
| Construction, Property/Building | Contract | Contract Entries <$50,000 | [10 empty] | 3122.64 | 3646.33 | 6768.97
|  | Contract Total | [11 empty] | 3122.64 | 3646.33 | 6768.97
| Construction, Property/Building Total | [12 empty] | 3122.64 | 3646.33 | 6768.97
| Contract Consult/Contract Ord to Ord | Contract | Contract Entries <$50,000 | [5 empty] | 1254.17 | [6 empty] | 1254.17
|  | Contract Total | [6 empty] | 1254.17 | [6 empty] | 1254.17
| Contract Consult/Contract Ord to Ord Total | [7 empty] | 1254.17 | [6 empty] | 1254.17
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 988.83 | 988.83
|  | Labor Total | [12 empty] | 988.83 | 988.83
| ELEC SYS PLANNING Total | [13 empty] | 988.83 | 988.83
| Electrical Construction, Substations | Contract | Contract Entries <$50,000 | [8 empty] | 13656 |  |  |  | 13656
|  |  | PAR ELECTRICAL CONTRACTORS INC |  |  | 299876 | 2188248 | 4108350.8 | 2319980.8 |  | 771205.12 | 6364877 | 9087298.07 | 7497461.77 | 17621104.2 | 50258401.76
|  | Contract Total |  |  |  | 299876 | 2188248 | 4108350.8 | 2319980.8 |  | 771205.12 | 6378533 | 9087298.07 | 7497461.77 | 17621104.2 | 50272057.76
| Electrical Construction, Substations Total |  |  |  |  | 299876 | 2188248 | 4108350.8 | 2319980.8 |  | 771205.12 | 6378533 | 9087298.07 | 7497461.77 | 17621104.2 | 50272057.76
| Electrical Services | Contract | Contract Entries <$50,000 |  |  |  | 11713.7 |  | 8242.5 | [6 empty] | 19956.2
|  | Contract Total |  |  |  |  | 11713.7 |  | 8242.5 | [6 empty] | 19956.2
| Electrical Services Total | [5 empty] | 11713.7 |  | 8242.5 | [6 empty] | 19956.2
| ENGINEERING | Labor | Labor Entries <$5,000 | 169.41 | 540.94 | 321.75 | 153.65 |  | 324.97 |  | 330.12 | 1320.37 | 573.93 | 521.45 |  | 4256.59
|  | Labor Total |  | 169.41 | 540.94 | 321.75 | 153.65 |  | 324.97 |  | 330.12 | 1320.37 | 573.93 | 521.45 |  | 4256.59
| ENGINEERING Total |  |  | 169.41 | 540.94 | 321.75 | 153.65 |  | 324.97 |  | 330.12 | 1320.37 | 573.93 | 521.45 |  | 4256.59
| GRID OPS | Labor | Labor Entries <$5,000 | [11 empty] | 878.81 | 878.81
|  | Labor Total | [12 empty] | 878.81 | 878.81
| GRID OPS Total | [13 empty] | 878.81 | 878.81
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 |  |  | 1397 | 2381 | 8494.7 | -647.75 |  |  |  | 12647.5 | 6665 | 2963 | 33900.45
|  | Contract Total |  |  |  | 1397 | 2381 | 8494.7 | -647.75 |  |  |  | 12647.5 | 6665 | 2963 | 33900.45
| Hauling / Industrial Moving Services Total |  |  |  |  | 1397 | 2381 | 8494.7 | -647.75 |  |  |  | 12647.5 | 6665 | 2963 | 33900.45
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 |  | 1224 | [6 empty] | 13212.36 | 15564 |  | 154016.43 | 184016.79
|  |  | CROWN TECHNICAL SYSTEMS | [10 empty] | 200045.25 |  | 200045.25
|  |  | PAR ELECTRICAL CONTRACTORS INC | [5 empty] | 234000 | [6 empty] | 234000
|  | Contract Total |  |  | 1224 |  |  |  | 234000 |  |  | 13212.36 | 15564 | 200045.25 | 154016.43 | 618062.04
| Major Construction, Turnkey, Trans/Subs Total |  |  |  | 1224 |  |  |  | 234000 |  |  | 13212.36 | 15564 | 200045.25 | 154016.43 | 618062.04
| SC&M | Labor | Labor Entries <$5,000 | 871.92 |  | 1657.24 | 1282.46 | 1643.97 | 2487.94 | 1546.17 | 2068.59 | 1374.43 | 1794.67 | 1720.12 | 1748.27 | 18195.78
|  | Labor Total |  | 871.92 |  | 1657.24 | 1282.46 | 1643.97 | 2487.94 | 1546.17 | 2068.59 | 1374.43 | 1794.67 | 1720.12 | 1748.27 | 18195.78
| SC&M Total |  |  | 871.92 |  | 1657.24 | 1282.46 | 1643.97 | 2487.94 | 1546.17 | 2068.59 | 1374.43 | 1794.67 | 1720.12 | 1748.27 | 18195.78
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  |  | 205.88 | 124.63 | 455.53 | 207.07 |  |  |  | 140.77 | 103.18 | 1237.06
|  | Labor Total |  |  |  |  | 205.88 | 124.63 | 455.53 | 207.07 |  |  |  | 140.77 | 103.18 | 1237.06
| SCM HOME CENTER Total | [5 empty] | 205.88 | 124.63 | 455.53 | 207.07 |  |  |  | 140.77 | 103.18 | 1237.06
| Security / Protection Services | Contract | Contract Entries <$50,000 | 26759 | 35528.29 | 28863.62 | 31838.64 | 28931.31 | 37820.04 | 48560.55 | 49795.69 | 40216.97 | 2053.11 | 44765.19 | 4383.11 | 379515.52
|  |  | WACKENHUT CORPORATION (THE) | [9 empty] | 56556.04 |  | 80100.38 | 136656.42
|  | Contract Total |  | 26759 | 35528.29 | 28863.62 | 31838.64 | 28931.31 | 37820.04 | 48560.55 | 49795.69 | 40216.97 | 58609.15 | 44765.19 | 84483.49 | 516171.94
| Security / Protection Services Total |  |  | 26759 | 35528.29 | 28863.62 | 31838.64 | 28931.31 | 37820.04 | 48560.55 | 49795.69 | 40216.97 | 58609.15 | 44765.19 | 84483.49 | 516171.94
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | 17190.86 | 26640.32 | 36209.65 | 32625.02 | 36246.97 | -43964.17 | 53272.54 | 60214.14 | 55837.84 | 33147.55 | 69564.15 | 35587.64 | 412572.51
|  | Contract Total |  | 17190.86 | 26640.32 | 36209.65 | 32625.02 | 36246.97 | -43964.17 | 53272.54 | 60214.14 | 55837.84 | 33147.55 | 69564.15 | 35587.64 | 412572.51
| Short Term Equipment Rent Total |  |  | 17190.86 | 26640.32 | 36209.65 | 32625.02 | 36246.97 | -43964.17 | 53272.54 | 60214.14 | 55837.84 | 33147.55 | 69564.15 | 35587.64 | 412572.51
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 |  |  | 82 | 82 | 328 |  |  |  |  | 328 | 164 | 82 | 1066
|  | Labor Total |  |  |  | 82 | 82 | 328 |  |  |  |  | 328 | 164 | 82 | 1066
| TSD-HERC - Crane Svs Total |  |  |  |  | 82 | 82 | 328 |  |  |  |  | 328 | 164 | 82 | 1066
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 |  |  | 82 | 82 | 246 | 164 | 164 | 328 | 246 | 410 | 82 | 246 | 2050
|  | Labor Total |  |  |  | 82 | 82 | 246 | 164 | 164 | 328 | 246 | 410 | 82 | 246 | 2050
| TSD-HERC - Rental Total |  |  |  |  | 82 | 82 | 246 | 164 | 164 | 328 | 246 | 410 | 82 | 246 | 2050
3. Construction Total |  |  |  | 168581.77 | 205024.86 | 1105459.23 | 2406474.83 | 4207691.16 | 2561534.64 | 402987.1 | 918825.77 | 6506997.81 | 9255593.98 | 7868508.91 | 17958229.54 | 53565909.6
4. Allocated | Chargebacks | Chargeback | BR Reprographics / DWG MGMT REPRGRAPHC | [8 empty] | 5862.75 |  |  |  | 5862.75
|  |  | Chargeback Entries <$5,000 | -33034.5 | 16537.37 | 32058.92 | 26092.24 | -38865.79 | 25787.09 | -217765.48 | 24634.08 | -82234.3 | -424003.56 | -484497.38 | -19312.44 | -1174603.75
|  |  | MATERIAL MANAGEM | 169916.5 |  |  |  | 170887.52 |  | 94518.52 |  |  | 122095.76 | 146802.19 | 159188.3 | 863408.79
|  |  | PDP-RedBluff -MPO | 114173.23 | 483941.53 | 610693.54 | 638558.88 | 336020.52 | 415583.78 | 878002.74 | 4473282.87 |  | 1270528.77 | 742429.66 | 348067.21 | 10311282.73
|  |  | PROCUREMENT TDBU |  | 17313.45 | 25944.49 | 27048.92 | 51293.84 | 48595.9 | 9154.79 | 10343.86 | 36397.38 | 87774.87 | 84085.33 | 154045.88 | 551998.71
|  |  | Red Bluff Sub-ESCI-Subsurface Soil in Ly | [10 empty] | 7864.76 |  | 7864.76
|  |  | Red Bluff Substation Cost Allocation |  | 5434.53 | 24389.2 | 63910.14 | 280020.77 | 295475.84 | 247300.98 | 374151.01 | 107655.92 | 351802.5 | 562782.21 | 935956.89 | 3248879.99
|  |  | TDBU Vehicle Cost | 7461.52 | [8 empty] | 7845.12 |  |  | 15306.64
|  | Chargeback Total |  | 258516.75 | 523226.88 | 693086.15 | 755610.18 | 799356.86 | 785442.61 | 1011211.55 | 4882411.82 | 67681.75 | 1416043.46 | 1059466.77 | 1577945.84 | 13830000.62
| Chargebacks Total |  |  | 258516.75 | 523226.88 | 693086.15 | 755610.18 | 799356.86 | 785442.61 | 1011211.55 | 4882411.82 | 67681.75 | 1416043.46 | 1059466.77 | 1577945.84 | 13830000.62
| Labor - Other | Labor | Division Overhead | 97649.27 | 241845.13 | 302592.09 | 309911.44 | 599891.13 | 482031.44 | 150181.93 | 121643.13 | 363772.49 | 1172399.09 | 346246.6 | 894666.91 | 5082830.65
|  |  | Labor Entries <$5,000 | 14685.28 | 7959.25 | 3945.47 | 7330.88 | 4278.17 | 4935.43 | 3309.82 | 4571.23 | -5277.1 | 11609.71 | 1266.52 | 1905.43 | 60520.09
|  |  | Paid Absence | 14015.58 | 9434.93 | 5830.74 |  | 6826.04 | 8443.29 | 5071.62 | 7176.03 |  | 16717.19 | 5778.01 | 7209.05 | 86502.48
|  | Labor Total |  | 126350.13 | 259239.31 | 312368.3 | 317242.32 | 610995.34 | 495410.16 | 158563.37 | 133390.39 | 358495.39 | 1200725.99 | 353291.13 | 903781.39 | 5229853.22
| Labor - Other Total |  |  | 126350.13 | 259239.31 | 312368.3 | 317242.32 | 610995.34 | 495410.16 | 158563.37 | 133390.39 | 358495.39 | 1200725.99 | 353291.13 | 903781.39 | 5229853.22
| Other | Other | Other | [8 empty] | 398.92 |  |  | 161.67 | 560.59
|  | Other Total | [9 empty] | 398.92 |  |  | 161.67 | 560.59
| Other Total | [10 empty] | 398.92 |  |  | 161.67 | 560.59
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -52501.28 | 52501.28 |  |  | 0
|  | Overhead Total | [9 empty] | -52501.28 | 52501.28 |  |  | 0
| Overhead Correction Total | [10 empty] | -52501.28 | 52501.28 |  |  | 0
4. Allocated Total |  |  |  | 384866.88 | 782466.19 | 1005454.45 | 1072852.5 | 1410352.2 | 1280852.77 | 1169774.92 | 5015802.21 | 374074.78 | 2669270.73 | 1412757.9 | 2481888.9 | 19060414.43
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 197756.27 | 16282.92 | [6 empty] | 781718.03 | 995757.22
|  |  | Capitalized Overhead - A&G | 85814.15 | 108328.41 | 186487.87 | 191480.54 | 873921.63 | 321762.09 | 116172.32 | 191076.98 | 405030.23 | 373010.4 | 411879.95 | 776148.46 | 4041113.03
|  |  | Capitalized Overhead - Inj & Damages | 1128.83 | 5777.17 | 4147.62 | 2087.67 | 48921.48 | 7118.47 | 1721.08 | 6639.83 | 4160.37 | 4250.67 | 10589.11 | 9597.11 | 106139.41
|  |  | Capitalized Overhead - P&B/Payroll Tax | 52200.88 | 59360.83 | 63201.23 | 70247.92 | 110713.21 | 106730.21 | 73229.58 | 62653.33 | 4157.85 | 67728.62 | 48236.67 | 141764.49 | 860224.82
|  |  | Corporate Overheads Correction |  |  |  |  | -239710.4 | [7 empty] | -239710.4
|  | Non Budgeted Total |  | 139143.86 | 173466.41 | 253836.72 | 461572.4 | 810128.84 | 435610.77 | 191122.98 | 260370.14 | 413348.45 | 444989.69 | 470705.73 | 1709228.09 | 5763524.08
| Non Budget - Other Total |  |  | 139143.86 | 173466.41 | 253836.72 | 461572.4 | 810128.84 | 435610.77 | 191122.98 | 260370.14 | 413348.45 | 444989.69 | 470705.73 | 1709228.09 | 5763524.08
5. Corporate Overhead Total |  |  |  | 139143.86 | 173466.41 | 253836.72 | 461572.4 | 810128.84 | 435610.77 | 191122.98 | 260370.14 | 413348.45 | 444989.69 | 470705.73 | 1709228.09 | 5763524.08
Grand Total |  |  |  | 1117895.29 | 4958466.38 | 6742497.43 | 8821029.42 | 12284017.86 | 13618392.39 | 4728906.17 | 9484572.97 | 8047879.9 | 20566201.41 | 10061126.27 | 18436180.68 | 118867166.17

## 900247848
Pin: 6929 | Project: Red Bluff
Order: 900247848 | 900247848- Devers: Modify Existing CA Series Capaci
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 | [8 empty] | 381.68 |  |  |  | 381.68
|  | Labor Total | [9 empty] | 381.68 |  |  |  | 381.68
| BP&FM Total | [10 empty] | 381.68 |  |  |  | 381.68
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | 214.21 | 707.23 | [9 empty] | 6556.33 | 7477.77
|  | Labor Total |  | 214.21 | 707.23 | [9 empty] | 6556.33 | 7477.77
| ELEC SYS PLANNING Total |  |  | 214.21 | 707.23 | [9 empty] | 6556.33 | 7477.77
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 |  | 528.15 |  |  |  |  | 168.76 |  |  | 39.67 |  |  | 736.58
|  | Labor Total |  |  | 528.15 |  |  |  |  | 168.76 |  |  | 39.67 |  |  | 736.58
| ENG ADVANCEMENT Total |  |  |  | 528.15 |  |  |  |  | 168.76 |  |  | 39.67 |  |  | 736.58
| ENGINEERING | Labor | Engineer Sr |  |  |  |  | 5078.4 | [5 empty] | 5078.4 |  | 10156.8
|  |  | Labor Entries <$5,000 | 258.67 | 981.04 | 2581.8 | 6460.74 | 1224.67 | 7513.71 | 7670.59 | 5612.07 | 4020.85 | 10830.82 | 4530.9 | 1692.28 | 53378.14
|  | Labor Total |  | 258.67 | 981.04 | 2581.8 | 6460.74 | 6303.07 | 7513.71 | 7670.59 | 5612.07 | 4020.85 | 10830.82 | 9609.3 | 1692.28 | 63534.94
| ENGINEERING Total |  |  | 258.67 | 981.04 | 2581.8 | 6460.74 | 6303.07 | 7513.71 | 7670.59 | 5612.07 | 4020.85 | 10830.82 | 9609.3 | 1692.28 | 63534.94
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | [6 empty] | 6452.5 | 4590.5 |  | 44506.25 | 7666.25 | 18754.5 | 81970
|  | Contract Total | [7 empty] | 6452.5 | 4590.5 |  | 44506.25 | 7666.25 | 18754.5 | 81970
| Engineering/Technical Professional Servi Total | [8 empty] | 6452.5 | 4590.5 |  | 44506.25 | 7666.25 | 18754.5 | 81970
| Environmental/Safety Professional Servic | Contract | GENERAL ELECTRIC INTERNATIONAL INC | 89950 | [11 empty] | 89950
|  | Contract Total |  | 89950 | [11 empty] | 89950
| Environmental/Safety Professional Servic Total |  |  | 89950 | [11 empty] | 89950
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  | -44.25 | -44.25 | -97.93 | -57.65 | -156.8 | -145.42 | -86.24 | -60.79 | -339.47 | -107.98 | -1140.78
|  | IMM Correction Total |  |  |  | -44.25 | -44.25 | -97.93 | -57.65 | -156.8 | -145.42 | -86.24 | -60.79 | -339.47 | -107.98 | -1140.78
| IMM/Allocated - Correction Total |  |  |  |  | -44.25 | -44.25 | -97.93 | -57.65 | -156.8 | -145.42 | -86.24 | -60.79 | -339.47 | -107.98 | -1140.78
| Labor - Other | Labor | Labor Entries <$5,000 | -18.04 | 449.97 | -450.76 | 233.13 | 1401.93 | -1953.15 | -234.22 | 489.06 | -5.94 | 1354.31 | -2199.62 | 1580.26 | 646.93
|  | Labor Total |  | -18.04 | 449.97 | -450.76 | 233.13 | 1401.93 | -1953.15 | -234.22 | 489.06 | -5.94 | 1354.31 | -2199.62 | 1580.26 | 646.93
| Labor - Other Total |  |  | -18.04 | 449.97 | -450.76 | 233.13 | 1401.93 | -1953.15 | -234.22 | 489.06 | -5.94 | 1354.31 | -2199.62 | 1580.26 | 646.93
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | 282.6 | 1448.57 | 1763.4 | 1918.96 | 1647.33 | 741.35 | 864.55 | 1881.89 | 617.59 | 986.66 | 741.04 | 771.73 | 13665.67
|  | Labor Total |  | 282.6 | 1448.57 | 1763.4 | 1918.96 | 1647.33 | 741.35 | 864.55 | 1881.89 | 617.59 | 986.66 | 741.04 | 771.73 | 13665.67
| MAJOR PROJECT ORG Total |  |  | 282.6 | 1448.57 | 1763.4 | 1918.96 | 1647.33 | 741.35 | 864.55 | 1881.89 | 617.59 | 986.66 | 741.04 | 771.73 | 13665.67
| Other | Other | Other |  | 133.2 | 111.9 | 137.8 | 311.36 | 24.98 | 174.27 | 12.22 | 24503.25 | -23965.02 | 44.96 | 13340.39 | 14829.31
|  | Other Total |  |  | 133.2 | 111.9 | 137.8 | 311.36 | 24.98 | 174.27 | 12.22 | 24503.25 | -23965.02 | 44.96 | 13340.39 | 14829.31
| Other Total |  |  |  | 133.2 | 111.9 | 137.8 | 311.36 | 24.98 | 174.27 | 12.22 | 24503.25 | -23965.02 | 44.96 | 13340.39 | 14829.31
| SC&M | Labor | Labor Entries <$5,000 | [11 empty] | 347.65 | 347.65
|  | Labor Total | [12 empty] | 347.65 | 347.65
| SC&M Total | [13 empty] | 347.65 | 347.65
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 2384 | 6705 | 6705 | 13538.19 | 8734.5 | 22326.93 | 15580.44 | 8476.25 | 7910.08 | 6928.56 | 7749.58 | 14475.57 | 121514.1
|  | Contract Total |  | 2384 | 6705 | 6705 | 13538.19 | 8734.5 | 22326.93 | 15580.44 | 8476.25 | 7910.08 | 6928.56 | 7749.58 | 14475.57 | 121514.1
| Temporary/Supplementary - Trade/Labor Total |  |  | 2384 | 6705 | 6705 | 13538.19 | 8734.5 | 22326.93 | 15580.44 | 8476.25 | 7910.08 | 6928.56 | 7749.58 | 14475.57 | 121514.1
1. Project Support Total |  |  |  | 93071.44 | 10953.16 | 10667.09 | 22244.57 | 18300.26 | 28596.17 | 30520.09 | 20916.57 | 37341.27 | 40620.46 | 23272.04 | 57410.73 | 393913.85
2. Material | Material - Other | Material | Material - Other | [10 empty] | 0.3 | 844.46 | 844.76
|  | Material Total | [11 empty] | 0.3 | 844.46 | 844.76
| Material - Other Total | [12 empty] | 0.3 | 844.46 | 844.76
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | Steel / Fabricated / Structural-DP | [11 empty] | 10668.9 | 10668.9
|  | Material - Direct Purchase Total | [12 empty] | 10668.9 | 10668.9
| Steel / Fabricated / Structural-DP Total | [13 empty] | 10668.9 | 10668.9
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 | [10 empty] | 944.92 | 2949.15 | 3894.07
|  | Material - Direct Purchase Total | [11 empty] | 944.92 | 2949.15 | 3894.07
| Transportation & Mobile Equip-DP Total | [12 empty] | 944.92 | 2949.15 | 3894.07
2. Material Total | [13 empty] | 945.22 | 14462.51 | 15407.73
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  |  |  | 1300 |  | 1430 |  |  | 1300 |  |  | 4490.26 | 8520.26
|  | Contract Total |  |  |  |  | 1300 |  | 1430 |  |  | 1300 |  |  | 4490.26 | 8520.26
| Construction Management Services Total | [5 empty] | 1300 |  | 1430 |  |  | 1300 |  |  | 4490.26 | 8520.26
| ENGINEERING | Labor | Labor Entries <$5,000 | 169.41 |  |  | 167.72 | 500.61 | 166.69 | 500.61 | 333.75 | 166.87 | 333.74 |  |  | 2339.4
|  | Labor Total |  | 169.41 |  |  | 167.72 | 500.61 | 166.69 | 500.61 | 333.75 | 166.87 | 333.74 |  |  | 2339.4
| ENGINEERING Total |  |  | 169.41 |  |  | 167.72 | 500.61 | 166.69 | 500.61 | 333.75 | 166.87 | 333.74 |  |  | 2339.4
| S/E SUBS MTCETST&APP | Labor | Labor Entries <$5,000 | [5 empty] | 2650.31 | 2936.32 | [5 empty] | 5586.63
|  | Labor Total | [6 empty] | 2650.31 | 2936.32 | [5 empty] | 5586.63
| S/E SUBS MTCETST&APP Total | [7 empty] | 2650.31 | 2936.32 | [5 empty] | 5586.63
| SC&M | Labor | Labor Entries <$5,000 |  |  |  | 350.96 | [5 empty] | 325.45 | 534.67 | 559.55 | 1770.63
|  | Labor Total |  |  |  |  | 350.96 | [5 empty] | 325.45 | 534.67 | 559.55 | 1770.63
| SC&M Total | [5 empty] | 350.96 | [5 empty] | 325.45 | 534.67 | 559.55 | 1770.63
| SCM HOME CENTER | Labor | Labor Entries <$5,000 | [11 empty] | 206.35 | 206.35
|  | Labor Total | [12 empty] | 206.35 | 206.35
| SCM HOME CENTER Total | [13 empty] | 206.35 | 206.35
3. Construction Total |  |  |  | 169.41 |  |  | 1818.68 | 500.61 | 4247 | 3436.93 | 333.75 | 1466.87 | 659.19 | 534.67 | 5256.16 | 18423.27
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 762.11 | 384.97 | 391.63 | 964.5 | 949.35 | 1199.1 | 1833.98 | 794.93 | 659.73 | 1680.76 | 1369.13 | 3391.65 | 14381.84
|  | Chargeback Total |  | 762.11 | 384.97 | 391.63 | 964.5 | 949.35 | 1199.1 | 1833.98 | 794.93 | 659.73 | 1680.76 | 1369.13 | 3391.65 | 14381.84
| Chargebacks Total |  |  | 762.11 | 384.97 | 391.63 | 964.5 | 949.35 | 1199.1 | 1833.98 | 794.93 | 659.73 | 1680.76 | 1369.13 | 3391.65 | 14381.84
| Labor - Other | Labor | Labor Entries <$5,000 | 7607.87 | 1784.24 | 1803.63 | 4138.94 | 3810.02 | 4325.5 | 5641.16 | 3686.24 | 2214 | 8946.29 | 2536.03 | 5451.56 | 51945.48
|  | Labor Total |  | 7607.87 | 1784.24 | 1803.63 | 4138.94 | 3810.02 | 4325.5 | 5641.16 | 3686.24 | 2214 | 8946.29 | 2536.03 | 5451.56 | 51945.48
| Labor - Other Total |  |  | 7607.87 | 1784.24 | 1803.63 | 4138.94 | 3810.02 | 4325.5 | 5641.16 | 3686.24 | 2214 | 8946.29 | 2536.03 | 5451.56 | 51945.48
4. Allocated Total |  |  |  | 8369.98 | 2169.21 | 2195.26 | 5103.44 | 4759.37 | 5524.6 | 7475.14 | 4481.17 | 2873.73 | 10627.05 | 3905.16 | 8843.21 | 66327.32
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 1720.31 | 118.63 | [6 empty] | 4424.62 | 6263.56
|  |  | Capitalized Overhead - A&G | 5670.85 | 384.44 | 458.47 | 1040.1 | 1960.91 | 1369.36 | 1454.8 | 727.82 | 769.58 | 1974.19 | 757.33 | 2082.68 | 18650.53
|  |  | Capitalized Overhead - Inj & Damages | 8.68 | 11.08 | 6.5 | 11.88 | 132.32 | 18.88 | 17.74 | 16.51 | 7.22 | 78.91 | 21.78 | 41.06 | 372.56
|  |  | Capitalized Overhead - P&B/Payroll Tax | 618.48 | 4760.88 | 3993.16 | 11734.75 | 14864.8 | 11918.92 | 15155.59 | 6760.95 | 7423.26 | 6779.25 | 7408.62 | 27398.97 | 118817.63
|  | Non Budgeted Total |  | 6298.01 | 5156.4 | 4458.13 | 14507.04 | 17076.66 | 13307.16 | 16628.13 | 7505.28 | 8200.06 | 8832.35 | 8187.73 | 33947.33 | 144104.28
| Non Budget - Other Total |  |  | 6298.01 | 5156.4 | 4458.13 | 14507.04 | 17076.66 | 13307.16 | 16628.13 | 7505.28 | 8200.06 | 8832.35 | 8187.73 | 33947.33 | 144104.28
5. Corporate Overhead Total |  |  |  | 6298.01 | 5156.4 | 4458.13 | 14507.04 | 17076.66 | 13307.16 | 16628.13 | 7505.28 | 8200.06 | 8832.35 | 8187.73 | 33947.33 | 144104.28
Grand Total |  |  |  | 107908.84 | 18278.77 | 17320.48 | 43673.73 | 40636.9 | 51674.93 | 58060.29 | 33236.77 | 49881.93 | 60739.05 | 36844.82 | 119919.94 | 638176.45

## 800380461
Pin: 6929 | Project: Red Bluff
Order: 800380461 | 800380461- Red Bluff: Commence the Siting Study for
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [9 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11
1. Project Support | 3rd Party Billable A&G - Collectible Ord | WO Postings / Contributions | 3rd Party Billable A&G - Collectible Ord | 10615.85 | 1777.06 | 1917.67 | 54.51 |  | 70.24 | 87.25 | -82.87 | 101.82 | -7.63 | 14533.9
|  | WO Postings / Contributions Total |  | 10615.85 | 1777.06 | 1917.67 | 54.51 |  | 70.24 | 87.25 | -82.87 | 101.82 | -7.63 | 14533.9
| 3rd Party Billable A&G - Collectible Ord Total |  |  | 10615.85 | 1777.06 | 1917.67 | 54.51 |  | 70.24 | 87.25 | -82.87 | 101.82 | -7.63 | 14533.9
| Consultants / Prof Services - Correction | Contract | Contract Entries <$50,000 | [7 empty] | -8237.81 | 8237.81 |  | 0
|  | Contract Total | [8 empty] | -8237.81 | 8237.81 |  | 0
| Consultants / Prof Services - Correction Total | [9 empty] | -8237.81 | 8237.81 |  | 0
| Customer Advance (for advances billed) | WO Postings / Contributions | Customer Advance (for advances billed) |  |  |  |  | 0 | [5 empty] | 0
|  | WO Postings / Contributions Total | [5 empty] | 0 | [5 empty] | 0
| Customer Advance (for advances billed) Total | [6 empty] | 0 | [5 empty] | 0
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  | -40.04 |  |  |  |  | 8237.81 | -8237.81 | -54.37 | -94.41
|  | IMM Correction Total |  |  |  | -40.04 |  |  |  |  | 8237.81 | -8237.81 | -54.37 | -94.41
| IMM/Allocated - Correction Total |  |  |  |  | -40.04 |  |  |  |  | 8237.81 | -8237.81 | -54.37 | -94.41
| Labor - Other | Labor | Labor Entries <$5,000 | [6 empty] | 9.12 |  |  |  | 9.12
|  | Labor Total | [7 empty] | 9.12 |  |  |  | 9.12
| Labor - Other Total | [8 empty] | 9.12 |  |  |  | 9.12
| Marketing Professional Services | Contract | Contract Entries <$50,000 |  | 5931 | [8 empty] | 5931
|  | Contract Total |  |  | 5931 | [8 empty] | 5931
| Marketing Professional Services Total |  |  |  | 5931 | [8 empty] | 5931
| Other | Other | Other | 75665.36 |  | 12979.92 | [7 empty] | 88645.28
|  | Other Total |  | 75665.36 |  | 12979.92 | [7 empty] | 88645.28
| Other Total |  |  | 75665.36 |  | 12979.92 | [7 empty] | 88645.28
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 |  | 135.52 | [8 empty] | 135.52
|  | Contract Total |  |  | 135.52 | [8 empty] | 135.52
| Temporary/Supplementary - Trade/Labor Total |  |  |  | 135.52 | [8 empty] | 135.52
1. Project Support Total |  |  |  | 86281.21 | 7843.58 | 14857.55 | 54.51 | 0 | 70.24 | 96.37 | -82.87 | 101.82 | -62 | 109160.41
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 |  | 40.04 | 728.44 | 388.5 |  | 500.62 | 612.75 | -54.37 | 54.37 |  | 2270.35
|  |  | Law-Red Bluff (ARRA) |  | 6007.5 | [8 empty] | 6007.5
|  | Chargeback Total |  |  | 6047.54 | 728.44 | 388.5 |  | 500.62 | 612.75 | -54.37 | 54.37 |  | 8277.85
| Chargebacks Total |  |  |  | 6047.54 | 728.44 | 388.5 |  | 500.62 | 612.75 | -54.37 | 54.37 |  | 8277.85
| Labor - Other | Labor | Labor Entries <$5,000 |  | 552.06 | [5 empty] | -536.28 | 671.38 |  | 687.16
|  | Labor Total |  |  | 552.06 | [5 empty] | -536.28 | 671.38 |  | 687.16
| Labor - Other Total |  |  |  | 552.06 | [5 empty] | -536.28 | 671.38 |  | 687.16
4. Allocated Total |  |  |  |  | 6599.6 | 728.44 | 388.5 |  | 500.62 | 612.75 | -590.65 | 725.75 |  | 8965.01
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - Inj & Damages | 70.77 | 1.02 | 13.65 |  |  |  | 0.01 | 6.93 | -23.74 | -0.09 | 68.55
|  |  | Capitalized Overhead - P&B/Payroll Tax | [6 empty] | 9.83 |  |  |  | 9.83
|  |  | Corporate Overheads Correction |  |  |  |  | -516.04 | [5 empty] | -516.04
|  | Non Budgeted Total |  | 70.77 | 1.02 | 13.65 |  | -516.04 |  | 9.84 | 6.93 | -23.74 | -0.09 | -437.66
| Non Budget - Other Total |  |  | 70.77 | 1.02 | 13.65 |  | -516.04 |  | 9.84 | 6.93 | -23.74 | -0.09 | -437.66
5. Corporate Overhead Total |  |  |  | 70.77 | 1.02 | 13.65 |  | -516.04 |  | 9.84 | 6.93 | -23.74 | -0.09 | -437.66
Grand Total |  |  |  | 86351.98 | 14444.2 | 15599.64 | 443.01 | -516.04 | 570.86 | 718.96 | -666.59 | 803.83 | -62.09 | 117687.76

## Colorado River
WO | SumOfYTD2012 | Order | Project
800466294- Colorado River Substation Expansion: Lic | -3242.99 | 800466294 | CRS Expansion
800404139- Colorado River Sub Expansion: Equipment | 37478102.18 | 800404139 | CRS Expansion

## 800466294
Pin: 7076 | Project: CRS Expansion
Order: 800466294 | 800466294- Colorado River Substation Expansion: Lic
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 |  |  |  | 2012 Total
SubCategory | Prime | Group | Details | 2 | 5 | 9 | 10
1. Project Support | 3rd Party Billable A&G - Collectible Ord | WO Postings / Contributions | 3rd Party Billable A&G - Collectible Ord | -2.13 |  | 0.74 | -0.76 | -2.15
|  | WO Postings / Contributions Total |  | -2.13 |  | 0.74 | -0.76 | -2.15
| 3rd Party Billable A&G - Collectible Ord Total |  |  | -2.13 |  | 0.74 | -0.76 | -2.15
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction |  |  | -15.21 | 15.21 | 0
|  | IMM Correction Total |  |  |  | -15.21 | 15.21 | 0
| IMM/Allocated - Correction Total |  |  |  |  | -15.21 | 15.21 | 0
| Labor - Other | Labor | Labor Entries <$5,000 |  |  | 14.94 | -14.94 | 0
|  | Labor Total |  |  |  | 14.94 | -14.94 | 0
| Labor - Other Total |  |  |  |  | 14.94 | -14.94 | 0
1. Project Support Total |  |  |  | -2.13 |  | 0.47 | -0.49 | -2.15
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | -15.21 |  | 1.43 | -1.2 | -14.98
|  | Chargeback Total |  | -15.21 |  | 1.43 | -1.2 | -14.98
| Chargebacks Total |  |  | -15.21 |  | 1.43 | -1.2 | -14.98
| Labor - Other | Labor | Labor Entries <$5,000 |  |  | 3.88 | -4.24 | -0.36
|  | Labor Total |  |  |  | 3.88 | -4.24 | -0.36
| Labor - Other Total |  |  |  |  | 3.88 | -4.24 | -0.36
| Overhead Correction | Overhead | Overhead Correction |  |  | 0.27 | -0.27 | 0
|  | Overhead Total |  |  |  | 0.27 | -0.27 | 0
| Overhead Correction Total |  |  |  |  | 0.27 | -0.27 | 0
4. Allocated Total |  |  |  | -15.21 |  | 5.58 | -5.71 | -15.34
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Capitalized Overhead - Inj & Damages | -0.03 |  |  | -0.02 | -0.05
|  |  | Capitalized Overhead - P&B/Payroll Tax | -14.39 |  | 20.81 | -7.1 | -0.68
|  |  | Corporate Overheads Correction |  | -3224.77 |  |  | -3224.77
|  | Non Budgeted Total |  | -14.42 | -3224.77 | 20.81 | -7.12 | -3225.5
| Non Budget - Other Total |  |  | -14.42 | -3224.77 | 20.81 | -7.12 | -3225.5
5. Corporate Overhead Total |  |  |  | -14.42 | -3224.77 | 20.81 | -7.12 | -3225.5
Grand Total |  |  |  | -31.76 | -3224.77 | 26.86 | -13.32 | -3242.99

## 800404139
Pin: 7076 | Project: CRS Expansion
Order: 800404139 | 800404139- Colorado River Sub Expansion: Equipment
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | BP&FM | Labor | Labor Entries <$5,000 |  |  | 162.01 | 114.52 | 272.05 | 1536.13 | 814.17 | 931.62 | 680.49 | 1237.22 | 931.59 | 756.93 | 7436.73
|  | Labor Total |  |  |  | 162.01 | 114.52 | 272.05 | 1536.13 | 814.17 | 931.62 | 680.49 | 1237.22 | 931.59 | 756.93 | 7436.73
| BP&FM Total |  |  |  |  | 162.01 | 114.52 | 272.05 | 1536.13 | 814.17 | 931.62 | 680.49 | 1237.22 | 931.59 | 756.93 | 7436.73
| Cleaning / Janitorial Services | Contract | Contract Entries <$50,000 | [5 empty] | 1271.44 | 194.35 | 194.35 | 194.35 | 194.35 | 194.35 | 194.35 | 2437.54
|  | Contract Total | [6 empty] | 1271.44 | 194.35 | 194.35 | 194.35 | 194.35 | 194.35 | 194.35 | 2437.54
| Cleaning / Janitorial Services Total | [7 empty] | 1271.44 | 194.35 | 194.35 | 194.35 | 194.35 | 194.35 | 194.35 | 2437.54
| Con - Consults/Prof Srvcs/Out Ord to Ord | Contract | Contract Entries <$50,000 | [10 empty] | 5738.5 |  | 5738.5
|  | Contract Total | [11 empty] | 5738.5 |  | 5738.5
| Con - Consults/Prof Srvcs/Out Ord to Ord Total | [12 empty] | 5738.5 |  | 5738.5
| Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 1356429.71 |  |  | 1356429.71
|  |  | Contract Entries <$50,000 | [8 empty] | -1356429.71 |  |  |  | -1356429.71
|  | Contract Total | [9 empty] | -1356429.71 | 1356429.71 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -1356429.71 | 1356429.71 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 2663.51 | 2663.51
|  | Labor Total | [12 empty] | 2663.51 | 2663.51
| ELEC SYS PLANNING Total | [13 empty] | 2663.51 | 2663.51
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 2979.66 | 45.93 | 1819.85 | 664.5 | 663.74 |  | 351.72 |  |  |  |  | 39.58 | 6564.98
|  | Labor Total |  | 2979.66 | 45.93 | 1819.85 | 664.5 | 663.74 |  | 351.72 |  |  |  |  | 39.58 | 6564.98
| ENG ADVANCEMENT Total |  |  | 2979.66 | 45.93 | 1819.85 | 664.5 | 663.74 |  | 351.72 |  |  |  |  | 39.58 | 6564.98
| ENGINEERING | Labor | Engineer | [9 empty] | 5421.52 |  |  | 5421.52
|  |  | Labor Entries <$5,000 | 3624.41 | 4264.42 | 4126.03 | 1757.16 | 7107.29 | 9650.35 | 6406.77 | 3890.58 | 2545.01 | 2010.03 | 5633 | 1794.88 | 52809.93
|  | Labor Total |  | 3624.41 | 4264.42 | 4126.03 | 1757.16 | 7107.29 | 9650.35 | 6406.77 | 3890.58 | 2545.01 | 7431.55 | 5633 | 1794.88 | 58231.45
| ENGINEERING Total |  |  | 3624.41 | 4264.42 | 4126.03 | 1757.16 | 7107.29 | 9650.35 | 6406.77 | 3890.58 | 2545.01 | 7431.55 | 5633 | 1794.88 | 58231.45
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | [11 empty] | 12239 | 12239
|  |  | HYUNDAI CORPORATION USA | [11 empty] | 100000 | 100000
|  | Contract Total | [12 empty] | 112239 | 112239
| Engineering/Technical Professional Servi Total | [13 empty] | 112239 | 112239
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 1527117.72 | -1527117.72 |  |  | 0
|  | IMM Correction Total | [9 empty] | 1527117.72 | -1527117.72 |  |  | 0
| IMM/Allocated - Correction Total | [10 empty] | 1527117.72 | -1527117.72 |  |  | 0
| Labor - Other | Labor | ALH- Sub Order for Colorado River Sub Ex | [9 empty] | 59871.39 | 118332.06 | 156177.75 | 334381.2
|  |  | Labor Correction | [9 empty] | 16057.18 |  |  | 16057.18
|  |  | Labor Entries <$5,000 | -79.75 | 740.63 | -650.8 | 135.52 | 1713.75 | -2459.78 | 0.1 | -66314.72 | 48397.31 | -63023.84 | -1713.45 | 1405.08 | -81849.95
|  | Labor Total |  | -79.75 | 740.63 | -650.8 | 135.52 | 1713.75 | -2459.78 | 0.1 | -66314.72 | 48397.31 | 12904.73 | 116618.61 | 157582.83 | 268588.43
| Labor - Other Total |  |  | -79.75 | 740.63 | -650.8 | 135.52 | 1713.75 | -2459.78 | 0.1 | -66314.72 | 48397.31 | 12904.73 | 116618.61 | 157582.83 | 268588.43
| MAJOR PROJECT ORG | Labor | Labor Entries <$5,000 | [8 empty] | 279.25 |  |  |  | 279.25
|  | Labor Total | [9 empty] | 279.25 |  |  |  | 279.25
| MAJOR PROJECT ORG Total | [10 empty] | 279.25 |  |  |  | 279.25
| Other | Other | Other | 95122.05 | 624648.34 | 146471.27 | 1300879.92 | -1987508.62 | -26613.71 | 188906.4 | 77688.37 | 239509.89 | 87700.45 | 167671.39 | -640935.86 | 273539.89
|  | Other Total |  | 95122.05 | 624648.34 | 146471.27 | 1300879.92 | -1987508.62 | -26613.71 | 188906.4 | 77688.37 | 239509.89 | 87700.45 | 167671.39 | -640935.86 | 273539.89
| Other Total |  |  | 95122.05 | 624648.34 | 146471.27 | 1300879.92 | -1987508.62 | -26613.71 | 188906.4 | 77688.37 | 239509.89 | 87700.45 | 167671.39 | -640935.86 | 273539.89
| SC&M | Labor | Labor Entries <$5,000 |  | 824.2 | 956.7 | 1041.91 | 342.57 |  | 256.64 | 396.11 | 1050.66 | 1346.52 | 550.14 | 971.53 | 7736.98
|  | Labor Total |  |  | 824.2 | 956.7 | 1041.91 | 342.57 |  | 256.64 | 396.11 | 1050.66 | 1346.52 | 550.14 | 971.53 | 7736.98
| SC&M Total |  |  |  | 824.2 | 956.7 | 1041.91 | 342.57 |  | 256.64 | 396.11 | 1050.66 | 1346.52 | 550.14 | 971.53 | 7736.98
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -1446.77 | 1446.77 |  |  | 0
|  | Contract Total | [9 empty] | -1446.77 | 1446.77 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -1446.77 | 1446.77 |  |  | 0
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 679.42 | 727.95 | 533.83 | 698.52 | 494.07 | 2407.09 | 4699.19 | 2908.5 | 2908.5 | 3389.32 | 2848.51 | 7195.09 | 29489.99
|  | Contract Total |  | 679.42 | 727.95 | 533.83 | 698.52 | 494.07 | 2407.09 | 4699.19 | 2908.5 | 2908.5 | 3389.32 | 2848.51 | 7195.09 | 29489.99
| Temporary/Supplementary - Trade/Labor Total |  |  | 679.42 | 727.95 | 533.83 | 698.52 | 494.07 | 2407.09 | 4699.19 | 2908.5 | 2908.5 | 3389.32 | 2848.51 | 7195.09 | 29489.99
1. Project Support Total |  |  |  | 102325.79 | 631251.47 | 153418.89 | 1305292.05 | -1976915.15 | -14208.48 | 201629.34 | 19694.81 | 464806.7 | -55037.1 | 300186.09 | -357498.16 | 774946.25
2. Material | Breakers - Circuit-DP | Material - Direct Purchase | ABB INC |  |  | 1046010 | 987048 |  |  | 35933.48 | [5 empty] | 2068991.48
|  | Material - Direct Purchase Total |  |  |  | 1046010 | 987048 |  |  | 35933.48 | [5 empty] | 2068991.48
| Breakers - Circuit-DP Total |  |  |  |  | 1046010 | 987048 |  |  | 35933.48 | [5 empty] | 2068991.48
| Building, Shop & Industrial Products/Eqp | Material - Direct Purchase | Building, Shop & Industrial Products/Eqp | [6 empty] | 77984.98 |  |  |  |  | 193372.57 | 271357.55
|  |  | CAL-DUCT INC | [9 empty] | 5712.5 |  |  | 5712.5
|  |  | JENSEN PRECAST |  | 9120 | 17084.6 |  | 32808.28 |  | 38087 | 23271.6 |  |  |  |  | 120371.48
|  |  | Material Entries <$5,000 |  |  |  | 1655.3 | 2880 |  |  | 110.86 | 1322.22 | 1755 |  |  | 7723.38
|  | Material - Direct Purchase Total |  |  | 9120 | 17084.6 | 1655.3 | 35688.28 |  | 116071.98 | 23382.46 | 1322.22 | 7467.5 |  | 193372.57 | 405164.91
| Building, Shop & Industrial Products/Eqp Total |  |  |  | 9120 | 17084.6 | 1655.3 | 35688.28 |  | 116071.98 | 23382.46 | 1322.22 | 7467.5 |  | 193372.57 | 405164.91
| Cabinets, Panels and Switchboards-DP | Material - Direct Purchase | Cabinets, Panels and Switchboards-DP | [11 empty] | 164697 | 164697
|  |  | ELECTRICAL POWER PRODUCTS INC | [7 empty] | 295663 |  | 209451 |  | 24088 | 529202
|  | Material - Direct Purchase Total | [8 empty] | 295663 |  | 209451 |  | 188785 | 693899
| Cabinets, Panels and Switchboards-DP Total | [9 empty] | 295663 |  | 209451 |  | 188785 | 693899
| Electric Wiring and Components-DP | Material - Direct Purchase | Material Entries <$5,000 | [9 empty] | 4350 | 1716.87 | 4717.05 | 10783.92
|  |  | ONESOURCE SUPPLY SOLUTIONS, LLC |  |  |  | 5112.04 |  |  |  |  | 67520.6 | 7939.04 |  |  | 80571.68
|  |  | SOUTHWIRE COMPANY | [8 empty] | 46450 |  |  |  | 46450
|  | Material - Direct Purchase Total |  |  |  |  | 5112.04 |  |  |  |  | 113970.6 | 12289.04 | 1716.87 | 4717.05 | 137805.6
| Electric Wiring and Components-DP Total | [5 empty] | 5112.04 |  |  |  |  | 113970.6 | 12289.04 | 1716.87 | 4717.05 | 137805.6
| Fuels, Chemicals & Petrochem-DP | Material - Direct Purchase | COMPASS POWER SERVICES CO |  |  |  | 12424.5 | [8 empty] | 12424.5
|  |  | Material Entries <$5,000 | [6 empty] | 106.22 | 15.02 |  |  |  |  | 121.24
|  | Material - Direct Purchase Total |  |  |  |  | 12424.5 |  |  | 106.22 | 15.02 |  |  |  |  | 12545.74
| Fuels, Chemicals & Petrochem-DP Total | [5 empty] | 12424.5 |  |  | 106.22 | 15.02 |  |  |  |  | 12545.74
| Labor - Other | Labor | Labor Entries <$5,000 | [9 empty] | 499.32 |  | 671.65 | 1170.97
|  | Labor Total | [10 empty] | 499.32 |  | 671.65 | 1170.97
| Labor - Other Total | [11 empty] | 499.32 |  | 671.65 | 1170.97
| Line Switches & Switchgear-DP | Material - Direct Purchase | SOUTHERN STATES LLC |  |  | 128172 | 571738 | 453222 |  |  | 45735 |  |  |  |  | 1198867
|  | Material - Direct Purchase Total |  |  |  | 128172 | 571738 | 453222 |  |  | 45735 |  |  |  |  | 1198867
| Line Switches & Switchgear-DP Total |  |  |  |  | 128172 | 571738 | 453222 |  |  | 45735 |  |  |  |  | 1198867
| Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -53.67 | 53.67 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -53.67 | 53.67 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -53.67 | 53.67 |  |  | 0
| Material - Inventory | Material | Material - Inventory | 14955.43 |  |  |  | 1239.56 | 1438.55 | 7426.04 | 99650.56 | 117323.39 | 2179.85 | 378.07 | 348728.63 | 593320.08
|  | Material Total |  | 14955.43 |  |  |  | 1239.56 | 1438.55 | 7426.04 | 99650.56 | 117323.39 | 2179.85 | 378.07 | 348728.63 | 593320.08
| Material - Inventory Total |  |  | 14955.43 |  |  |  | 1239.56 | 1438.55 | 7426.04 | 99650.56 | 117323.39 | 2179.85 | 378.07 | 348728.63 | 593320.08
| Material - Other | Material | Material - Other | 1175.4 | 53449.98 | 131124.66 | 445805.19 | 62525.75 | 84761.93 | 108496.69 | 282563.91 | 31945.65 | 98637.4 | 116145.3 | 425372.52 | 1842004.38
|  | Material Total |  | 1175.4 | 53449.98 | 131124.66 | 445805.19 | 62525.75 | 84761.93 | 108496.69 | 282563.91 | 31945.65 | 98637.4 | 116145.3 | 425372.52 | 1842004.38
| Material - Other Total |  |  | 1175.4 | 53449.98 | 131124.66 | 445805.19 | 62525.75 | 84761.93 | 108496.69 | 282563.91 | 31945.65 | 98637.4 | 116145.3 | 425372.52 | 1842004.38
| Material Handling Services | Contract | Contract Entries <$50,000 | [7 empty] | 960 |  | 3850 | 3175 | 58874 | 66859
|  | Contract Total | [8 empty] | 960 |  | 3850 | 3175 | 58874 | 66859
| Material Handling Services Total | [9 empty] | 960 |  | 3850 | 3175 | 58874 | 66859
| Metals & Fabricated Metal Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [5 empty] | 2846.62 | [5 empty] | 4902.09 | 7748.71
|  | Material - Direct Purchase Total | [6 empty] | 2846.62 | [5 empty] | 4902.09 | 7748.71
| Metals & Fabricated Metal Products-DP Total | [7 empty] | 2846.62 | [5 empty] | 4902.09 | 7748.71
| Meters, Monitor and Warnings-DP | Material - Direct Purchase | MAGNETIC INSTRUMENTATION INC | [8 empty] | 111565 |  |  |  | 111565
|  | Material - Direct Purchase Total | [9 empty] | 111565 |  |  |  | 111565
| Meters, Monitor and Warnings-DP Total | [10 empty] | 111565 |  |  |  | 111565
| Monitor Equipment, Gauges and Hoses-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 185.57 | 185.57
|  | Material - Direct Purchase Total | [12 empty] | 185.57 | 185.57
| Monitor Equipment, Gauges and Hoses-DP Total | [13 empty] | 185.57 | 185.57
| Office & Office Support Products-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 321.36 |  | 1397.54 | 446 | 2164.9
|  | Material - Direct Purchase Total | [9 empty] | 321.36 |  | 1397.54 | 446 | 2164.9
| Office & Office Support Products-DP Total | [10 empty] | 321.36 |  | 1397.54 | 446 | 2164.9
| Pipe/Tubing, Fittings and Gaskets-DP | Material - Direct Purchase | Material Entries <$5,000 | [11 empty] | 2821.71 | 2821.71
|  |  | Pipe/Tubing, Fittings and Gaskets-DP | [6 empty] | 7964.8 | [5 empty] | 7964.8
|  | Material - Direct Purchase Total | [7 empty] | 7964.8 |  |  |  |  | 2821.71 | 10786.51
| Pipe/Tubing, Fittings and Gaskets-DP Total | [8 empty] | 7964.8 |  |  |  |  | 2821.71 | 10786.51
| Pole Line Hdwe & Connectors-DP | Material - Direct Purchase | Material Entries <$5,000 | [7 empty] | 286.15 | 4.97 | 1846.23 |  |  | 2137.35
|  |  | Pole Line Hdwe & Connectors-DP | [11 empty] | 305024.74 | 305024.74
|  | Material - Direct Purchase Total | [8 empty] | 286.15 | 4.97 | 1846.23 |  | 305024.74 | 307162.09
| Pole Line Hdwe & Connectors-DP Total | [9 empty] | 286.15 | 4.97 | 1846.23 |  | 305024.74 | 307162.09
| Protection and Test-DP | Material - Direct Purchase | ABB INC | [9 empty] | 15534 |  |  | 15534
|  |  | Material Entries <$5,000 | [9 empty] | 188.69 |  | 1296.37 | 1485.06
|  | Material - Direct Purchase Total | [10 empty] | 15722.69 |  | 1296.37 | 17019.06
| Protection and Test-DP Total | [11 empty] | 15722.69 |  | 1296.37 | 17019.06
| Reactors and Line Traps-DP | Material - Direct Purchase | HAEFELY TRENCH LIMITED | [5 empty] | 18450 | [6 empty] | 18450
|  |  | Material Entries <$5,000 | [11 empty] | -93600 | -93600
|  |  | Reactors and Line Traps-DP | [11 empty] | 575400 | 575400
|  | Material - Direct Purchase Total | [6 empty] | 18450 | [5 empty] | 481800 | 500250
| Reactors and Line Traps-DP Total | [7 empty] | 18450 | [5 empty] | 481800 | 500250
| Steel / Fabricated / Structural-DP | Material - Direct Purchase | COAST IRON & STEEL CO |  | 664905.25 | 285637.17 | 64510.28 | 78693.72 | 762402.5 |  |  |  | 238466 |  |  | 2094614.92
|  |  | Material Entries <$5,000 | [5 empty] | 1132.2 |  |  | 1096.8 |  |  | 310 | 2539
|  |  | PARCELL STEEL CO |  |  | 196800.12 |  | 9602.4 | [7 empty] | 206402.52
|  | Material - Direct Purchase Total |  |  | 664905.25 | 482437.29 | 64510.28 | 88296.12 | 763534.7 |  |  | 1096.8 | 238466 |  | 310 | 2303556.44
| Steel / Fabricated / Structural-DP Total |  |  |  | 664905.25 | 482437.29 | 64510.28 | 88296.12 | 763534.7 |  |  | 1096.8 | 238466 |  | 310 | 2303556.44
| Transformers - Distribution-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 3732 |  |  |  | 3732
|  | Material - Direct Purchase Total | [9 empty] | 3732 |  |  |  | 3732
| Transformers - Distribution-DP Total | [10 empty] | 3732 |  |  |  | 3732
| Transformers - Power Substation-DP | Material - Direct Purchase | HYUNDAI CORPORATION USA |  |  |  | 3960000 |  |  | 1160000 | 3071000 |  |  |  |  | 8191000
|  | Material - Direct Purchase Total |  |  |  |  | 3960000 |  |  | 1160000 | 3071000 |  |  |  |  | 8191000
| Transformers - Power Substation-DP Total | [5 empty] | 3960000 |  |  | 1160000 | 3071000 |  |  |  |  | 8191000
| Transportation & Mobile Equip-DP | Material - Direct Purchase | Material Entries <$5,000 |  |  |  | 2804.8 | 2016.97 |  |  |  | 5.87 | 88.25 | 925.58 | 44.87 | 5886.34
|  |  | Transportation & Mobile Equip-DP |  |  |  | 10908.74 | 16828.8 |  |  |  |  | 48750 | 146250 |  | 222737.54
|  | Material - Direct Purchase Total |  |  |  |  | 13713.54 | 18845.77 |  |  |  | 5.87 | 48838.25 | 147175.58 | 44.87 | 228623.88
| Transportation & Mobile Equip-DP Total | [5 empty] | 13713.54 | 18845.77 |  |  |  | 5.87 | 48838.25 | 147175.58 | 44.87 | 228623.88
| Wire, Cable & Bus Bar-DP | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | 955.1 | 204.6 |  |  | 1159.7
|  | Material - Direct Purchase Total | [9 empty] | 955.1 | 204.6 |  |  | 1159.7
| Wire, Cable & Bus Bar-DP Total | [10 empty] | 955.1 | 204.6 |  |  | 1159.7
2. Material Total |  |  |  | 16130.83 | 727475.23 | 1804828.55 | 6062006.85 | 659817.48 | 871031.8 | 1435999.21 | 3819256.1 | 382189.29 | 639505.55 | 269988.36 | 2017352.77 | 18705582.02
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 |  | 375 | 375 |  |  |  | 13487.6 |  | 8370 | 11618.95 | 8688.75 | 20868.45 | 63783.75
|  | Contract Total |  |  | 375 | 375 |  |  |  | 13487.6 |  | 8370 | 11618.95 | 8688.75 | 20868.45 | 63783.75
| Construction Management Services Total |  |  |  | 375 | 375 |  |  |  | 13487.6 |  | 8370 | 11618.95 | 8688.75 | 20868.45 | 63783.75
| Construction Services - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -970.2 | 970.2 |  |  | 0
|  | Contract Total | [9 empty] | -970.2 | 970.2 |  |  | 0
| Construction Services - Correction Total | [10 empty] | -970.2 | 970.2 |  |  | 0
| Construction, Civil/Structural | Contract | Contract Entries <$50,000 | [5 empty] | 2873.69 | [6 empty] | 2873.69
|  | Contract Total | [6 empty] | 2873.69 | [6 empty] | 2873.69
| Construction, Civil/Structural Total | [7 empty] | 2873.69 | [6 empty] | 2873.69
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 498.1 | 498.1
|  | Labor Total | [12 empty] | 498.1 | 498.1
| ELEC SYS PLANNING Total | [13 empty] | 498.1 | 498.1
| Electrical Construction, Substations | Contract | PAR ELECTRICAL CONTRACTORS INC |  | 323527.44 |  | 1287294.21 | 2316940.58 | 135878.07 |  | 148600.7 |  |  |  |  | 4212241
|  |  | WILSON UTILITY CONSTRUCTION | [8 empty] | 397029.36 | 406061.37 | 520054.19 | 2080867.82 | 3404012.74
|  | Contract Total |  |  | 323527.44 |  | 1287294.21 | 2316940.58 | 135878.07 |  | 148600.7 | 397029.36 | 406061.37 | 520054.19 | 2080867.82 | 7616253.74
| Electrical Construction, Substations Total |  |  |  | 323527.44 |  | 1287294.21 | 2316940.58 | 135878.07 |  | 148600.7 | 397029.36 | 406061.37 | 520054.19 | 2080867.82 | 7616253.74
| ENGINEERING | Labor | Labor Entries <$5,000 |  |  | 858.37 | 768.27 |  |  |  |  | 333.74 | 161.81 | 329.73 |  | 2451.92
|  | Labor Total |  |  |  | 858.37 | 768.27 |  |  |  |  | 333.74 | 161.81 | 329.73 |  | 2451.92
| ENGINEERING Total |  |  |  |  | 858.37 | 768.27 |  |  |  |  | 333.74 | 161.81 | 329.73 |  | 2451.92
| Hauling / Industrial Moving Services | Contract | Contract Entries <$50,000 | [5 empty] | 1733.25 |  | 1221 |  | 2479.5 | 2619.5 |  | 8053.25
|  | Contract Total | [6 empty] | 1733.25 |  | 1221 |  | 2479.5 | 2619.5 |  | 8053.25
| Hauling / Industrial Moving Services Total | [7 empty] | 1733.25 |  | 1221 |  | 2479.5 | 2619.5 |  | 8053.25
| Major Construction, Turnkey, Trans/Subs | Contract | Contract Entries <$50,000 | [6 empty] | 6933.57 | 20949.61 | 21038.59 |  |  |  | 48921.77
|  | Contract Total | [7 empty] | 6933.57 | 20949.61 | 21038.59 |  |  |  | 48921.77
| Major Construction, Turnkey, Trans/Subs Total | [8 empty] | 6933.57 | 20949.61 | 21038.59 |  |  |  | 48921.77
| SC&M | Labor | Labor Entries <$5,000 | 740.43 | 791.04 | 1101.24 | 1638.93 | 1764.17 | 2307.73 | 2573.07 | 3141.71 | 2727.65 | 1757.21 | 596.27 | 1174.35 | 20313.8
|  | Labor Total |  | 740.43 | 791.04 | 1101.24 | 1638.93 | 1764.17 | 2307.73 | 2573.07 | 3141.71 | 2727.65 | 1757.21 | 596.27 | 1174.35 | 20313.8
| SC&M Total |  |  | 740.43 | 791.04 | 1101.24 | 1638.93 | 1764.17 | 2307.73 | 2573.07 | 3141.71 | 2727.65 | 1757.21 | 596.27 | 1174.35 | 20313.8
| SCM HOME CENTER | Labor | Labor Entries <$5,000 |  |  | 125.78 | 123.53 | 623.15 | [5 empty] | 140.77 |  | 1013.23
|  | Labor Total |  |  |  | 125.78 | 123.53 | 623.15 | [5 empty] | 140.77 |  | 1013.23
| SCM HOME CENTER Total |  |  |  |  | 125.78 | 123.53 | 623.15 | [5 empty] | 140.77 |  | 1013.23
| Short Term Equipment Rent | Contract | Contract Entries <$50,000 | [5 empty] | 22189.13 |  | 1249.9 | 8075.87 |  | 4968.37 | 1491.77 | 37975.04
|  | Contract Total | [6 empty] | 22189.13 |  | 1249.9 | 8075.87 |  | 4968.37 | 1491.77 | 37975.04
| Short Term Equipment Rent Total | [7 empty] | 22189.13 |  | 1249.9 | 8075.87 |  | 4968.37 | 1491.77 | 37975.04
| TSD-HERC - Crane Svs | Labor | Labor Entries <$5,000 | [5 empty] | 82 |  | 82 |  | 82 | 82 |  | 328
|  | Labor Total | [6 empty] | 82 |  | 82 |  | 82 | 82 |  | 328
| TSD-HERC - Crane Svs Total | [7 empty] | 82 |  | 82 |  | 82 | 82 |  | 328
| TSD-HERC - Rental | Labor | Labor Entries <$5,000 | [8 empty] | 82 | 410 | 246 | 164 | 902
|  | Labor Total | [9 empty] | 82 | 410 | 246 | 164 | 902
| TSD-HERC - Rental Total | [10 empty] | 82 | 410 | 246 | 164 | 902
3. Construction Total |  |  |  | 740.43 | 324693.48 | 2460.39 | 1289824.94 | 2319327.9 | 165063.87 | 22994.24 | 175244.92 | 436687.01 | 423541.04 | 537725.58 | 2105064.49 | 7803368.29
4. Allocated | Chargebacks | Chargeback | Chargeback Entries <$5,000 | 72759.87 | -54964.74 | -13797.04 | 418091.49 | -568130.73 | 169527.92 | 14998.74 | -550123.52 | -111758.18 | -52915.97 | 12394.43 | 6524.75 | -657392.98
|  |  | COLORADO RIVER SUB COST ALLOCATION | 15223.24 | 63674.78 | 289492.5 | 207176 | 320459.94 | 185898.21 | 364199.89 | 238583.79 | 32374.33 | 305691.82 | 275152.71 | 554215.01 | 2852142.22
|  |  | CRS Switchyard & Expansion Share Costs |  | 105596.05 |  |  | 447056.66 | 17922.66 |  | 647354.57 |  |  |  |  | 1217929.94
|  |  | MATERIAL MANAGEM | 5711.48 | [6 empty] | 13004.4 | 21200.34 |  |  | 46834.26 | 86750.48
|  |  | PDP- Colorado Rvr Switchyd/Sub-MPO | 159728.55 | 238475.83 | 382068.9 | 376970.85 | 223894.27 | 85080.04 | 330601.74 | 57598.09 |  | 145699.74 | 86261.21 | 87351.79 | 2173731.01
|  |  | PDP-Colorado River Substation-MPO |  |  | 119225.4 |  |  |  |  | 54703.2 |  |  |  |  | 173928.6
|  |  | PDP-DPV2 General Mtg Support-MPO |  | 56172.62 |  | 7583.07 | [8 empty] | 63755.69
|  |  | PROCUREMENT TDBU |  | 6591.13 | 11052.44 | 45567.68 | 19229.01 | 6131.37 | 8881.25 | 23832.04 |  | 15317.14 |  | 22862.03 | 159464.09
|  | Chargeback Total |  | 253423.14 | 415545.67 | 788042.2 | 1055389.09 | 442509.15 | 464560.2 | 718681.62 | 484952.57 | -58183.51 | 413792.73 | 373808.35 | 717787.84 | 6070309.05
| Chargebacks Total |  |  | 253423.14 | 415545.67 | 788042.2 | 1055389.09 | 442509.15 | 464560.2 | 718681.62 | 484952.57 | -58183.51 | 413792.73 | 373808.35 | 717787.84 | 6070309.05
| Labor - Other | Labor | ALH- Sub Order for Colorado River Sub Ex | [9 empty] | 11814.98 | 30274.25 | 62327.73 | 104416.96
|  |  | Division Overhead |  | 90900.51 | 127292.66 | 517171.92 | 201127.53 | 62682.56 | 104051.05 | 275045.59 |  | 189425.26 | 9506.36 | 138454.19 | 1715657.63
|  |  | Labor Entries <$5,000 | 4178.74 | 2281.51 | 2814.65 | 2201.5 | 4142.81 | 3449.36 | 3451.55 | -18971.2 | -39833.6 | 7516.24 | 9559.32 | 2788.99 | -16420.13
|  |  | Paid Absence | [9 empty] | 5925.69 |  |  | 5925.69
|  | Labor Total |  | 4178.74 | 93182.02 | 130107.31 | 519373.42 | 205270.34 | 66131.92 | 107502.6 | 256074.39 | -39833.6 | 214682.17 | 49339.93 | 203570.91 | 1809580.15
| Labor - Other Total |  |  | 4178.74 | 93182.02 | 130107.31 | 519373.42 | 205270.34 | 66131.92 | 107502.6 | 256074.39 | -39833.6 | 214682.17 | 49339.93 | 203570.91 | 1809580.15
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -30244.37 | 30244.37 |  |  | 0
|  | Overhead Total | [9 empty] | -30244.37 | 30244.37 |  |  | 0
| Overhead Correction Total | [10 empty] | -30244.37 | 30244.37 |  |  | 0
4. Allocated Total |  |  |  | 257601.88 | 508727.69 | 918149.51 | 1574762.51 | 647779.49 | 530692.12 | 826184.22 | 741026.96 | -128261.48 | 658719.27 | 423148.28 | 921358.75 | 7879889.2
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 156292.6 | 10104.51 | [6 empty] | 284147.24 | 450544.35
|  |  | AFUDC - Debt/Equity |  |  | 92082.5 | -92082.5 | [8 empty] | 0
|  |  | Capitalized Overhead - A&G | 15728.56 | 45929.1 | 97519.32 | 318507.68 | 302762.53 | 56361.85 | 82076.91 | 132580.29 | 35761.89 | 44475.43 | 38020.17 | 151706.51 | 1321430.24
|  |  | Capitalized Overhead - Inj & Damages | 133.68 | 1936.47 | 2477.54 | 6027.39 | 3975.58 | 1516.46 | 1525.37 | 4799.76 | 1544.35 | -1483.27 | 939 | 2933.04 | 26325.37
|  |  | Capitalized Overhead - P&B/Payroll Tax | 17059.9 | 26829.99 | 34023.02 | 30035.92 | 56940.61 | 38041.76 | 31215.32 | -32760.33 | 1071.19 | 47140.61 | 98536.61 | 345522.67 | 693657.27
|  |  | Corporate Overheads Correction |  |  |  |  | -177640.81 | [7 empty] | -177640.81
|  | Non Budgeted Total |  | 32922.14 | 74695.56 | 226102.38 | 418781.09 | 196142.42 | 95920.07 | 114817.6 | 104619.72 | 38377.43 | 90132.77 | 137495.78 | 784309.46 | 2314316.42
| Non Budget - Other Total |  |  | 32922.14 | 74695.56 | 226102.38 | 418781.09 | 196142.42 | 95920.07 | 114817.6 | 104619.72 | 38377.43 | 90132.77 | 137495.78 | 784309.46 | 2314316.42
5. Corporate Overhead Total |  |  |  | 32922.14 | 74695.56 | 226102.38 | 418781.09 | 196142.42 | 95920.07 | 114817.6 | 104619.72 | 38377.43 | 90132.77 | 137495.78 | 784309.46 | 2314316.42
Grand Total |  |  |  | 409721.07 | 2266843.43 | 3104959.72 | 10650667.44 | 1846152.14 | 1648499.38 | 2601624.61 | 4859842.51 | 1193798.95 | 1756861.53 | 1668544.09 | 5470587.31 | 37478102.18

## West of Devers
WO | SumOfYTD2012 | Order | Project
800062511- Morongo Relocation: Preliminary Engineer | 8860283.01 | 800062511 | West of Devers (WOD)

## 800062511
Pin: 6420 | Project: West of Devers (WOD)
Order: 800062511 | 800062511- Morongo Relocation: Preliminary Engineer
Sum of Amt |  |  |  | Year | Month
|  |  |  | 2012 | [11 empty] | 2012 Total
SubCategory | Prime | Group | Details | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Project Support | Consultants / Prof Services - Correction | Contract | Consultants / Prof Services - Correction | [9 empty] | 1771472.12 |  |  | 1771472.12
|  |  | Contract Entries <$50,000 | [8 empty] | -1771472.12 |  |  |  | -1771472.12
|  | Contract Total | [9 empty] | -1771472.12 | 1771472.12 |  |  | 0
| Consultants / Prof Services - Correction Total | [10 empty] | -1771472.12 | 1771472.12 |  |  | 0
| ELEC SYS PLANNING | Labor | Labor Entries <$5,000 | [11 empty] | 510.27 | 510.27
|  | Labor Total | [12 empty] | 510.27 | 510.27
| ELEC SYS PLANNING Total | [13 empty] | 510.27 | 510.27
| ENG ADVANCEMENT | Labor | Labor Entries <$5,000 | 6712.22 | 1102.23 | 374.73 | [9 empty] | 8189.18
|  | Labor Total |  | 6712.22 | 1102.23 | 374.73 | [9 empty] | 8189.18
| ENG ADVANCEMENT Total |  |  | 6712.22 | 1102.23 | 374.73 | [9 empty] | 8189.18
| ENGINEERING | Labor | Labor Entries <$5,000 | 901.04 | 127.72 | 219.63 |  | 566.71 | 848.79 | 529.22 | [5 empty] | 3193.11
|  | Labor Total |  | 901.04 | 127.72 | 219.63 |  | 566.71 | 848.79 | 529.22 | [5 empty] | 3193.11
| ENGINEERING Total |  |  | 901.04 | 127.72 | 219.63 |  | 566.71 | 848.79 | 529.22 | [5 empty] | 3193.11
| Engineering/Technical Professional Servi | Contract | Contract Entries <$50,000 | 3456 | 2160 | [10 empty] | 5616
|  | Contract Total |  | 3456 | 2160 | [10 empty] | 5616
| Engineering/Technical Professional Servi Total |  |  | 3456 | 2160 | [10 empty] | 5616
| IMM/Allocated - Correction | IMM Correction | IMM/Allocated - Correction | [8 empty] | 2042243.32 | -2042243.32 |  |  | 0
|  | IMM Correction Total | [9 empty] | 2042243.32 | -2042243.32 |  |  | 0
| IMM/Allocated - Correction Total | [10 empty] | 2042243.32 | -2042243.32 |  |  | 0
| Labor - Other | Labor | Labor - Other | [9 empty] | 29040.83 |  |  | 29040.83
|  |  | Labor Correction | [9 empty] | 144478.83 |  |  | 144478.83
|  |  | Labor Entries <$5,000 | 2595.48 | 2167.03 | 1683.17 | 3168.63 | 2059.3 | 2340.37 | 1811.83 | 1869.67 | -12641.5 | -154148.34 | 1355.37 | 9237.42 | -138501.57
|  |  | SUBORDER*ENGINEERING ONLY-West of Dever | [10 empty] | 6411.33 |  | 6411.33
|  | Labor Total |  | 2595.48 | 2167.03 | 1683.17 | 3168.63 | 2059.3 | 2340.37 | 1811.83 | 1869.67 | -12641.5 | 19371.32 | 7766.7 | 9237.42 | 41429.42
| Labor - Other Total |  |  | 2595.48 | 2167.03 | 1683.17 | 3168.63 | 2059.3 | 2340.37 | 1811.83 | 1869.67 | -12641.5 | 19371.32 | 7766.7 | 9237.42 | 41429.42
| Legal Professional Services (OC & Attys) | Contract | Contract Entries <$50,000 |  | 4402.5 | [10 empty] | 4402.5
|  | Contract Total |  |  | 4402.5 | [10 empty] | 4402.5
| Legal Professional Services (OC & Attys) Total |  |  |  | 4402.5 | [10 empty] | 4402.5
| Other | Other | Other | -20653.5 |  | 24.98 | 15.54 | 22.2 | 40.53 | 9.44 | 13.32 | -56097.83 | 56097.83 |  | 3336 | -17191.49
|  | Other Total |  | -20653.5 |  | 24.98 | 15.54 | 22.2 | 40.53 | 9.44 | 13.32 | -56097.83 | 56097.83 |  | 3336 | -17191.49
| Other Total |  |  | -20653.5 |  | 24.98 | 15.54 | 22.2 | 40.53 | 9.44 | 13.32 | -56097.83 | 56097.83 |  | 3336 | -17191.49
| SC&M | Labor | Labor Entries <$5,000 |  |  |  |  | 259.74 | [7 empty] | 259.74
|  | Labor Total | [5 empty] | 259.74 | [7 empty] | 259.74
| SC&M Total | [6 empty] | 259.74 | [7 empty] | 259.74
| Temporary / Supplemental - Correction | Contract | Contract Entries <$50,000 | [8 empty] | -599.48 | 599.48 |  |  | 0
|  | Contract Total | [9 empty] | -599.48 | 599.48 |  |  | 0
| Temporary / Supplemental - Correction Total | [10 empty] | -599.48 | 599.48 |  |  | 0
| Temporary/Supplementary - Technical/Prof | Contract | Contract Entries <$50,000 | 31905.12 | 4590.6 | 3978.66 | 9021.12 | 7297.9 | 12106.36 | 18901.95 | 2126.53 | 11129.38 | 6695.1 | 13189.71 | 19941.89 | 140884.32
|  | Contract Total |  | 31905.12 | 4590.6 | 3978.66 | 9021.12 | 7297.9 | 12106.36 | 18901.95 | 2126.53 | 11129.38 | 6695.1 | 13189.71 | 19941.89 | 140884.32
| Temporary/Supplementary - Technical/Prof Total |  |  | 31905.12 | 4590.6 | 3978.66 | 9021.12 | 7297.9 | 12106.36 | 18901.95 | 2126.53 | 11129.38 | 6695.1 | 13189.71 | 19941.89 | 140884.32
| Temporary/Supplementary - Trade/Labor | Contract | Contract Entries <$50,000 | 135.52 | [11 empty] | 135.52
|  | Contract Total |  | 135.52 | [11 empty] | 135.52
| Temporary/Supplementary - Trade/Labor Total |  |  | 135.52 | [11 empty] | 135.52
| TRANSMISSION | Labor | Labor Entries <$5,000 |  |  | 191.1 | [9 empty] | 191.1
|  | Labor Total |  |  |  | 191.1 | [9 empty] | 191.1
| TRANSMISSION Total |  |  |  |  | 191.1 | [9 empty] | 191.1
| TRNS CAPITAL | Labor | Labor Entries <$5,000 | 675.79 | 396.37 | 1528.5 | 908.22 | 1154.67 |  |  | 102.8 |  | 205.42 |  |  | 4971.77
|  | Labor Total |  | 675.79 | 396.37 | 1528.5 | 908.22 | 1154.67 |  |  | 102.8 |  | 205.42 |  |  | 4971.77
| TRNS CAPITAL Total |  |  | 675.79 | 396.37 | 1528.5 | 908.22 | 1154.67 |  |  | 102.8 |  | 205.42 |  |  | 4971.77
1. Project Support Total |  |  |  | 25727.67 | 14946.45 | 8000.77 | 13113.51 | 11360.52 | 15336.05 | 21252.44 | 4112.32 | 212561.77 | -187802.05 | 20956.41 | 33025.58 | 192591.44
2. Material | Material - Direct Purchase - Correction | Material - Direct Purchase | Material Entries <$5,000 | [8 empty] | -59.32 | 59.32 |  |  | 0
|  | Material - Direct Purchase Total | [9 empty] | -59.32 | 59.32 |  |  | 0
| Material - Direct Purchase - Correction Total | [10 empty] | -59.32 | 59.32 |  |  | 0
| Material - Other | Material | Material - Other | 0.66 |  |  | 1.91 |  | 1.13 | 0.49 | 3.7 | 60.26 | 65.32 | 27.44 | 41.65 | 202.56
|  | Material Total |  | 0.66 |  |  | 1.91 |  | 1.13 | 0.49 | 3.7 | 60.26 | 65.32 | 27.44 | 41.65 | 202.56
| Material - Other Total |  |  | 0.66 |  |  | 1.91 |  | 1.13 | 0.49 | 3.7 | 60.26 | 65.32 | 27.44 | 41.65 | 202.56
2. Material Total |  |  |  | 0.66 |  |  | 1.91 |  | 1.13 | 0.49 | 3.7 | 0.94 | 124.64 | 27.44 | 41.65 | 202.56
3. Construction | Construction Management Services | Contract | Contract Entries <$50,000 | [5 empty] | 4448 | 2224 |  |  | 165 | 1112 | 4576.8 | 12525.8
|  | Contract Total | [6 empty] | 4448 | 2224 |  |  | 165 | 1112 | 4576.8 | 12525.8
| Construction Management Services Total | [7 empty] | 4448 | 2224 |  |  | 165 | 1112 | 4576.8 | 12525.8
| Construction, Earthwork | Contract | Contract Entries <$50,000 |  | -75514 | [10 empty] | -75514
|  | Contract Total |  |  | -75514 | [10 empty] | -75514
| Construction, Earthwork Total |  |  |  | -75514 | [10 empty] | -75514
| GRID OPS | Labor | Labor Entries <$5,000 | [8 empty] | 234.97 | 271.57 | 192.9 | 200.27 | 899.71
|  | Labor Total | [9 empty] | 234.97 | 271.57 | 192.9 | 200.27 | 899.71
| GRID OPS Total | [10 empty] | 234.97 | 271.57 | 192.9 | 200.27 | 899.71
| TRANSMISSION | Labor | Labor Entries <$5,000 | 493.79 |  | 203.59 |  |  | 153.42 | [6 empty] | 850.8
|  | Labor Total |  | 493.79 |  | 203.59 |  |  | 153.42 | [6 empty] | 850.8
| TRANSMISSION Total |  |  | 493.79 |  | 203.59 |  |  | 153.42 | [6 empty] | 850.8
3. Construction Total |  |  |  | 493.79 | -75514 | 203.59 |  |  | 4601.42 | 2224 |  | 234.97 | 436.57 | 1304.9 | 4777.07 | -61237.69
4. Allocated | Chargebacks | Chargeback | BA-West of Devers-MPO | 5351.71 | 28666.72 | 25474.04 | 248662.14 | 225573.97 | 410006.68 | 206115.91 | 151001.28 |  | 301722.74 | 112286.94 | 71184.11 | 1786046.24
|  |  | Chargeback Entries <$5,000 | 17651.54 | 16586.11 | 22232.24 | -10258.61 | -158741.63 | -169419.07 | -30790.67 | -42734.07 | 6920.3 | -11555.07 | 14620.72 | -189755.89 | -535244.1
|  |  | Law/4504-5013--WEST OF DEVERS 230KV |  | 23490 | 27226.87 | 18940.34 | 15424.31 | 7544.72 | 5758.57 | 26545.49 |  | 54500.8 | 64326.9 | 54160.65 | 297918.65
|  |  | PDP-West of Devers-MPO | 47966.15 | 102179.48 | 218200.46 | 395632.9 | 91536.15 | 28884.75 | 24986.18 | 31309.43 |  | 57964.39 | 166050.51 | 44534.23 | 1209244.63
|  |  | WOD - TDBU LICENSING | 143949.55 | 214307.17 | 259741.94 | 197508.66 | 258177.19 | 354509.74 | 522549.24 | 641658.85 | 271126.5 | 629578.85 | 228668.47 | 649793.29 | 4371569.45
|  | Chargeback Total |  | 214918.95 | 385229.48 | 552875.55 | 850485.43 | 431969.99 | 631526.82 | 728619.23 | 807780.98 | 278046.8 | 1032211.71 | 585953.54 | 629916.39 | 7129534.87
| Chargebacks Total |  |  | 214918.95 | 385229.48 | 552875.55 | 850485.43 | 431969.99 | 631526.82 | 728619.23 | 807780.98 | 278046.8 | 1032211.71 | 585953.54 | 629916.39 | 7129534.87
| Labor - Other | Labor | Division Overhead | [9 empty] | 92329.64 |  |  | 92329.64
|  |  | Labor Entries <$5,000 | 3569.53 | -1451.14 | 1399.89 | 967.13 | 1105.75 | 1503.17 | 1554.69 | 600.03 | -92074.42 | 43467.29 | 3027.87 | 2764.1 | -33566.11
|  | Labor Total |  | 3569.53 | -1451.14 | 1399.89 | 967.13 | 1105.75 | 1503.17 | 1554.69 | 600.03 | -92074.42 | 135796.93 | 3027.87 | 2764.1 | 58763.53
| Labor - Other Total |  |  | 3569.53 | -1451.14 | 1399.89 | 967.13 | 1105.75 | 1503.17 | 1554.69 | 600.03 | -92074.42 | 135796.93 | 3027.87 | 2764.1 | 58763.53
| Overhead Correction | Overhead | Overhead Correction | [8 empty] | -39955.16 | 39955.16 |  |  | 0
|  | Overhead Total | [9 empty] | -39955.16 | 39955.16 |  |  | 0
| Overhead Correction Total | [10 empty] | -39955.16 | 39955.16 |  |  | 0
4. Allocated Total |  |  |  | 218488.48 | 383778.34 | 554275.44 | 851452.56 | 433075.74 | 633029.99 | 730173.92 | 808381.01 | 146017.22 | 1207963.8 | 588981.41 | 632680.49 | 7188298.4
5. Corporate Overhead | Non Budget - Other | Non Budgeted | Ad Valorem Tax |  |  |  | 42529.27 | 2759.99 | [6 empty] | 81449.31 | 126738.57
|  |  | Capitalized Overhead - A&G | 14809.85 | 9468.84 | 20049.4 | 30831 | 36990.2 | 23304.64 | 26462.87 | 22981.74 | 16074.49 | 26372.21 | 16154.18 | 18732.25 | 262231.67
|  |  | Capitalized Overhead - Inj & Damages | 103.02 | 315.85 | 146.71 | 291.08 | 100.09 | 377.77 | 97.65 | 134.42 | 1791.45 | -4801.25 | 455.32 | -8.6 | -996.49
|  |  | Capitalized Overhead - P&B/Payroll Tax | 55550.21 | 92982.33 | 93335.87 | 101574.09 | 176073.02 | 150545.78 | 131583.01 | 85707.47 | -103559.98 | 145829.79 | 82524.89 | 293389.97 | 1305536.45
|  |  | Corporate Overheads Correction |  |  |  |  | -153081.9 | [7 empty] | -153081.9
|  | Non Budgeted Total |  | 70463.08 | 102767.02 | 113531.98 | 175225.44 | 62841.4 | 174228.19 | 158143.53 | 108823.63 | -85694.04 | 167400.75 | 99134.39 | 393562.93 | 1540428.3
| Non Budget - Other Total |  |  | 70463.08 | 102767.02 | 113531.98 | 175225.44 | 62841.4 | 174228.19 | 158143.53 | 108823.63 | -85694.04 | 167400.75 | 99134.39 | 393562.93 | 1540428.3
5. Corporate Overhead Total |  |  |  | 70463.08 | 102767.02 | 113531.98 | 175225.44 | 62841.4 | 174228.19 | 158143.53 | 108823.63 | -85694.04 | 167400.75 | 99134.39 | 393562.93 | 1540428.3
Grand Total |  |  |  | 315173.68 | 425977.81 | 676011.78 | 1039793.42 | 507277.66 | 827196.78 | 911794.38 | 921320.66 | 273120.86 | 1188123.71 | 710404.55 | 1064087.72 | 8860283.01