## DCR
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
4847 | Devers-Colorado River |  | 238832.2736 | 21677 | 260509.2736
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 6907.4682 | 1437.1 | 8344.5682
| 2 | Engineering and Design | 2960.3435 | 615.9 | 3576.2435
| 3 | Regulatory, Licensing, and Legal Costs | 1688 | 648 | 2336
| Total |  | 11555.8117 | 2701 | 14256.8117
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 1858.0648 | 0 | 1858.0648
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | 1858.0648 | 0 | 1858.0648
Construction
| 1 | Civil and Structural Construction | 5000 | 8500 | 13500
| 2 | Electrical Construction | 163000 | 8500 | 171500
| 3 | Construction Management Services | 15348.0965 | 0 | 15348.0965
| Total |  | 183348.0965 | 17000 | 200348.0965
Environmental
| 1 | Environmental | 14145.1031 | 1197 | 15342.1031
| Total |  | 14145.1031 | 1197 | 15342.1031
Real Properties
| 1 | Real Properties Acquisitions | 100 | 0 | 100
| Total |  | 100 | 0 | 100
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 7569.9436 | 779 | 8348.9436
| Total |  | 7569.9436 | 779 | 8348.9436
Contingency
| 1 | Contingency | 20255.2539 | 0 | 20255.2539
| Total |  | 20255.2539 | 0 | 20255.2539

## TRTP Seg 3B
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
7183 | TRTP Segment 3B |  |  |  | 2579.637 | 0 | 2579.637
[8 empty] | 17693 | 7401 | 2970 | 28064
[8 empty] | TL | HW SS | AC Mitigation | Total
| Project Support | [6 empty] | 1370 | 922 | 544 | 2836
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 42.56 | 0 | 42.56 | 135 | 142 | 109 | 386
| 2 | 16 |  | Engineering and Design | 164.2 | 0 | 164.2 | 377 | 0 | 339 | 716
| 3 | 20 |  | Environmental | 476.313 | 0 | 476.313 | 833 | 755 | 86 | 1674
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 69.1 | 0 | 69.1 | 25 | 25 | 10 | 60
| Total |  |  |  | 752.173 | 0 | 752.173
| Materials | [6 empty] | 1053 | 1283 | 0 | 2336
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0 | 200 |  |  | 200
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0 | 100 |  |  | 100
| 3 |  |  | Transformers | 0 | 0 | 0 |  |  |  | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0 | 100 |  |  | 100
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0 |  | 670 |  | 670
| 6 |  |  | Civil Materials and Misc Hardware | 33.564 | 0 | 33.564 | 653 | 613 |  | 1266
| Total |  |  |  | 33.564 | 0 | 33.564
| Construction | [6 empty] | 13420 | 4706 | 2350 | 20476
| 1 |  |  | Civil and Structural Construction | 1442.4 | 0 | 1442.4 | 8789 | 3445 | 2350 | 14584
| 2 |  |  | Electrical Construction | 0 | 0 | 0 | 4431 | 1261 |  | 5692
| 3 |  |  | Construction Management Services | 76.4 | 0 | 76.4 | 200 |  |  | 200
| Total |  |  |  | 1518.8 | 0 | 1518.8
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 13.4 | 0 | 13.4
| Total |  |  |  | 13.4 | 0 | 13.4
| Allocated | [6 empty] | 1850 | 490 | 76 | 2416
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 261.7 | 0 | 261.7 | 1850 | 490 | 76 | 2416
| Total |  |  |  | 261.7 | 0 | 261.7
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 3C
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
7014 | TRTP Segment 3C |  |  |  | 6458.87 | 0 | 6458.87
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 84.1 | 0 | 84.1
| 2 | 16 |  | Engineering and Design | 208.3 | 0 | 208.3
| 3 | 20 |  | Environmental | 5 | 0 | 5
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 297.4 | 0 | 297.4
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 354.4 | 0 | 354.4
| Total |  |  |  | 354.4 | 0 | 354.4
Construction
| 1 |  |  | Civil and Structural Construction | 1000 | 0 | 1000
| 2 |  |  | Electrical Construction Inc. Wire Stringing & Testing | 3109.9 | 0 | 3109.9
| 3 |  |  | Transformers Setting & Testing | 1002 | 0 | 1002
| Total |  |  |  | 5111.9 | 0 | 5111.9
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 695.17 | 0 | 695.17
| Total |  |  |  | 695.17 | 0 | 695.17
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 4
PIN # | Description |  |  |  | Forecast | Forecast |  |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6435 | TRTP Segment 4 |  |  |  | 8765.88 | 0 | 8765.88
[8 empty] | Cuml WP1 | 13796.88 | 1686 | 15482.88
0
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 212 | 0 | 212
| 2 | 16 |  | Engineering and Design | 304 | 0 | 304
| 3 | 20 |  | Environmental | 2163 | 0 | 2163
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 2679 | 0 | 2679
Materials
| 1 |  |  | Steel and Hardware (e.g. Yard 28 Relocation and Storage) | 1403 | 0 | 1403
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 270 | 0 | 270
| Total |  |  |  | 1673 | 0 | 1673
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 2501.88 | 0 | 2501.88
| 3 |  |  | Construction Management Services | 613 | 0 | 613
| Total |  |  |  | 3114.88 | 0 | 3114.88
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 667 | 0 | 667
| Total |  |  |  | 667 | 0 | 667
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 632 | 0 | 632
| Total |  |  |  | 632 | 0 | 632
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 5
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
5472 | TRTP Segment 5 |  |  |  | 3013 | 1686 | 4699
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 964 | 0 | 964
| 2 | 16 |  | Engineering and Design | -304 | 0 | -304
| 3 | 20 |  | Environmental | 2450 | 1686 | 4136
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 1037 | 0 | 1037
| Total |  |  |  | 4147 | 1686 | 5833
Materials
| 1 |  |  | Steel and Hardware (e.g. Marker Balls) | -1321 | 0 | -1321
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | -270 | 0 | -270
| Total |  |  |  | -1591 | 0 | -1591
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | -2058 | 0 | -2058
| 3 |  |  | Construction Management Services | 940 | 0 | 940
| Total |  |  |  | -1118 | 0 | -1118
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 1061 | 0 | 1061
| Total |  |  |  | 1061 | 0 | 1061
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 514 | 0 | 514
| Total |  |  |  | 514 | 0 | 514
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 6
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
5243 | TRTP Segment 6 |  |  |  | 89588.3406 | 22778.2656 | 112366.6062
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 8270.9367 | 760 | 9030.9367
| 2 | 16 |  | Engineering and Design | 483.1546 | 40 | 523.1546
| 3 | 20 |  | Environmental | 5223.6477 | 6532.7693 | 11756.4169
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 13977.739 | 7332.7693 | 21310.5082
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 291.6649 | 0 | 291.6649
| 2 |  |  | Conductor and Conductor Hardware |  | 0 | 0
| 3 |  |  | Transformers |  | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) |  | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) |  | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware |  | 0 | 0
| Total |  |  |  | 291.6649 | 0 | 291.6649
Construction
| 1 |  |  | Civil and Structural Construction | 69829.2902 | 15013.777 | 84843.0672
| 2 |  |  | Electrical Construction | 0 |  | 0
| 3 |  |  | Construction Management Services |  |  | 0
| Total |  |  |  | 69829.2902 | 15013.777 | 84843.0672
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0.77779 | 0 | 0.77779
| Total |  |  |  | 0.77779 | 0 | 0.77779
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 5488.8687 | 431.7193 | 5920.588
| Total |  |  |  | 5488.8687 | 431.7193 | 5920.588
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 7
PIN # | Description |  |  |  | Forecast | Forecast |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6438 | TRTP Segment 7 |  |  |  | 22505 | 22017.78 | 44522.78
[8 empty] | 85145 | 81883.78 | 167028.78
173460
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 3000 | 2575 | 5575
| 2 | 16 |  | Engineering and Design | 288 | 0 | 288
| 3 | 20 |  | Environmental | 4708 | 8253.78 | 12961.78
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 7996 | 10828.78 | 18824.78
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Construction
| 1 |  |  | Civil and Structural Construction | 2000 | 0 | 2000
| 2 |  |  | Electrical Construction | 7407 | 10191 | 17598
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 9407 | 10191 | 19598
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 3100 | 0 | 3100
| Total |  |  |  | 3100 | 0 | 3100
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 2002 | 998 | 3000
| Total |  |  |  | 2002 | 998 | 3000
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 8
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6439 | TRTP Segment 8 |  |  |  | 62640 | 59866 | 122506
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 9501 | 6270 | 15771
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 20 |  | Environmental | 7575 | 12600 | 20175
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 17076 | 18870 | 35946
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 5367 | 37400 | 42767
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 5367 | 37400 | 42767
Construction
| 1 |  |  | Civil and Structural Construction | 2109 | 0 | 2109
| 2 |  |  | Electrical Construction | 31753 | 0 | 31753
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 33862 | 0 | 33862
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 360 | 0 | 360
| Total |  |  |  | 360 | 0 | 360
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 5975 | 3596 | 9571
| Total |  |  |  | 5975 | 3596 | 9571
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 9
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6440 | TRTP Segment 9 |  | 21384.124 | 6023.712 | 27407.836
Project Support
| 1 | Windhub Sub | 104.3659 | 0 | 104.3659
| 2 | Whirlwind Sub | 831.1162 | 0 | 831.1162
| 3 | Antelope Sub | 611.2753 | 0 | 611.2753
| 4 | Vincent Sub | 1747.8419 | 1147 | 2894.8419
| 5 | Other Substations | 631.7757 | 156.432 | 788.2077
| Total |  | 3926.375 | 1303.432 | 5229.807
Materials
| 1 | Windhub Sub | -25.3 | 0 | -25.3
| 2 | Whirlwind Sub | 102.5093 | 0 | 102.5093
| 3 | Antelope Sub | 9.2173 | 0 | 9.2173
| 4 | Vincent Sub | 41.1565 | 100 | 141.1565
| 5 | Other Substations | 389.0578 | 0 | 389.0578
| Total |  | 516.6408 | 100 | 616.6408
Construction
| 1 | Windhub Sub | 799.2998 | 0 | 799.2998
| 2 | Whirlwind Sub | 1066.7331 | 0 | 1066.7331
| 3 | Antelope Sub | 62.7489 | 0 | 62.7489
| 4 | Vincent Sub | 11029.2165 | 3574 | 14603.2165
| 5 | Other Substations | 1756.9777 | 476.4 | 2233.3777
| Total |  | 14714.976 | 4050.4 | 18765.376
Real Properties
| 1 | Corporate Real Estate | 0.17957 | 0 | 0.17957
| Total |  | 0.17957 | 0 | 0.17957
Allocated
| 1 | Windhub Sub | 99.0892 | 0 | 99.0892
| 2 | Whirlwind Sub | 131.0099 | 0 | 131.0099
| 3 | Antelope Sub | 112.2106 | 0 | 112.2106
| 4 | Vincent Sub | 1438.5091 | 447 | 1885.5091
| 5 | Other Substations | 445.1339 | 122.88 | 568.0139
| Total |  | 2225.9527 | 569.88 | 2795.8327
Contingency
| 1 | Windhub Sub | 0 | 0 | 0
| 2 | Whirlwind Sub | 0 | 0 | 0
| 3 | Antelope Sub | 0 | 0 | 0
| 4 | Vincent Sub | 0 | 0 | 0
| 5 | Other Substations | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Note on D3: Heiss, Dean: Added in Order 900817489

## TRTP Seg 10
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6441 | TRTP Segment 10 |  |  |  | 2018 | 0 | 2018
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 355 | 0 | 355
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 20 |  | Environmental | 586 | 0 | 586
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 941 | 0 | 941
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles and Anchor Bolts) | 30 | 0 | 30
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 30 | 0 | 30
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 747 | 0 | 747
| Total |  |  |  | 747 | 0 | 747
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 300 | 0 | 300
| Total |  |  |  | 300 | 0 | 300
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 11
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6442 | TRTP Segment 11 |  |  |  | 21162.4349 | 62177.1741 | 83339.6091
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 4545.453 | 7766.25 | 12311.703
| 2 | 16 |  | Engineering and Design | 239.2344 | 408.75 | 647.9844
| 3 | 20 |  | Environmental | 2933.6717 | 7564.4655 | 10498.1372
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 7718.3591 | 15739.4655 | 23457.8246
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 8553.4871 |  | 8553.4871
| 2 |  |  | Conductor and Conductor Hardware |  | 3000 | 3000
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 8553.4871 | 3000 | 11553.4871
Construction
| 1 |  |  | Civil and Structural Construction | 3901.231 | 42310.314 | 46211.545
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 3901.231 | 42310.314 | 46211.545
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 3.8348 | 0 | 3.8348
| Total |  |  |  | 3.8348 | 0 | 3.8348
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 985.5229 | 1127.3946 | 2112.9175
| Total |  |  |  | 985.5229 | 1127.3946 | 2112.9175
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## EITP
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6551 | Eldorado-Ivanpah Transmission |  | 167426 | 1474 | 168900
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 3660 | 384 | 4044
| 2 | Engineering and Design | 5472 | 0 | 5472
| 3 | Regulatory and Licensing | 150 | 0 | 150
| Total |  | 9282 | 384 | 9666
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 685 | 0 | 685
| 2 | Conductor and Conductor Hardware | 273 | 0 | 273
| 3 | Transformers | 471 | 0 | 471
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 89 | 0 | 89
| 6 | Civil Materials and Misc Hardware | 2787 | 0 | 2787
| Total |  | 4305 | 0 | 4305
Construction
| 1 | Civil and Structural Construction |  |  | 0
| 2 | Electrical Construction | 125576 | 0 | 125576
| 3 | Construction Management Services | 7608 | 0 | 7608
| Total |  | 133184 | 0 | 133184
Environmental
| 1 | Environmental | 13556 | 1090 | 14646
| Total |  | 13556 | 1090 | 14646
Real Properties
| 1 | Real Properties Acquisitions | 183 | 0 | 183
| Total |  | 183 | 0 | 183
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 6916 | 0 | 6916
| Total |  | 6916 | 0 | 6916
Contingency
| 1 | Contingency |  |  | 0
| Total |  | 0 | 0 | 0

## Lugo-Pisgah
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
7018 | Lugo-Pisgah Transmission |  | 0 | 0 | 0
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 0 | 0 | 0
| 2 | Engineering and Design | 0 | 0 | 0
| 3 | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Construction
| 1 | Civil and Structural Construction | 0 | 0 | 0
| 2 | Electrical Construction | 0 | 0 | 0
| 3 | Construction Management Services | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Environmental
| 1 | Environmental |  |  | 0
| Total |  | 0 | 0 | 0
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## Red Bluff
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6929 | Red Bluff Substation |  | 81631.6 | 1668.648 | 83300.248
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 3000 | 598.648 | 3598.648
| 2 | Engineering and Design | 900 | 50 | 950
| 3 | Regulatory and Licensing | 100 | 20 | 120
| Total |  | 4000 | 668.648 | 4668.648
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) |  |  | 0
| 2 | Conductor and Conductor Hardware |  |  | 0
| 3 | Transformers |  |  | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) |  |  | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) |  |  | 0
| 6 | Civil Materials and Misc Hardware | 5700 |  | 5700
| Total |  | 5700 | 0 | 5700
Construction
| 1 | Civil and Structural Construction | 6000 |  | 6000
| 2 | Electrical Construction | 53441.6 |  | 53441.6
| 3 | Construction Management Services | 2700 |  | 2700
| Total |  | 62141.6 | 0 | 62141.6
Environmental
| 1 | Environmental | 2000 | 900 | 2900
| Total |  | 2000 | 900 | 2900
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 4000 | 100 | 4100
| Total |  | 4000 | 100 | 4100
Contingency
| 1 | Contingency | 3790 |  | 3790
| Total |  | 3790 | 0 | 3790

## CRSX
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
7076 | Colorado River Substation Expansion |  | 25666.78 | 649.266 | 26316.046
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 1200 | 549.266 | 1749.266
| 2 | Engineering and Design | 400 | 0 | 400
| 3 | Regulatory and Licensing | 50 | 0 | 50
| Total |  | 1650 | 549.266 | 2199.266
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) |  |  | 0
| 2 | Conductor and Conductor Hardware |  |  | 0
| 3 | Transformers |  |  | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) |  |  | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) |  |  | 0
| 6 | Civil Materials and Misc Hardware | 3500 |  | 3500
| Total |  | 3500 | 0 | 3500
Construction
| 1 | Civil and Structural Construction |  |  | 0
| 2 | Electrical Construction | 14727.36 |  | 14727.36
| 3 | Construction Management Services | 1600 |  | 1600
| Total |  | 16327.36 | 0 | 16327.36
Environmental
| 1 | Environmental | 797 |  | 797
| Total |  | 797 | 0 | 797
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 1860 | 100 | 1960
| Total |  | 1860 | 100 | 1960
Contingency
| 1 | Contingency | 1532.42 | 0 | 1532.42
| Total |  | 1532.42 | 0 | 1532.42

## Whirlwind
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
7054/ 7066/ 7067/ 7068/ 7069 | Whirlwind Substation Expansion |  | 22871 | 16100 | 38971
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 167 | 200 | 367
| 2 | Engineering and Design | 381 | 800 | 1181
| 3 | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  | 548 | 1000 | 1548
0
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 300 | 300
| 2 | Conductor and Conductor Hardware | 100 | 250 | 350
| 3 | Transformers | 7630 | 5250 | 12880
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 100 | 100
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 6236 | 3100 | 9336
| 6 | Civil Materials and Misc Hardware | 169 | 200 | 369
| Total |  | 14135 | 9200 | 23335
Construction
| 1 | Civil and Structural Construction | 2500 | 500 | 3000
| 2 | Electrical Construction | 1294 | 2860 | 4154
| 3 | Construction Management Services | 200 |  | 200
| Total |  | 3994 | 3360 | 7354
Environmental
| 1 | Environmental | 50 | 40 | 90
| Total |  | 50 | 40 | 90
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 1838 | 1500 | 3338
| Total |  | 1838 | 1500 | 3338
Contingency
| 1 | Contingency | 2306 | 1000 | 3306
| Total |  | 2306 | 1000 | 3306

## Coolwater Lugo
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
7091 | Coolwater Lugo Transmission Project (Including Jasper) |  | 12072.0003 | 9105.5011 | 21177.5014
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 4458.675 | 2176.55 | 6635.225
| 2 | Engineering and Design | 3811.0399 | 5342.08 | 9153.1199
| 3 | Regulatory and Licensing | 205.25 | 137.09 | 342.34
| Total |  | 8474.9649 | 7655.72 | 16130.6849
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Construction
| 1 | Civil and Structural Construction | 0 | 0 | 0
| 2 | Electrical Construction | 0 | 0 | 0
| 3 | Construction Management Services | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Environmental
| 1 | Environmental | 3507.6621 | 1383.4501 | 4891.1122
| Total |  | 3507.6621 | 1383.4501 | 4891.1122
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 89.3733 | 66.331 | 155.7043
| Total |  | 89.3733 | 66.331 | 155.7043
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## WOD
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2013 - 12/31/2013 | 1/1/2014 - 9/30/2014 | Total
6420 | West of Devers Transmission |  | 9515.373 | 4565 | 14080.373
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 566.62 | 450 | 1016.62
| 2 | Engineering and Design | 3177.45 | 1415 | 4592.45
| 3 | Regulatory and Licensing | 1801.1 | 1094 | 2895.1
| Total |  | 5545.17 | 2959 | 8504.17
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) |  |  | 0
| 2 | Conductor and Conductor Hardware |  |  | 0
| 3 | Transformers |  |  | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) |  |  | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) |  |  | 0
| 6 | Civil Materials and Misc Hardware |  |  | 0
| Total |  | 0 | 0 | 0
Construction
| 1 | Civil and Structural Construction |  |  | 0
| 2 | Electrical Construction |  |  | 0
| 3 | Construction Management Services |  |  | 0
| Total |  | 0 | 0 | 0
Environmental
| 1 | Environmental | 2906.313 | 1261 | 4167.313
| Total |  | 2906.313 | 1261 | 4167.313
Real Properties
| 1 | Real Properties Acquisitions |  |  | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 763.89 | 345 | 1108.89
| Total |  | 763.89 | 345 | 1108.89
Contingency
| 1 | Contingency | 300 | 0 | 300
| Total |  | 300 | 0 | 300