## DCR
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
4847 | Devers-Colorado River |  | 394076.9506 | 234262.2172 | 628339.1678
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 3501.3 | 2501 | 6002.3
| 2 | Engineering and Design | 4000 | 2000 | 6000
| 3 | Environmental | 51990.4122 | 15417 | 67407.4122
| 4 | Regulatory and Licensing | 2087.8859 | 499.8246 | 2587.7105
| Total |  | 61579.5981 | 20417.8246 | 81997.4227
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 17191.6359 | 0 | 17191.6359
| 2 | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 | Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 34579.4704 | 3832 | 38411.4704
| 4 | Supply Management Chargeback & Cost | 2000 | 741 | 2741
| Total |  | 53771.1063 | 4573 | 58344.1063
Construction
| 1 | Civil and Structural Construction | 92773.4727 | 18119 | 110892.4727
| 2 | Electrical Construction | 137531.182 | 131789.7 | 269320.882
| 3 | Construction Management Services | 20695.7341 | 12210.3 | 32906.0341
| Total |  | 251000.3887 | 162119 | 413119.3887
Real Properties
| 1 | Real Properties Acquisitions | 514.9219 | 385 | 899.9219
| Total |  | 514.9219 | 385 | 899.9219
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 23645.64 | 11967.3927 | 35613.0327
| Total |  | 23645.64 | 11967.3927 | 35613.0327
Contingency
| 1 | Contingency | 3565.2955 | 34800 | 38365.2955
| Total |  | 3565.2955 | 34800 | 38365.2955

## TRTP Seg 3B
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
7183 | TRTP Segment 3B |  |  |  | 25215 | 0 | 25215
[8 empty] | 17693 | 7401 | 2970 | 28064
[8 empty] | TL | HW SS | AC Mitigation | Total
| Project Support | [6 empty] | 1370 | 922 | 544 | 2836
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 277 | 0 | 277 | 135 | 142 | 109 | 386
| 2 | 16 |  | Engineering and Design | 377 | 0 | 377 | 377 | 0 | 339 | 716
| 3 | 20 |  | Environmental | 1588 | 0 | 1588 | 833 | 755 | 86 | 1674
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 50 | 0 | 50 | 25 | 25 | 10 | 60
| Total |  |  |  | 2292 | 0 | 2292
| Materials | [6 empty] | 1053 | 1283 | 0 | 2336
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 200 | 0 | 200 | 200 |  |  | 200
| 2 |  |  | Conductor and Conductor Hardware | 100 | 0 | 100 | 100 |  |  | 100
| 3 |  |  | Transformers | 0 | 0 | 0 |  |  |  | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 100 | 0 | 100 | 100 |  |  | 100
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 670 | 0 | 670 |  | 670 |  | 670
| 6 |  |  | Civil Materials and Misc Hardware | 1266 | 0 | 1266 | 653 | 613 |  | 1266
| Total |  |  |  | 2336 | 0 | 2336
| Construction | [6 empty] | 13420 | 4706 | 2350 | 20476
| 1 |  |  | Civil and Structural Construction | 12234 | 0 | 12234 | 8789 | 3445 | 2350 | 14584
| 2 |  |  | Electrical Construction | 5692 | 0 | 5692 | 4431 | 1261 |  | 5692
| 3 |  |  | Construction Management Services | 200 | 0 | 200 | 200 |  |  | 200
| Total |  |  |  | 18126 | 0 | 18126
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 121 | 0 | 121
| Total |  |  |  | 121 | 0 | 121
| Allocated | [6 empty] | 1850 | 490 | 76 | 2416
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 2340 | 0 | 2340 | 1850 | 490 | 76 | 2416
| Total |  |  |  | 2340 | 0 | 2340
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 3C
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
7014 | TRTP Segment 3C |  |  |  | 41715.2 | 400 | 42115.2
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 577.2 | 60 | 637.2
| 2 | 16 |  | Engineering and Design | 1248 | 0 | 1248
| 3 | 20 |  | Environmental | 244 | 0 | 244
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 2069.2 | 60 | 2129.2
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 11963 | 0 | 11963
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 6584 | 100 | 6684
| 6 |  |  | Civil Materials and Misc Hardware | 199 | 0 | 199
| Total |  |  |  | 18746 | 100 | 18846
Construction
| 1 |  |  | Civil and Structural Construction | 4267 | 0 | 4267
| 2 |  |  | Electrical Construction Inc. Wire Stringing & Testing | 8265 | 0 | 8265
| 3 |  |  | Transformers Setting & Testing | 4025 | 200 | 4225
| Total |  |  |  | 16557 | 200 | 16757
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 4343 | 40 | 4383
| Total |  |  |  | 4343 | 40 | 4383
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 4
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6435 | TRTP Segment 4 |  |  |  | 17379.093 | 2948 | 20327.093
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 4947.093 | 890 | 5837.093
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 20 |  | Environmental | 3500 | 1800 | 5300
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 8447.093 | 2690 | 11137.093
Materials
| 1 |  |  | Steel and Hardware (e.g. Yard 28 Relocation and Storage) | 265 | 0 | 265
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 265 | 0 | 265
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 4450 | 0 | 4450
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 4450 | 0 | 4450
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 270 | 0 | 270
| Total |  |  |  | 270 | 0 | 270
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 3947 | 258 | 4205
| Total |  |  |  | 3947 | 258 | 4205
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 5
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
5472 | TRTP Segment 5 |  |  |  | 48526 | 3612 | 52138
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 5996 | 850 | 6846
| 2 | 16 |  | Engineering and Design | 197 | 0 | 197
| 3 | 20 |  | Environmental | 1779 | 2250 | 4029
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 796 | 0 | 796
| Total |  |  |  | 8768 | 3100 | 11868
Materials
| 1 |  |  | Steel and Hardware (e.g. Marker Balls) | 498 | 0 | 498
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 498 | 0 | 498
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 31714 | 195 | 31909
| 3 |  |  | Construction Management Services | 3153 | 0 | 3153
| Total |  |  |  | 34867 | 195 | 35062
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 183 | 0 | 183
| Total |  |  |  | 183 | 0 | 183
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 4210 | 317 | 4527
| Total |  |  |  | 4210 | 317 | 4527
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 6
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
5243 | TRTP Segment 6 |  |  |  | 46775 | 62567 | 109342
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 3827 | 3473 | 7300
| 2 | 16 |  | Engineering and Design | 159 | 145 | 304
| 3 | 20 |  | Environmental | 4595 | 6354 | 10949
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 8581 | 9972 | 18553
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 8343 | 0 | 8343
| 2 |  |  | Conductor and Conductor Hardware | 397 | 0 | 397
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 30 | 0 | 30
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 8770 | 0 | 8770
Construction
| 1 |  |  | Civil and Structural Construction | 21913 | 39293 | 61206
| 2 |  |  | Electrical Construction | 0 | 4585 | 4585
| 3 |  |  | Construction Management Services | 4810 | 4875 | 9685
| Total |  |  |  | 26723 | 48753 | 75476
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 31 | 0 | 31
| Total |  |  |  | 31 | 0 | 31
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 2670 | 3842 | 6512
| Total |  |  |  | 2670 | 3842 | 6512
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 7
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6438 | TRTP Segment 7 |  |  |  | 38386 | 23804 | 62190
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 3354 | 1846 | 5200
| 2 | 16 |  | Engineering and Design | 600 | 450 | 1050
| 3 | 20 |  | Environmental | 3423 | 5359 | 8782
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 7377 | 7655 | 15032
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | -959 | 0 | -959
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | -959 | 0 | -959
Construction
| 1 |  |  | Civil and Structural Construction | 19112 | 6782 | 25894
| 2 |  |  | Electrical Construction | 4629 | 3588 | 8217
| 3 |  |  | Construction Management Services | 5567 | 4175 | 9742
| Total |  |  |  | 29308 | 14545 | 43853
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 14 | 10 | 24
| Total |  |  |  | 14 | 10 | 24
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 2646 | 1594 | 4240
| Total |  |  |  | 2646 | 1594 | 4240
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 8
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6439 | TRTP Segment 8 |  |  |  | 67950 | 56786 | 124736
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 4890 | 6126 | 11016
| 2 | 16 |  | Engineering and Design | 1200 | 900 | 2100
| 3 | 20 |  | Environmental | 10772 | 10718 | 21490
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 697 | 448 | 1145
| Total |  |  |  | 17559 | 18192 | 35751
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 5618 | 0 | 5618
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 5618 | 0 | 5618
Construction
| 1 |  |  | Civil and Structural Construction | 32404 | 22406 | 54810
| 2 |  |  | Electrical Construction | 247 | 4035 | 4282
| 3 |  |  | Construction Management Services | 9595 | 7196 | 16791
| Total |  |  |  | 42246 | 33637 | 75883
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 1618 | 1286 | 2904
| Total |  |  |  | 1618 | 1286 | 2904
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 909 | 3671 | 4580
| Total |  |  |  | 909 | 3671 | 4580
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 9
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6440 | TRTP Segment 9 |  | 38595.6955 | 12218 | 50813.6955
Project Support
| 1 | Windhub Sub | -159.2675 | 0 | -159.2675
| 2 | Whirlwind Sub | 5728.0509 | 3446 | 9174.0509
| 3 | Antelope Sub | 493.004 | 0 | 493.004
| 4 | Vincent Sub | 2540.701 | 1085 | 3625.701
| 5 | Other Substations | 732.8435 | 33 | 765.8435
| Total |  | 9335.3319 | 4564 | 13899.3319
Materials
| 1 | Windhub Sub | -118.6542 | 0 | -118.6542
| 2 | Whirlwind Sub | 94.41 | 0 | 94.41
| 3 | Antelope Sub | 158.0068 | 0 | 158.0068
| 4 | Vincent Sub | 319.1642 | 0 | 319.1642
| 5 | Other Substations | 671.076 | 83 | 754.076
| Total |  | 1124.0028 | 83 | 1207.0028
Construction
| 1 | Windhub Sub | -51.7705 | 0 | -51.7705
| 2 | Whirlwind Sub | 7320.5756 | 0 | 7320.5756
| 3 | Antelope Sub | 1425.465 | 0 | 1425.465
| 4 | Vincent Sub | 11050.8789 | 6796 | 17846.8789
| 5 | Other Substations | 3139.792 | 365 | 3504.792
| Total |  | 22884.9411 | 7161 | 30045.9411
Real Properties
| 1 | Corporate Real Estate | 8.4852 | 0 | 8.4852
| Total |  | 8.4852 | 0 | 8.4852
Allocated
| 1 | Windhub Sub | 1214.7461 | 0 | 1214.7461
| 2 | Whirlwind Sub | 978.6627 | 0 | 978.6627
| 3 | Antelope Sub | 402.0763 | 0 | 402.0763
| 4 | Vincent Sub | 2104.419 | 358 | 2462.419
| 5 | Other Substations | 543.0303 | 52 | 595.0303
| Total |  | 5242.9345 | 410 | 5652.9345
Contingency
| 1 | Windhub Sub | 0 | 0 | 0
| 2 | Whirlwind Sub | 0 | 0 | 0
| 3 | Antelope Sub | 0 | 0 | 0
| 4 | Vincent Sub | 0 | 0 | 0
| 5 | Other Substations | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## TRTP Seg 10
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6441 | TRTP Segment 10 |  |  |  | 13735 | 2767 | 16502
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 4061 | 500 | 4561
| 2 | 16 |  | Engineering and Design | 28 | 0 | 28
| 3 | 20 |  | Environmental | 2900 | 2025 | 4925
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 6989 | 2525 | 9514
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles and Anchor Bolts) | 15 | 0 | 15
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 15 | 0 | 15
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 4885 | 0 | 4885
| 3 |  |  | Construction Management Services | 80 | 0 | 80
| Total |  |  |  | 4965 | 0 | 4965
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 59 | 0 | 59
| Total |  |  |  | 59 | 0 | 59
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 1707 | 242 | 1949
| Total |  |  |  | 1707 | 242 | 1949
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 11
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6442 | TRTP Segment 11 |  |  |  | 16663 | 5969 | 22632
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 1859 | 1742 | 3601
| 2 | 16 |  | Engineering and Design | 465 | 436 | 901
| 3 | 20 |  | Environmental | 748 | 3391 | 4139
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 3072 | 5569 | 8641
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 8824 | 0 | 8824
| 2 |  |  | Conductor and Conductor Hardware | 274 | 0 | 274
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 9098 | 0 | 9098
Construction
| 1 |  |  | Civil and Structural Construction | 411 | 0 | 411
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 411 | 0 | 411
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 3157 | 0 | 3157
| Total |  |  |  | 3157 | 0 | 3157
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 925 | 400 | 1325
| Total |  |  |  | 925 | 400 | 1325
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## EITP
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6551 | Eldorado-Ivanpah Transmission |  | 119420.4 | 106169 | 225589.4
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 3320 | 2766 | 6086
| 2 | Engineering and Design | 3609 | 1602 | 5211
| 3 | Environmental | 12837 | 7454 | 20291
| 4 | Regulatory and Licensing | 70 | 0 | 70
| 5 | Corporate Real Estate | 218 | 0 | 218
| Total |  | 20054 | 11822 | 31876
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 28204 | 6650 | 34854
| 2 | Conductor and Conductor Hardware | 5387 | 0 | 5387
| 3 | Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 8322 | 0 | 8322
| 4 | Civil Materials | 4090 | 1640 | 5730
| Total |  | 46003 | 8290 | 54293
Construction
| 1 | Civil and Structural Construction | 20827 | 29500 | 50327
| 2 | Electrical Construction | 15638 | 23814 | 39452
| 3 | Construction Management Services | 8079 | 6769 | 14848
| Total |  | 44544 | 60083 | 104627
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 8819.4 | 6210 | 15029.4
| Total |  | 8819.4 | 6210 | 15029.4
Contingency
| 1 | Contingency | 0 | 19764 | 19764
| Total |  | 0 | 19764 | 19764

## Lugo-Pisgah
PIN # | Description |  |  |  | Forecast* | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
7018 | Lugo-Pisgah Transmission |  |  |  | 0 | 0 | 0
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 0 | 0 | 0
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 20 |  | Environmental | 0 | 0 | 0
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## Red Bluff
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6929 | Red Bluff Substation |  |  |  | 99915.2 | 68212.04 | 168128
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 2668.5 | 1628.91 | 4297.41
| 2 | 16 |  | Engineering and Design | 2964.6 | 2036.34 | 5000.94
| 3 | 20 |  | Environmental | 9740 | 1753.2 | 11493.2
| 4 | 26 |  | Regulatory and Licensing | 0 | 0 | 0
| 5 | 18 |  | Corporate Real Estate | 0 | 0 | 0
| Total |  |  |  | 15373.1 | 5418.45 | 20791.55
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 4051.8 | 0 | 4051.8
| 2 |  |  | Conductor and Conductor Hardware | 375.3 | 0 | 375.3
| 3 |  |  | Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 20692.8 | 14435.82 | 35128.62
| 4 |  |  | Civil Materials | 0 | 0 | 0
| Total |  |  |  | 25119.9 | 14435.82 | 39555.72
Construction
| 1 |  |  | Civil and Structural Construction | 36756.9 | 8944.02 | 45700.92
| 2 |  |  | Electrical Construction | 3512.7 | 21765.51 | 25278.21
| 3 |  |  | Construction Management Services | 1965.6 | 4863.24 | 6828.84
| Total |  |  |  | 42235.2 | 35572.77 | 77807.97
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 8110 | 5963.4 | 14073.4
| Total |  |  |  | 8110 | 5963.4 | 14073.4
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 9077 | 6821.6 | 15898.6
| Total |  |  |  | 9077 | 6821.6 | 15898.6

## CRSX
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
7076 | Colorado River Substation Expansion |  |  |  | 36401.5759 | 30893.2926 | 67294.8685
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 2363.6592 | 3600 | 5963.6592
| 2 | 16 |  | Engineering and Design | 63.8811 | 709.2 | 773.0811
| 3 | 20 |  | Environmental | 3632.667 | 576 | 4208.667
| 4 | 26 |  | Regulatory and Licensing | 0 | 129.6 | 129.6
| 5 | 18 |  | Corporate Real Estate | 0 | 39.6 | 39.6
| Total |  |  |  | 6060.2073 | 5054.4 | 11114.6073
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 1234.6956 |  | 1234.6956
| 2 |  |  | Conductor and Conductor Hardware |  |  | 0
| 3 |  |  | Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 17087.836 | 9119 | 26206.836
| 4 |  |  | Civil Materials | 0 | 0 | 0
| Total |  |  |  | 18322.5316 | 9119 | 27441.5316
Construction
| 1 |  |  | Civil and Structural Construction | 11612.837 | 2055.127 | 13667.964
| 2 |  |  | Electrical Construction | 0 | 9049.799 | 9049.799
| 3 |  |  | Construction Management Services | 0 | 3285.9666 | 3285.9666
| Total |  |  |  | 11612.837 | 14390.8926 | 26003.7296
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 406 | 720 | 1126
| Total |  |  |  | 406 | 720 | 1126
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 1609 | 1609
| Total |  |  |  | 0 | 1609 | 1609

## Whirlwind
PIN # | Description |  |  |  | Forecast* | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
7054/ 7066/ 7067/ 7068/ 7069 | Whirlwind Substation Expansion |  |  |  | 6500 | 28414 | 34914
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 142 | 76 | 218
| 2 | 16 |  | Engineering and Design | 1165 | 717 | 1882
| 3 | 20 |  | Environmental | 0 | 0 | 0
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 1307 | 793 | 2100
0
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 303 | 2158 | 2461
| 2 |  |  | Conductor and Conductor Hardware | 537 | 511 | 1048
| 3 |  |  | Transformers | 0 | 14026 | 14026
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 1748 | 4745 | 6493
| 6 |  |  | Civil Materials and Misc Hardware | 150 | 10 | 160
| Total |  |  |  | 2738 | 21450 | 24188
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 416 | 416
| 2 |  |  | Electrical Construction | 1860 | 1120 | 2980
| 3 |  |  | Construction Management Services | 134 | 79 | 213
| Total |  |  |  | 1994 | 1615 | 3609
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 428 | 1704 | 2132
| Total |  |  |  | 428 | 1704 | 2132
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 33 | 2852 | 2885
| Total |  |  |  | 33 | 2852 | 2885

## SOK
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
7091/ 6902 | South of Kramer Transmission (Including Jasper) |  |  |  | 6250.0563 | 6433.1977 | 12683.254
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 779.7946 | 326.4361 | 1106.2306
| 2 | 16 |  | Engineering and Design | 2612.8821 | 4346.8165 | 6959.6986
| 3 | 20 |  | Environmental | 1696.7448 | 955.05 | 2651.7948
| 4 | 26 |  | Regulatory and Licensing | 123.6002 | 111.8002 | 235.4004
| 5 | 18 |  | Corporate Real Estate | 1037.0347 | 693.0949 | 1730.1296
| Total |  |  |  | 6250.0563 | 6433.1977 | 12683.254
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 4 |  |  | Civil Materials | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## WOD
PIN # | Description |  |  |  | Forecast* | Forecast
[5 empty] | 1/1/2012 - 12/31/2012 | 1/1/2013 - 9/30/2013 | Total
6420 | West of Devers Transmission |  |  |  | 8000 | 7665 | 15665
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 681 | 629 | 1310
| 2 | 16 |  | Engineering and Design | 3375 | 5247 | 8622
| 3 | 20 |  | Environmental | 2387 | 472 | 2859
| 4 | 26 |  | Regulatory, Licensing, and Legal Costs | 1557 | 1317 | 2874
| Total |  |  |  | 8000 | 7665 | 15665
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0